## Sheet1
| Tasks |  |  | Plan |  | Actual |  | Resources
|  | Dependencies | Man Days | Start Date | End Date | Start Date | End Date
1 | Iteration 1 |  | 116
1.1 | Analysis |  | 9
1.1.1 | Requirement Gathering |  | 2
1.1.2 | Understanding of Exisitng System |  | 2
1.1.3 | Understanding of DB Design |  | 5
1.2 | Design |  | 4
1.2.1 | High Level Architecture Design |  | 2
1.2.2 | Detailed Level Architecture Design |  | 2
1.3 | Development |  | 65
1.3.1 | Code Structure Creation |  | 10
1.3.1.1 | Projects Structure Creation & ORM Model Creation |  | 1
1.3.1.2 | DataAccessLayer Creation |  | 3
1.3.1.3 | BusinessLogicLayer and Service Creation |  | 3
1.3.1.4 | Unit Test Structure Creation |  | 2
1.3.1.5 | Infrastructure & Integration Services Creation (like Message Queue) |  | 1
1.3.2 | Code Copy from Existing Apps |  | 8
1.3.2.1 | UI Structure Creation from Nexelus App |  | 3
1.3.2.2 | Copying the usable code for UI & Logic from Demo App of APAutomation |  | 5
1.3.3 | Document Status Management |  | 4
1.3.3.1 | Document Listing UI Creation |  | 3
1.3.3.2 | Unit Test Creation for Document Listing Logic |  | 1
1.3.4 | Textract Service Integration |  | 4
1.3.4.1 | Background Agent Service Creation |  | 2
1.3.4.2 | Integration with Message Queue |  | 2
1.3.5 | Model Creation Functionality |  | 14
1.3.5.1 | Backend logic creation for Document Field Mapping Functionality |  | 8
1.3.5.2 | UI Creation of Document Field Mapping Functionality |  | 4
1.3.5.2 | Unit Test Creation for Model Creation Functionality |  | 2
1.3.6 | Model Search Functionality |  | 4
1.3.6.1 | Creation of Model Search Functionality |  | 3
1.3.6.2 | Unit Test Creation for Model Search Functionality |  | 1
1.3.7 | ERP Integration |  | 11
1.3.7.1 | Creation of Generalized Adapter Interface for Data Push and Pull |  | 1
1.3.4.2 | Integration with Message Queue |  | 2
1.3.7.2 | Creation of Data Pull functionality for Nexelus Adapter |  | 3
1.3.7.3 | Creation of Data Push functionality for Nexelus Adapter |  | 3
1.3.7.4 | Unit Test Creation for Adapter Interface |  | 2
1.3.8 | Security, Login and Multi Tenant Functionality implementation |  | 10
1.3.8.1 | Creation of Security Token Service |  | 2
1.3.8.2 | Login Creation |  | 3
1.3.8.3 | Automatic DB Creation, ERP System Integration, Primary Data Fetching |  | 5
| Test & Deployment |  | 36
| Release 1 & Testing |  | 12
| Deployment on on-prem env for Release 1 and Demo |  | 2
| Test Cycle 1 |  | 5
| Debug Cycle 1 |  | 5
| Release 2 & Testing |  | 11
| Deployment on cloud for Release 2 |  | 1
| Test Cycle 2 |  | 5
| Debug Cycle 2 |  | 5
| Release 3 & Testing |  | 11
| Deployment on cloud for Release 3 |  | 1
| Test Cycle 3 |  | 5
| Debug Cycle 3 |  | 5
| Testing for Beta Release to Clients |  | 2
| Fine tuning and small fixes |  | 2
| Deploy |  | 2
| Preparation for RTM environment for beta |  | 2
Iteration 2