## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | AP Automation Phase 3 | 348 hrs | July 5, 2021 10:00 AM | September 8, 2021 3:00 PM |  | 0
1 | Yes | Auto Scheduled | Development Sprints | 188 hrs | July 5, 2021 10:00 AM | August 11, 2021 3:00 PM |  | 1
2 | Yes | Auto Scheduled | Development of Version V3 (New Feature Branch) | 188 hrs | July 5, 2021 10:00 AM | August 11, 2021 3:00 PM |  | 2
3 | Yes | Auto Scheduled | Version 2.9.1 | 188 hrs | July 5, 2021 10:00 AM | August 11, 2021 3:00 PM |  | 3
4 | Yes | Auto Scheduled | Code Refactoring | 40 hrs | July 9, 2021 10:00 AM | July 16, 2021 10:00 AM |  | 4
5 | Yes | Auto Scheduled | Deployment Data Search Service (DSS) | 24 hrs | July 5, 2021 10:00 AM | July 8, 2021 10:00 AM |  | 4
6 | Yes | Auto Scheduled | Performance Improvement of DSS | 24 hrs | July 8, 2021 10:00 AM | July 13, 2021 10:00 AM | 5 | 4
7 | Yes | Auto Scheduled | Integration with Data Search Service | 16 hrs | July 9, 2021 10:00 AM | July 13, 2021 10:00 AM |  | 4
8 | Yes | Auto Scheduled | Business Logic for Invoice Routing | 40 hrs | July 16, 2021 10:00 AM | July 29, 2021 10:00 AM | 4 | 4
9 | Yes | Auto Scheduled | Test Case Creation | 40 hrs | July 12, 2021 10:00 AM | July 23, 2021 10:00 AM |  | 4
10 | Yes | Auto Scheduled | Discussions And Management Activities | 24 hrs | July 13, 2021 10:00 AM | July 16, 2021 10:00 AM | 7 | 4
11 | Yes | Auto Scheduled | Build Release | 16 hrs | July 16, 2021 10:00 AM | July 26, 2021 10:00 AM | 10 | 4
12 | Yes | Auto Scheduled | Testing | 40 hrs | July 23, 2021 10:00 AM | July 30, 2021 10:00 AM | 9 | 4
13 | Yes | Auto Scheduled | Bug Fixing for Business Logic for Invoice Routing | 40 hrs | July 29, 2021 10:00 AM | August 5, 2021 10:00 AM | 8 | 4
14 | Yes | Auto Scheduled | Bug Fixing Data Search Service | 40 hrs | July 13, 2021 10:00 AM | July 26, 2021 10:00 AM | 6 | 4
15 | Yes | Auto Scheduled | Discussions And Management Activities | 32 hrs | July 26, 2021 10:00 AM | July 30, 2021 10:00 AM | 11 | 4
16 | Yes | Auto Scheduled | Build Release | 8 hrs | July 30, 2021 10:00 AM | August 2, 2021 10:00 AM | 15 | 4
17 | Yes | Auto Scheduled | Data Analysis | 40 hrs | July 26, 2021 10:00 AM | August 2, 2021 10:00 AM | 14 | 4
18 | Yes | Auto Scheduled | R&D on ML Algos | 60 hrs | August 2, 2021 10:00 AM | August 11, 2021 3:00 PM | 17 | 4
19 | Yes | Auto Scheduled | Development of Version V2.1 (Bug Fixing Branch) | 160 hrs | August 11, 2021 3:00 PM | September 8, 2021 3:00 PM | 2 | 1
20 | Yes | Auto Scheduled | Version 2.0.1 | 160 hrs | August 11, 2021 3:00 PM | September 8, 2021 3:00 PM |  | 2
21 | Yes | Auto Scheduled | Change Assessment on Client feedback for change request | 16 hrs | August 11, 2021 3:00 PM | August 13, 2021 3:00 PM |  | 3
22 | Yes | Auto Scheduled | Bug Fixing | 40 hrs | August 11, 2021 3:00 PM | August 18, 2021 3:00 PM |  | 3
23 | Yes | Auto Scheduled | Test Case Creation | 40 hrs | August 18, 2021 3:00 PM | August 25, 2021 3:00 PM | 22 | 3
24 | Yes | Auto Scheduled | Discussions And Management Activities | 16 hrs | August 13, 2021 3:00 PM | August 17, 2021 3:00 PM | 21 | 3
25 | Yes | Auto Scheduled | Build Release | 8 hrs | August 18, 2021 3:00 PM | August 19, 2021 3:00 PM | 21,22 | 3
26 | Yes | Auto Scheduled | Testing | 40 hrs | August 25, 2021 3:00 PM | September 1, 2021 3:00 PM | 23 | 3
27 | Yes | Auto Scheduled | Bug Fixing | 40 hrs | August 18, 2021 3:00 PM | August 25, 2021 3:00 PM | 22 | 3
28 | Yes | Auto Scheduled | Build Release | 8 hrs | August 19, 2021 3:00 PM | August 20, 2021 3:00 PM | 25 | 3
29 | Yes | Auto Scheduled | Testing | 40 hrs | September 1, 2021 3:00 PM | September 8, 2021 3:00 PM | 26 | 3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Faisal Ahmed Farooqui | FAF | Work |  | Manager, Dev | faisalf@nexelus.net | faisalf@nexelus.net | 100% | $0.00/h | 0
2 | Zeeshan Akhtar | ZA | Work |  | Dev | zeeshana@nexelus.net | zeeshana@nexelus.net | 100% | $0.00/h | 0
3 | Shoaib Alauddin | SA | Work |  | Dev |  |  | 100% | $0.00/h | 0
4 | Tao Lin | TL | Work |  | QA | taol@nexelus.net | taol@nexelus.net | 100% | $0.00/h | 0
5 | Muhammad Naeem | MN | Work |  | QA |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Code Refactoring | Zeeshan Akhtar | 0 | 40h | 100%
Deployment Data Search Service (DSS) | Shoaib Alauddin | 0.80000000000000004 | 24h | 100%
Performance Improvement of DSS | Shoaib Alauddin | 0 | 24h | 100%
Integration with Data Search Service | Faisal Ahmed Farooqui | 0 | 16h | 100%
Business Logic for Invoice Routing | Zeeshan Akhtar | 0 | 40h | 100%
Test Case Creation | Muhammad Naeem | 0 | 40h | 100%
Discussions And Management Activities | Faisal Ahmed Farooqui | 0 | 24h | 100%
Build Release | Faisal Ahmed Farooqui | 0 | 16h | 100%
Testing | Muhammad Naeem | 0 | 40h | 100%
Bug Fixing for Business Logic for Invoice Routing | Zeeshan Akhtar | 0 | 40h | 100%
Bug Fixing Data Search Service | Shoaib Alauddin | 0 | 40h | 100%
Discussions And Management Activities | Faisal Ahmed Farooqui | 0 | 32h | 100%
Build Release | Faisal Ahmed Farooqui | 0 | 8h | 100%
Data Analysis | Shoaib Alauddin | 0 | 40h | 100%
R&D on ML Algos | Shoaib Alauddin | 0 | 60h | 100%
Change Assessment on Client feedback for change request | Faisal Ahmed Farooqui | 0 | 16h | 100%
Bug Fixing | Zeeshan Akhtar | 0 | 40h | 100%
Test Case Creation | Muhammad Naeem | 0 | 40h | 100%
Discussions And Management Activities | Faisal Ahmed Farooqui | 0 | 16h | 100%
Build Release | Faisal Ahmed Farooqui | 0 | 8h | 100%
Testing | Muhammad Naeem | 0 | 40h | 100%
Bug Fixing | Zeeshan Akhtar | 0 | 40h | 100%
Build Release | Faisal Ahmed Farooqui | 0 | 8h | 100%
Testing | Muhammad Naeem | 0 | 40h | 100%