## Sheet1
RACI Matrix for Change Management
(R)esponsible, (A)ccountable, (C)onsulted, and (I)nformed (RACI) diagram
Task | Activity | Client | Management | Product Management | Development | QA | Release Management
1 | Request for Change (RFC) | A | A/R | R |  |  |  | Legend | Description
2 | Assessment of RFC | I | R | R/A |  | C/I |  | R | Responsible
3 | Reject RFC | C/I | R | C |  |  |  | A | Accountable
4 | Assign Change Owner | I | R | R/A | C | C |  | C | Consulted
5 | Requirement Specifications | C | C | R | C | C |  | I | Informed
6 | Impact Analysis | I | C | R | R | C
7 | System Design and Specifications | I | C | A | R | C
8 | Estimate | I | I | R/A | C | C
9 | Review/Update Requirement Specification | I | I | A | R | C
10 | Development |  | I | C | R/A
11 | Deployment on QA Environment |  | I | I | C | R/A
12 | Review Change on QA Environment and Rebuild Decision |  | I | I | C | R/A
13 | Deployment on Release Environment |  | I | C/I | I | R/A
14 | Review Change on Release Environment and Rebuild Decision |  | I | I | C | R/A
15 | Deployment on UAT Envronment | I | I | I | I | C | R/A
16 | Client Verification and Rebuild Decision | R/A | I | C
17 | Client Sign-off | R/A | C/I | I
18 | Deploy on Production Environment | I | I | C |  | C | R/A
19 | Client Review | R/A | I | C |  | I
20 | Close Change |  | I | R/A
21 | Conduct Formal Turnover to Support |  | C | R |  | A
22 | Perform Post Implementation Review (PIR) |  | C/I | R/A | C | R
23 | Notify Requestor of Change Results | I | I | R
24 | Close RFC | I | C | A |  | R