## Action Items
SOC Compliance – Meeting Agenda
Date: January 30, 2024, 8:30AM to 9:00AM (ET)
Attendees: Nexelus and HiQuSystems
Weekly Action Items
Item # | Date | Area | Descripion | Action | Responsibility | Due Date | Status
1 | 2024-01-30 | Policy Documents | Following policies are expiring in February 2024. Please let us know if any changes are required in these policies. 1. Acceptable Use Policy 2. Information Security Policy 3. Code of Conduct Policy | Upload policies with No change | Tauseef | 2024-02-06 | Done
2 | 2024-01-30 | CyberSecurity | Rapid7 report is generating Login error on Report execution. |  | Tao | 2024-02-07
3 | 2024-01-30 | CyberSecurity | Resolve Vulnerability Issues before January 29 |  | Abid | 2024-02-29 | In Progress
4 | 2024-01-30 | CyberSecurity | Penetration Testing Results will expire by July 12 Assign third party for Annual Penetration Testing | Reminder in May | Tauseef | 2024-05-01 | On Hold
5 | 2024-01-30 | Trainings | Put Trainings on Calender |  | Tauseef

## Sheet1
Vendor Portal
Add Naming Convention

## Codes (hidden)
Status | Ticket type | Fix Nature | Customers
Open | UI | Sp change | HealthStar
Development | Application Crash | ASPX | Pursuit
QA | Data Corruption | JS | 72 & sunny
Deployment | Report | DLL
Closed | user understanding | Data fix
On Hold | setup issue | NA
change request/text change
sp change
Java Script