## Network - US
Service | Network Support Service
Service Value | 2
Risk Identification |  | Risk Valuation / Inherent Risk Valuation |  |  |  | Risk Treatment | Risk Owner | Risk Acceptance | Contigency Plan
Dependencies | Vulnerabilities | Probability | Impact | Risk Value | Risk Level | Avoid/Reduce/Mitigate/Transfer
Verizon/AT&T Internet Providers | service down issues | 2 | 3 | 12 | High | Backup Internet link available, plus work from home somewhat mitigates the risk. | Tao/Peter | Yes | Management accepts this risk and can manage it as such
Servers | Server is down | 1 | 3 | 6 | Medium | Backup Internet or go into the office and troubleshoot the issue | Peter | No | Complaint log/ email SLA complience procedure procurement procedure
| Server is hacked | 1 | 4 | 8 | Medium |  | Peter
| Is stolen or removed from office | 1 | 4 | 8 | Medium | Server is locked behind a locked door and only key personel can access the server room | Peter | No | Estimated fund requirements are approved and allocated at start of fiscal year in financial budget.
3rd Backup (Remote) | device is down | 1 | 2 | 4 | Low | Incident reporting from Everyone to Nework department | Peter | Yes | N/A
| Storage is out of space | 1 | 2 | 4 | Low | Maintain sufficient space to store data | Peter | Yes
| Is stolen or removed from office | 1 | 4 | 8 | Medium | Server is locked behind a locked door and only key personel can access the server room | Peter | Yes
8x8 Phone service | phone service is down | 1 | 1 | 2 | Low | Backup Internet | Tao/Peter | Yes
| Stolen phone | 1 | 1 | 2 | Low | Decommission the phone line immediately | Tao/Peter | Yes
Card Key (Integrated Systems) | System is down | 1 | 2 | 4 | Low | Backup physical key | Tao/Peter | Yes
| Stolen Key Card | 1 | 4 | 8 | Medium | Key card that are lost must be reported to leadership for decommission | Tao/Peter | Yes
Note on A14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Imran Rahman , for our tenant, Peter is suggesting to have them sign an agreement or something because are taking on responsibility of non-employee accessing the office. Reply: I believe we have a subtenant agreement

## Network - PK
Service | Network Support Service
Service Value | 3
Risk Identification |  | Risk Valuation / Inherent Risk Valuation |  |  |  | Risk Treatment | Risk Owner | Risk Acceptance | Contigency Plan
Dependencies | Vulnerabilities | Probability | Impact | Risk Value | Risk Level | Avoid/Reduce/Mitigate/Transfer
Multinet/ Nayatel | service down issues | 1 | 3 | 9 | Medium | Backup Internet link available | Network Administrator | No | Switch Internet link to Backup ISP
| payment issues | 1 | 2 | 6 | Medium | Sufficient funds available and payment made without delay | CEO | Yes | Estimated fund requirements are approved and allocated at start of fiscal year in financial budget.
| support solution delay | 1 | 2 | 6 | Medium | Switch to alternate link to avoid service delay | Network Manager | No | Network admin will switch Network service to the backup ISP
| response time delay | 1 | 3 | 9 | Medium | Shift to backup link to avoid service delay | Network Manager | No | Network admin will switch Network service to the backup ISP
procurement approvals | capacity management | 1 | 3 | 9 | Medium | Backup Internet link available | General Manager | No | Complaint log/ email SLA complience procedure procurement procedure
| budgeting | 1 | 3 | 9 | Medium | Backup Internet link available | CEO | No | Estimated fund requirements are approved and allocated at start of fiscal year in financial budget.
| management approvals | 1 | 3 | 9 | Medium | Alternate Internet link has been aquired from different ISP | CEO | No | Estimated fund requirements are approved and allocated at start of fiscal year in financial budget.
Availability of Network Services | Network service down | 1 | 3 | 6 | Medium | Incident reporting from Everyone to Nework department | Network Admin | Yes | N/A
Availability of System Support Services | Support Service delay | 2 | 2 | 8 | Medium | Incident reporting from Everyone to Nework department | Network Admin | Yes | N/A
| Hardware not working properly | 1 | 3 | 6 | Medium | Incident reporting from Everyone to Nework department | Network Admin | Yes | N/A
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Imran Rahman @Tauseef Shezad , Hi Tauseef, please revise your list with exact services and hardware. See US tab for example.

## System Support Service
Service | System Support Service
Service Value | 3
Risk Identification |  | Risk Valuation / Inherent Risk Valuation |  |  |  | Risk Treatment | Risk Owner | Risk Acceptance | Contigency Plan
Dependencies | Vulnerabilities | Probability | Impact | Risk Value | Risk Level | Avoid/Reduce/Mitigate/Transfer
VPN | Lack of internet/ network services | 1 | 3 | 9 | Medium | Contact ISPs | Peter
| Unauthorized Access | 1 | 4 | 12 | High | Disable account | Peter
Laptop/Workstation

## Product Support Services
Service | Product Support Services
Service Value | 2
Risk Identification |  | Risk Valuation / Inherent Risk Valuation |  |  |  | Risk Treatment | Risk Owner | Risk Acceptance | Contigency Plan
Dependencies | Vulnerabilities | Probability | Impact | Risk Value | Risk Level | Avoid/Reduce/Mitigate/Transfer
DevOps Availability | DevOps Service for ticketing is not accessible | 1 | 2 | 4 | Low | 1. Microsoft SLA covers over 99% availability 2. Contact Microsoft Support 3. Developers have source code on their workstations that they can use to continue their work. | Network Admin | Yes | Alternate Internet available
Availability of Support Resources | Unavailability of support/development resources | 1 | 3 | 6 | Medium | Alternate resource is available | General Manager | Yes | Inform client.
| Lack of skills of development and QA resources | 1 | 1 | 2 | Low | Training | General Manager | Yes | Hire skilled resource
| Delay in delivery | 1 | 3 | 6 | Medium | Common development pool with resources is available | General Manager | Yes | Assign additional resources
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Imran Rahman @Tauseef Shezad , Hi Tauseef, why do we need this tab? We are strictly doing security and reliability of production systems as far as I understand. Reply: I thought we need to decide which SOC2 area we are doing We can hide this tab if only security is required.

## Cloud Infrastructure
Service | Cloud Infrstructure
Service Value | 3
Risk Identification |  | Risk Valuation / Inherent Risk Valuation |  |  |  | Risk Treatment | Risk Owner | Risk Acceptance | Contigency Plan
Dependencies | Vulnerabilities | Probability | Impact | Risk Value | Risk Level | Avoid/Reduce/Mitigate/Transfer
Office 365 | Unauthorized Access | 1 | 4 | 12 | High | Disable account and investigate | Tao/Peter | Yes
| Unauthorized Data Retreival | 1 | 4 | 12 | High | Open incident report with security team for further investigation. | Tao/Peter
| Deletion of files | 1 | 2 | 6 | Medium | The data will be restored | Tao/Peter
DevOps | Unauthorized Access | 1 | 4 | 12 | High | Disable account and investigate | Tao/Peter | Yes
| Unauthorized Data Retreival | 1 | 3 | 9 | Medium | Open incident report with security team for further investigation. | Tao/Peter | Yes
| Deletion of files | 1 | 1 | 3 | Low | The data will be restored | Tao/Peter | Yes
Azure Production | Unauthorized Access | 1 | 4 | 12 | High | Disable account and investigate | Tao/Peter | Yes
| Unauthorized Data Retreival | 1 | 4 | 12 | High | Open incident report with security team for further investigation. | Tao/Peter
| Deletion of files and objects | 1 | 4 | 12 | High | The data will be restored and object will be recreated using scripts | Tao/Peter
Azure Development | Unauthorized Access | 1 | 4 | 12 | High | Disable account and investigate | Tao/Peter | Yes
| Unauthorized Data Retreival | 1 | 3 | 9 | Medium | Open incident report with security team for further investigation. | Tao/Peter
| Deletion of files and objects | 1 | 2 | 6 | Medium | The data will be restored and object will be recreated using scripts | Tao/Peter
AWS | Unauthorized Access | 1 | 4 | 12 | High | Disable account and investigate | Tao/Peter | Yes
| Unauthorized Data Retreival | 1 | 3 | 9 | Medium | Open incident report with security team for further investigation. | Tao/Peter
| Deletion of files and objects | 1 | 2 | 6 | Medium | The data will be restored and object will be recreated using scripts | Tao/Peter

## HR services
Service | HR Services
Service Value | 2
Risk Identification |  | Risk Valuation / Inherent Risk Valuation |  |  |  | Risk Treatment | Risk Owner | Risk Acceptance | Contigency Plan
Dependencies | Vulnerabilities | Probability | Impact | Risk Value | Risk Level | Avoid/Reduce/Mitigate/Transfer
New hire requisition request | Timely request generation | 1 | 2 | 4 | Low | Escalate to management for necessary actions | HR/Admin | Yes | N/A
Approval for requisition request | Delay in approval or rejection from management | 2 | 2 | 8 | Medium | Follow up with General Manager | HR/Admin | Yes | N/A
Approval for Employee engagement activities | Delay in approval or rejection from management | 2 | 2 | 8 | Medium | Follow up with GM Development | HR/Admin | Yes | N/A
Training approval | Delay in approval or rejection from management | 1 | 2 | 4 | Low | Follow up with management | HR/Admin | Yes | N/A
| Availability of trainer | 1 | 2 | 4 | Low | Alternate trainer will be arranged | HR/Admin | Yes | N/A
| Availability of venue | 1 | 2 | 4 | Low | Alternate venue will be arranged | HR/Admin | Yes | N/A
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Imran Rahman @Tauseef Shezad , please review this section Reply: I have asked Moiz for a sample Risk register, and I struggling with these number assignments. There has to a simple way to handle this....

## Admintrative Services - US
Service | Admintrative Services - USA
Service Value | 2
Risk Identification |  | Risk Valuation / Inherent Risk Valuation |  |  |  | Risk Treatment | Risk Owner | Risk Acceptance | Contigency Plan
Dependencies | Vulnerabilities | Probability | Impact | Risk Value | Risk Level | Avoid/Reduce/Mitigate/Transfer
Submission of expenses reimbursement forms | Delay in submission | 2 | 3 | 12 | High | Communicate the deadline of submission No expection after deadline | Manager Admin | Yes | N/A
| Approval of expenses from management | 1 | 3 | 6 | Medium | Follow up with management | Manager Admin | Yes | N/A
Training approval | Delay in approval or rejection from management | 2 | 3 | 12 | High | Follow up with management | Manager Admin | Yes | N/A
| Availability of trainer | 1 | 2 | 4 | Low | Alternate trainer will be arranged | Manager Admin | Yes | N/A
| Availability of venue | 1 | 2 | 4 | Low | Alternate venue will be arranged | Manager Admin | Yes | N/A
Input from employees & Team Leads | Delay in submission | 2 | 3 | 12 | High | Communicate the deadline Escalate to the management | Manager Admin | Yes | N/A
| Delay from management | 1 | 2 | 4 | Low | Follow up with management | Manager Admin | Yes | N/A
Availability of necessary medicines for First aid | Procurement of medicines | 1 | 1 | 2 | Low | Immediately buying the medicines | Manager Admin | Yes | N/A
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Imran Rahman , please review this section

## Admintrative Services - PK
Service | Admintrative Services
Service Value | 2
Risk Identification |  | Risk Valuation / Inherent Risk Valuation |  |  |  | Risk Treatment | Risk Owner | Risk Acceptance | Contigency Plan
Dependencies | Vulnerabilities | Probability | Impact | Risk Value | Risk Level | Avoid/Reduce/Mitigate/Transfer
Submission of expenses reimbursement forms | Delay in submission | 1 | 3 | 6 | Medium | Communicate the deadline of submission No expection after deadline | Manager Admin | Yes | N/A
| Approval of expenses from management | 1 | 3 | 6 | Medium | Follow up with management | Manager Admin | Yes | N/A
Submission of medical reimbursement forms | Delay in submission | 1 | 2 | 4 | Low | Communicate the deadline of submission | Manager Admin | Yes | N/A
Training approval | Delay in approval or rejection from management | 1 | 3 | 6 | Medium | Follow up with management | Manager Admin | Yes | N/A
| Availability of trainer | 1 | 2 | 4 | Low | Alternate trainer will be arranged | Manager Admin | Yes | N/A
| Availability of venue | 1 | 2 | 4 | Low | Alternate venue will be arranged | Manager Admin | Yes | N/A
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Tauseef Shezad @Arshad Sadal , please review this section

## Legends
Risk Register Values
Probability | Risk | Value
If occures once or more in a week | Certain | 5
if occure in 2 to 4 months | Likely | 4
If occurs in 4 to 6 months | Possible | 3
If occures once or more in six months | Unlikely | 2
If occures once or more in a year | Rare | 1
Impact Value | Risk | Value
Greater than 16.0 | Critical | 4
Greater than 9.0 but less than or equal to 16.0 | High | 3
Greater than 4.0 but less than or equal to 9.0 | Medium | 2
Less than or equal to 4.0 | Low | 1
CALCULATION | SERVICE VALUE x PROBABILITY x IMPACT
Note on A10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Imran Rahman @Tauseef Shezad , I have reorganized the Impact Value. The numbering didn't make sense to me and the calculation seems to be odd. Based on our policy value provided from least to most critical is 1 through 5. @Tauseef Shezad , please review the tabs that you've created.