## Nexelus
Sr. # | Steps | Tables Involved | Responsibility | ETA | Status
Database Setup
1 | Take backup of existing database from Test Server - Nex_JG_JPN |  | Imran
2 | Restore backup from step above on Production - Nex_JG_JPN |  | Imran
3 | Views and Sps Poining if DB name is different on test and production |  | Imran
4 | Set mail flag=0 in pdd_resources from "EMPL" | pdd_resources | Imran
5 | IPC configuration pointing if any | pdd_lookup_ipc_entities_header | Imran
5.1 |  | pdd_customer_profile_ipc_ad_tool | Imran
5.2 |  | pdm_company_ipc | Imran
5.3 |  | pdd_lookup_ipc_entities_detail | Imran
5.4 |  | pdd_invoice_detail_ipc_ad_tool | Imran
5.5 |  | pdm_company_ipc_ad_tool | Imran
5.6 |  | pdd_delivery_search_ad_tools_campaign | Imran
5.7 |  | pdd_level3_ipc_ad_tool | Imran
5.8 |  | pdd_ipc_cache_adwords_accounts_for_budget_orders | Imran
5.9 |  | pdd_invoice_header_ipc_ad_tool | Imran
6 | Set Integration code=0 if UAT instance of Financial ERP is not available, otherwise as required: - 16 = NetSuite | Pdm_company | Imran
6.3 | NetSuite | pdd_Netsuite_configuration pdd_netsuite_item_mapping | Tao
7 | Update email profile setting | Nex_Enterprise_TSY..ent_email_profile | Imran
8 | Insert a record in enterprise for new company with next company code | Nex_Enterprise_TSY..pdi_site | Imran
8.1 | - voucher_doc_path - web_app_path - nex_vp_url - report_server_path - database_server_esmte - database_name_esmte - database_server_esm - database_name_esm |  | Imran
9 | Reset application pool for step 8 |  | Tauseef Shahzad
10 | Clean transactional data | Clear scripts | Imran
11 | Clean/reset setup data | As per requirement | Imran
12 | Change company code | Company code scripts | Imran
Web Deployment
1 | Deploy Web Application |  | Tauseef Shahzad
2 | Deploy Core Applications |  | Tauseef Shahzad
Verificartion
1 | Process Verification |  | Bilal, Tao

## APWorks
Item | Assigned To | Responsibility | ETA | Status
1 | Company DNS Setup tsy-uat.apworks.ai | Tao
2 | Create S3 Buckets and execute setup scripts justglobal-jpn-prod-apautomation | Tao
3 | Copy Template from UAT to Production S# Bucket | Imran Haq
3 | Create Company Database from JustGlobal UAT Backup uat_apautomation_tsy | Arif Khan / Imran Haq
4 | Enter JustGlobal-Japan information in Common Database - ent_client - ent_domain | Imran Haq
5 | Update apam_company table for JustGlobal Japan | Imran Haq
6 | Cleanup Database - transactional Data - Model Data - Master Data | Imran Haq
7 | Import Model data for JustGlobal Japan in Common and company database | Imran Haq
8 | Generate Nexelus API Key and update Database | Tao / Imran Haq
9 | Verify APWorks (Media and Production) | Bilal / Tao