## Employee
Annual Performance Evaluation
Employee Information
Employee ID | 013
Employee Name | Abid Ali
Designation | Dev Manager
Department | Development
Joining Date | 07/03/2023
Experience With Hiqu Systems | 1.2
Assessment Year | 2024-25
Overall Performance
Personal Traits | % |  | Technical Skills |  |  | % |  | Leadership |  |  | %
General attitude |  |  | Product Domain |  |  |  |  | Project Management
Office decorum/appearance |  |  | Database understanding |  |  |  |  | Task Estimation Skills
Proactive behavior/eagerness to learn |  |  | Ability to troubleshoot product |  |  |  |  | Leadership Skills
Attitude towards team members |  |  | Verbal Communications |  |  |  |  | Conflict Management
Loyalty towards the company |  |  | Written Communications |  |  |  |  | Motivational Skills
Overall Commitment |  |  | Technical Skills |  |  |  |  | Communication Skills
Interpersonal Communication |  |  | Technical Documentation |  |  |  |  | Responsibility Delegation
Written Communication | [7 empty] | Task Distribution
Punctuality
Punctuality | July | August | September | October | November | December | January | February | March | April | May | June
Total Working Days |  | 22
Employee Working Days |  | 22
Leaves |  | 0
Days Worked over 8 hours |  | 22
Days Worked under 8 hours |  | 0
Weekends |  | 0
Late Arrivals |  | 0
Short Leaves |  | 0

## September 24
Project Profile
Abid Ali
Period: September 2024
Project / Release | Task | Project Overhead |  | Analysis | Design | Development Time |  |  | Bug Fixing Time |  |  | Total |  | Number of Bugs
|  | Mgmt | Deployment |  |  | Estimate | Actual | Diff % | Planned | Actual | Variance | Difference | Smoke | QA | UAT | Post-Prod | Total
APWORKS 2024.2 - PHASE 3
| Add Media Type/S |  |  | 2 |  |  |  | 0% | 0 | 0 | 0% | 100% | Passed | 0 | 0 | 0 | 0
| Broadcast Inv: I |  |  | 1
| Google Drive int |  |  | 2
| Project Overhead | 1 | 2.5
| Total | 1 | 2.5 | 5 |  | 0 | 0 | 0% | 0 | 0 | 0% | 100% |  | 0 | 0 | 0 | 0
APWORKS PHASE2
| Bug Fixing | [6 empty] | 0% | 0 | 26 | 100% | 100% |  | 1
[6 empty] | 0 | 0 | 0% | 0 | 26 | 100% | 100% |  | 1 | 0 | 0 | 1
NEXELUS 2024.2
| Production Issue | [6 empty] | 0% | 0 | 9 | 100% | 100% |  | 1
[6 empty] | 0 | 0 | 0% | 0 | 9 | 100% | 100% |  | 1 | 0 | 0 | 1
Overall Performance | [5 empty] | 0 | 0 | 0% | 0 | 26 | 0% |  |  | 1 | 0 | 0 | 1