## Sheet1
Nexelus RACI matrix for Change Management
(R)esponsible, (A)ccountable, (C)onsulted, and (I)nformed (RACI) diagram
Process ID | Activity | Change Manager | Change Requestor | Change Coordinator | Change Advisory Board(CAB) | Change Approver (or ECAB) | Change Owner
2.1 | Register RFC | A | R | R
2.1.3 | Perform RFC Assessment | A | I | R |  | C/I
2.1.5 | Reject RFC | C/I | R | R | R
2.1.6 | Assign Change Owner | R | R | R
2.2.1 | Identify Standard Change Model and Change Owner | R/A | R | I |  |  | I
2.2.2 | Prioritize Standard Change | R/A | C/I | I |  |  | R
2.2.3 | Plan and Schedule Standard Change | R/A | I | R |  |  | R
2.2.4 | Execute Standard Change | R/A | I | R |  |  | R
2.2.6 | Remove Standard Change Model | R | I | I |  |  | C/I
2.3.1 | Assess Change | R/C | I | R |  |  | R
2.3.3 | Determine Approval Requirements | R | C/I | C/I |  |  | A
2.3.5 | TCAB Approval | R/A | I | I | R
2.3.8 | Coordinate Build and Test | R.A | I | R |  |  | R
2.3.10 | Schedule for Normal Change | R/A | I | R |  |  | R
2.3.12 | Create and Submit Deployment Plan | A | I | R |  |  | R
2.3.13 | DCAB Approval | R/A | I | I | R
2.3.15 | Decision on Rebuild | R/A |  |  | R
2.3.17 | Review RFC after Rebuild Decision | A | I | R |  |  | R
2.3.19 | Review RFC after DCAB Approval | A | I | R |  |  | R
2.3.21 | Coordinate and Monitor Change Implementation | R/A | I | R/C |  |  | R
2.3.23 | Provide CMDB Updates | R/A | I | R |  |  | R
2.3.26 | Assess Change Success | R/A | I | R |  |  | R
2.4 | Emergency Change | R/A | C/I |  | R | R | R
2.4.3 | Convene ECAB | R/A |  |  |  | C/I | R
2.4.4 | Approve Emergency Change | A/C |  |  |  | R
2.4.6 | Plan and Design Solution | R/A |  | I |  |  | R
2.4.8 | Coordinate Emergency Change Build and Test | R/A | I | R |  |  | R
2.4.10 | Coordinate Emergency Change Implementation | R/A |  |  |  |  | R
2.4.11 | Abandon the Change | R | C | I |  |  | R
2.5 | Review and Close Change | R/A | C | R |  |  | R/C
2.5.3 | Conduct Formal Turnover to Support | C/I | C | A/C |  |  | R
2.5.4 | Perform PIR | A | C/I | R |  |  | R
2.5.5 | Notify Requestor of Change Results | A/C | I | R |  |  | R
2.5.6 | Close RFC | R/A | C | R |  |  | R