## Action Items
SOC Compliance – Meeting Agenda
Date: April 24, 2024, 8:30AM to 9:00AM (ET)
Attendees: Nexelus and HiQuSystems
Weekly Action Items
Item # | Date | Area | Descripion | Action | Responsibility | Due Date | Status
1 | 2024-01-30 | Policy Documents | Following policies are expiring in February 2024. Please let us know if any changes are required in these policies. 1. Acceptable Use Policy 2. Information Security Policy 3. Code of Conduct Policy | Upload policies with No change | Tauseef | 2024-02-06 | Done
2 | 2024-01-30 | CyberSecurity | Rapid7 report is generating Login error on Report execution. | Resolved by running report multiple times | Tao | 2024-02-07 | Done
3 | 2024-01-30 | CyberSecurity | Resolve Vulnerability Issues | We will start work on this Task from February 28 | Abid | 2024-03-29 | In Progress
4 | 2024-01-30 | CyberSecurity | Penetration Testing Results will expire by July 12 Assign third party for Annual Penetration Testing | Reminder in May | Tauseef | 2024-05-01 | On Hold
5 | 2024-01-30 | Trainings | Put Trainings on Calender | Drata does not provide training expiry dates | Tauseef |  | Closed
6 | 2024-02-27 | Policy Documents | Following policies are expiring in March 2024. Please let us know if any changes are required in these policies. 1. Asset management Policy 2. Backup Policy 3. Data Classification Policy 4. Data Retention Policy 5. Data Protection Policy 6. Encryption Policy 7. Password Policy 8. System Access Control Policy 9. Vulnerability Management Policy 10. Incident Repsponse Plan | The policies will be uploaded with same version | Tauseef Shahzad | 2024-02-28 | Done
7 | 2024-02-27 | Expiring Evidences | Recently Advertised Job Descriptions | Arshad and Asiya will review the JDs | Arshad | 29/2/2024 | Done
8 | 2024-02-27 | Expiring Evidences | Nexelus Architectural Diagram | Asim will review Nexelus Architecture Diagram | Asim | 29/2/2024 | Done
9 | 2024-02-27 | Expiring Evidences | Nexelus Network Diagram | Peter will review Nexelus Network Diagram | Peter | 29/2/20224 | Open
10 | 2024-02-27 | Expiring Evidences | Risk Register | All Stake Holders will review Rise Register Update: Risk Register will be reviewed on Tuesday March 19, 2024 | Tauseef Shahzad | 19/3/2024 | Done
11 | 2024-02-27 | Expiring Evidences | Risk Assessment Report | Imran Rahman will review Risk Assessment Repe Report | Imran Rahman | 29/2/2024 | Open
12 | 2024-03-19 | Expiring Evidences | Orginizational Chart |  | Imran Rahman | 2024-04-02 | Open
13 | 2024-03-26 | Expiring Evidences | Disaster Recovery Exercise |  | Tao
15 | 2024-03-26 | Expiring Evidences | Internal Audit |  | Tauseef | 2024-04-30 | In Progress

## Sheet1
Vendor Portal
Add Naming Convention

## Codes (hidden)
Status | Ticket type | Fix Nature | Customers
Open | UI | Sp change | HealthStar
Development | Application Crash | ASPX | Pursuit
QA | Data Corruption | JS | 72 & sunny
Deployment | Report | DLL
Closed | user understanding | Data fix
On Hold | setup issue | NA
change request/text change
sp change
Java Script