## Consolidated
Project Profile
Period: September 2024 - June 2025
Project / | Task | Planned |  |  | Project Overhead | [5 empty] | Test | Code | Analysis | Design | Development Time |  |  | Testing |  |  | Bug Fixing Time |  |  | Total | Total
Release |  | Development | QA | Bug Fixing | Mgmt | Training | Meetings | Deployments | Document | Client Items | Cases | Review |  |  | Estimate | Actual | Difference | Planned | Actual | Variance | Planned | Actual | Variance | Planned | Hours
APWORKS 2024.2 - PHASE 3 | [17 empty] | 0 |  |  | 0
| Add Media Type/Service type/Roles | 4 | 8 |  |  |  | 4 |  |  |  | 11 |  | 2 |  | 4 |  |  | 8 | 70 | -62 | 0 |  |  | 12 | 87
| Google Drive integration. (Setup and Integration development) | 44 | 8 |  |  |  | 5 |  | 15 |  | 42 | 4 |  |  | 44 | 91 | -47 | 8 | 67.5 | -59.5 | 0 | 23 |  | 52 | 232.5
| Ability to automatically attach additional documents (tear sheets, afidavit) to the invoice | 30 | 20 |  |  |  | 11 |  |  |  | 44 |  | 1.5 |  | 30 | 31 | -1 | 20 | 49 | -29 | 0 | 8 |  | 50 | 144.5
| We need to read the company on the invoice document to route to the right company. If the company is not detected properly we will default to a company and mark it with a status. | 56 | 20 | [11 empty] | 56 |  |  | 20 |  |  | 0 |  |  | 76 | 0
| Broadcast Invoices | [16 empty] | 0 |  |  | 0 |  |  | 0 | 0
| We will need a separate node for "Broadcast Invoices" added at the end of Production Invoices. | 4 | [12 empty] | 4 | 8 | -4 | 0 |  |  | 0 |  |  | 4 | 8
| User Group management changes | 12 | [12 empty] | 12 |  |  | 0 |  |  | 0 |  |  | 12 | 0
| Dashboard | 16 | [12 empty] | 16 |  |  | 0 |  |  | 0 |  |  | 16 | 0
| Manage Invoice Documents | 4 | [12 empty] | 4 |  |  | 0 |  |  | 0 |  |  | 4 | 0
| Invoice List UI | 32 | [10 empty] | 2 |  | 32 | 2 | 30 | 0 |  |  | 0 |  |  | 32 | 4
| EDI file processing | 62 | 40 | [7 empty] | 6 | 13 | 2 |  | 62 | 37.5 | 24.5 | 40 | 52.5 | -12.5 | 0 |  |  | 102 | 111
| PDF file generation | 50 | 6 | [9 empty] | 5 |  | 50 | 28 | 22 | 6 | 10.5 | -4.5 | 0 |  |  | 56 | 43.5
| Invoice View UI | 30 | 12 | [8 empty] | 2 |  |  | 30 | 18 | 12 | 12 |  |  | 0 | 3 |  | 42 | 23
| Customer Information : Selection of the client on the vendor invoice header level. This will help route the invoice to the appropriate client team. - (Sync and a lookup field on invoice) | 16 | 4 | [9 empty] | 4.5 | 6 | 16 | 29 | -13 | 4 | 4 | 0 | 0 | 5 |  | 20 | 48.5
| We will need to introduce tolerance by media type. | 20 | [12 empty] | 20 |  |  | 0 |  |  | 0 |  |  | 20 | 0
| Read data from Media Ocean Jobs, IOs (buying), Customer Master, Vendor Master, Currencies, Tax codes, Payment terms, EDI?, payment information | 80 | 40 | [11 empty] | 80 |  |  | 40 |  |  | 0 |  |  | 120 | 0
| vendor/stations/sites can be associated to multiple pay to. EX: Bell Media is linked to Bill pay to | 32 | [12 empty] | 32 |  |  | 0 |  |  | 0 |  |  | 32 | 0
| Checkbox to filter discrepant lines | 8 | [12 empty] | 8 |  |  | 0 | 2 |  | 0 |  |  | 8 | 2
| Ability to assign Employees to Roles by Media type and by Client | 70 | 8 |  |  |  | 16 |  |  |  | 22 | 3 | 3 |  | 70 | 192 | -122 | 8 | 62 | -54 | 0 | 13 |  | 78 | 311
| Ability to automatically attach additional documents to Invoice | 30 | [15 empty] | 0 |  |  | 0 |  |  | 0 | 0
| Associate vendor/stations/sites to multiple pay to | 32 | [15 empty] | 0 |  |  | 0 |  |  | 0 | 0
| Enhancement in vendor mapping(Parse Table) | [16 empty] | 0 |  |  | 0 | 4 |  |  | 4
| Master Data: Payment Terms | [16 empty] | 0 |  |  | 0 |  |  | 0 | 0
| Switch Company on Invoice | [7 empty] | 1 |  |  |  | 4 | 13 |  | 31 |  | 0 | 12 |  | 0 |  |  | 0 | 60
| Route invoice from one company to another | 56 | [10 empty] | 2 |  |  | 14 |  | 0 |  |  | 0 | 9 |  | 0 | 25
| Vendor/stations/sites associated to multiple pay to. | 32 | [13 empty] | 8 |  | 0 | 31 |  | 0 | 2 |  | 0 | 41
| Apply discount based on Payment Terms Setting | [19 empty] | 0 | 4
| Project Overhead |  |  |  | 9 |  | 49 | 42 |  |  |  |  | 13.5 |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 113.5
| Documentation | [7 empty] | 1 | [11 empty] | 0
NEXELUS 2024.1 SP2 | [17 empty] | 0 |  |  | 0 |  |  |  | 0
| Project Overhead | [5 empty] | 12 |  | 17 |  |  |  | 4 |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 16
| Client Lines (New Lines, Generate Schedule) | 67 | 40 | 20 |  |  | 2.5 | [6 empty] | 35 | 67 | 30 | 37 | 40 |  |  | 20 |  |  |  | 67.5
| eConnect shell change to service | [11 empty] | 16 |  | 0 | 16 |  | 0 |  |  | 0 |  |  |  | 32
| Backup Table for vendor/client lines relationship | 38 | 12 | 8 | [10 empty] | 38 | 3 | 35 | 12 |  |  | 8 |  |  |  | 3
| Need to support UDF & naming convention fields in RFP (Bulksheet only) | [13 empty] | 0 |  |  | 0 |  |  | 0
| Vendor Portal Proposal | 76 |  | 24 | [10 empty] | 76 | 57 | 19 | 0 |  |  | 24
| Nexelus Export only on Proposal | 24 | 8 | 4 | [10 empty] | 24 |  |  | 8 |  |  | 4
| Nexelus RFP (Import/Export) | 68 | 24 | 16 | [10 empty] | 68 |  |  | 24 |  |  | 16
| Generate client lines based on media type | [13 empty] | 0 |  |  | 0 |  |  | 0
| Client Profile | 1 | [12 empty] | 1 |  |  | 0 |  |  | 0
| Level3 | 1 | [12 empty] | 1 |  |  | 0 |  |  | 0
| Media Plan Vendor lines (new, import/export) | 34 | 8 | 8 | [10 empty] | 34 |  |  | 8 |  |  | 8
| Client Lines (new line, generate schedule) | 67 | 40 | 20 | [10 empty] | 67 |  |  | 40 |  |  | 20
| Media Plan approval | 8 | 4 | 2 | [10 empty] | 8 |  |  | 4 |  |  | 2
| Media Plan: Import/Export Flighting | [13 empty] | 0 |  |  | 0 |  |  | 0
| Client Profile: Media > Flag to make the vendor inactive | 24 | 8 | 2 | [10 empty] | 24 |  |  | 8 |  |  | 2
| Custom field 3/AdServing able to take formulas (on hold) | [13 empty] | 0 |  |  | 0 |  |  | 0
| Mngt Fee renamable everywhere | 4 | 4 | 1 | [10 empty] | 4 |  |  | 4 |  |  | 1
| Separate broadcast label rename | [13 empty] | 0 |  |  | 0 |  |  | 0
| CHECK: tiered rate on new lines only or all lines? What happens if spend is added to a billed month. | [13 empty] | 0 |  |  | 0 |  |  | 0
0
AP WORKFLOW | [17 empty] | 0 |  |  | 0 |  |  |  | 0
| Analysis of the new project/assignment/task | [11 empty] | 5 |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 5
| Regular bug fixing activity | [16 empty] | 0 | 3 |  | 0 | 13 |  | 0 | 16
| Cient UAT Upgrade | [16 empty] | 0 |  |  | 0 | 22 |  | 0 | 22
| Client Items | [16 empty] | 0 |  |  | 0 |  |  | 0 | 0
| Internal Meetings | [5 empty] | 1 | [10 empty] | 0 |  |  | 0 |  |  | 0 | 1
| Analysis of production issues reported by support team | [16 empty] | 0 | 10 |  | 0 | 5 |  | 0 | 15
| QA Environment Upgrade | [6 empty] | 1 | [12 empty] | 0
| Release Environment Upgrade | [6 empty] | 6 | [12 empty] | 0
[18 empty] | 0 |  |  | 0 |  |  |  | 0
APWORKS PHASE2 | [17 empty] | 0 |  |  | 0 |  |  | 0 | 0
| Admin & Misc. | [5 empty] | 31 |  | 1 | [8 empty] | 0 |  |  | 0 |  |  |  | 31
| Analysis | [14 empty] | 6 |  | 0 |  |  | 0 |  |  | 0 | 6
| Bug Fixing | [16 empty] | 0 | 21 |  | 0 | 248 |  | 0 | 269
| Cient UAT Upgrad | [6 empty] | 10.5 |  | 11 | [7 empty] | 0 | 8 |  | 0 |  |  |  | 29.5
| Client Items | [16 empty] | 0 | 13 |  | 0 |  |  |  | 13
| Dev Support | [5 empty] | 1 | [10 empty] | 0 |  |  | 0 | 4 | -4 | 0 | 5
| Development DB | [14 empty] | 15 |  | 0 |  |  | 0 |  |  |  | 15
| Internal Meeting | [5 empty] | 34 | [10 empty] | 0 | 30 |  | 0 |  |  |  | 64
| Production Issue | [8 empty] | 15 |  |  | 11 |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 26
| QA | [16 empty] | 0 | 228.5 | -228.5 | 0 | 184 |  | 0 | 412.5
| QA Environment Upgrade | [16 empty] | 0 | 13 | -13 | 0 |  |  | 0 | 13
| Requirement Analysis | [16 empty] | 0 | 11 |  | 0 | 16 |  |  | 27
| Requirement Writing | [7 empty] | 18.5 | [8 empty] | 0 |  |  | 0 |  |  |  | 0
| Support Items | [5 empty] | 1 | [10 empty] | 0 |  |  | 0 |  |  |  | 1
NEXELUS 2024.2 | [17 empty] | 0 |  |  | 0 |  |  |  | 0
| Analysis of the new project/assignment/task | [11 empty] | 22 | 6 |  |  |  | 0 |  |  | 0 |  |  |  | 28
| Client Items | [5 empty] | 1 |  |  | 92 | [5 empty] | 2 |  | 0 |  |  | 0 |  |  |  | 95
| Development of new project/assignment/task | [14 empty] | 3 |  | 0 |  |  | 0 |  |  |  | 3
| Meetings, mails, communication, TFS, Interviews | [5 empty] | 3 | [10 empty] | 0 | 24 |  | 0 |  |  |  | 27
| Regular bug fixing activity | [14 empty] | 44 |  | 0 | 6 |  | 0 |  |  |  | 50
| Regular testing and QA new project/assignment/task | [16 empty] | 0 | 1 |  | 0 |  |  |  | 1
| Support Items | [8 empty] | 140 |  |  | 4 |  |  |  |  | 0 |  |  | 0 | 2 |  |  | 146
| Time Off - Planned | [16 empty] | 0 |  |  | 0 |  |  |  | 0
| Analysis of the new project/assignment/task | [11 empty] | 6 | 7 |  |  |  | 0 |  |  | 0 |  |  |  | 13
| Regular bug fixing activity | [16 empty] | 0 |  |  | 0 | 1 |  |  | 1
| Client Items | [8 empty] | 40 | [7 empty] | 0 |  |  | 0 |  |  |  | 40
| In-house Training | [5 empty] | 1 | [10 empty] | 0 |  |  | 0 |  |  |  | 1
| Analysis of production issues reported by support team | [11 empty] | 19 |  |  |  |  | 0 |  |  | 0 | 13 |  |  | 32
| Regular testing and QA new project/assignment/task | [7 empty] | 6 | [8 empty] | 0 |  |  | 0 |  |  |  | 0
| Document review/understanding Requirement Specifications | [7 empty] | 7 | [8 empty] | 0 |  |  | 0 |  |  |  | 0
| Support Items | [8 empty] | 148 | [7 empty] | 0 |  |  | 0 | 5 |  |  | 153
NEXELUS 2024.2 | [17 empty] | 0 |  |  | 0 |  |  |  | 0
PR-0013 | [17 empty] | 0 |  |  | 0 |  |  |  | 0
| Meetings, mails, communication, TFS, Interviews |  |  |  | 5 |  | 57 | [5 empty] | 23 |  |  |  |  | 0 |  |  | 0 |  |  |  | 85
| Cient UAT Upgrade | [11 empty] | 7 |  |  |  |  | 0 | 15 |  | 0 |  |  |  | 22
| Development of new project/assignment/task | [8 empty] | 63 | [7 empty] | 0 |  |  | 0 | 10 |  |  | 73
| In-house Training |  |  |  |  | 40 | [11 empty] | 0 |  |  | 0 |  |  |  | 0
| Internal Meetings | [5 empty] | 30 | [8 empty] | 3 |  | 0 |  |  | 0 | 2 |  |  | 35
| Analysis of production issues reported by support team |  |  |  | 2.7 |  | 27 |  |  | 26.5 |  |  | 35 |  |  |  |  | 0 | 5 |  | 0 |  |  |  | 96.2
| Session with US team | [16 empty] | 0 |  |  | 0 |  |  |  | 0
PR-0014 | [17 empty] | 0 |  |  | 0 |  |  |  | 0
| CI-DentsuCreativ | [8 empty] | 29 | [7 empty] | 0 |  |  | 0 |  |  |  | 29
| CI-HY | [8 empty] | 11 | [7 empty] | 0 |  |  | 0 |  |  |  | 11
| CI-JustGlobal | [8 empty] | 16 | [7 empty] | 0 |  |  | 0 |  |  |  | 16
| CI-PropelHealth | [8 empty] | 11 | [7 empty] | 0 |  |  | 0 |  |  |  | 11
| CI-TheShipyard | [8 empty] | 36 | [7 empty] | 0 |  |  | 0 |  |  |  | 36
[18 empty] | 0 |  |  | 0 |  |  |  | 0
[18 empty] | 0 |  |  | 0 |  |  |  | 0
[18 empty] | 0 |  |  | 0 |  |  |  | 0
[18 empty] | 0 |  |  | 0 |  |  |  | 0
Overall Performance |  | 1132 | 314 | 105 | 16.7 | 40 | 286.5 | 59.5 | 66.5 | 638.5 | 125 | 22 | 191.5 | 67 | 982 | 668.5 | -7.5 | 314 | 749 | -463 | 105 | 596 | -4 | 736 | 3352.2
Score Card of planned Activities (For Activities with both Planned and Actual Data)
[15 empty] | Plan - Actual (Development) |  |  | Plan - Actual (Testing) |  |  | Plan - Actual (Bug Fix) |  |  | Plan - Actual (Total)
[15 empty] | Planned | Actual | Diff | Planned | Actual | Diff | Planned | Actual | Diff | Planned | Actual | Diff
[15 empty] | 519 | 526.5 | -7.5 | 94 | 315.5 | -221.5 | 0 | 0 | 0 | 456 | 1015 | -559
[17 empty] | -1.445% |  |  | -235.6% |  |  | 100% |  |  | -122.6%
Note on T120: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is difference for tasks where estimate is provided and Actual Work is performed

## September 2024
Project Profile
Period: September 2024
Project / Release | Task | Planned |  |  | Project Overhead | [5 empty] | Test | Code | Analysis | Design | Development Time |  |  | Testing |  |  | Bug Fixing Time |  |  | Total | Total
|  | Development | QA | Bug Fixing | Mgmt | Training | Meetings | Deployments | Document | Client Items | Cases | Review |  |  | Estimate | Actual | Difference | Planned | Actual | Variance | Planned | Actual | Variance | Planned | Hours
APWORKS 2024.2 - PHASE 3 | [8 empty] | 1 | [15 empty] | 1
| Add Media Type/Service type/Roles | 4 | 8 | [7 empty] | 9 |  | 2 |  | 4 |  |  | 8 | [5 empty] | 12 | 11
| Google Drive integration. (Setup and Integration development) | 44 | 8 |  |  |  | 5 |  | 15 |  | 39 |  |  |  | 44 | 58 | -14 | 8 | [5 empty] | 52 | 117
| Ability to automatically attach additional documents (tear sheets, afidavit) to the invoice | 30 | 20 |  |  |  | 7 |  |  |  | 16 |  | 0.5 |  | 30 |  |  | 20 | [5 empty] | 50 | 23.5
| We need to read the company on the invoice document to route to the right company. If the company is not detected properly we will default to a company and mark it with a status. | 56 | 20 | [11 empty] | 56 |  |  | 20 | [5 empty] | 76 | 0
| Broadcast Invoices | [13 empty] | 0 |  |  | 0 | [5 empty] | 0 | 0
| We will need a separate node for "Broadcast Invoices" added at the end of Production Invoices. | 4 | [12 empty] | 4 | 8 | -4 | 0 | [5 empty] | 4 | 8
| User Group management changes | 12 | [12 empty] | 12 | 4 | 8 | 0 | [5 empty] | 12 | 4
| Dashboard | 16 | [12 empty] | 16 |  |  | 0 | [5 empty] | 16 | 0
| Manage Invoice Documents | 4 | [12 empty] | 4 | 2 | 2 | 0 | [5 empty] | 4 | 2
| Invoice List UI | 32 | [12 empty] | 32 |  |  | 0 | [5 empty] | 32 | 0
| EDI file processing | 62 | 40 | [11 empty] | 62 | 10.5 | 51.5 | 40 | [5 empty] | 102 | 10.5
| PDF file generation | 50 | 6 | [9 empty] | 5 |  | 50 | 5 | 45 | 6 | [5 empty] | 56 | 10
| Invoice View UI | 30 | 12 | [8 empty] | 2 |  |  | 30 | 16 | 14 | 12 | [5 empty] | 42 | 18
| Manage Non-Mapped Broadcast Invoices | [14 empty] | 2 | [8 empty] | 2
| Customer Information : Selection of the client on the vendor invoice header level. This will help route the invoice to the appropriate client team. - (Sync and a lookup field on invoice) | 16 | 4 | [9 empty] | 0.5 |  | 16 |  |  | 4 | [5 empty] | 20 | 0.5
| We will need to introduce tolerance by media type. | 20 | [12 empty] | 20 |  |  | 0 | [5 empty] | 20 | 0
| Read data from Media Ocean Jobs, IOs (buying), Customer Master, Vendor Master, Currencies, Tax codes, Payment terms, EDI?, payment information | 80 | 40 | [11 empty] | 80 |  |  | 40 | [5 empty] | 120 | 0
| vendor/stations/sites can be associated to multiple pay to. EX: Bell Media is linked to Bill pay to | 32 | [12 empty] | 32 |  |  | 0 | [5 empty] | 32 | 0
| Checkbox to filter discrepant lines | 8 | [12 empty] | 8 |  |  | 0 | [5 empty] | 8 | 0
| Ability to assign Employees to Roles by Media type and by Client | 70 | 8 |  |  |  | 16 |  |  |  | 19 |  | 3 |  | 70 | 112 | -42 | 8 | [5 empty] | 78 | 150
| Ability to automatically attach additional documents to Invoice | 30 | [12 empty] | 30 |  |  | 0 | [5 empty] | 30 | 0
| Associate vendor/stations/sites to multiple pay to | 32 | [10 empty] | 1 | 3 | 32 | 23 | 9 | 0 | [5 empty] | 32 | 27
| Enhancement in vendor mapping(Parse Table) | [13 empty] | 0 |  |  | 0 | [5 empty] | 0 | 0
| Master Data: Payment Terms | [13 empty] | 0 |  |  | 0 | [6 empty] | 0
| Switch Company on Invoice | [13 empty] | 0 |  |  | 0 | [6 empty] | 0
| Route invoice from one company to another | 56 | [10 empty] | 1 |  | 56 |  |  | 0 | [6 empty] | 1
| Vendor/stations/sites associated to multiple pay to. | 32 | [12 empty] | 32 |  |  | 0 | [6 empty] | 0
| Project Overhead |  |  |  | 1 |  | 20.5 | 2.5 |  |  |  |  | 4 |  | 0 |  |  | 0 | [6 empty] | 28
AP WORKFLOW | [14 empty] | 0 |  |  | 0 | [6 empty] | 0
| Analysis of the new project/assignment/task | [11 empty] | 5 |  | 0 |  |  | 0 | [5 empty] | 0 | 5
| Regular bug fixing activity | [13 empty] | 0 |  |  | 0 | 13 |  |  |  |  | 0 | 13
| Cient UAT Upgrade | [13 empty] | 0 |  |  | 0 | 4 |  |  |  |  | 0 | 4
| QA Environment Upgrade | [6 empty] | 1 | [6 empty] | 0 |  |  | 0 | [6 empty] | 1
| Release Environment Upgrade | [6 empty] | 6 | [6 empty] | 0 |  |  | 0 | [6 empty] | 6
APWORKS PHASE2 | [14 empty] | 0 |  |  | 0 | [5 empty] | 0 | 0
| Analysis of the new project/assignment/task | [13 empty] | 0 | 6 | -6 | 0 | [5 empty] | 0 | 6
| Dev Support | [5 empty] | 1 |  |  | 4 |  |  |  |  | 0 |  |  | 0 | [5 empty] | 0 | 5
| Meetings, mails, communication, TFS, Interviews | [5 empty] | 25 | [6 empty] | 1 | 0 |  |  | 0 | [5 empty] | 0 | 26
| Regular bug fixing activity | [13 empty] | 0 |  |  | 0 | 180 | -180 |  | 21 | -21 | 0 | 201
| Regular testing and QA new project/assignment/task | [13 empty] | 0 |  |  | 0 | 21 | -21 | 0 | 184 | -184 | 0 | 205
| Support Items | [5 empty] | 1 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1
NEXELUS 2024.2 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| Analysis of the new project/assignment/task | [11 empty] | 22 | 6 | 0 |  |  | 0 |  |  | 0 |  |  |  | 28
| Client Items | [5 empty] | 1 |  |  | 92 |  |  |  |  | 0 | 2 | -2 | 0 |  |  | 0 |  |  |  | 95
| Development of new project/assignment/task | [13 empty] | 0 | 3 | -3 | 0 |  |  | 0 |  |  |  | 3
| Meetings, mails, communication, TFS, Interviews | [5 empty] | 30 | [7 empty] | 0 |  |  | 0 | 30 | -30 | 0 |  |  |  | 60
| Regular bug fixing activity | [13 empty] | 0 | 44 | -44 | 0 | 6 | -6 | 0 |  |  |  | 50
| Regular testing and QA new project/assignment/task | [13 empty] | 0 |  |  | 0 | 194.5 | -194.5 | 0 |  |  |  | 194.5
| Analysis of production issues reported by support team | [8 empty] | 15 |  |  | 11
| QA Environment Upgrade | [17 empty] | 4 | -4
| Document review/understanding Requirement Specifications | [17 empty] | 11 | -11
| Requirement Specifications document writing | [7 empty] | 18.5
| Support Items | [5 empty] | 1 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 1
| Time Off - Planned | [13 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
PR-0013 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| Meetings, mails, communication, TFS, Interviews | [5 empty] | 51 | [5 empty] | 7.5 |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 58.5
| Cient UAT Upgrade | [8 empty] | 3.5 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 3.5
| Development of new project/assignment/task | [13 empty] | 0 | 28 |  | 0 | 35 | -35 | 0 |  |  |  | 63
| Internal Meetings | [7 empty] | 4 | [5 empty] | 0 | 11 |  | 0 |  |  | 0 |  |  |  | 15
| Analysis of production issues reported by support team | [11 empty] | 48 |  | 0 |  |  | 0 | 4 | -4 | 0 | 12 |  |  | 64
| Production upgrades | [6 empty] | 3 | [6 empty] | 0 |  |  | 0 | 10 | -10 | 0 |  |  |  | 13
| Session with US team | [5 empty] | 24.7 |  |  | 18.5 |  |  | 3 |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 46.2
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
[15 empty] | 0 |  |  | 0 | [6 empty] | 0
Overall Performance |  | 720 | 166 | 0 | 1 |  | 183.2 | 12.5 |  | 133 | 83 | 2 | 113.5 | 10 | 720 | 334.5 | 14.5 | 166 | 512.5 | -495.5 | 0 | 217 | -205 | 798 | 1581.2
Score Card of planned Activities (For Activities with Active Data)
[15 empty] | Plan - Actual (Development) |  |  | Plan - Actual (Testing) |  |  | Plan - Actual (Bug Fix) |  |  | Plan - Actual (Bug Fix)
[15 empty] | Planned | Actual | Diff | Planned | Actual | Diff | Planned | Actual | Diff | Planned | Actual | Diff
[15 empty] | 1028 | 573 | 455 | 166 | 512.5 | -346.5 | 0 | 0 | 0 | 1262 | 1962.7 | -700.7
Note on T75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is difference for tasks where estimate is provided and Actual Work is performed

## October 2024
Project Profile
Period: October 2024
Project / | Task | Planned |  |  | Project Overhead | [5 empty] | Test | Code | Analysis | Design | Development Time |  |  | Testing |  |  | Bug Fixing Time |  |  | Total | Total
Release |  | Development | QA | Bug Fixing | Mgmt | Training | Meetings | Deployments | Document | Client Items | Cases | Review |  |  | Estimate | Actual | Difference | Planned | Actual | Variance | Planned | Actual | Variance | Planned | Hours
APWORKS 2024.2 - PHASE 3 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| Ability to automatically attach additional documents to Invoice | 30 | 20 |  |  |  | 4 |  |  |  | 28 |  | 1 |  | 30 | 31 |  | 20 | 49 |  | 0 | 8 |  | 50 | 121
| Add Media Type/Service type/Roles | 4 | 8 |  |  |  | 4 |  |  |  | 2 |  |  |  | 4 |  |  | 8 | 70 |  | 0 |  |  | 12 | 76
| Ability to assign Employees to Roles by Media type and by Client | 70 | 8 | [7 empty] | 3 | 3 |  |  | 70 | 80 |  | 8 | 62 |  | 0 | 13 |  | 78 | 161
| Google Drive integration. (Setup and Integration development) | 44 | 8 |  |  |  | 15 |  |  |  | 3 | 4 | 7 |  | 44 | 33 |  | 8 | 67.5 |  | 0 | 23 |  | 52 | 152.5
| Project Overhead |  |  |  | 8 |  | 28.5 | 39.5 |  |  |  |  | 9.5 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 85.5
| Associate vendor/stations/sites to multiple pay to | 32 | [9 empty] | 2 |  |  | 32 | 12 |  | 0 |  |  | 0 | 10 |  | 32 | 24
| Broadcast Invoice | [13 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| EDI File Processing | 62 | 40 | [7 empty] | 6 | 13 | 2 |  | 62 | 27 |  | 40 | 52.5 |  | 0 |  |  | 102 | 100.5
| Invoice View UI | 30 | 12 | [11 empty] | 30 | 2 |  | 12 |  |  | 0 | 3 |  | 42 | 5
| PDF file generation | 50 | 6 | [11 empty] | 50 | 23 |  | 6 | 10.5 |  | 0 |  |  | 56 | 33.5
| Manage Invoice Documents | 4 | [12 empty] | 4 | 4 |  | 0 |  |  | 0 |  |  | 4 | 4
| Checkbox to filter discrepant lines | 8 | [12 empty] | 8 |  |  | 0 | 2 |  | 0 |  |  | 8 | 2
| Enhancement in vendor mapping(Parse Table) | [13 empty] | 0 |  |  | 0 |  |  | 0 | 4 |  |  | 4
| Master Data: Payment Terms | [13 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| Switch Company on Invoice | [7 empty] | 1 |  |  |  | 4 | 13 | 0 | 31 |  | 0 |  |  | 0 | 12 |  | 0 | 61
| Vendor Inv: Select Client on Header | [11 empty] | 3 | 6 | 0 | 25 |  | 0 |  |  | 0 | 2 |  | 0 | 36
| Customer Information: Select Client on Vendor Invoice | 16.4 | [10 empty] | 4 | 6 | 16.4 | 29 |  | 0 | 4 |  | 0 | 5 |  | 16.4 | 48
| Route invoice from one company to another | 56 | [10 empty] | 1 |  | 56 | 14 |  | 0 |  |  | 0 | 9 |  | 56 | 24
| Vendor/stations/sites associated to multiple pay to. | 32 | [12 empty] | 32 | 8 |  | 0 | 31 |  | 0 | 2 |  | 32 | 41
| Apply discount based on Payment terms settings | [17 empty] | 4
APWORKS PHASE2 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| Meetings, mails, communication, TFS, Interviews | [5 empty] | 6 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 6
| Regular bug fixing activity | [13 empty] | 0 |  |  | 0 |  |  | 0 | 68 |  |  | 68
| Cient UAT Upgrade | [6 empty] | 10.5 |  | 11 |  |  |  |  | 0 |  |  | 0 | 8 |  | 0 |  |  |  | 29.5
| Client Items | [13 empty] | 0 |  |  | 0 | 13 |  | 0 |  |  |  | 13
| Development of new project/assignment/task | [13 empty] | 0 | 15 |  | 0 |  |  | 0 |  |  |  | 15
| Internal Meetings | [5 empty] | 4 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 4
| Regular testing and QA new project/assignment/task | [13 empty] | 0 |  |  | 0 | 34 |  | 0 |  |  |  | 34
| QA Environment Upgrade | [13 empty] | 0 |  |  | 0 | 9 |  | 0 |  |  |  | 9
AP WORKFLOW | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| Regular bug fixing activity | [13 empty] | 0 |  |  | 0 | 3 |  | 0 |  |  | 0 | 3
| Internal Meetings | [5 empty] | 1 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1
| Analysis of production issues reported by support team | [13 empty] | 0 |  |  | 0 |  |  | 0 | 15 |  | 0 | 15
NEXELUS 2024.1 SP2 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| Project Overhead | [5 empty] | 12 |  | 17 |  |  |  | 4 |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 33
| Client Lines (New Lines, Generate Schedule) | 67 | 40 | 20 |  |  | 2.5 | [6 empty] | 35 | 67 | 30 |  | 40 |  |  | 20 |  |  |  | 67.5
| eConnect shell change to service | [11 empty] | 16 |  | 0 | 16 |  | 0 |  |  | 0 |  |  |  | 32
| Backup Table | 38 | 12 | 8 | [10 empty] | 38 | 3 |  | 12 |  |  | 8 |  |  |  | 3
NEXELUS 2024.2 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| Analysis of the new project/assignment/task | [11 empty] | 6 | 7 | 0 |  |  | 0 |  |  | 0 |  |  |  | 13
| Regular bug fixing activity | [13 empty] | 0 |  |  | 0 |  |  | 0 | 1 |  |  | 1
| Client Items | [8 empty] | 40 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 40
| Cient UAT Upgrade | [17 empty] | 4
| In-house Training | [5 empty] | 1 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 1
| Analysis of production issues reported by support team | [11 empty] | 19 |  | 0 |  |  | 0 |  |  | 0 | 13 |  |  | 32
| Regular testing and QA new project/assignment/task | [7 empty] | 6 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 6
| Document review/understanding Requirement Specifications | [7 empty] | 7 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 7
| Support Items | [8 empty] | 148 |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 5 |  |  | 153
PR-0013 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| Cient UAT Upgrade | [11 empty] | 7 |  | 0 |  |  | 0 | 15 |  | 0 |  |  |  | 22
| Development of new project/assignment/task | [8 empty] | 63 |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 10 |  |  | 73
| In-house Training |  |  |  |  | 40 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 40
| Internal Meetings | [5 empty] | 52 | [7 empty] | 0 | 3 |  | 0 |  |  | 0 | 2 |  |  | 57
| Analysis of production issues reported by support team | [11 empty] | 31 |  | 0 |  |  | 0 | 16 |  | 0 |  |  |  | 47
| Session with US team |  |  |  | 2.7 |  | 27 |  |  | 26.5 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 56.2
PR-0014 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| CI-DentsuCreativ | [8 empty] | 29 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 29
| CI-HY | [8 empty] | 11 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 11
| CI-JustGlobal | [8 empty] | 16 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 16
| CI-PropelHealth | [8 empty] | 11 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 11
| CI-TheShipyard | [8 empty] | 36 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 36
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
Overall Performance |  | 543.4 | 154 | 28 | 10.7 |  | 157 | 50 |  | 391.5 | 42 | 22 | 114.5 | 67 | 543.4 | 386 | 0 | 154 | 454.5 | 0 | 28 | 205 | 0 | 540.4 | 1963.2
Note on T71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is difference for tasks where estimate is provided and Actual Work is performed