## Project Performance
Project Performance Report
2025-07-08
|  |  |  | Resources |  |  | Planned Hours | [10 empty] | Accumulated Hours to Date | [10 empty] | Plan Vs
Key | Project |  | Status | Dev | DB | QA | Design | RS Review | Dev | DB | Review | Bug Fixing | Bug Review | Test Case | QA | QA Review | Total | Design | RS Review | Dev | DB | Review | Bug Fixing | Bug Review | Test Case | QA | QA Review |  | Actual | Start Date |  |  | End Date
[7 empty] | 140 | 80 | 602 | 340 | 71 | 156 | 9 | 76 | 207 | 26.5 | 1707.5 | 8 | 82.5 | 711.45 | 97.5 | 82.5 | 31.5 | 10.5 | 76.5 | 134 | 10.5 | 1101.05 | 606.45 | Planned | Actual |  | Planned | Actual
| ADHOC-ITEMS | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 |  |  |  |  | 9 |  | 36 | -36 | 0 | 2025-06-30 |  | 0 | 2025-07-14
ADHOC-ITEMS:Voucher, AP rule flag and 4 sided entry - v3 | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | [14 empty] | 0 |  |  |  | 20.5 |  |  |  |  | 9 |  | 29.5 | -29.5
ADHOC-ITEMS:No rates alert and error |  | No rates alert and error | [18 empty] | 6.5 | [7 empty] | 0 |  | 2025-06-30 |  |  | 2025-07-15
ADHOC-ITEMS:R&D on Report Server |  | R&D on Report Server | [26 empty] | 0 |  | 2025-07-14 |  |  | 2025-07-14
| APWORKS - TEST AUTOMATION | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 |  | 48 | [7 empty] | 56 | -56 | 0 | 2025-04-14 |  | 0 | 2025-04-16
APWORKS - TEST AUTOMATION:Media approval: approve invoices | APWORKS - TEST AUTOMATION | Media approval: approve invoices | [14 empty] | 0 |  |  | 24 | [7 empty] | 24 | -24
APWORKS - TEST AUTOMATION:Media: Discrepant Invoices - Make Corrections | APWORKS - TEST AUTOMATION | Media: Discrepant Invoices - Make Corrections | [14 empty] | 0 |  |  | 19 | [7 empty] | 19 | -19 |  | 2025-04-14 |  |  | 2025-04-16
APWORKS - TEST AUTOMATION:Media: Read Data diven excel files for the correspinding data | APWORKS - TEST AUTOMATION | Media: Read Data diven excel files for the correspinding data | [14 empty] | 0 | 8 | [9 empty] | 8 | -8 |  | 2025-04-25 |  |  | 2025-07-21
APWORKS - TEST AUTOMATION:Project Overhead | APWORKS - TEST AUTOMATION | Project Overhead |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 2025-04-30 |  |  | 2025-04-30
APWORKS - TEST AUTOMATION:Media: Validate and input data header fields |  | Media: Validate and input data header fields | [17 empty] | 5 | [8 empty] | 0 |  | 2025-05-19 |  |  | 2025-07-21
| APWORKS 2025.3 | [5 empty] | 94 | 30 | 330 | 66 | 35 | 46 | 9 | 38 | 79 | 16.5 | 743.5 |  | 52.5 | 290.9 | 32.5 | 52.5 | 28.5 | 10.5 | 42 | 89.5 | 10.5 | 609.4 | 134.1 | 0 | 2025-06-16 |  | 0 | 2025-06-27
APWORKS 2025.3:Flag an invoice in Discrepant bucket for searching |  | Flag an invoice in Discrepant bucket for searching | 100% | Ali | Yasir | Ayesha | 8 | 2 | 36 | 20 | 10 | 8 | 0 | 6 | 10 | 3 | 103 |  | 5 | 17 | 1 | 5 | 3 | 2 | 4 | 8 | 2 | 47 | 56 | 2025-06-17
APWORKS 2025.3:Hide Favorite button: Does not work ( Fix or hide) |  | Hide Favorite button: Does not work ( Fix or hide) | 100% | Arslan | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 4.5 |  |  | 8.7 | 4 |  |  |  |  | 4.5 |  | 17.2 | -12.7 | 2025-06-17 | 2025-06-20 | Early Start |  | 2025-07-24
APWORKS 2025.3:Manually mark invoice Archived |  | Manually mark invoice Archived | 50% | Asad | Yasir | Kashif | 8 | 8 | 48 | 24 | 8 | 16 | 0 | 12 | 30 | 4 | 158 |  | 4 | 54.2 | 22.5 | 4 | 3 |  | 9 | 29 |  | 125.7 | 32.3 | 2025-06-25 | 2025-06-23 | Early Start |  | 2025-07-25
APWORKS 2025.3:Net Amount Total: Add field in header to sum Invoice Net Amount |  | Net Amount Total: Add field in header to sum Invoice Net Amount | 100% | Arslan | 0 | Kashif | 4 | 2 | 24 | 6 | 2 | 2 | 1 | 4 | 6 | 1 | 52 |  | 2.5 | 9 | 3 | 2.5 | 6 |  | 5 | 11 |  | 39 | 13 | 2025-06-17 | 2025-06-23 | Early Start |  | 2025-07-25
APWORKS 2025.3:Project Overhead |  | Project Overhead | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 2025-06-20 | Early Start |  | 2025-07-24
APWORKS 2025.3:Rename Invoice amount to invoice net amount |  | Rename Invoice amount to invoice net amount | 0% | Arslan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2 | [7 empty] | 2 | -2 | 2025-06-17 | 2025-06-16 | Early Start |  | 2025-07-25
APWORKS 2025.3:Retain user-specific report views and filter preferences during |  | Retain user-specific report views and filter preferences during | 90% | Ali | 0 | Ayesha | 8 | 6 | 72 | 0 | 12 | 12 | 8 | 12 | 24 | 6 | 160 |  | 3.5 | 126.5 |  | 3.5 | 15.5 | 8.5 | 13 | 24 | 8.5 | 203 | -43 | 2025-06-17 | 2025-06-23 | Early Start |  | 2025-07-10
APWORKS 2025.3:Show routing history - Invoice comment log |  | Show routing history - Invoice comment log | 100% | Arslan | 0 | Kashif | 6 | 4 | 16 | 8 | 2 | 8 | 0 | 4 | 8 | 2 | 58 |  | 5.5 | 15.5 | 2 | 5.5 | 1 |  | 11 | 9 |  | 49.5 | 8.5 | 2025-06-17 | 2025-06-17 |  |  | 2025-07-25
APWORKS 2025.3:Upgrade ApWorks application to dotnet Core 8.0 from 7.0 |  | Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | 100% | Asad | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 |  |  | 13.5 | [7 empty] | 13.5 | 18.5 | 2025-06-24 | 2025-06-20 | Early Start |  | 2025-07-24
APWORKS 2025.3:eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) |  | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | 0% | Shoaib | Yasir | Ayesha | 60 | 8 | 100 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 176 |  | 32 | 44.5 |  | 32 | [5 empty] | 108.5 | 67.5 | 2025-06-19 | 2025-06-24 | Early Start |  | 2025-06-27
APWORKS 2025.3:Format all amounts to be trwo decimals |  | Format all amounts to be trwo decimals | 0% | Ali | 0 | Ayesha | 2 | 2 | 16 | 0 | 4 | 2 | 0 | 4 | 6 | 2 | [9 empty] | 4 |  |  | 0 | 2025-06-17
| NEXELUS 2025.3 | [5 empty] | 46 | 50 | 272 | 274 | 36 | 110 | 0 | 38 | 128 | 10 | 964 |  | 30 | 185.65 | 38 | 30 | 3 |  | 34.5 | 35.5 |  | 275.65 | 688.35 | 2025-07-24 | 2025-06-16 |  | 0 | 2025-06-27
NEXELUS 2025.3:DENTSU _ Implementing a custom upload error log in Excel |  | DENTSU _ Implementing a custom upload error log in Excel | 0% | Arslan | Arif | Hamza | 8 | 12 | 46 | 20 | 8 | 16 | 0 | 16 | 16 | 8 | 150 |  | 8.25 | 35.5 | 8 | 8.25 | 3 |  | 10 | 23.5 |  | 96.5 | 53.5 | 2025-08-19 |  |  | 2025-08-19
NEXELUS 2025.3:PO numbers to be appended automatically to campaign names |  | PO numbers to be appended automatically to campaign names | 0% | Abid, Muzamal | 0 | 0 | 6 | 6 | 24 | 0 | 6 | 6 | 0 | 4 | 8 | 0 | 60 |  | 6.75 | 37.25 |  | 6.75 |  |  |  | 5 |  | 55.75 | 4.25 | 2025-07-25 | 2025-06-30 | Early Start | 2025-07-25 | 2025-07-25
NEXELUS 2025.3:pre-populate objective field from media plan |  | pre-populate objective field from media plan | 0% | Arslan | Arif | Hamza | 8 | 12 | 40 | 10 | 2 | 10 | 0 | 6 | 8 | 2 | 98 |  | 8 | 5 | 6 | 8 |  |  | 7 |  |  | 34 | 64 |  | 2025-06-26 |  |  | 2025-07-18
NEXELUS 2025.3:Project Overhead |  | Project Overhead | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 |  | 2025-06-26 |  | 0 | 2025-07-10
NEXELUS 2025.3:Show old vs. new values on revision screens (Design and Rev) |  | Show old vs. new values on revision screens (Design and Rev) | 0% | Abid, Asim | 0 | 0 | 16 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 |  | 4 | 59.9 |  | 4 |  |  | 6.5 |  |  | 74.4 | -46.4 |  | 2025-06-16 |  | 2025-07-03 | 2025-07-24
NEXELUS 2025.3:Vulnerability Report |  | Vulnerability Report | 0% | Muzamal | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 |  |  | 8 | [5 empty] | 7 |  | 15 | 15 | 2025-07-25 | 2025-06-26 | Early Start | 2025-07-25 | 2025-07-25
NEXELUS 2025.3:Enable multiple media plans under one Bing IO |  | Enable multiple media plans under one Bing IO | 0% | Asim | Arif | Bilal | 8 | 8 | 100 | 40 | 20 | 40 | 0 | 12 | 40 | 0 | 268 |  | 3 | 1.5 | 7.5 | 3 |  |  | 6 |  |  | 21 | 247 | 2025-08-27 | 2025-06-23 | Early Start | 2025-08-27 | 2025-06-27
NEXELUS 2025.3:Show old vs. new values on revision screens - DV360 |  | Show old vs. new values on revision screens - DV360 | 0% | Shoaib | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 6 | 0 | 0 | 8 | 0 | 50 |  |  | 6 | [7 empty] | 6 | 44 | 2025-08-04 | 2025-07-08 | Early Start | 2025-08-04 | 2025-07-25
NEXELUS 2025.3:Show old vs. new values on revision screens - LinkedIn |  | Show old vs. new values on revision screens - LinkedIn | 0% | Abid | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 6 | 0 | 0 | 8 | 0 | 50 |  |  | 13 | [7 empty] | 13 | 37 | 2025-08-08 | 2025-07-17 | Early Start | 2025-08-08 | 2025-07-21
NEXELUS 2025.3:Show old vs. new values on revision screens - Meta |  | Show old vs. new values on revision screens - Meta | 0% | Shoaib | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 6 | 0 | 0 | 8 | 0 | 50 |  |  | 12 | [7 empty] | 12 | 38 | 2025-08-12 | 2025-07-18 | Early Start | 2025-08-12 | 2025-07-25
NEXELUS 2025.3:Show old vs. new values on revision screens - Twiter |  | Show old vs. new values on revision screens - Twiter | 0% | Muzamal | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 6 | 0 | 0 | 8 | 0 | 50 |  |  | 4 | [7 empty] | 4 | 46 | 2025-08-13 | 2025-07-14 | Early Start | 2025-08-13 | 2025-07-21
NEXELUS 2025.3:MC rates for PBG |  | MC rates for PBG | 0% | Abid | Arif | Bilal | 0 | 0 | 32 | 24 | 0 | 8 | 0 | 0 | 16 | 0 | 80 |  |  |  | 16.5 |  |  |  | 5 |  |  | 21.5 | 58.5 | 2025-08-01 | 2025-07-17 | Early Start | 2025-08-01 | 2025-07-22
NEXELUS 2025.3:Show old vs. new values on revision screens - TTD |  | Show old vs. new values on revision screens - TTD | 0% | Muzamal | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 6 | 0 | 0 | 8 | 0 | 50 |  |  | 3.5 | [7 empty] | 3.5 | 46.5 | 2025-07-24 | 2025-07-08 | Early Start | 2025-07-24 | 2025-07-23
NEXELUS 2025.3:Ability to toggle advantage campaign budget on/off via API |  | Ability to toggle advantage campaign budget on/off via API | 0% | Arslan | Arif | Hamza | 8 | 12 | 40 | 10 | 20 | 10 | 0 | 6 | 6 | 3 | [12 empty] | 0 | 2025-07-31 | 2025-07-18 | Early Start | 2025-07-31 | 2025-07-25
| NEXELUSAPP - MAUI | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 186.9 | [7 empty] | 124 | -124 | 0 | 2025-06-02 |  | 0 | 2025-06-20
NEXELUSAPP - MAUI:Auth Pages: Key Page |  | Auth Pages: Key Page | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [7 empty] | 18 | -18
NEXELUSAPP - MAUI:Auth Pages: Login Page + Flow |  | Auth Pages: Login Page + Flow | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 33 | [7 empty] | 33 | -33 |  | 2025-06-02 |  |  | 2025-06-20
NEXELUSAPP - MAUI:Project Overhead |  | Project Overhead | [14 empty] | 0 | [10 empty] | 0 | 0 |  | 2025-06-16 |  |  | 2025-07-04
NEXELUSAPP - MAUI:TimeSheet: Add New |  | TimeSheet: Add New | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 16 | [7 empty] | 16 | -16 |  | 2025-06-02 |  |  | 2025-07-10
NEXELUSAPP - MAUI:TimeSheet: Chart |  | TimeSheet: Chart | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 13 | [7 empty] | 13 | -13 |  | 2025-06-25 |  |  | 2025-07-03
NEXELUSAPP - MAUI:TimeSheet: Edit |  | TimeSheet: Edit | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2 | [7 empty] | 2 | -2 |  | 2025-07-02 |  |  | 2025-07-04
NEXELUSAPP - MAUI:TimeSheet: Main Page |  | TimeSheet: Main Page | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 29.75 | [7 empty] | 29.75 | -29.75 |  | 2025-06-25 |  |  | 2025-06-25
NEXELUSAPP - MAUI:TimeSheet: Pending Transaction |  | TimeSheet: Pending Transaction | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12.25 | [7 empty] | 12.25 | -12.25
NEXELUSAPP - MAUI:Expense: Add New |  | Expense: Add New | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 10.5 | [7 empty] | 10.5 | -10.5
NEXELUSAPP - MAUI:Expense: Assignment Page |  | Expense: Assignment Page | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 13.5 | [7 empty] | 13.5 | -13.5 |  | 2025-07-07 |  |  | 2025-07-25
NEXELUSAPP - MAUI:Expense: Main Page |  | Expense: Main Page | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16.9 | [7 empty] | 16.9 | -16.9 |  | 2025-07-07 |  |  | 2025-07-24
NEXELUSAPP - MAUI:Expense: Pending Expense Report |  | Expense: Pending Expense Report | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2.5 | [7 empty] | 2.5 | -2.5 |  | 2025-07-08 |  |  | 2025-07-18
NEXELUSAPP - MAUI:Expense: Permissions |  | Expense: Permissions | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [7 empty] | 9 | -9 |  | 2025-07-14 |  |  | 2025-07-14
NEXELUSAPP - MAUI:Expense: Storage Functionality |  | Expense: Storage Functionality | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6 | [7 empty] | 6 | -6 |  | 2025-07-10 |  |  | 2025-07-18
NEXELUSAPP - MAUI:Expense: Transactions Page + Nested listing |  | Expense: Transactions Page + Nested listing | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4.5 | [7 empty] | 4.5 | -4.5 |  | 2025-07-11 |  |  | 2025-07-21
[17 empty] | 0 | [10 empty] | 0
Formulas:
Start Date = MIN([Start Date, row below]:AF10)
Start Date = IFERROR(VLOOKUP([Key],'Project Estimate'!$A9:S137,5,FALSE),"")
End Date = MIN([End Date, row below]:AI10)
End Date = IFERROR(VLOOKUP([Key],'Project Estimate'!$A9:S137,5,FALSE),"")

## Working 1
Row Labels | Analysis | Design | Development | Documentation | Meetings | Planinng | Post_dep_fixes | Project Mgmt | SRS-Review | Task Domain | Task/Code Review | Test Case Dev | Testing | Bug Fixing | DB Dev | Deployment | No Workbench | Research | TFS | Bug Review | Support Tickets | Leave | Grand Total
ADHOC-ITEMS | 2 |  |  |  | 7 | [5 empty] | 7 |  | 9 |  | 27 |  |  | 4 |  |  |  |  | 56
Voucher, AP rule flag and 4 sided entry - v3 |  |  |  |  | 6 | [5 empty] | 7 |  | 9 |  | 20.5 | [7 empty] | 42.5
No rates alert and error |  |  |  |  | 1 | [9 empty] | 6.5 | [7 empty] | 7.5
R&D on Report Server | 2 | [16 empty] | 4 |  |  |  |  | 6
APWORKS - TEST AUTOMATION | 12 | 8 | 52 |  |  | 3 |  |  |  | 6 | [6 empty] | 2 | [5 empty] | 83
Media approval: approve invoices |  |  | 24 | [19 empty] | 24
Media: Discrepant Invoices - Make Corrections |  |  | 23 | [19 empty] | 23
Media: Read Data diven excel files for the correspinding data |  | 8 | [20 empty] | 8
Project Overhead | 12 |  |  |  |  | 3 |  |  |  | 6 | [6 empty] | 2 | [5 empty] | 23
Media: Validate and input data header fields |  |  | 5 | [19 empty] | 5
APWORKS 2025.3 | 51.5 |  | 290.9 | 1.5 | 70.3 | 17 | 40.2 | 16 | 52.5 | 24 | 11.5 | 42 | 89.5 | 28.5 | 32.5 | 15 | 2 | 49 |  | 10.5 | 0.5 |  | 844.9
Flag an invoice in Discrepant bucket for searching |  |  | 17 |  | 2.5 |  |  |  | 5 |  |  | 4 | 8 | 3 | 1 |  |  |  |  | 2 |  |  | 42.5
Hide Favorite button: Does not work ( Fix or hide) |  |  | 8.7 |  | 1.5 | [7 empty] | 4.5 |  | 4 | [7 empty] | 18.7
Manually mark invoice Archived |  |  | 54.2 |  | 5 |  |  |  | 4 |  |  | 9 | 29 | 3 | 22.5 | [7 empty] | 126.7
Net Amount Total: Add field in header to sum Invoice Net Amount |  |  | 9 |  | 3.5 |  |  |  | 2.5 |  | 3 | 5 | 11 | 6 | 3 | [7 empty] | 43
Project Overhead | 8.5 |  |  |  | 44.3 | 17 | 40.2 | 16 |  | 24 | [5 empty] | 15 | 2 | 5 |  |  | 0.5 |  | 172.5
Rename Invoice amount to invoice net amount |  |  | 2 |  | 1 | [17 empty] | 3
Retain user-specific report views and filter preferences during |  |  | 126.5 |  | 1.5 |  |  |  | 3.5 |  | 2 | 13 | 24 | 15.5 |  |  |  | 2 |  | 8.5 |  |  | 196.5
Show routing history - Invoice comment log |  |  | 15.5 |  | 2.5 |  |  |  | 5.5 |  | 2.5 | 11 | 9 | 1 | 2 | [7 empty] | 49
Upgrade ApWorks application to dotnet Core 8.0 from 7.0 |  |  | 13.5 | [19 empty] | 13.5
eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | 43 |  | 44.5 | 1.5 | 8.5 |  |  |  | 32 |  | 4 | [6 empty] | 42 |  |  |  |  | 175.5
Format all amounts to be trwo decimals | [12 empty] | 4 | [9 empty] | 4
NEXELUS 2025.3 | 14.5 |  | 214.65 | 6.5 | 22.75 | 11 | 4 | 17.5 | 30 | 24 | 5.5 | 34.5 | 35.5 | 3 | 38 | 3 | 3 | 3.5 | 9 |  | 7 | 8 | 494.9
DENTSU _ Implementing a custom upload error log in Excel |  |  | 35.5 |  | 11.25 |  |  |  | 8.25 |  | 3.5 | 10 | 23.5 | 3 | 8 | [7 empty] | 103
PO numbers to be appended automatically to campaign names |  |  | 37.25 | [5 empty] | 6.75 |  | 2 |  | 5 | [9 empty] | 51
pre-populate objective field from media plan |  |  | 5 |  | 2 |  |  |  | 8 |  |  | 7 |  |  | 6 | [7 empty] | 28
Project Overhead | 14.5 |  |  | 6.5 | 5 | 11 | 4 | 17.5 |  | 24 | [5 empty] | 3 | 3 | 3.5 | 9 |  | 7 |  | 108
Show old vs. new values on revision screens (Design and Rev) |  |  | 71.9 |  | 3.5 |  |  |  | 4 |  |  | 6.5 | [10 empty] | 85.9
Vulnerability Report |  |  | 8 | [9 empty] | 7 | [9 empty] | 15
Enable multiple media plans under one Bing IO |  |  | 12 | [5 empty] | 3 |  |  | 6 |  |  | 7.5 | [7 empty] | 28.5
Show old vs. new values on revision screens - DV360 |  |  | 6 | [19 empty] | 6
Show old vs. new values on revision screens - LinkedIn |  |  | 18.5 |  | 0.5 | [17 empty] | 19
Show old vs. new values on revision screens - Meta |  |  | 12 | [19 empty] | 12
Show old vs. new values on revision screens - Twiter |  |  | 4 | [19 empty] | 4
MC rates for PBG | [11 empty] | 5 |  |  | 16.5 | [7 empty] | 21.5
Show old vs. new values on revision screens - TTD |  |  | 4.5 |  | 0.5 | [17 empty] | 5
NEXELUSAPP - MAUI | 19 |  | 195.4 | 14.5 | 2.25 | [17 empty] | 231.15
Auth Pages: Key Page |  |  | 18 | [19 empty] | 18
Auth Pages: Login Page + Flow |  |  | 33 | [19 empty] | 33
Project Overhead | 19 |  |  | 14.5 | 1 | [17 empty] | 34.5
TimeSheet: Add New |  |  | 16 | [19 empty] | 16
TimeSheet: Chart |  |  | 13 | [19 empty] | 13
TimeSheet: Edit |  |  | 2 | [19 empty] | 2
TimeSheet: Main Page |  |  | 29.75 | [19 empty] | 29.75
TimeSheet: Pending Transaction |  |  | 12.25 | [19 empty] | 12.25
Expense: Add New |  |  | 14 |  | 1.25 | [17 empty] | 15.25
Expense: Assignment Page |  |  | 18.5 | [19 empty] | 18.5
Expense: Main Page |  |  | 16.9 | [19 empty] | 16.9
Expense: Pending Expense Report |  |  | 2.5 | [19 empty] | 2.5
Expense: Permissions |  |  | 9 | [19 empty] | 9
Expense: Storage Functionality |  |  | 6 | [19 empty] | 6
Expense: Transactions Page + Nested listing |  |  | 4.5 | [19 empty] | 4.5
Grand Total | 99 | 8 | 752.95 | 22.5 | 102.3 | 31 | 44.2 | 33.5 | 82.5 | 54 | 24 | 76.5 | 134 | 31.5 | 97.5 | 18 | 7 | 56.5 | 9 | 10.5 | 7.5 | 8 | 1709.95

## Project Estimate
|  |  | Dev |  |  | Resources |  |  | Planned Hours
Key | Project |  | Start Date | End Date | Status | Dev | DB | QA | Design | RS Review | Dev | DB | Review | Bug Fixing | Bug Review | Test Case | QA | QA Review
ADHOC-ITEMS
ADHOC-ITEMS:Flag an invoice in Discrepant bucket for searching | ADHOC-ITEMS | Troubleshoot RM/PM in Nexelus Timesheet | 2025-01-01 |  | 50%
ADHOC-ITEMS:Format all amounts to be trwo decimals | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | 2025-01-01 |  | 50%
ADHOC-ITEMS:Hide Favorite button: Does not work ( Fix or hide) |  | No rates alert and error | 2025-05-07
ADHOC-ITEMS:Manually mark invoice Archived |  | R&D on Report Server | 1901-08-10
APWORKS - TEST AUTOMATION
APWORKS - TEST AUTOMATION:Manually mark invoice Archived | APWORKS - TEST AUTOMATION | Media approval: approve invoices |  |  | 0%
APWORKS - TEST AUTOMATION:Net Amount Total: Add field in header to sum Invoice Net Amount | APWORKS - TEST AUTOMATION | Media approval: identify approval access |  |  | 0%
APWORKS - TEST AUTOMATION:Project Overhead | APWORKS - TEST AUTOMATION | Media Approval: Re-login from user with access for approval |  |  | 0%
APWORKS - TEST AUTOMATION:Reintroduce the Invoice Number option in Vendor Mapping | APWORKS - TEST AUTOMATION | Media: Discrepant Invoices - Make Corrections |  |  | 0%
APWORKS - TEST AUTOMATION:Rename Invoice amount to invoice net amount | APWORKS - TEST AUTOMATION | Media: Make Corrections and save- Proceed to approval section |  |  | 0%
APWORKS - TEST AUTOMATION:Retain user-specific report views and filter preferences during | APWORKS - TEST AUTOMATION | Media: Read Data diven excel files for the correspinding data |  |  | 0%
APWORKS - TEST AUTOMATION:Show routing history - Invoice comment log | APWORKS - TEST AUTOMATION | Media: Replace invoice |  |  | 0%
APWORKS - TEST AUTOMATION:Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | APWORKS - TEST AUTOMATION | Media: Route to Employee |  |  | 0%
APWORKS - TEST AUTOMATION:QA Iteration 2 | APWORKS - TEST AUTOMATION | Media: Validate and input data details lines and fields |  |  | 0%
APWORKS - TEST AUTOMATION: | APWORKS - TEST AUTOMATION | Media: Validate and input data header fields |  |  | 0%
APWORKS - TEST AUTOMATION:Ability to toggle advantage campaign budget on/off via API | APWORKS - TEST AUTOMATION | Project Overhead |  |  | 0%
APWORKS 2025.3
APWORKS 2025.3:Ability to control Email alerts | APWORKS 2025.3 | Ability to control Email alerts | 2025-07-23 |  | 100% | Ali |  | Ayesha |  |  | 4 |  | 2 |  |  |  | 2 | 1
APWORKS 2025.3:Flag an invoice in Discrepant bucket for searching | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | 2025-06-17 | 2025-07-21 | 100% | Ali | Yasir | Ayesha | 8 | 2 | 36 | 20 | 10 | 8 |  | 6 | 10 | 3
APWORKS 2025.3:Format all amounts to be trwo decimals | APWORKS 2025.3 | Format all amounts to be trwo decimals | 2025-06-17 | 2025-07-25 |  | Ali |  | Ayesha | 2 | 2 | 16 |  | 4 | 2 |  | 4 | 6 | 2
APWORKS 2025.3:Hide Favorite button: Does not work ( Fix or hide) | APWORKS 2025.3 | Hide Favorite button: Does not work ( Fix or hide) | 2025-06-17 | 2025-07-18 | 100% | Arslan |  |  |  |  | 2 |  | 1 |  |  |  | 1 | 0.5
APWORKS 2025.3:Manually mark invoice Archived | APWORKS 2025.3 | Manually mark invoice Archived | 2025-06-25 | 2025-07-24 | 50% | Asad | Yasir | Kashif | 8 | 8 | 48 | 24 | 8 | 16 |  | 12 | 30 | 4
APWORKS 2025.3:Net Amount Total: Add field in header to sum Invoice Net Amount | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | 2025-06-17 | 2025-07-11 | 100% | Arslan |  | Kashif | 4 | 2 | 24 | 6 | 2 | 2 | 1 | 4 | 6 | 1
APWORKS 2025.3:Project Overhead | APWORKS 2025.3 | Project Overhead
APWORKS 2025.3:Reintroduce the Invoice Number option in Vendor Mapping | APWORKS 2025.3 | Reintroduce the Invoice Number option in Vendor Mapping |  |  | 0%
APWORKS 2025.3:Rename Invoice amount to invoice net amount | APWORKS 2025.3 | Rename Invoice amount to invoice net amount | 2025-06-17 | 2025-07-02 | 0% | Arslan
APWORKS 2025.3:Retain user-specific report views and filter preferences during | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | 2025-06-17 | 2025-07-11 | 90% | Ali |  | Ayesha | 8 | 6 | 72 |  | 12 | 12 | 8 | 12 | 24 | 6
APWORKS 2025.3:Show routing history - Invoice comment log | APWORKS 2025.3 | Show routing history - Invoice comment log | 2025-06-17 | 2025-07-08 | 100% | Arslan |  | Kashif | 6 | 4 | 16 | 8 | 2 | 8 |  | 4 | 8 | 2
APWORKS 2025.3:Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | APWORKS 2025.3 | Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | 2025-06-24 | 2025-07-01 | 100% | Asad |  |  |  |  | 32
APWORKS 2025.3:eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) |  | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | 2025-06-19 | 2025-11-05 | 0% | Shoaib | Yasir | Ayesha | 60 | 8 | 100 | 8
APWORKS 2025.3:QA Iteration 2 | APWORKS 2025.3 | QA Iteration 2 | 2025-08-20 |  | 0% | Muzamal, Shoaib | Arif | Bilal, Hamza | [5 empty] | 160 | 80
NEXELUS 2025.3
NEXELUS 2025.3:Ability to toggle advantage campaign budget on/off via API | NEXELUS 2025.3 | Ability to toggle advantage campaign budget on/off via API | 2025-06-30 | 2025-07-31 | 0% | Arslan | Arif | Hamza | 8 | 12 | 40 | 10 | 20 | 10 |  | 6 | 6 | 3
NEXELUS 2025.3:Add KPI input fields for all metric types, not just Viewability | NEXELUS 2025.3 | Add KPI input fields for all metric types, not just Viewability | 2025-06-30 | 2025-08-05 | 0% | Muzamal |  | Hamza | 4 | 6 | 16 |  | 2 | 4 |  | 6 | 4
NEXELUS 2025.3:DENTSU _ Implementing a custom upload error log in Excel | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | 2025-07-01 | 2025-08-19 | 0% | Arslan | Arif | Hamza | 8 | 12 | 46 | 20 | 8 | 16 |  | 16 | 16 | 8
NEXELUS 2025.3:Enable multiple media plans under one Bing IO | NEXELUS 2025.3 | Enable multiple media plans under one Bing IO | 2025-07-03 | 2025-08-27 | 0% | Asim | Arif | Bilal | 8 | 8 | 100 | 40 | 20 | 40 |  | 12 | 40
NEXELUS 2025.3:PO numbers to be appended automatically to campaign names | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | 2025-06-27 | 2025-07-25 | 0% | Abid, Muzamal |  |  | 6 | 6 | 24 |  | 6 | 6 |  | 4 | 8
NEXELUS 2025.3:pre-populate objective field from media plan | NEXELUS 2025.3 | pre-populate objective field from media plan | 2025-06-30 |  | 0% | Arslan | Arif | Hamza | 8 | 12 | 40 | 10 | 2 | 10 |  | 6 | 8 | 2
NEXELUS 2025.3:Project Overhead | NEXELUS 2025.3 | Project Overhead
NEXELUS 2025.3:Push Package as Campaign Group | NEXELUS 2025.3 | Push Package as Campaign Group
NEXELUS 2025.3:Push placements as Meta ad sets | NEXELUS 2025.3 | Push placements as Meta ad sets
NEXELUS 2025.3:Show old vs. new values on revision screens | NEXELUS 2025.3 | Show old vs. new values on revision screens | 2025-06-30 | 2025-08-15
NEXELUS 2025.3:Show old vs. new values on revision screens (Design and Rev) | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | 2025-06-30 | 2025-07-03 | 0% | Abid, Asim |  |  | 16 | 12
NEXELUS 2025.3:Show old vs. new values on revision screens - DB Tasks | NEXELUS 2025.3 | Show old vs. new values on revision screens - DB Tasks | 2025-08-05 | 2025-08-13 | 0% |  | Arif |  |  |  |  | 20
NEXELUS 2025.3:Show old vs. new values on revision screens - DV360 | NEXELUS 2025.3 | Show old vs. new values on revision screens - DV360 | 2025-07-28 | 2025-08-04 | 0% | Shoaib | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - TTD | NEXELUS 2025.3 | Show old vs. new values on revision screens - TTD | 2025-07-14 | 2025-07-24 | 0% | Muzamal | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - Twiter | NEXELUS 2025.3 | Show old vs. new values on revision screens - Twiter | 2025-08-05 | 2025-08-13 | 0% | Muzamal | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - LinkedIn | NEXELUS 2025.3 | Show old vs. new values on revision screens - LinkedIn | 2025-07-30 | 2025-08-08 | 0% | Abid | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - Meta | NEXELUS 2025.3 | Show old vs. new values on revision screens - Meta | 2025-08-06 | 2025-08-12 | 0% | Shoaib | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - IPC BingAd | NEXELUS 2025.3 | Show old vs. new values on revision screens - IPC BingAd | 2025-07-22 | 2025-07-24 | 0% | Shoaib | [5 empty] | 12
NEXELUS 2025.3:Show old vs. new values on revision screens - IPC DV360 | NEXELUS 2025.3 | Show old vs. new values on revision screens - IPC DV360 | 2025-07-24 | 2025-04-28 | 0% | Shoaib | [5 empty] | 12
NEXELUS 2025.3:Show old vs. new values on revision screens - IPC Meta | NEXELUS 2025.3 | Show old vs. new values on revision screens - IPC Meta | 2025-08-04 | 2025-08-06 | 0% | Shoaib | [5 empty] | 12
NEXELUS 2025.3:Show old vs. new values on revision screens - Test Cases | NEXELUS 2025.3 | Show old vs. new values on revision screens - Test Cases | 2025-07-03 | 2025-07-09 | 0% |  |  | Hamza | [7 empty] | 24
NEXELUS 2025.3:Show old vs. new values on revision screens - QA Review | NEXELUS 2025.3 | Show old vs. new values on revision screens - QA Review | 2025-07-24 | 2025-08-06 | 0% |  |  | Bilal | [9 empty] | 40
NEXELUS 2025.3:Show old vs. new values on revision screens - Review and Manage | NEXELUS 2025.3 | Show old vs. new values on revision screens - Review and Manage | 2025-08-05 | 2025-08-15 | 0% | Abid | [6 empty] | 40
NEXELUS 2025.3:Vulnerability Report | NEXELUS 2025.3 | Vulnerability Report | 2025-06-27 | 2025-07-25 | 0% | Muzamal |  |  |  |  | 30
NEXELUS 2025.3:MC rates for PBG | NEXELUS 2025.3 | MC rates for PBG | 2025-07-14 | 2025-08-01 | 0% | Abid | Arif | Bilal |  |  | 32 | 24 |  | 8 |  |  | 16
NEXELUS 2025.3:QA Iteration 2 | NEXELUS 2025.3 | QA Iteration 2 | 2025-08-27 | 2025-09-05 | 0% | Asad |  | Bilal, Kashif | [5 empty] | 40 | 80
NEXELUSAPP - MAUI
NEXELUSAPP - MAUI:Auth Pages: Key Page | NEXELUSAPP - MAUI | Auth Pages: Key Page |  |  | 100%
NEXELUSAPP - MAUI:Auth Pages: Login Page + Flow | NEXELUSAPP - MAUI | Auth Pages: Login Page + Flow |  |  | 50%
NEXELUSAPP - MAUI:TimeSheet: Main Page | NEXELUSAPP - MAUI | TimeSheet: Main Page |  |  | 100%
NEXELUSAPP - MAUI:TimeSheet: Chart | NEXELUSAPP - MAUI | TimeSheet: Chart |  |  | 100%
NEXELUSAPP - MAUI:TimeSheet: Add New | NEXELUSAPP - MAUI | TimeSheet: Add New |  |  | 100%
NEXELUSAPP - MAUI:TimeSheet: Edit | NEXELUSAPP - MAUI | TimeSheet: Edit |  |  | 100%
NEXELUSAPP - MAUI:TimeSheet: Pending Transaction | NEXELUSAPP - MAUI | TimeSheet: Pending Transaction |  |  | 100%
NEXELUSAPP - MAUI:Expense: Main Page | NEXELUSAPP - MAUI | Expense: Main Page |  |  | 100%
NEXELUSAPP - MAUI:Expense: Add New | NEXELUSAPP - MAUI | Expense: Add New |  |  | 80%
NEXELUSAPP - MAUI:Expense: Transactions Page + Nested listing | NEXELUSAPP - MAUI | Expense: Transactions Page + Nested listing |  |  | 0%
NEXELUSAPP - MAUI:Expense: Assignment Page | NEXELUSAPP - MAUI | Expense: Assignment Page
NEXELUSAPP - MAUI:Expense: Storage Functionality | NEXELUSAPP - MAUI | Expense: Storage Functionality
NEXELUSAPP - MAUI:Expense: Permissions | NEXELUSAPP - MAUI | Expense: Permissions
NEXELUSAPP - MAUI:Expense: Pending Expense Report | NEXELUSAPP - MAUI | Expense: Pending Expense Report
NEXELUSAPP - MAUI:Time Approval: Main Page | NEXELUSAPP - MAUI | Time Approval: Main Page
NEXELUSAPP - MAUI:Time Approval: 1st listing page | NEXELUSAPP - MAUI | Time Approval: 1st listing page
NEXELUSAPP - MAUI:Time Approval: Transaction details | NEXELUSAPP - MAUI | Time Approval: Transaction details
NEXELUSAPP - MAUI:Time Approval: Comment Popup | NEXELUSAPP - MAUI | Time Approval: Comment Popup
NEXELUSAPP - MAUI:Expense Approval: Main Page | NEXELUSAPP - MAUI | Expense Approval: Main Page
NEXELUSAPP - MAUI:Expense Approval: 1st listing page | NEXELUSAPP - MAUI | Expense Approval: 1st listing page
NEXELUSAPP - MAUI:Expense Approval: 2nd listing page | NEXELUSAPP - MAUI | Expense Approval: 2nd listing page
NEXELUSAPP - MAUI:Expense Approval: 3rd listing page | NEXELUSAPP - MAUI | Expense Approval: 3rd listing page
NEXELUSAPP - MAUI:Expense Approval: Transaction details | NEXELUSAPP - MAUI | Expense Approval: Transaction details
NEXELUSAPP - MAUI:Expense Approval: Comment Popup | NEXELUSAPP - MAUI | Expense Approval: Comment Popup
NEXELUSAPP - MAUI:Expense Approval: Pending Expense report | NEXELUSAPP - MAUI | Expense Approval: Pending Expense report
NEXELUSAPP - MAUI:Common Pages: Notification Page | NEXELUSAPP - MAUI | Common Pages: Notification Page
NEXELUSAPP - MAUI:Common Pages: Profile Page | NEXELUSAPP - MAUI | Common Pages: Profile Page
NEXELUSAPP - MAUI:Common Pages: User Settings | NEXELUSAPP - MAUI | Common Pages: User Settings
NEXELUSAPP - MAUI:Common Pages: Pending Expense Report | NEXELUSAPP - MAUI | Common Pages: Pending Expense Report
NEXELUSAPP - MAUI:API and Logic : Removal of deprecated Controls + Apis | NEXELUSAPP - MAUI | API and Logic : Removal of deprecated Controls + Apis
NEXELUSAPP - MAUI:API and Logic : App Icons and Splash Changes | NEXELUSAPP - MAUI | API and Logic : App Icons and Splash Changes
NEXELUSAPP - MAUI:API and Logic : IOS Related Issues and fixing | NEXELUSAPP - MAUI | API and Logic : IOS Related Issues and fixing
NEXELUSAPP - MAUI:API and Logic : Notifications Support + Flow | NEXELUSAPP - MAUI | API and Logic : Notifications Support + Flow
NEXELUSAPP - MAUI:API and Logic : Handlers + Other Services | NEXELUSAPP - MAUI | API and Logic : Handlers + Other Services
NEXELUSAPP - MAUI:API and Logic : OkTA Login, Tesseract | NEXELUSAPP - MAUI | API and Logic : OkTA Login, Tesseract
NEXELUSAPP - MAUI
Formulas:
Dev = MIN([Dev, row below]:D59)
End Date = MAX([End Date, row below]:E59)

## Data
employee | level2_key | level3_description | task_code | appliedmonth | Hours
Abid Ali | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Analysis | 2025-06 | 3
Abid Ali | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Documentation | 2025-07 | 1.5
Abid Ali | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | SRS-Review | 2025-07 | 8
Abid Ali | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Task/Code Review | 2025-07 | 1
Abid Ali | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | SRS-Review | 2025-06 | 1
Abid Ali | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | SRS-Review | 2025-06 | 1
Abid Ali | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Task/Code Review | 2025-06 | 1
Abid Ali | APWORKS 2025.3 | Project Overhead | Deployment | 2025-07 | 9.5
Abid Ali | APWORKS 2025.3 | Project Overhead | Planinng | 2025-06 | 11
Abid Ali | APWORKS 2025.3 | Project Overhead | Planinng | 2025-07 | 6
Abid Ali | APWORKS 2025.3 | Project Overhead | Project Mgmt | 2025-06 | 4
Abid Ali | APWORKS 2025.3 | Project Overhead | Project Mgmt | 2025-07 | 12
Abid Ali | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | SRS-Review | 2025-06 | 0.5
Abid Ali | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Task/Code Review | 2025-07 | 2
Abid Ali | APWORKS 2025.3 | Show routing history - Invoice comment log | SRS-Review | 2025-06 | 0.5
Abid Ali | APWORKS 2025.3 | Show routing history - Invoice comment log | Task/Code Review | 2025-06 | 1
Abid Ali | APWORKS 2025.3 | Show routing history - Invoice comment log | Task/Code Review | 2025-07 | 1.5
Abid Ali | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | Task/Code Review | 2025-07 | 3
Abid Ali | NEXELUS 2025.3 | Enable multiple media plans under one Bing IO | SRS-Review | 2025-07 | 2
Abid Ali | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | SRS-Review | 2025-06 | 1
Abid Ali | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | SRS-Review | 2025-07 | 1
Abid Ali | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | Task/Code Review | 2025-07 | 2
Abid Ali | NEXELUS 2025.3 | pre-populate objective field from media plan | SRS-Review | 2025-06 | 1
Abid Ali | NEXELUS 2025.3 | pre-populate objective field from media plan | SRS-Review | 2025-07 | 1
Abid Ali | NEXELUS 2025.3 | Project Overhead | Planinng | 2025-06 | 9
Abid Ali | NEXELUS 2025.3 | Project Overhead | Project Mgmt | 2025-07 | 4.5
Abid Ali | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | SRS-Review | 2025-06 | 1.5
Abid Ali | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | SRS-Review | 2025-07 | 1
Abid Ali | NEXELUSAPP - MAUI | Project Overhead | Meetings | 2025-07 | 1
Aimen nasar | NEXELUS 2025.3 | Enable multiple media plans under one Bing IO | Development | 2025-07 | 5
Aimen nasar | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | Development | 2025-07 | 2
Aimen nasar | NEXELUS 2025.3 | Show old vs. new values on revision screens - DV360 | Development | 2025-07 | 4
Aimen nasar | NEXELUS 2025.3 | Show old vs. new values on revision screens - LinkedIn | Development | 2025-07 | 6
Aimen nasar | NEXELUS 2025.3 | Show old vs. new values on revision screens - Meta | Development | 2025-07 | 10
Aimen nasar | NEXELUS 2025.3 | Show old vs. new values on revision screens - Twiter | Development | 2025-07 | 2
Aimen nasar | NEXELUSAPP - MAUI | Auth Pages: Key Page | Development | 2025-06 | 13
Aimen nasar | NEXELUSAPP - MAUI | Auth Pages: Login Page + Flow | Development | 2025-06 | 22
Aimen nasar | NEXELUSAPP - MAUI | Auth Pages: Login Page + Flow | Development | 2025-07 | 6.5
Aimen nasar | NEXELUSAPP - MAUI | Expense: Add New | Development | 2025-07 | 9.5
Aimen nasar | NEXELUSAPP - MAUI | Expense: Assignment Page | Development | 2025-07 | 18.5
Aimen nasar | NEXELUSAPP - MAUI | Expense: Main Page | Development | 2025-07 | 11
Aimen nasar | NEXELUSAPP - MAUI | Expense: Pending Expense Report | Development | 2025-07 | 2.5
Aimen nasar | NEXELUSAPP - MAUI | Expense: Permissions | Development | 2025-07 | 9
Aimen nasar | NEXELUSAPP - MAUI | Expense: Storage Functionality | Development | 2025-07 | 6
Aimen nasar | NEXELUSAPP - MAUI | Expense: Transactions Page + Nested listing | Development | 2025-07 | 4.5
Aimen nasar | NEXELUSAPP - MAUI | TimeSheet: Add New | Development | 2025-06 | 10
Aimen nasar | NEXELUSAPP - MAUI | TimeSheet: Add New | Development | 2025-07 | 6
Aimen nasar | NEXELUSAPP - MAUI | TimeSheet: Chart | Development | 2025-07 | 10.5
Aimen nasar | NEXELUSAPP - MAUI | TimeSheet: Edit | Development | 2025-06 | 2
Aimen nasar | NEXELUSAPP - MAUI | TimeSheet: Main Page | Development | 2025-06 | 7
Aimen nasar | NEXELUSAPP - MAUI | TimeSheet: Pending Transaction | Development | 2025-06 | 8
Ali Junaid | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | Bug Fixing | 2025-07 | 2.5
Ali Junaid | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | Development | 2025-07 | 17
Ali Junaid | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | SRS-Review | 2025-07 | 1
Ali Junaid | APWORKS 2025.3 | Hide Favorite button: Does not work ( Fix or hide) | Development | 2025-07 | 5.7
Ali Junaid | APWORKS 2025.3 | Manually mark invoice Archived | Development | 2025-07 | 6.7
Ali Junaid | APWORKS 2025.3 | Project Overhead | Analysis | 2025-07 | 2
Ali Junaid | APWORKS 2025.3 | Project Overhead | Meetings | 2025-06 | 2.5
Ali Junaid | APWORKS 2025.3 | Project Overhead | Post_dep_fixes | 2025-07 | 19.7
Ali Junaid | APWORKS 2025.3 | Rename Invoice amount to invoice net amount | Development | 2025-07 | 2
Ali Junaid | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Bug Fixing | 2025-07 | 15.5
Ali Junaid | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Development | 2025-06 | 64
Ali Junaid | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Development | 2025-07 | 62.5
Ali Junaid | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Research | 2025-07 | 2
Arif Khan Arif | ADHOC-ITEMS | No rates alert and error | DB Dev | 2025-07 | 1.5
Arif Khan Arif | ADHOC-ITEMS | No rates alert and error | Meetings | 2025-07 | 1
Arif Khan Arif | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | DB Dev | 2025-06 | 3
Arif Khan Arif | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | DB Dev | 2025-07 | 8
Arif Khan Arif | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | Task/Code Review | 2025-07 | 1
Arif Khan Arif | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | SRS-Review | 2025-07 | 2
Arif Khan Arif | APWORKS 2025.3 | Project Overhead | Research | 2025-07 | 3
Arif Khan Arif | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | Meetings | 2025-07 | 0.5
Arif Khan Arif | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | SRS-Review | 2025-07 | 0.5
Arif Khan Arif | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | Task/Code Review | 2025-07 | 0.5
Arif Khan Arif | NEXELUS 2025.3 | Enable multiple media plans under one Bing IO | DB Dev | 2025-07 | 7.5
Arif Khan Arif | NEXELUS 2025.3 | Enable multiple media plans under one Bing IO | SRS-Review | 2025-07 | 1
Arif Khan Arif | NEXELUS 2025.3 | MC rates for PBG | DB Dev | 2025-07 | 16.5
Arif Khan Arif | NEXELUS 2025.3 | pre-populate objective field from media plan | DB Dev | 2025-07 | 6
Arif Khan Arif | NEXELUS 2025.3 | Project Overhead | Deployment | 2025-07 | 0.5
Arif Khan Arif | NEXELUS 2025.3 | Project Overhead | Planinng | 2025-07 | 2
Arif Khan Arif | NEXELUS 2025.3 | Project Overhead | Research | 2025-07 | 3.5
Arif Khan Arif | NEXELUS 2025.3 | Project Overhead | TFS | 2025-06 | 0.5
Arif Khan Arif | NEXELUS 2025.3 | Project Overhead | TFS | 2025-07 | 8.5
Arslan Khalid | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | SRS-Review | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | Meetings | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | SRS-Review | 2025-06 | 1.5
Arslan Khalid | APWORKS 2025.3 | Hide Favorite button: Does not work ( Fix or hide) | Development | 2025-06 | 2
Arslan Khalid | APWORKS 2025.3 | Hide Favorite button: Does not work ( Fix or hide) | Development | 2025-07 | 1
Arslan Khalid | APWORKS 2025.3 | Manually mark invoice Archived | SRS-Review | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Bug Fixing | 2025-07 | 6
Arslan Khalid | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Development | 2025-06 | 9
Arslan Khalid | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Meetings | 2025-06 | 3
Arslan Khalid | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | SRS-Review | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Task/Code Review | 2025-06 | 2
Arslan Khalid | APWORKS 2025.3 | Rename Invoice amount to invoice net amount | Meetings | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Meetings | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | SRS-Review | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Show routing history - Invoice comment log | Bug Fixing | 2025-07 | 1
Arslan Khalid | APWORKS 2025.3 | Show routing history - Invoice comment log | Development | 2025-06 | 9
Arslan Khalid | APWORKS 2025.3 | Show routing history - Invoice comment log | Development | 2025-07 | 6.5
Arslan Khalid | APWORKS 2025.3 | Show routing history - Invoice comment log | Meetings | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Show routing history - Invoice comment log | SRS-Review | 2025-06 | 4
Arslan Khalid | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | Bug Fixing | 2025-07 | 2
Arslan Khalid | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | Development | 2025-07 | 35.5
Arslan Khalid | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | Meetings | 2025-07 | 10.75
Arslan Khalid | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | SRS-Review | 2025-07 | 7.75
Arslan Khalid | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | SRS-Review | 2025-07 | 0.5
Arslan Khalid | NEXELUS 2025.3 | pre-populate objective field from media plan | Development | 2025-07 | 5
Arslan Khalid | NEXELUS 2025.3 | pre-populate objective field from media plan | Meetings | 2025-07 | 2
Arslan Khalid | NEXELUS 2025.3 | pre-populate objective field from media plan | SRS-Review | 2025-07 | 6
Arslan Khalid | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | Development | 2025-07 | 7.5
Arslan Khalid | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | SRS-Review | 2025-07 | 1.5
Arslan Khalid | NEXELUS 2025.3 | Show old vs. new values on revision screens - DV360 | Development | 2025-07 | 2
Arslan Khalid | NEXELUS 2025.3 | Show old vs. new values on revision screens - LinkedIn | Development | 2025-07 | 12.5
Arslan Khalid | NEXELUS 2025.3 | Show old vs. new values on revision screens - LinkedIn | Meetings | 2025-07 | 0.5
Arslan Khalid | NEXELUS 2025.3 | Show old vs. new values on revision screens - Meta | Development | 2025-07 | 2
Arslan Khalid | NEXELUS 2025.3 | Show old vs. new values on revision screens - TTD | Development | 2025-07 | 4.5
Arslan Khalid | NEXELUS 2025.3 | Show old vs. new values on revision screens - TTD | Meetings | 2025-07 | 0.5
Arslan Khalid | NEXELUS 2025.3 | Show old vs. new values on revision screens - Twiter | Development | 2025-07 | 2
Asad Mahmood | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Meetings | 2025-07 | 2
Asad Mahmood | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | SRS-Review | 2025-06 | 5.5
Asad Mahmood | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | SRS-Review | 2025-07 | 4.5
Asad Mahmood | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Task/Code Review | 2025-07 | 3
Asad Mahmood | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | Meetings | 2025-06 | 1.5
Asad Mahmood | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | SRS-Review | 2025-06 | 1.5
Asad Mahmood | APWORKS 2025.3 | Hide Favorite button: Does not work ( Fix or hide) | Meetings | 2025-06 | 1.5
Asad Mahmood | APWORKS 2025.3 | Manually mark invoice Archived | Bug Fixing | 2025-07 | 2
Asad Mahmood | APWORKS 2025.3 | Manually mark invoice Archived | Development | 2025-07 | 47.5
Asad Mahmood | APWORKS 2025.3 | Manually mark invoice Archived | Meetings | 2025-06 | 1.5
Asad Mahmood | APWORKS 2025.3 | Manually mark invoice Archived | Meetings | 2025-07 | 1
Asad Mahmood | APWORKS 2025.3 | Manually mark invoice Archived | SRS-Review | 2025-07 | 2
Asad Mahmood | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Meetings | 2025-06 | 0.5
Asad Mahmood | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | SRS-Review | 2025-06 | 0.5
Asad Mahmood | APWORKS 2025.3 | Project Overhead | Deployment | 2025-07 | 2.5
Asad Mahmood | APWORKS 2025.3 | Project Overhead | Post_dep_fixes | 2025-07 | 16.5
Asad Mahmood | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Meetings | 2025-06 | 0.5
Asad Mahmood | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | SRS-Review | 2025-06 | 2
Asad Mahmood | APWORKS 2025.3 | Show routing history - Invoice comment log | Meetings | 2025-06 | 0.5
Asad Mahmood | APWORKS 2025.3 | Show routing history - Invoice comment log | SRS-Review | 2025-06 | 1
Asad Mahmood | APWORKS 2025.3 | Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | Development | 2025-06 | 13.5
Ayesha Qurban | APWORKS - TEST AUTOMATION | Project Overhead | Task Domain | 2025-07 | 6
Ayesha Qurban | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | SRS-Review | 2025-07 | 8
Ayesha Qurban | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | Bug Review | 2025-07 | 2
Ayesha Qurban | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | Test Case Dev | 2025-07 | 4
Ayesha Qurban | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | Testing | 2025-07 | 8
Ayesha Qurban | APWORKS 2025.3 | Format all amounts to be trwo decimals | Testing | 2025-07 | 4
Ayesha Qurban | APWORKS 2025.3 | Hide Favorite button: Does not work ( Fix or hide) | Testing | 2025-07 | 4.5
Ayesha Qurban | APWORKS 2025.3 | Project Overhead | Analysis | 2025-07 | 3.5
Ayesha Qurban | APWORKS 2025.3 | Project Overhead | Meetings | 2025-06 | 4
Ayesha Qurban | APWORKS 2025.3 | Project Overhead | Meetings | 2025-07 | 5.5
Ayesha Qurban | APWORKS 2025.3 | Project Overhead | Task Domain | 2025-06 | 9
Ayesha Qurban | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Bug Review | 2025-07 | 8.5
Ayesha Qurban | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Test Case Dev | 2025-06 | 13
Ayesha Qurban | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Testing | 2025-07 | 24
Bilal Afzal Raja | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | Testing | 2025-07 | 9
Bilal Afzal Raja | APWORKS 2025.3 | Project Overhead | Meetings | 2025-06 | 7
Bilal Afzal Raja | APWORKS 2025.3 | Project Overhead | Meetings | 2025-07 | 3
Bilal Afzal Raja | APWORKS 2025.3 | Project Overhead | Task Domain | 2025-06 | 11
Bilal Afzal Raja | NEXELUS 2025.3 | Project Overhead | Meetings | 2025-07 | 5
Bilal Afzal Raja | NEXELUS 2025.3 | Project Overhead | Project Mgmt | 2025-07 | 13
Bilal Afzal Raja | NEXELUS 2025.3 | Project Overhead | Support Tickets | 2025-07 | 7
Bilal Afzal Raja | NEXELUS 2025.3 | Project Overhead | Task Domain | 2025-07 | 15
Hamza Nouman | APWORKS 2025.3 | Project Overhead | Meetings | 2025-06 | 4
Hamza Nouman | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | Test Case Dev | 2025-06 | 1
Hamza Nouman | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | Test Case Dev | 2025-07 | 9
Hamza Nouman | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | Testing | 2025-07 | 23.5
Hamza Nouman | NEXELUS 2025.3 | Enable multiple media plans under one Bing IO | Test Case Dev | 2025-07 | 6
Hamza Nouman | NEXELUS 2025.3 | MC rates for PBG | Test Case Dev | 2025-07 | 5
Hamza Nouman | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | Testing | 2025-07 | 5
Hamza Nouman | NEXELUS 2025.3 | pre-populate objective field from media plan | Test Case Dev | 2025-06 | 1
Hamza Nouman | NEXELUS 2025.3 | pre-populate objective field from media plan | Test Case Dev | 2025-07 | 6
Hamza Nouman | NEXELUS 2025.3 | Project Overhead | Analysis | 2025-06 | 4
Hamza Nouman | NEXELUS 2025.3 | Project Overhead | Analysis | 2025-07 | 5
Hamza Nouman | NEXELUS 2025.3 | Project Overhead | No Workbench | 2025-07 | 3
Hamza Nouman | NEXELUS 2025.3 | Project Overhead | Task Domain | 2025-06 | 2
Hamza Nouman | NEXELUS 2025.3 | Project Overhead | Task Domain | 2025-07 | 7
Hamza Nouman | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | Test Case Dev | 2025-06 | 1
Hamza Nouman | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | Test Case Dev | 2025-07 | 5.5
Hamza Nouman | NEXELUS 2025.3 | Vulnerability Report | Testing | 2025-06 | 7
Imran UL Haq | ADHOC-ITEMS | R&D on Report Server | Analysis | 2025-07 | 2
Imran UL Haq | ADHOC-ITEMS | R&D on Report Server | Research | 2025-07 | 4
Kashif Hayat | APWORKS - TEST AUTOMATION | Media approval: approve invoices | Development | 2025-04 | 24
Kashif Hayat | APWORKS - TEST AUTOMATION | Media: Discrepant Invoices - Make Corrections | Development | 2025-04 | 4
Kashif Hayat | APWORKS - TEST AUTOMATION | Media: Discrepant Invoices - Make Corrections | Development | 2025-07 | 19
Kashif Hayat | APWORKS - TEST AUTOMATION | Media: Read Data diven excel files for the correspinding data | Design | 2025-04 | 8
Kashif Hayat | APWORKS - TEST AUTOMATION | Media: Validate and input data header fields | Development | 2025-07 | 5
Kashif Hayat | APWORKS - TEST AUTOMATION | Project Overhead | Analysis | 2025-06 | 6
Kashif Hayat | APWORKS - TEST AUTOMATION | Project Overhead | Analysis | 2025-07 | 5
Kashif Hayat | APWORKS - TEST AUTOMATION | Project Overhead | No Workbench | 2025-07 | 2
Kashif Hayat | APWORKS - TEST AUTOMATION | Project Overhead | Planinng | 2025-07 | 3
Kashif Hayat | APWORKS 2025.3 | Manually mark invoice Archived | Test Case Dev | 2025-06 | 9
Kashif Hayat | APWORKS 2025.3 | Manually mark invoice Archived | Testing | 2025-07 | 29
Kashif Hayat | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Test Case Dev | 2025-06 | 4
Kashif Hayat | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Test Case Dev | 2025-07 | 1
Kashif Hayat | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Testing | 2025-07 | 11
Kashif Hayat | APWORKS 2025.3 | Project Overhead | Meetings | 2025-06 | 8
Kashif Hayat | APWORKS 2025.3 | Project Overhead | Meetings | 2025-07 | 10.3
Kashif Hayat | APWORKS 2025.3 | Project Overhead | No Workbench | 2025-07 | 2
Kashif Hayat | APWORKS 2025.3 | Project Overhead | Task Domain | 2025-06 | 4
Kashif Hayat | APWORKS 2025.3 | Show routing history - Invoice comment log | Test Case Dev | 2025-07 | 11
Kashif Hayat | APWORKS 2025.3 | Show routing history - Invoice comment log | Testing | 2025-07 | 9
Muhammad Hamayun | APWORKS 2025.3 | Project Overhead | Support Tickets | 2025-07 | 0.5
Muhammad Yasir | ADHOC-ITEMS | No rates alert and error | DB Dev | 2025-07 | 5
Muhammad Yasir | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | DB Dev | 2025-07 | 9.5
Muhammad Yasir | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | Meetings | 2025-07 | 6
Muhammad Yasir | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | Task/Code Review | 2025-07 | 6
Muhammad Yasir | APWORKS - TEST AUTOMATION | Project Overhead | Analysis | 2025-05 | 1
Muhammad Yasir | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Analysis | 2025-07 | 0.5
Muhammad Yasir | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | Bug Fixing | 2025-07 | 0.5
Muhammad Yasir | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | DB Dev | 2025-07 | 1
Muhammad Yasir | APWORKS 2025.3 | Hide Favorite button: Does not work ( Fix or hide) | DB Dev | 2025-06 | 4
Muhammad Yasir | APWORKS 2025.3 | Manually mark invoice Archived | Bug Fixing | 2025-07 | 1
Muhammad Yasir | APWORKS 2025.3 | Manually mark invoice Archived | DB Dev | 2025-06 | 8
Muhammad Yasir | APWORKS 2025.3 | Manually mark invoice Archived | DB Dev | 2025-07 | 14.5
Muhammad Yasir | APWORKS 2025.3 | Manually mark invoice Archived | Meetings | 2025-06 | 1
Muhammad Yasir | APWORKS 2025.3 | Manually mark invoice Archived | Meetings | 2025-07 | 1.5
Muhammad Yasir | APWORKS 2025.3 | Manually mark invoice Archived | SRS-Review | 2025-06 | 1
Muhammad Yasir | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | DB Dev | 2025-06 | 3
Muhammad Yasir | APWORKS 2025.3 | Project Overhead | Analysis | 2025-07 | 3
Muhammad Yasir | APWORKS 2025.3 | Project Overhead | Deployment | 2025-07 | 3
Muhammad Yasir | APWORKS 2025.3 | Project Overhead | Post_dep_fixes | 2025-06 | 1
Muhammad Yasir | APWORKS 2025.3 | Project Overhead | Post_dep_fixes | 2025-07 | 3
Muhammad Yasir | APWORKS 2025.3 | Project Overhead | Research | 2025-07 | 2
Muhammad Yasir | APWORKS 2025.3 | Show routing history - Invoice comment log | DB Dev | 2025-06 | 2
Muhammad Yasir | APWORKS 2025.3 | Show routing history - Invoice comment log | Meetings | 2025-06 | 1
Muhammad Yasir | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | DB Dev | 2025-07 | 8
Muhammad Yasir | NEXELUS 2025.3 | Project Overhead | Deployment | 2025-07 | 2.5
Muhammad Yasir | NEXELUS 2025.3 | Project Overhead | Post_dep_fixes | 2025-06 | 4
Muzammil Shahzad | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | Bug Fixing | 2025-07 | 1
Muzammil Shahzad | NEXELUS 2025.3 | Enable multiple media plans under one Bing IO | Development | 2025-07 | 7
Muzammil Shahzad | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | Development | 2025-07 | 35.25
Muzammil Shahzad | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | SRS-Review | 2025-07 | 4.25
Muzammil Shahzad | NEXELUS 2025.3 | Project Overhead | Analysis | 2025-07 | 5.5
Muzammil Shahzad | NEXELUS 2025.3 | Project Overhead | Documentation | 2025-06 | 3
Muzammil Shahzad | NEXELUS 2025.3 | Project Overhead | Documentation | 2025-07 | 3.5
Muzammil Shahzad | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | Development | 2025-07 | 41.9
Muzammil Shahzad | Nexelus 2025.3 | Vulnerability Report | Development | 2025-06 | 8
Muzammil Shahzad | NEXELUSAPP - MAUI | Auth Pages: Key Page | Development | 2025-06 | 5
Muzammil Shahzad | NEXELUSAPP - MAUI | Auth Pages: Login Page + Flow | Development | 2025-06 | 4.5
Muzammil Shahzad | NEXELUSAPP - MAUI | Expense: Add New | Development | 2025-07 | 4.5
Muzammil Shahzad | NEXELUSAPP - MAUI | Expense: Add New | Meetings | 2025-07 | 1.25
Muzammil Shahzad | NEXELUSAPP - MAUI | Expense: Main Page | Development | 2025-07 | 5.9
Muzammil Shahzad | NEXELUSAPP - MAUI | Project Overhead | Analysis | 2025-06 | 19
Muzammil Shahzad | NEXELUSAPP - MAUI | Project Overhead | Documentation | 2025-06 | 14.5
Muzammil Shahzad | NEXELUSAPP - MAUI | TimeSheet: Chart | Development | 2025-07 | 2.5
Muzammil Shahzad | NEXELUSAPP - MAUI | TimeSheet: Main Page | Development | 2025-06 | 19.75
Muzammil Shahzad | NEXELUSAPP - MAUI | TimeSheet: Main Page | Development | 2025-07 | 3
Muzammil Shahzad | NEXELUSAPP - MAUI | TimeSheet: Pending Transaction | Development | 2025-07 | 4.25
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Analysis | 2025-06 | 34
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Analysis | 2025-07 | 5.5
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Development | 2025-06 | 4
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Development | 2025-07 | 40.5
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Meetings | 2025-06 | 2
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Meetings | 2025-07 | 4.5
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Research | 2025-07 | 42
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | SRS-Review | 2025-06 | 3
Shoaib Hassan | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | Development | 2025-07 | 22.5
Shoaib Hassan | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | Meetings | 2025-07 | 3.5

## Data2
Project Key | level2_key | level3_description | START_DATE | END_DATE
ADHOC-ITEMS:No rates alert and error | ADHOC-ITEMS | No rates alert and error | 2025-07-14 | 2025-07-14
ADHOC-ITEMS:R&D on Report Server | ADHOC-ITEMS | R&D on Report Server | 2025-07-09 | 2025-07-24
ADHOC-ITEMS:Voucher, AP rule flag and 4 sided entry - v3 | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | 2025-06-30 | 2025-07-15
APWORKS - TEST AUTOMATION:Media approval: approve invoices | APWORKS - TEST AUTOMATION | Media approval: approve invoices | 2025-04-14 | 2025-04-16
APWORKS - TEST AUTOMATION:Media: Discrepant Invoices - Make Corrections | APWORKS - TEST AUTOMATION | Media: Discrepant Invoices - Make Corrections | 2025-04-25 | 2025-07-21
APWORKS - TEST AUTOMATION:Media: Read Data diven excel files for the correspinding data | APWORKS - TEST AUTOMATION | Media: Read Data diven excel files for the correspinding data | 2025-04-30 | 2025-04-30
APWORKS - TEST AUTOMATION:Media: Validate and input data header fields | APWORKS - TEST AUTOMATION | Media: Validate and input data header fields | 2025-07-16 | 2025-07-16
APWORKS - TEST AUTOMATION:Project Overhead | APWORKS - TEST AUTOMATION | Project Overhead | 2025-05-19 | 2025-07-21
APWORKS 2025.3:eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | 2025-06-18 | 2025-07-21
APWORKS 2025.3:Flag an invoice in Discrepant bucket for searching | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | 2025-06-20 | 2025-07-24
APWORKS 2025.3:Format all amounts to be trwo decimals | APWORKS 2025.3 | Format all amounts to be trwo decimals | 2025-07-24 | 2025-07-24
APWORKS 2025.3:Hide Favorite button: Does not work ( Fix or hide) | APWORKS 2025.3 | Hide Favorite button: Does not work ( Fix or hide) | 2025-06-23 | 2025-07-25
APWORKS 2025.3:Manually mark invoice Archived | APWORKS 2025.3 | Manually mark invoice Archived | 2025-06-23 | 2025-07-25
APWORKS 2025.3:Net Amount Total: Add field in header to sum Invoice Net Amount | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | 2025-06-20 | 2025-07-24
APWORKS 2025.3:Project Overhead | APWORKS 2025.3 | Project Overhead | 2025-06-16 | 2025-07-25
APWORKS 2025.3:Rename Invoice amount to invoice net amount | APWORKS 2025.3 | Rename Invoice amount to invoice net amount | 2025-06-23 | 2025-07-10
APWORKS 2025.3:Retain user-specific report views and filter preferences during | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | 2025-06-17 | 2025-07-25
APWORKS 2025.3:Show routing history - Invoice comment log | APWORKS 2025.3 | Show routing history - Invoice comment log | 2025-06-20 | 2025-07-24
APWORKS 2025.3:Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | APWORKS 2025.3 | Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | 2025-06-24 | 2025-06-27
NEXELUS 2025.3:Ability to toggle advantage campaign budget on/off via API | NEXELUS 2025.3 | Ability to toggle advantage campaign budget on/off via API | 2025-07-25 | 2025-07-25
NEXELUS 2025.3:DENTSU _ Implementing a custom upload error log in Excel | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | 2025-06-30 | 2025-07-25
NEXELUS 2025.3:Enable multiple media plans under one Bing IO | NEXELUS 2025.3 | Enable multiple media plans under one Bing IO | 2025-07-08 | 2025-07-25
NEXELUS 2025.3:MC rates for PBG | NEXELUS 2025.3 | MC rates for PBG | 2025-07-08 | 2025-07-23
NEXELUS 2025.3:PO numbers to be appended automatically to campaign names | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | 2025-06-26 | 2025-07-18
NEXELUS 2025.3:pre-populate objective field from media plan | NEXELUS 2025.3 | pre-populate objective field from media plan | 2025-06-26 | 2025-07-10
NEXELUS 2025.3:Project Overhead | NEXELUS 2025.3 | Project Overhead | 2025-06-16 | 2025-07-24
NEXELUS 2025.3:Show old vs. new values on revision screens (Design and Rev) | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | 2025-06-26 | 2025-07-25
NEXELUS 2025.3:Show old vs. new values on revision screens - DV360 | NEXELUS 2025.3 | Show old vs. new values on revision screens - DV360 | 2025-07-17 | 2025-07-21
NEXELUS 2025.3:Show old vs. new values on revision screens - LinkedIn | NEXELUS 2025.3 | Show old vs. new values on revision screens - LinkedIn | 2025-07-18 | 2025-07-25
NEXELUS 2025.3:Show old vs. new values on revision screens - Meta | NEXELUS 2025.3 | Show old vs. new values on revision screens - Meta | 2025-07-14 | 2025-07-21
NEXELUS 2025.3:Show old vs. new values on revision screens - TTD | NEXELUS 2025.3 | Show old vs. new values on revision screens - TTD | 2025-07-18 | 2025-07-25
NEXELUS 2025.3:Show old vs. new values on revision screens - Twiter | NEXELUS 2025.3 | Show old vs. new values on revision screens - Twiter | 2025-07-17 | 2025-07-22
Nexelus 2025.3:Vulnerability Report | Nexelus 2025.3 | Vulnerability Report | 2025-06-23 | 2025-06-27
NEXELUSAPP - MAUI:Auth Pages: Key Page | NEXELUSAPP - MAUI | Auth Pages: Key Page | 2025-06-02 | 2025-06-20
NEXELUSAPP - MAUI:Auth Pages: Login Page + Flow | NEXELUSAPP - MAUI | Auth Pages: Login Page + Flow | 2025-06-16 | 2025-07-04
NEXELUSAPP - MAUI:Expense: Add New | NEXELUSAPP - MAUI | Expense: Add New | 2025-07-07 | 2025-07-25
NEXELUSAPP - MAUI:Expense: Assignment Page | NEXELUSAPP - MAUI | Expense: Assignment Page | 2025-07-07 | 2025-07-24
NEXELUSAPP - MAUI:Expense: Main Page | NEXELUSAPP - MAUI | Expense: Main Page | 2025-07-08 | 2025-07-18
NEXELUSAPP - MAUI:Expense: Pending Expense Report | NEXELUSAPP - MAUI | Expense: Pending Expense Report | 2025-07-14 | 2025-07-14
NEXELUSAPP - MAUI:Expense: Permissions | NEXELUSAPP - MAUI | Expense: Permissions | 2025-07-10 | 2025-07-18
NEXELUSAPP - MAUI:Expense: Storage Functionality | NEXELUSAPP - MAUI | Expense: Storage Functionality | 2025-07-11 | 2025-07-21
NEXELUSAPP - MAUI:Expense: Transactions Page + Nested listing | NEXELUSAPP - MAUI | Expense: Transactions Page + Nested listing | 2025-07-08 | 2025-07-10
NEXELUSAPP - MAUI:Project Overhead | NEXELUSAPP - MAUI | Project Overhead | 2025-06-02 | 2025-07-10
NEXELUSAPP - MAUI:TimeSheet: Add New | NEXELUSAPP - MAUI | TimeSheet: Add New | 2025-06-25 | 2025-07-03
NEXELUSAPP - MAUI:TimeSheet: Chart | NEXELUSAPP - MAUI | TimeSheet: Chart | 2025-07-02 | 2025-07-04
NEXELUSAPP - MAUI:TimeSheet: Edit | NEXELUSAPP - MAUI | TimeSheet: Edit | 2025-06-25 | 2025-06-25
| NEXELUSAPP - MAUI | TimeSheet: Main Page | 2025-06-18 | 2025-07-01
| NEXELUSAPP - MAUI | TimeSheet: Pending Transaction | 2025-06-26 | 2025-07-04

## SQL
select level2_key,level3_key,level3_description from pdd_level3 where level2_key in ('APWORKS 2025.3','NEXELUS 2025.3','APWORKS - TEST AUTOMATION', 'ADHOC-ITEMS','NEXELUSAPP - MAUI') order by level2_key,level3_key
SQL 1 | select employee,level2_key,level3_description,task_code,appliedmonth,sum(Hours) Hours from pdv_timesheet_summary where level2_key in ('APWORKS 2025.3','NEXELUS 2025.3','APWORKS - TEST AUTOMATION', 'ADHOC-ITEMS','NEXELUSAPP - MAUI') group by employee,level2_key,level3_description,task_code,appliedmonth order by employee,level2_key,level3_description,task_code,appliedmonth
SQL 2 | select level2_key,level3_description,min(Start_date) START_DATE, max(End_Date) END_DATE from pdv_timesheet_span where level2_key in ('APWORKS 2025.3','NEXELUS 2025.3','APWORKS - TEST AUTOMATION', 'ADHOC-ITEMS','NEXELUSAPP - MAUI') group by level2_key, level3_description order by level2_key, level3_description

## Pivot
appliedmonth | (All)
Sum of Hours | Column Labels
Row Labels | Analysis | Design | Development | Documentation | Meetings | Planinng | Post_dep_fixes | Project Mgmt | SRS-Review | Task Domain | Task/Code Review | Test Case Dev | Testing | Bug Fixing | DB Dev | Deployment | No Workbench | Research | TFS | Bug Review | Support Tickets | Grand Total
ADHOC-ITEMS | 2 |  |  |  | 7 | [5 empty] | 7 |  | 9 |  | 27 |  |  | 4 |  |  |  | 56
Voucher, AP rule flag and 4 sided entry - v3 |  |  |  |  | 6 | [5 empty] | 7 |  | 9 |  | 20.5 | [6 empty] | 42.5
No rates alert and error |  |  |  |  | 1 | [9 empty] | 6.5 | [6 empty] | 7.5
R&D on Report Server | 2 | [16 empty] | 4 |  |  |  | 6
APWORKS - TEST AUTOMATION | 12 | 8 | 52 |  |  | 3 |  |  |  | 6 | [6 empty] | 2 |  |  |  |  | 83
Media approval: approve invoices |  |  | 24 | [18 empty] | 24
Media: Discrepant Invoices - Make Corrections |  |  | 23 | [18 empty] | 23
Media: Read Data diven excel files for the correspinding data |  | 8 | [19 empty] | 8
Project Overhead | 12 |  |  |  |  | 3 |  |  |  | 6 | [6 empty] | 2 |  |  |  |  | 23
Media: Validate and input data header fields |  |  | 5 | [18 empty] | 5
APWORKS 2025.3 | 51.5 |  | 290.9 | 1.5 | 70.3 | 17 | 40.2 | 16 | 52.5 | 24 | 11.5 | 42 | 89.5 | 28.5 | 32.5 | 15 | 2 | 49 |  | 10.5 | 0.5 | 844.9
Flag an invoice in Discrepant bucket for searching |  |  | 17 |  | 2.5 |  |  |  | 5 |  |  | 4 | 8 | 3 | 1 |  |  |  |  | 2 |  | 42.5
Hide Favorite button: Does not work ( Fix or hide) |  |  | 8.7 |  | 1.5 | [7 empty] | 4.5 |  | 4 | [6 empty] | 18.7
Manually mark invoice Archived |  |  | 54.2 |  | 5 |  |  |  | 4 |  |  | 9 | 29 | 3 | 22.5 | [6 empty] | 126.7
Net Amount Total: Add field in header to sum Invoice Net Amount |  |  | 9 |  | 3.5 |  |  |  | 2.5 |  | 3 | 5 | 11 | 6 | 3 | [6 empty] | 43
Project Overhead | 8.5 |  |  |  | 44.3 | 17 | 40.2 | 16 |  | 24 | [5 empty] | 15 | 2 | 5 |  |  | 0.5 | 172.5
Rename Invoice amount to invoice net amount |  |  | 2 |  | 1 | [16 empty] | 3
Retain user-specific report views and filter preferences during |  |  | 126.5 |  | 1.5 |  |  |  | 3.5 |  | 2 | 13 | 24 | 15.5 |  |  |  | 2 |  | 8.5 |  | 196.5
Show routing history - Invoice comment log |  |  | 15.5 |  | 2.5 |  |  |  | 5.5 |  | 2.5 | 11 | 9 | 1 | 2 | [6 empty] | 49
Upgrade ApWorks application to dotnet Core 8.0 from 7.0 |  |  | 13.5 | [18 empty] | 13.5
eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | 43 |  | 44.5 | 1.5 | 8.5 |  |  |  | 32 |  | 4 | [6 empty] | 42 |  |  |  | 175.5
Format all amounts to be trwo decimals | [12 empty] | 4 | [8 empty] | 4
NEXELUS 2025.3 | 14.5 |  | 214.65 | 6.5 | 22.75 | 11 | 4 | 17.5 | 30 | 24 | 5.5 | 34.5 | 35.5 | 3 | 38 | 3 | 3 | 3.5 | 9 |  | 7 | 486.9
DENTSU _ Implementing a custom upload error log in Excel |  |  | 35.5 |  | 11.25 |  |  |  | 8.25 |  | 3.5 | 10 | 23.5 | 3 | 8 | [6 empty] | 103
PO numbers to be appended automatically to campaign names |  |  | 37.25 | [5 empty] | 6.75 |  | 2 |  | 5 | [8 empty] | 51
pre-populate objective field from media plan |  |  | 5 |  | 2 |  |  |  | 8 |  |  | 7 |  |  | 6 | [6 empty] | 28
Project Overhead | 14.5 |  |  | 6.5 | 5 | 11 | 4 | 17.5 |  | 24 | [5 empty] | 3 | 3 | 3.5 | 9 |  | 7 | 108
Show old vs. new values on revision screens (Design and Rev) |  |  | 71.9 |  | 3.5 |  |  |  | 4 |  |  | 6.5 | [9 empty] | 85.9
Vulnerability Report |  |  | 8 | [9 empty] | 7 | [8 empty] | 15
Enable multiple media plans under one Bing IO |  |  | 12 | [5 empty] | 3 |  |  | 6 |  |  | 7.5 | [6 empty] | 28.5
Show old vs. new values on revision screens - DV360 |  |  | 6 | [18 empty] | 6
Show old vs. new values on revision screens - LinkedIn |  |  | 18.5 |  | 0.5 | [16 empty] | 19
Show old vs. new values on revision screens - Meta |  |  | 12 | [18 empty] | 12
Show old vs. new values on revision screens - Twiter |  |  | 4 | [18 empty] | 4
MC rates for PBG | [11 empty] | 5 |  |  | 16.5 | [6 empty] | 21.5
Show old vs. new values on revision screens - TTD |  |  | 4.5 |  | 0.5 | [16 empty] | 5
NEXELUSAPP - MAUI | 19 |  | 195.4 | 14.5 | 2.25 | [16 empty] | 231.15
Auth Pages: Key Page |  |  | 18 | [18 empty] | 18
Auth Pages: Login Page + Flow |  |  | 33 | [18 empty] | 33
Project Overhead | 19 |  |  | 14.5 | 1 | [16 empty] | 34.5
TimeSheet: Add New |  |  | 16 | [18 empty] | 16
TimeSheet: Chart |  |  | 13 | [18 empty] | 13
TimeSheet: Edit |  |  | 2 | [18 empty] | 2
TimeSheet: Main Page |  |  | 29.75 | [18 empty] | 29.75
TimeSheet: Pending Transaction |  |  | 12.25 | [18 empty] | 12.25
Expense: Add New |  |  | 14 |  | 1.25 | [16 empty] | 15.25
Expense: Assignment Page |  |  | 18.5 | [18 empty] | 18.5
Expense: Main Page |  |  | 16.9 | [18 empty] | 16.9
Expense: Pending Expense Report |  |  | 2.5 | [18 empty] | 2.5
Expense: Permissions |  |  | 9 | [18 empty] | 9
Expense: Storage Functionality |  |  | 6 | [18 empty] | 6
Expense: Transactions Page + Nested listing |  |  | 4.5 | [18 empty] | 4.5
Grand Total | 99 | 8 | 752.95 | 22.5 | 102.3 | 31 | 44.2 | 33.5 | 82.5 | 54 | 24 | 76.5 | 134 | 31.5 | 97.5 | 18 | 7 | 56.5 | 9 | 10.5 | 7.5 | 1701.95