## Sheet1
RACI Matrix - Change Management
[6 empty] | Legend | Description
| (R)esponsible, (A)ccountable, (C)onsulted, and (I)nformed (RACI) diagram |  |  |  |  | R | Responsible
[6 empty] | A | Accountable
[6 empty] | C | Consulted
[6 empty] | I | Informed
Task | Activity | Leadership | Product Management | Development | QA | Release Management | Client
1 | Request for Change (RFC) | R/A | R
2 | Assessment of RFC | R/C | R/A |  | C/I
3 | Approval / Rejection of RFC | R/A | R
4 | Assign / Change Owner | I | R/A | C | I
5 | Requirement Specifications | C | R/A | R/C | C
6 | Brain Storming / Impact Analysis | C/I | R/A | R/C | C
7 | System Design and Specifications | I | A | R | C
8 | Plan/Estimate | I | R/A | R/C | C
9 | Review/Update Requirement Specification | I | A | R/A | C
10 | Development | I | C | R/A | I
11 | Build Packaging for Deployment | I | C | R/A | I
12 | Deployment on QA Environment | I | I | C | R/A
13 | Review Change on QA Environment and Rebuild Decision | I | A | C | R
14 | Deployment on Release Environments | I | C/I | I | R/A | I
15 | Review Change on Release Environment and Rebuild Decision | I | A | C | C | R
16 | Final Release Decision | C | A | I | I | R/A
17 | Release Notes | I | R/A |  | I | C | I
18 | Deployment on UAT Envronments | I | I | I | C | R/A | I
19 | UAT Verification | I | I | I | I |  | R/A
20 | UAT Verification Sign-off | I | A | I | I |  | R
21 | Deployment on Production Environments | I | I | I | C | R/A | I
22 | Close RFC | I | R/A