## APWorks
Item | Assigned To | Responsibility | ETA | Status
1 | Company DNS Setup plusco-uat02.apworks.ai | Tao |  | Done
2 | Create S3 Buckets and execute setup scripts plusco-uat02-apautomation | Tao | 2024-11-04
3 | Create Company Database from PlusCo AZF Environment Backup uat02_apautomation_plusco | Arif Khan / Imran Haq
4 | Enter Helm information in Common Database - ent_client - ent_domain | Arif Khan / Imran Haq | 2024-10-29
5 | Update apam_company table in TSY database | Arif Khan / Imran Haq | 2024-10-29
6 | Cleanup Database - transactional Data - Model Data - Master Data | Arif Khan / Imran Haq | 2024-10-29
7 | Generate Nexelus API Key and update Database | Tao / Imran Haq | 2024-10-25
8 | Verify APWorks (Media and Production) | Bilal / Tao | 10/29/2024-10/30/2024
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not required