## APWorks
Item | Assigned To | Responsibility | ETA | Status
1 | Company DNS Setup Theshipyard.apworks.ai | Tao | 2025-01-15 | Done
2 | Create S3 Buckets and execute setup scripts a. theshipyard-prod-apautomation b. theshipyard-helm-prod-apautomation | Tao | 2025-01-15 | Done
3 | Backup Company Database from JustGlobal UAT Backup prod_apautomation_tsy | Arif Khan / Imran Haq | 2025-01-16
4 | Restore Back database on Production prod_apautomation_tsy | Arif Khan / Imran Haq | 2025-01-16
5 | Import TSY and Helm Model / VendorMapping data from UAT to Prodcution Common Database | Arif Khan / Imran Haq | 2025-01-16
6 | Copy Model PDF files from UAT to Production S3 Buckets | Tauseef Shahzad | 2025-01-16
7 | Enter Helm information in Common Database - ent_client - ent_domain | Arif Khan / Imran Haq | 2025-01-16
8 | Update apam_company table in TSY database | Arif Khan / Imran Haq | 2025-01-16
9 | Cleanup Database - transactional Data - Model Data - Master Data | Arif Khan / Imran Haq | 2025-01-16
10 | Generate Nexelus API Key | Tao | 2025-01-16 | Done
11 | update API Key in Database | Imran Haq | 2025-01-16
12 | Deploy APWorks in Production Environment | Abid | 2025-01-16
13 | Verify APWorks (Media and Production) | Bilal / Tao | 2025-01-16
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not required

## VendorPortal
Item | Assigned To | Responsibility | ETA | Status
1 | Backup and Restore Database from UAT to Production Nex_vendorportal_tsy | Arif Khan /Imran Haq | 2024-01-16
2 | Clean Database | Arif Khan /Imran Haq | 2024-01-16
3 | Update following tables 1. pdi_companies | Arif Khan /Imran Haq | 2024-01-16
4 | Update vendorportal url in PDM_ENTERPRISE_TSY.pdi_site | Arif Khan /Imran Haq | 2024-01-16
5 | Deploy Vendor Portal Application | Tauseef Shahzad | 2024-01-16
6 | Validation/Verification | Bilal | 2024-01-16