## Sheet1
Item | Assigned To | Responsibility | ETA | Status
1 | Company DNS Setup PropelHealth.apworks.ai | Tao | 2025-05-23
2 | Create S3 Buckets and execute setup scripts s3://ph-hstar-prod-apautomation s3://ph-scs-prod-apautomation s3://ph-phc-prod-apautomation s3://ph-phma-prod-apautomation | Tao | 2025-05-23
3 | Copy Template from UAT to Production S3 Bucket | Hamayun | 2025-05-26
4 | Backup Company Database for PropelHealth from UAT uat_apautomation_propelhealth | Imran Haq | 2025-05-26
5 | Backup PropelHealth data from UAT Common Database | Imran Haq | 2025-05-26
6 | Create Company Database from PropelHealth UAT Backup prod_apautomation_propelhealth | Imran Haq | 2025-05-26
7 | Enter PropelHealth information in Common Database - ent_client - ent_domain | Imran Haq | 2025-05-27
8 | Update apam_company table in prod_apautomation_propelhealth | Hamayun | 2025-05-27
9 | Cleanup Client Database - transactional Data | Imran Haq | 2025-05-27
10 | Import Model data for PropelHealth in Common and company database | Imran Haq | 2025-05-27
11 | Generate Nexelus API Key and update Database | Tao | 2025-05-27
12 | Disable all use Login accounts except Nexelus | Hamayun
13 | Verify APWorks (Media and Production) | Bilal / Tao | 2025-05-27