## AI Usage
AI Assistance Queries
Period | Resource | Review Tech Spec | DB Queries | Development | Unit Testng | Test Case | Automated Test Cases
2024-11-01 | Abid Ali | 0 | 0 | 0 | 0 | 0 | 0
2024-11-01 | Arsalan Khalid | 0 | 15 | 20 | 0 | 0 | 0
2024-11-01 | Asad Mahmood | 0 | 4 | 12 | 0 | 0 | 0
2024-11-01 | Fawad Ahmad | 0 | 10 | 15 | 0 | 0 | 0
2024-11-01 | Imran Haq | 0 | 0 | 0 | 0 | 0 | 0
2024-11-01 | Arif Khan | 0 | 15 | 0 | 0 | 0 | 0
2024-11-01 | Bilal Raja | 0 | 0 | 0 | 0 | 2 | 0
2024-11-01 | Ayesha Qurban | 0 | 0 | 0 | 0 | 4 | 0
2024-11-01 | Hamza Nauman | 0 | 0 | 0 | 0 | 4 | 0
2024-11-01 | Kashif Hayat | 0 | 0 | 0 | 0 | 8 | 12
2024-12-01 | Abid Ali | 0 | 0 | 0 | 0 | 0 | 0
2024-12-01 | Arsalan Khalid | 0 | 10 | 24 | 0 | 0 | 0
2024-12-01 | Asad Mahmood | 0 | 8 | 20 | 0 | 0 | 0
2024-12-01 | Fawad Ahmad | 0 | 6 | 22 | 0 | 0 | 0
2024-12-01 | Imran Haq | 0 | 0 | 0 | 0 | 0 | 0
2024-12-01 | Arif Khan | 0 | 20 | 0 | 0 | 0 | 0
2024-12-01 | Bilal Raja | 0 | 0 | 0 | 0 | 0 | 0
2024-12-01 | Ayesha Qurban | 0 | 0 | 0 | 0 | 0 | 0
2024-12-01 | Hamza Nauman | 0 | 0 | 0 | 0 | 0 | 0
2024-12-01 | Kashif Hayat | 0 | 0 | 0 | 0 | 0 | 12

## By Employee -Task
Sum of Hours | Column Labels
Row Labels | Admin | Analysis | Bug Fixing | Client Items | Deployment | Design | Development | Documentation | Domain Learning | Holiday-Time Off | HR Management | Interview | Leave | Meetings | No Workbench | PMO | Post_dep_fixes | Project Mgmt | Research | SOC Compliance | Task/Code Review | Test Case Dev | Testing | Training | Unassigned time | Support Tickets | NULL | OffshoreMeeting | JustGlobal | Support&Maint | TheShipyard | Demo | Accounts | TaxAndBank | HY | SupportMeetings | Grand Total
Abid Ali |  | 49 | 65 | 51 | 86.5 |  | 65.5 |  |  | 63.5 |  |  |  | 162.2 |  |  | 9 | 89.2 |  |  | 31 |  | 24.5 |  |  | 1 | 142 | 13 | 1 | 22.5 | 10 | [5 empty] | 885.9
Anees Rahman |  |  |  | 435 | 6.5 | [21 empty] | 36 |  |  |  |  | 240 |  |  |  |  | 717.5
Arif Khan Arif |  | 156.5 | 114 | 70 | 15 |  | 124 | 2 |  | 9 |  |  |  | 32 | [8 empty] | 1 |  | 62.5 |  | 95.5 |  | 4.5 | 1.5 | [6 empty] | 687.5
Arshad Sadal | [18 empty] | 11 | [17 empty] | 11
Arslan Khalid |  | 19 | 253 | 15 |  | 22 | 253 |  |  | 38 |  |  |  | 67.5 | [6 empty] | 1 |  | 7.5 | 4 |  |  | 144 | [9 empty] | 824
Asad Mahmood |  | 2.5 | 220 |  | 3 |  | 281 |  |  | 56 |  |  |  | 60 |  |  | 16 | [5 empty] | 35 |  |  |  | 144 | [9 empty] | 817.5
Asim Jameel | 3 | 12 |  | 100.9 |  |  | 44 | 128.5 |  | 24 |  |  |  | 120.85 |  |  |  | 3.5 |  |  |  |  | 5 |  |  |  | 84.9 |  |  | 8.75 | [6 empty] | 535.4
Asiya Bibi | 278.5 | [8 empty] | 3 | 212 | 16.5 |  | 48.5 | [12 empty] | 103.5 | [5 empty] | 12 | 20 |  |  | 694
Ayesha Qurban |  | 46 |  | 86 |  |  |  | 4 |  | 57 |  |  |  | 47 | [7 empty] | 68 | 330 |  |  | 3 | 142 |  |  | 2 | [6 empty] | 785
Bilal Afzal Raja |  | 115 | 2.5 |  |  |  | 5 | 49.5 | 6.5 | 57 |  |  |  | 123.5 | [7 empty] | 12 | 297 |  |  |  | 143.5 | [9 empty] | 811.5
Farooq Azam | [26 empty] | 40 | [9 empty] | 40
Fawad Ahmed |  | 35 | 58 | 0 | 6.8 |  | 410.75 | 5 |  | 12 |  |  |  | 28.65 |  |  | 1 |  |  |  | 3 |  | 23.75 | 8.5 | [12 empty] | 592.45
Hamza Nouman |  | 19 | 5 | 51 |  |  |  | 15.5 |  | 58.5 |  |  | 8 | 79 | 1.5 |  | 7 |  |  |  |  | 48 | 429.5 |  | 2 |  | 81 | [9 empty] | 805
Imran UL Haq |  | 21 | 112 | 404 | 7 |  | 99.5 |  |  | 16 |  |  |  | 9.5 |  |  | 16 | [9 empty] | 158 |  |  | 12 | 2 |  |  |  | 4 |  | 861
Kashif Hayat |  | 99 | 16 | 54 |  |  |  | 1 |  | 96 |  |  | 8 | 37 | [7 empty] | 17 | 364 | 2 |  |  | 135 | [9 empty] | 829
Saad Saeed | 1 | 1 |  |  |  |  | 131.5 |  | 64 | 8 |  |  |  | 9.6 | 3.3 |  |  |  | 56.1 |  |  |  | 29.85 | 5.3 | [11 empty] | 0.75 | 310.4
Shafiq Ahmed | 624 | [13 empty] | 120 | [11 empty] | 96 | [9 empty] | 840
Tauseef Shahzad | 56 |  |  | 10 | 11 |  | 1 |  |  | 19 | 4 | 30 | 64 | 174 |  | 149 |  | 4 |  | 100 | [6 empty] | 136.5 | [9 empty] | 758.5
Grand Total | 962.5 | 575 | 845.5 | 1276.9 | 135.8 | 22 | 1415.25 | 205.5 | 70.5 | 517 | 216 | 46.5 | 80 | 999.3 | 124.8 | 149 | 49 | 96.7 | 67.1 | 100 | 35 | 145 | 1547.1 | 19.8 | 64.5 | 4 | 1681.9 | 13 | 5.5 | 46.75 | 12 | 240 | 12 | 20 | 4 | 0.75 | 11805.65

## By Employee - Dev and QA
AppliedMonth | (All)
Column Labels
| Admin |  | Analysis |  | Bug Fixing |  | Client Items |  | Deployment |  | Design |  | Development |  | Documentation |  | Domain Learning |  | Holiday-Time Off |  | HR Management |  | Interview |  | Leave |  | Meetings |  | No Workbench |  | Other |  | PMO |  | Post_dep_fixes |  | Project Mgmt |  | Research |  | SOC Compliance |  | Support Tickets |  | Task/Code Review |  | Test Case Dev |  | Testing |  | Training |  | Unassigned time |  | Total Estimate | Total Actual
Row Labels | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual | Estimate | Actual
Abid Ali |  |  | 0 | 49 | 0 | 65 |  | 56 | 0 | 86.5 |  |  | 0 | 65.5 | [5 empty] | 63.5 | [6 empty] | 0 | 175.2 |  |  | 0 | 142 |  |  | 0 | 9 | 0 | 89.2 | [5 empty] | 29.5 | 0 | 31 |  |  | 0 | 24.5 |  |  |  |  | 0 | 885.9
Anees Rahman | [7 empty] | 435 |  | 6.5 | [21 empty] | 36 | [10 empty] | 0 | 240 | [10 empty] | 0 | 717.5
Arif Khan Arif |  |  | 0 | 156.5 | 0 | 114 | 0 | 74.5 |  | 15 |  |  | 71.5 | 124 | 0 | 2 |  |  |  | 9 | [6 empty] | 0 | 32 |  |  | 0 | 95.5 | [11 empty] | 1.5 | [5 empty] | 1 |  |  | 0 | 62.5 | 71.5 | 687.5
Arshad Sadal | [39 empty] | 11 | [15 empty] | 11
Arslan Khalid |  |  | 12 | 19 | 0 | 253 |  | 15 |  |  | 0 | 22 | 86 | 253 |  |  |  |  | 0 | 38 | [6 empty] | 0 | 67.5 |  |  | 0 | 144 | [12 empty] | 0 | 1 |  |  | 0 | 7.5 |  | 4 |  |  | 98 | 824
Asad Mahmood |  |  | 0 | 2.5 | 0 | 220 |  |  |  | 3 |  |  | 0 | 281 |  |  |  |  | 0 | 56 | [6 empty] | 0 | 60 |  |  | 0 | 144 |  |  | 0 | 16 | [12 empty] | 0 | 35 |  |  |  |  | 0 | 817.5
Asim Jameel |  | 3 |  | 12 |  |  | 0 | 100.9 | [5 empty] | 44 | 0 | 128.5 |  |  |  | 24 | [6 empty] | 0 | 120.85 |  |  |  | 84.9 | [5 empty] | 3.5 | [5 empty] | 8.75 | [5 empty] | 5 |  |  |  |  | 0 | 535.4
Asiya Bibi | 0 | 310.5 | [17 empty] | 3 |  | 212 |  | 16.5 |  |  |  | 48.5 |  |  |  | 103.5 | [22 empty] | 0 | 694
Ayesha Qurban |  |  | 0 | 46 |  |  | 0 | 86 | [6 empty] | 0 | 4 |  |  | 0 | 57 | [6 empty] | 6.8 | 47 |  |  |  | 142 | [11 empty] | 5 |  |  | 13.2 | 68 | 11 | 330 |  |  |  |  | 31 | 785
Bilal Afzal Raja |  |  | 0 | 115 | 0 | 2.5 | [6 empty] | 0 | 5 | 0 | 49.5 |  | 6.5 | 0 | 57 | [6 empty] | 0 | 123.5 |  |  | 0 | 143.5 | [14 empty] | 0 | 12 | 0 | 297 |  |  |  |  | 0 | 811.5
Farooq Azam | [30 empty] | 0 | 40 | [22 empty] | 0 | 40
Fawad Ahmed |  |  | 0 | 35 | 40.9 | 58 | 0 | 0 | 0 | 6.8 |  |  | 12.9 | 410.75 | 0 | 5 |  |  | 0 | 12 | [6 empty] | 0 | 28.65 | [6 empty] | 0 | 1 | [9 empty] | 3 |  |  | 0 | 23.75 | 0 | 8.5 |  |  | 53.8 | 592.45
sq |  |  |  | 19 |  | 5 | 0 | 51 | [7 empty] | 15.5 |  |  | 0 | 58.5 |  |  |  |  | 0 | 8 | 0 | 79 |  | 1.5 | 0 | 81 |  |  |  | 7 | [10 empty] | 48 | 48 | 80 | 429.5 |  |  |  | 2 | 128 | 805
Imran UL Haq |  |  | 0 | 21 | 0 | 112 | 0 | 406 |  | 7 |  |  | 0 | 99.5 |  |  |  |  | 0 | 16 | [6 empty] | 0 | 9.5 |  |  | 0 | 158 |  |  |  | 16 | [7 empty] | 16 | [10 empty] | 0 | 861
Kashif Hayat |  |  | 0 | 99 | 0 | 16 | 0 | 54 | [6 empty] | 0 | 1 |  |  | 0 | 96 |  |  |  |  | 0 | 8 | 0 | 37 |  |  | 0 | 135 | [14 empty] | 8 | 17 | 4 | 364 |  | 2 |  |  | 12 | 829
Saad Saeed | 0 | 1 |  | 1 | [9 empty] | 131.5 |  |  |  | 64 |  | 8 | [7 empty] | 10.35 |  | 3.3 | [9 empty] | 56.1 | [9 empty] | 29.85 | 0 | 5.3 |  |  | 0 | 310.4
Shafiq Ahmed | 0 | 624 | [27 empty] | 120 |  | 96 | [22 empty] | 0 | 840
Tauseef Shahzad |  | 14 | [7 empty] | 4 |  |  |  | 1 | [5 empty] | 16 |  | 4 |  | 25 |  |  |  | 42 |  |  |  | 136.5 |  | 27 |  |  |  | 4 |  |  |  | 58 | [13 empty] | 331.5
Grand Total | 0 | 952.5 | 12 | 575 | 40.9 | 845.5 | 0 | 1278.4 | 0 | 128.8 | 0 | 22 | 170.4 | 1415.25 | 0 | 205.5 |  | 70.5 | 0 | 514 |  | 216 |  | 41.5 | 0 | 16 | 6.8 | 881.05 |  | 124.8 | 0 | 1681.9 |  | 27 | 0 | 49 | 0 | 96.7 |  | 67.1 |  | 58 | 0 | 300.75 | 0 | 35 | 69.2 | 145 | 95 | 1547.1 | 0 | 19.8 | 0 | 64.5 | 394.3 | 11378.65
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## By Project - Employee
Sum of Hours | Column Labels
Row Labels | Abid Ali | Anees Rahman | Arif Khan Arif | Arslan Khalid | Asad Mahmood | Asim Jameel | Asiya Bibi | Ayesha Qurban | Bilal Afzal Raja | Fawad Ahmed | Hamza Nouman | Imran UL Haq | Kashif Hayat | Saad Saeed | Shafiq Ahmed | Tauseef Shahzad | Arshad Sadal | Farooq Azam | Grand Total
AD-0001 | 39 |  |  |  | 37 | 118.85 | 647.5 |  |  |  | 32.5 |  | 16 | 15.05 | 840 | 616.5 |  |  | 2362.4
AP WORKFLOW | 127 |  |  | 113 | 138 |  |  | 139 | 77 | 0 | 75 | 52 | 143 | 1 |  | 33 |  |  | 898
APWORKS 2024.2 - PHASE 3 | 203 |  | 126 | 274 | 265 | 67.5 |  | 212 | 42.5 | 179 | 258 | 7 | 165 |  |  | 8 | 11 |  | 1818
APWORKS 2024.2 - PHASE 4 | 53.5 |  | 4.5 | 106.5 | 126.5 |  |  | 45 |  |  | 22 | 87 | 86 |  |  | 7 |  |  | 538
APWORKS 2024.2 PHASE 5 |  |  |  | 14 |  |  |  | 5 |  |  | 5 |  | 48 | [5 empty] | 72
APWORKS PHASE1 | [11 empty] | 1 | [6 empty] | 1
APWORKS PHASE2 | 41.5 |  | 42.5 | 198 | 219 | 18.5 |  | 182 | 60 | 5.5 | 58.5 | 38 | 245 | [5 empty] | 1108.5
NEXELUS 13.0 | [5 empty] | 9.8 | [11 empty] | 40 | 49.8
NEXELUS 14.0 | [10 empty] | 11 | [7 empty] | 11
NEXELUS 2024.1 SP2 | 76.5 |  | 25.5 |  |  | 95.5 |  |  | 102.5 | 322.05 | 67.5 | 3 |  | 219.35 |  |  |  |  | 911.9
NEXELUS 2024.2 | 116.5 | 477.5 | 106 |  |  | 87.6 |  | 60 | 173.5 | 46 | 113 | 345.5 |  | 3 |  | 14 |  |  | 1542.6
NEXELUS SUPPORT | 11 | 240 | 6 | [8 empty] | 7 | [6 empty] | 264
PR-0013 | 178.4 |  | 375 | 118.5 | 32 | 103.65 | 46.5 | 59 | 356 | 39.9 | 111.5 | 48.5 | 98 | 72 |  | 70 |  |  | 1708.95
Support and Maintenance | 39.5 |  | 2 |  |  | 34 |  | 83 |  |  | 51 | 272 | 28 |  |  | 10 |  |  | 519.5
Grand Total | 885.9 | 717.5 | 687.5 | 824 | 817.5 | 535.4 | 694 | 785 | 811.5 | 592.45 | 805 | 861 | 829 | 310.4 | 840 | 758.5 | 11 | 40 | 11805.65

## By Task - Employee
Sum of Hours | Column Labels
Row Labels | Abid Ali | Anees Rahman | Arif Khan Arif | Arslan Khalid | Asad Mahmood | Asim Jameel | Asiya Bibi | Ayesha Qurban | Bilal Afzal Raja | Fawad Ahmed | Hamza Nouman | Imran UL Haq | Kashif Hayat | Saad Saeed | Shafiq Ahmed | Tauseef Shahzad | Arshad Sadal | Farooq Azam | (blank) | Grand Total
Admin | [5 empty] | 3 | 310.5 | [6 empty] | 1 | 624 | 56 |  |  |  | 994.5
Analysis | 49 |  | 156.5 | 19 | 2.5 | 12 |  | 46 | 115 | 35 | 19 | 21 | 99 | 1 | [5 empty] | 575
Bug Fixing | 65 |  | 114 | 253 | 220 |  |  |  | 2.5 | 58 | 5 | 112 | 16 | [6 empty] | 845.5
Client Items | 56 | 435 | 74.5 | 15 |  | 100.9 |  | 86 |  | 0 | 51 | 406 | 54 |  |  | 10 |  |  |  | 1288.4
Deployment | 86.5 | 6.5 | 15 |  | 3 |  |  |  |  | 6.8 |  | 7 |  |  |  | 11 |  |  |  | 135.8
Design |  |  |  | 22 | [15 empty] | 22
Development | 65.5 |  | 124 | 253 | 281 | 44 |  |  | 5 | 410.75 |  | 99.5 |  | 131.5 |  | 1 |  |  |  | 1415.25
Documentation |  |  | 2 |  |  | 128.5 |  | 4 | 49.5 | 5 | 15.5 |  | 1 | [6 empty] | 205.5
Domain Learning | [8 empty] | 6.5 |  |  |  |  | 64 | [5 empty] | 70.5
Holiday-Time Off | 63.5 |  | 9 | 38 | 56 | 24 | 3 | 57 | 57 | 12 | 58.5 | 16 | 96 | 8 |  | 19 |  |  |  | 517
HR Management | [6 empty] | 212 | [8 empty] | 4 |  |  |  | 216
Interview | [6 empty] | 16.5 | [8 empty] | 30 |  |  |  | 46.5
Leave | [10 empty] | 8 |  | 8 |  |  | 64 |  |  |  | 80
Meetings | 175.2 |  | 32 | 67.5 | 60 | 120.85 | 48.5 | 47 | 123.5 | 28.65 | 79 | 9.5 | 37 | 10.35 |  | 174 |  |  |  | 1013.05
No Workbench | [10 empty] | 1.5 |  |  | 3.3 | 120 |  |  |  |  | 124.8
PMO | [15 empty] | 149 |  |  |  | 149
Post_dep_fixes | 9 |  |  |  | 16 |  |  |  |  | 1 | 7 | 16 | [7 empty] | 49
Project Mgmt | 89.2 |  |  |  |  | 3.5 | [9 empty] | 4 |  |  |  | 96.7
Research | [13 empty] | 56.1 |  |  | 11 |  |  | 67.1
SOC Compliance | [15 empty] | 100 |  |  |  | 100
Task/Code Review | 31 |  |  | 1 | [5 empty] | 3 | [9 empty] | 35
Test Case Dev | [7 empty] | 68 | 12 |  | 48 |  | 17 | [6 empty] | 145
Testing | 24.5 |  | 1 | 7.5 | 35 | 5 |  | 330 | 297 | 23.75 | 429.5 |  | 364 | 29.85 | [5 empty] | 1547.1
Training |  |  |  | 4 | [5 empty] | 8.5 |  |  | 2 | 5.3 | [5 empty] | 19.8
Unassigned time |  |  | 62.5 | [7 empty] | 2 | [8 empty] | 64.5
(blank)
Other | 142 | 36 | 95.5 | 144 | 144 | 84.9 | 103.5 | 142 | 143.5 |  | 81 | 158 | 135 |  | 96 | 136.5 |  | 40 |  | 1681.9
Support Tickets | 29.5 | 240 | 1.5 |  |  | 8.75 |  | 5 |  |  |  | 16 | [7 empty] | 300.75
Grand Total | 885.9 | 717.5 | 687.5 | 824 | 817.5 | 535.4 | 694 | 785 | 811.5 | 592.45 | 805 | 861 | 829 | 310.4 | 840 | 758.5 | 11 | 40 |  | 11805.65

## OH Tasks
Sum of Hours | Column Labels
Row Labels | Admin | Deployment | Documentation | Domain Learning | Holiday-Time Off | Interview | Leave | Meetings | No Workbench | Research | Task/Code Review | Test Case Dev | Unassigned time | Grand Total
Abid Ali |  | 86.5 |  |  | 63.5 |  |  | 175.2 |  |  | 31 |  |  | 356.2
Anees Rahman |  | 6.5 | [11 empty] | 6.5
Arif Khan Arif |  | 15 | 2 |  | 9 |  |  | 32 |  |  |  |  | 62.5 | 120.5
Arslan Khalid |  |  |  |  | 38 |  |  | 67.5 |  |  | 1 |  |  | 106.5
Asad Mahmood |  | 3 |  |  | 56 |  |  | 60 | [5 empty] | 119
Asim Jameel | 3 |  | 128.5 |  | 24 |  |  | 120.85 | [5 empty] | 276.35
Asiya Bibi | 310.5 |  |  |  | 3 | 16.5 |  | 48.5 | [5 empty] | 378.5
Ayesha Qurban |  |  | 4 |  | 57 |  |  | 47 |  |  |  | 68 |  | 176
Bilal Afzal Raja |  |  | 49.5 | 6.5 | 57 |  |  | 123.5 |  |  |  | 12 |  | 248.5
Fawad Ahmed |  | 6.8 | 5 |  | 12 |  |  | 28.65 |  |  | 3 |  |  | 55.45
Hamza Nouman |  |  | 15.5 |  | 58.5 |  | 8 | 79 | 1.5 |  |  | 48 | 2 | 212.5
Imran UL Haq |  | 7 |  |  | 16 |  |  | 9.5 | [5 empty] | 32.5
Kashif Hayat |  |  | 1 |  | 96 |  | 8 | 37 |  |  |  | 17 |  | 159
Saad Saeed | 1 |  |  | 64 | 8 |  |  | 10.35 | 3.3 | 56.1 |  |  |  | 142.75
Shafiq Ahmed | 624 | [7 empty] | 120 |  |  |  |  | 744
Tauseef Shahzad | 56 | 11 |  |  | 19 | 30 | 64 | 174 | [5 empty] | 354
Arshad Sadal | [9 empty] | 11 |  |  |  | 11
Grand Total | 994.5 | 135.8 | 205.5 | 70.5 | 517 | 46.5 | 80 | 1013.05 | 124.8 | 67.1 | 35 | 145 | 64.5 | 3499.25

## data
employee | LEVEL2_KEY | level3_key | LEVEL3_DESCRIPTION | TASK_CODE | AppliedMonth | Hours | Ncolumn | Est Hours | Identity
Abid Ali | AP WORKFLOW | Production Issue | Analysis of production issues reported by support team | Development | 2024-08 | 1 | 1 |  | AP WORKFLOW: Analysis of production issues reported by support team
Abid Ali | AP WORKFLOW | Production Issue | Analysis of production issues reported by support team | Other | 2024-08 | 1 | 1 |  | AP WORKFLOW: Analysis of production issues reported by support team
Abid Ali | AP WORKFLOW | Cient UAT Upgrad | Cient UAT Upgrade | Other | 2024-08 | 0.5 | 1 |  | AP WORKFLOW: Cient UAT Upgrade
Abid Ali | AP WORKFLOW | Development DotN | Development of new project/assignment/task | Bug Fixing | 2024-08 | 3 | 1 |  | AP WORKFLOW: Development of new project/assignment/task
Abid Ali | AP WORKFLOW | Development DotN | Development of new project/assignment/task | Development | 2024-08 | 2 | 1 | 0 | AP WORKFLOW: Development of new project/assignment/task
Abid Ali | AP WORKFLOW | Development DotN | Development of new project/assignment/task | Other | 2024-08 | 20.5 | 1 | 0 | AP WORKFLOW: Development of new project/assignment/task
Abid Ali | AP WORKFLOW | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-08 | 3 | 1 |  | AP WORKFLOW: Meetings, mails, communication, TFS, Interviews
Abid Ali | AP WORKFLOW | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 1 | 1 |  | AP WORKFLOW: Meetings, mails, communication, TFS, Interviews
Abid Ali | AP WORKFLOW | Planning | Project planning for new project/assignment/task | Other | 2024-08 | 20.5 | 1 | 0 | AP WORKFLOW: Project planning for new project/assignment/task
Abid Ali | AP WORKFLOW | QA Environment U | QA Environment Upgrade | Deployment | 2024-08 | 3.5 | 1 |  | AP WORKFLOW: QA Environment Upgrade
Abid Ali | AP WORKFLOW | QA Environment U | QA Environment Upgrade | Other | 2024-08 | 10 | 1 |  | AP WORKFLOW: QA Environment Upgrade
Abid Ali | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Meetings | 2024-08 | 9.5 | 1 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Project Mgmt | 2024-08 | 3 | 1 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Abid Ali | NEXELUS 2024.2 | Production Issue | Analysis of production issues reported by support team | Development | 2024-08 | 8 | 1 |  | NEXELUS 2024.2: Analysis of production issues reported by support team
Abid Ali | NEXELUS 2024.2 | Production Issue | Analysis of production issues reported by support team | Other | 2024-08 | 9 | 1 | 0 | NEXELUS 2024.2: Analysis of production issues reported by support team
Abid Ali | NEXELUS 2024.2 | Cient UAT Upgrad | Cient UAT Upgrade | Other | 2024-08 | 3.5 | 1 |  | NEXELUS 2024.2: Cient UAT Upgrade
Abid Ali | NEXELUS 2024.2 | Client Items | Client Items | Other | 2024-08 | 5 | 1 |  | NEXELUS 2024.2: Client Items
Abid Ali | NEXELUS 2024.2 | Dev Support | Dev Support | Other | 2024-08 | 2 | 1 |  | NEXELUS 2024.2: Dev Support
Abid Ali | NEXELUS 2024.2 | Internal Meeting | Internal Meetings | Other | 2024-08 | 17 | 1 |  | NEXELUS 2024.2: Internal Meetings
Abid Ali | NEXELUS 2024.2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Development | 2024-08 | 3 | 1 |  | NEXELUS 2024.2: Meetings, mails, communication, TFS, Interviews
Abid Ali | NEXELUS 2024.2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 18.5 | 1 | 0 | NEXELUS 2024.2: Meetings, mails, communication, TFS, Interviews
Abid Ali | NEXELUS 2024.2 | Session Meetings | Session with US team | Other | 2024-08 | 33.5 | 1 |  | NEXELUS 2024.2: Session with US team
Abid Ali | PR-0013 | Session Meetings | Session with US team | Meetings | 2024-08 | 2 | 1 |  | PR-0013: Session with US team
Abid Ali | AP WORKFLOW | National Gazette | National Gazetted Holidays | Leave | 2024-09 | 8 | 2 |  | AP WORKFLOW: National Gazetted Holidays
Abid Ali | AP WORKFLOW | QA Environment U | QA Environment Upgrade | Deployment | 2024-09 | 1 | 2 |  | AP WORKFLOW: QA Environment Upgrade
Abid Ali | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Analysis | 2024-09 | 3 | 2 |  | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Abid Ali | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Analysis | 2024-09 | 0.5 | 2 |  | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Abid Ali | APWORKS 2024.2 - PHASE 3 | 2 | Add Media Type/Service type/Roles | Analysis | 2024-09 | 2 | 2 |  | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles
Abid Ali | APWORKS 2024.2 - PHASE 3 | 7 | Associate vendor/stations/sites to multiple pay to | Analysis | 2024-09 | 1 | 2 |  | APWORKS 2024.2 - PHASE 3: Associate vendor/stations/sites to multiple pay to
Abid Ali | APWORKS 2024.2 - PHASE 3 | 10 | Broadcast Invoice: Invoice View UI | Task/Code Review | 2024-09 | 2 | 2 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Invoice View UI
Abid Ali | APWORKS 2024.2 - PHASE 3 | 9 | Broadcast Invoice: Manage Invoice Models List | Analysis | 2024-09 | 2 | 2 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Manage Invoice Models List
Abid Ali | APWORKS 2024.2 - PHASE 3 | 11 | Broadcast Invoice: PDF file generation | Analysis | 2024-09 | 5 | 2 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: PDF file generation
Abid Ali | APWORKS 2024.2 - PHASE 3 | 11 | Broadcast Invoice: PDF file generation | Development | 2024-09 | 5 | 2 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: PDF file generation
Abid Ali | APWORKS 2024.2 - PHASE 3 | 28 | Customer Information: Select Client on Vendor Invoice | Analysis | 2024-09 | 0.5 | 2 |  | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice
Abid Ali | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Deployment | 2024-09 | 2.5 | 2 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Meetings | 2024-09 | 13.5 | 2 | 0 | APWORKS 2024.2 - PHASE 3: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Project Mgmt | 2024-09 | 1 | 2 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 3 | 29 | Route invoice from one company - company identification | Analysis | 2024-09 | 1 | 2 |  | APWORKS 2024.2 - PHASE 3: Route invoice from one company - company identification
Abid Ali | APWORKS PHASE2 | Dev Support | Dev Support | Meetings | 2024-09 | 1 | 2 | 0 | APWORKS PHASE2: Dev Support
Abid Ali | APWORKS PHASE2 | Requirement Anal | Document review/understanding Requirement Specifications | Testing | 2024-09 | 11 | 2 |  | APWORKS PHASE2: Document review/understanding Requirement Specifications
Abid Ali | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-09 | 16 | 2 | 0 | APWORKS PHASE2: Regular bug fixing activity
Abid Ali | NEXELUS 2024.2 | Production Issue | Analysis of production issues reported by support team | Client Items | 2024-09 | 9 | 2 |  | NEXELUS 2024.2: Analysis of production issues reported by support team
Abid Ali | NEXELUS 2024.2 | National Gazette | National Gazetted Holidays | Leave | 2024-09 | 8 | 2 |  | NEXELUS 2024.2: National Gazetted Holidays
Abid Ali | PR-0013 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-09 | 10 | 2 |  | PR-0013: Analysis of production issues reported by support team
Abid Ali | PR-0013 | Production Issue | Analysis of production issues reported by support team | Bug Fixing | 2024-09 | 12 | 2 |  | PR-0013: Analysis of production issues reported by support team
Abid Ali | PR-0013 | Cient UAT Upgrad | Cient UAT Upgrade | Client Items | 2024-09 | 3.5 | 2 |  | PR-0013: Cient UAT Upgrade
Abid Ali | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 17.5 | 2 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Abid Ali | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 4 | 2 | 0 | PR-0013: Meetings, mails, communication, TFS, Interviews
Abid Ali | PR-0013 | Production Upgra | Production upgrades | Deployment | 2024-09 | 3 | 2 |  | PR-0013: Production upgrades
Abid Ali | PR-0013 | Session Meetings | Session with US team | Meetings | 2024-09 | 8.5 | 2 |  | PR-0013: Session with US team
Abid Ali | PR-0013 | Session Meetings | Session with US team | Meetings | 2024-09 | 2.7 | 2 |  | PR-0013: Session with US team
Abid Ali | PR-0013 | Time Off-Planned | Time Off - Planned | Leave | 2024-09 | 16 | 2 |  | PR-0013: Time Off - Planned
Abid Ali | AP WORKFLOW | Production Issue | Analysis of production issues reported by support team | Bug Fixing | 2024-10 | 5 | 3 | 0 | AP WORKFLOW: Analysis of production issues reported by support team
Abid Ali | AP WORKFLOW | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-10 | 3 | 3 | 0 | AP WORKFLOW: Regular bug fixing activity
Abid Ali | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Task/Code Review | 2024-10 | 3 | 3 |  | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Abid Ali | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Analysis | 2024-10 | 1 | 3 |  | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Abid Ali | APWORKS 2024.2 - PHASE 3 | 7 | Associate vendor/stations/sites to multiple pay to | Task/Code Review | 2024-10 | 1 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Associate vendor/stations/sites to multiple pay to
Abid Ali | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Analysis | 2024-10 | 2 | 3 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Abid Ali | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Development | 2024-10 | 7 | 3 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Abid Ali | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Task/Code Review | 2024-10 | 13 | 3 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Abid Ali | APWORKS 2024.2 - PHASE 3 | 11 | Broadcast Invoice: PDF file generation | Development | 2024-10 | 23 | 3 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: PDF file generation
Abid Ali | APWORKS 2024.2 - PHASE 3 | 11 | Broadcast Invoice: PDF file generation | Testing | 2024-10 | 10.5 | 3 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: PDF file generation
Abid Ali | APWORKS 2024.2 - PHASE 3 | 28 | Customer Information: Select Client on Vendor Invoice | Analysis | 2024-10 | 2 | 3 |  | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice
Abid Ali | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Bug Fixing | 2024-10 | 9 | 3 |  | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Abid Ali | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Task/Code Review | 2024-10 | 4 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Abid Ali | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Analysis | 2024-10 | 4.5 | 3 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Deployment | 2024-10 | 24.5 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Meetings | 2024-10 | 13.5 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Project Mgmt | 2024-10 | 8 | 3 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Analysis | 2024-10 | 1 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Abid Ali | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Development | 2024-10 | 2 | 3 |  | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Abid Ali | APWORKS PHASE2 | Cient UAT Upgrad | Cient UAT Upgrade | Deployment | 2024-10 | 10.5 | 3 | 0 | APWORKS PHASE2: Cient UAT Upgrade
Abid Ali | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-10 | 3 | 3 |  | APWORKS PHASE2: Regular bug fixing activity
Abid Ali | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Meetings | 2024-10 | 2.5 | 3 | 0 | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Abid Ali | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Analysis | 2024-10 | 4 | 3 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Abid Ali | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Meetings | 2024-10 | 12 | 3 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Abid Ali | PR-0013 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-10 | 1 | 3 |  | PR-0013: Analysis of production issues reported by support team
Abid Ali | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-10 | 13.5 | 3 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Abid Ali | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Project Mgmt | 2024-10 | 5 | 3 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Abid Ali | PR-0013 | Session Meetings | Session with US team | Meetings | 2024-10 | 10 | 3 |  | PR-0013: Session with US team
Abid Ali | PR-0013 | Session Meetings | Session with US team | Project Mgmt | 2024-10 | 2.7 | 3 |  | PR-0013: Session with US team
Abid Ali | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-10 | 1.5 | 3 |  | PR-0013: Time Off - Un Planned
Abid Ali | Support and Maintenance | 1 | Time | Client Items | 2024-10 | 2 | 3 |  | Support and Maintenance: Time
Abid Ali | AD-0001 | 1 | Meetings | Meetings | 2024-11 | 9.5 | 4 |  | AD-0001: Meetings
Abid Ali | AD-0001 | 1 | Meetings | Meetings | 2024-11 | 4 | 4 |  | AD-0001: Meetings
Abid Ali | AP WORKFLOW | Cient UAT Upgrad | Cient UAT Upgrade | Deployment | 2024-11 | 12 | 4 |  | AP WORKFLOW: Cient UAT Upgrade
Abid Ali | AP WORKFLOW | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Project Mgmt | 2024-11 | 18 | 4 |  | AP WORKFLOW: Meetings, mails, communication, TFS, Interviews
Abid Ali | AP WORKFLOW | QA Environment U | QA Environment Upgrade | Deployment | 2024-11 | 6 | 4 |  | AP WORKFLOW: QA Environment Upgrade
Abid Ali | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Deployment | 2024-11 | 5.5 | 4 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Project Mgmt | 2024-11 | 17 | 4 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 4 | 2 | A report to spot check the invoices processed | Development | 2024-11 | 3 | 4 |  | APWORKS 2024.2 - PHASE 4: A report to spot check the invoices processed
Abid Ali | APWORKS 2024.2 - PHASE 4 | 99 | EDI: Generate PDF - Updates | Development | 2024-11 | 11.5 | 4 |  | APWORKS 2024.2 - PHASE 4: EDI: Generate PDF - Updates
Abid Ali | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Analysis | 2024-11 | 1 | 4 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Deployment | 2024-11 | 6 | 4 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Project Mgmt | 2024-11 | 7 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Project Overhead
Abid Ali | NEXELUS 2024.1 SP2 | 5 | eConnect shell change to service | Testing | 2024-11 | 2 | 4 | 0 | NEXELUS 2024.1 SP2: eConnect shell change to service
Abid Ali | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Analysis | 2024-11 | 1 | 4 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Abid Ali | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Bug Fixing | 2024-11 | 10 | 4 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Abid Ali | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Deployment | 2024-11 | 5 | 4 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Abid Ali | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Meetings | 2024-11 | 10.5 | 4 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Abid Ali | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Post_dep_fixes | 2024-11 | 9 | 4 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Abid Ali | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Project Mgmt | 2024-11 | 2 | 4 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Abid Ali | PR-0013 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-11 | 2 | 4 | 0 | PR-0013: Analysis of production issues reported by support team
Abid Ali | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Project Mgmt | 2024-11 | 7.5 | 4 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Abid Ali | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2024-11 | 7.5 | 4 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Abid Ali | PR-0013 | Session Meetings | Session with US team | Meetings | 2024-11 | 11.5 | 4 |  | PR-0013: Session with US team
Abid Ali | Support and Maintenance | 1 | Time | Client Items | 2024-11 | 7 | 4 |  | Support and Maintenance: Time
Abid Ali | Support and Maintenance | 1 | Time | Support Tickets | 2024-11 | 1 | 4 |  | Support and Maintenance: Time
Abid Ali | Support and Maintenance | 1 | Time | Support Tickets | 2024-11 | 1 | 4 |  | Support and Maintenance: Time
Abid Ali | AD-0001 | 1 | Meetings | Meetings | 2024-12 | 9 | 5 |  | AD-0001: Meetings
Abid Ali | AD-0001 | 1 | Meetings | Meetings | 2024-12 | 16.5 | 5 |  | AD-0001: Meetings
Abid Ali | AP WORKFLOW | National Gazette | National Gazetted Holidays | Leave | 2024-12 | 8 | 5 |  | AP WORKFLOW: National Gazetted Holidays
Abid Ali | APWORKS 2024.2 - PHASE 4 | 105 | PDF based broadcast invoices - Import / Export lines | Task/Code Review | 2024-12 | 1 | 5 |  | APWORKS 2024.2 - PHASE 4: PDF based broadcast invoices - Import / Export lines
Abid Ali | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Deployment | 2024-12 | 7 | 5 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Meetings | 2024-12 | 1 | 5 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Abid Ali | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Project Mgmt | 2024-12 | 16 | 5 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Abid Ali | NEXELUS 2024.1 SP2 | 57 | AdTech Fee commission | Analysis | 2024-12 | 0.5 | 5 |  | NEXELUS 2024.1 SP2: AdTech Fee commission
Abid Ali | NEXELUS 2024.1 SP2 | 57 | AdTech Fee commission | Task/Code Review | 2024-12 | 1.5 | 5 | 0 | NEXELUS 2024.1 SP2: AdTech Fee commission
Abid Ali | NEXELUS 2024.1 SP2 | 5 | eConnect shell change to service | Testing | 2024-12 | 1 | 5 | 0 | NEXELUS 2024.1 SP2: eConnect shell change to service
Abid Ali | NEXELUS 2024.1 SP2 | 56 | Enhancement for Visual Indicators and Flighting Details in Place | Task/Code Review | 2024-12 | 2.5 | 5 | 0 | NEXELUS 2024.1 SP2: Enhancement for Visual Indicators and Flighting Details in Place
Abid Ali | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Bug Fixing | 2024-12 | 4 | 5 | 0 | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Abid Ali | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Task/Code Review | 2024-12 | 3 | 5 | 0 | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Abid Ali | NEXELUS 2024.1 SP2 | 59 | Media Plan: Import/Export Flighting | Analysis | 2024-12 | 1 | 5 | 0 | NEXELUS 2024.1 SP2: Media Plan: Import/Export Flighting
Abid Ali | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Analysis | 2024-12 | 2 | 5 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Abid Ali | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Project Mgmt | 2024-12 | 2 | 5 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Abid Ali | NEXELUS 2024.1 SP2 | 58 | Restrict Self Approval - Time and expense | Analysis | 2024-12 | 1 | 5 | 0 | NEXELUS 2024.1 SP2: Restrict Self Approval - Time and expense
Abid Ali | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2024-12 | 15 | 5 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Abid Ali | PR-0013 | Time Off-Planned | Time Off - Planned | Leave | 2024-12 | 8 | 5 |  | PR-0013: Time Off - Planned
Abid Ali | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-12 | 14 | 5 |  | PR-0013: Time Off - Un Planned
Abid Ali | Support and Maintenance | 2 | Time | Client Items | 2024-12 | 5 | 5 |  | Support and Maintenance: Time
Abid Ali | Support and Maintenance | 2 | Time | Client Items | 2024-12 | 1 | 5 |  | Support and Maintenance: Time
Abid Ali | Support and Maintenance | 2 | Time | Client Items | 2024-12 | 28.5 | 5 |  | Support and Maintenance: Time
Abid Ali | Support and Maintenance | 1 | Time | Support Tickets | 2024-12 | 5 | 5 |  | Support and Maintenance: Time
Anees Rahman | NEXELUS 2024.2 | Support Items | Support Items | Client Items | 2024-08 | 81 | 1 |  | NEXELUS 2024.2: Support Items
Anees Rahman | NEXELUS 2024.2 | Support Items | Support Items | Deployment | 2024-08 | 6.5 | 1 |  | NEXELUS 2024.2: Support Items
Anees Rahman | NEXELUS 2024.2 | Support Items | Support Items | Other | 2024-08 | 36 | 1 |  | NEXELUS 2024.2: Support Items
Anees Rahman | NEXELUS 2024.2 | Support Items | Support Items | Client Items | 2024-09 | 145 | 2 |  | NEXELUS 2024.2: Support Items
Anees Rahman | NEXELUS 2024.2 | Support Items | Support Items | Client Items | 2024-10 | 148 | 3 |  | NEXELUS 2024.2: Support Items
Anees Rahman | NEXELUS 2024.2 | Support Items | Support Items | Client Items | 2024-11 | 61 | 4 |  | NEXELUS 2024.2: Support Items
Anees Rahman | Support and Maintenance | 1 | Time | Support Tickets | 2024-11 | 88 | 4 | 0 | Support and Maintenance: Time
Anees Rahman | Support and Maintenance | 1 | Time | Support Tickets | 2024-12 | 152 | 5 |  | Support and Maintenance: Time
Arif Khan Arif | NEXELUS 2024.2 | Production Issue | Analysis of production issues reported by support team | Other | 2024-08 | 12 | 1 |  | NEXELUS 2024.2: Analysis of production issues reported by support team
Arif Khan Arif | NEXELUS 2024.2 | Client Items | Client Items | Other | 2024-08 | 8 | 1 | 0 | NEXELUS 2024.2: Client Items
Arif Khan Arif | NEXELUS 2024.2 | Development DB | Development of new project/assignment/task | Bug Fixing | 2024-08 | 4.5 | 1 |  | NEXELUS 2024.2: Development of new project/assignment/task
Arif Khan Arif | NEXELUS 2024.2 | Development DB | Development of new project/assignment/task | Other | 2024-08 | 32.5 | 1 |  | NEXELUS 2024.2: Development of new project/assignment/task
Arif Khan Arif | NEXELUS 2024.2 | Internal Meeting | Internal Meetings | Leave | 2024-08 | 1 | 1 |  | NEXELUS 2024.2: Internal Meetings
Arif Khan Arif | NEXELUS 2024.2 | Internal Meeting | Internal Meetings | Other | 2024-08 | 12 | 1 |  | NEXELUS 2024.2: Internal Meetings
Arif Khan Arif | NEXELUS 2024.2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 14.5 | 1 |  | NEXELUS 2024.2: Meetings, mails, communication, TFS, Interviews
Arif Khan Arif | NEXELUS 2024.2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Testing | 2024-08 | 1 | 1 |  | NEXELUS 2024.2: Meetings, mails, communication, TFS, Interviews
Arif Khan Arif | NEXELUS 2024.2 | National Gazette | National Gazetted Holidays | Other | 2024-08 | 8 | 1 |  | NEXELUS 2024.2: National Gazetted Holidays
Arif Khan Arif | NEXELUS 2024.2 | Session Meetings | Session with US team | Other | 2024-08 | 1 | 1 | 0 | NEXELUS 2024.2: Session with US team
Arif Khan Arif | NEXELUS 2024.2 | Support Items | Support Items | Documentation | 2024-08 | 2 | 1 | 0 | NEXELUS 2024.2: Support Items
Arif Khan Arif | NEXELUS 2024.2 | Support Items | Support Items | Other | 2024-08 | 7.5 | 1 |  | NEXELUS 2024.2: Support Items
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Development | 2024-09 | 6 | 2 | 59.5 | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 7 | Associate vendor/stations/sites to multiple pay to | Development | 2024-09 | 2 | 2 | 0 | APWORKS 2024.2 - PHASE 3: Associate vendor/stations/sites to multiple pay to
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Development | 2024-09 | 10.5 | 2 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Development | 2024-09 | 2 | 2 | 0 | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Analysis | 2024-09 | 4 | 2 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Arif Khan Arif | APWORKS PHASE2 | Internal Meeting | Internal Meetings | Meetings | 2024-09 | 4 | 2 |  | APWORKS PHASE2: Internal Meetings
Arif Khan Arif | APWORKS PHASE2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | No Workbench | 2024-09 | 4 | 2 |  | APWORKS PHASE2: Meetings, mails, communication, TFS, Interviews
Arif Khan Arif | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-09 | 22 | 2 |  | APWORKS PHASE2: Regular bug fixing activity
Arif Khan Arif | APWORKS PHASE2 | Time Off-Planned | Time Off - Planned | Leave | 2024-09 | 8 | 2 |  | APWORKS PHASE2: Time Off - Planned
Arif Khan Arif | NEXELUS 2024.2 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-09 | 2 | 2 | 0 | NEXELUS 2024.2: Analysis of production issues reported by support team
Arif Khan Arif | PR-0013 | Development DB | Development of new project/assignment/task | Bug Fixing | 2024-09 | 35 | 2 | 0 | PR-0013: Development of new project/assignment/task
Arif Khan Arif | PR-0013 | Internal Meeting | Internal Meetings | Development | 2024-09 | 11 | 2 | 0 | PR-0013: Internal Meetings
Arif Khan Arif | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Analysis | 2024-09 | 7.5 | 2 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Arif Khan Arif | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 5 | 2 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Arif Khan Arif | PR-0013 | Production Upgra | Production upgrades | Development | 2024-09 | 5 | 2 |  | PR-0013: Production upgrades
Arif Khan Arif | PR-0013 | Session Meetings | Session with US team | Analysis | 2024-09 | 3 | 2 | 0 | PR-0013: Session with US team
Arif Khan Arif | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | No Workbench | 2024-09 | 43 | 2 | 0 | PR-0013: Time Off - Un Planned
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Development | 2024-10 | 13 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 28 | Customer Information: Select Client on Vendor Invoice | Development | 2024-10 | 4 | 3 | 12 | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 14 | Enhancement in vendor mapping(Parse Table) | Bug Fixing | 2024-10 | 4 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Enhancement in vendor mapping(Parse Table)
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Deployment | 2024-10 | 15 | 3 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 31 | Vendor/stations/sites associated to multiple pay to. | Development | 2024-10 | 8 | 3 |  | APWORKS 2024.2 - PHASE 3: Vendor/stations/sites associated to multiple pay to.
Arif Khan Arif | NEXELUS 2024.1 SP2 | 6 | Backup Table for vendor/client lines relationship | Development | 2024-10 | 3 | 3 |  | NEXELUS 2024.1 SP2: Backup Table for vendor/client lines relationship
Arif Khan Arif | PR-0013 | Development DB | Development of new project/assignment/task | Bug Fixing | 2024-10 | 10 | 3 | 0 | PR-0013: Development of new project/assignment/task
Arif Khan Arif | PR-0013 | Development DB | Development of new project/assignment/task | Client Items | 2024-10 | 63 | 3 |  | PR-0013: Development of new project/assignment/task
Arif Khan Arif | PR-0013 | Internal Meeting | Internal Meetings | Development | 2024-10 | 3 | 3 | 0 | PR-0013: Internal Meetings
Arif Khan Arif | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Analysis | 2024-10 | 23 | 3 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Arif Khan Arif | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-10 | 21.5 | 3 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Arif Khan Arif | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | No Workbench | 2024-10 | 7.5 | 3 | 0 | PR-0013: Meetings, mails, communication, TFS, Interviews
Arif Khan Arif | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | No Workbench | 2024-10 | 8 | 3 | 0 | PR-0013: Time Off - Un Planned
Arif Khan Arif | Support and Maintenance | 1 | Time | Client Items | 2024-10 | 2 | 3 | 0 | Support and Maintenance: Time
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 7 | Associate vendor/stations/sites to multiple pay to | Development | 2024-11 | 4.5 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Associate vendor/stations/sites to multiple pay to
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Bug Fixing | 2024-11 | 5.5 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 14 | Enhancement in vendor mapping(Parse Table) | Development | 2024-11 | 19 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Enhancement in vendor mapping(Parse Table)
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 31 | Vendor/stations/sites associated to multiple pay to. | Bug Fixing | 2024-11 | 3 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Vendor/stations/sites associated to multiple pay to.
Arif Khan Arif | APWORKS 2024.2 - PHASE 4 | 8 | Production: Project should be available on summary as well. | Development | 2024-11 | 3.5 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Production: Project should be available on summary as well.
Arif Khan Arif | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-11 | 4.5 | 4 | 0 | APWORKS PHASE2: Regular bug fixing activity
Arif Khan Arif | NEXELUS 2024.1 SP2 | 7 | Billing by Media Type | Bug Fixing | 2024-11 | 7.5 | 4 |  | NEXELUS 2024.1 SP2: Billing by Media Type
Arif Khan Arif | NEXELUS 2024.1 SP2 | 1 | Client Profile: Media > Flag to make the vendor inactive | Development | 2024-11 | 4.5 | 4 |  | NEXELUS 2024.1 SP2: Client Profile: Media > Flag to make the vendor inactive
Arif Khan Arif | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Development | 2024-11 | 3.5 | 4 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Arif Khan Arif | PR-0013 | Development DB | Development of new project/assignment/task | Bug Fixing | 2024-11 | 6 | 4 | 0 | PR-0013: Development of new project/assignment/task
Arif Khan Arif | PR-0013 | Development DB | Development of new project/assignment/task | Client Items | 2024-11 | 5 | 4 |  | PR-0013: Development of new project/assignment/task
Arif Khan Arif | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Analysis | 2024-11 | 64 | 4 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Arif Khan Arif | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-11 | 1.5 | 4 | 0 | PR-0013: Meetings, mails, communication, TFS, Interviews
Arif Khan Arif | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Analysis | 2024-11 | 20.5 | 4 | 0 | PR-0013: Time Off - Un Planned
Arif Khan Arif | Support and Maintenance | 2 | Time | Client Items | 2024-11 | 4.5 | 4 | 0 | Support and Maintenance: Time
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 14 | Enhancement in vendor mapping(Parse Table) | Bug Fixing | 2024-12 | 12 | 5 | 0 | APWORKS 2024.2 - PHASE 3: Enhancement in vendor mapping(Parse Table)
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | 14 | Enhancement in vendor mapping(Parse Table) | Development | 2024-12 | 13.5 | 5 |  | APWORKS 2024.2 - PHASE 3: Enhancement in vendor mapping(Parse Table)
Arif Khan Arif | APWORKS 2024.2 - PHASE 4 | 13 | EDI file updating and upload | Development | 2024-12 | 1 | 5 |  | APWORKS 2024.2 - PHASE 4: EDI file updating and upload
Arif Khan Arif | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Development | 2024-12 | 7 | 5 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Arif Khan Arif | NEXELUS SUPPORT | 3 | Maintenance Activity | Support Tickets | 2024-12 | 1.5 | 5 |  | NEXELUS SUPPORT: Maintenance Activity
Arif Khan Arif | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Analysis | 2024-12 | 32.5 | 5 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Arshad Sadal | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Research | 2024-08 | 11 | 1 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Arslan Khalid | AP WORKFLOW | Analysis | Analysis of the new project/assignment/task | Other | 2024-08 | 12 | 1 |  | AP WORKFLOW: Analysis of the new project/assignment/task
Arslan Khalid | AP WORKFLOW | Development DB | Development of new project/assignment/task | Other | 2024-08 | 10 | 1 |  | AP WORKFLOW: Development of new project/assignment/task
Arslan Khalid | AP WORKFLOW | Development DotN | Development of new project/assignment/task | Other | 2024-08 | 57 | 1 |  | AP WORKFLOW: Development of new project/assignment/task
Arslan Khalid | AP WORKFLOW | Bug Fixing | Regular bug fixing activity | Other | 2024-08 | 9 | 1 | 0 | AP WORKFLOW: Regular bug fixing activity
Arslan Khalid | APWORKS PHASE2 | Development DotN | Development of new project/assignment/task | Other | 2024-08 | 46 | 1 |  | APWORKS PHASE2: Development of new project/assignment/task
Arslan Khalid | APWORKS PHASE2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Client Items | 2024-08 | 3 | 1 |  | APWORKS PHASE2: Meetings, mails, communication, TFS, Interviews
Arslan Khalid | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-08 | 29 | 1 | 0 | APWORKS PHASE2: Regular bug fixing activity
Arslan Khalid | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Other | 2024-08 | 10 | 1 | 0 | APWORKS PHASE2: Regular bug fixing activity
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 7 | Associate vendor/stations/sites to multiple pay to | Design | 2024-09 | 3 | 2 | 0 | APWORKS 2024.2 - PHASE 3: Associate vendor/stations/sites to multiple pay to
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 7 | Associate vendor/stations/sites to multiple pay to | Development | 2024-09 | 21 | 2 | 0 | APWORKS 2024.2 - PHASE 3: Associate vendor/stations/sites to multiple pay to
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 10 | Broadcast Invoice: Invoice View UI | Development | 2024-09 | 16 | 2 | 30 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Invoice View UI
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 25 | Broadcast Invoice: Manage Invoice Documents | Development | 2024-09 | 2 | 2 | 4 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Manage Invoice Documents
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 9 | Broadcast Invoice: Manage Invoice Models List | Development | 2024-09 | 2 | 2 | 0 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Manage Invoice Models List
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 24 | Broadcast Invoice: Manage Non-Mapped Broadcast Invoices | Development | 2024-09 | 2 | 2 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Manage Non-Mapped Broadcast Invoices
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 23 | Broadcast Invoice: User Group Management Changes | Development | 2024-09 | 4 | 2 | 12 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: User Group Management Changes
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 20 | separate node for "Broadcast Invoices" | Development | 2024-09 | 8 | 2 | 0 | APWORKS 2024.2 - PHASE 3: separate node for "Broadcast Invoices"
Arslan Khalid | APWORKS PHASE2 | Analysis | Analysis of the new project/assignment/task | Development | 2024-09 | 6 | 2 |  | APWORKS PHASE2: Analysis of the new project/assignment/task
Arslan Khalid | APWORKS PHASE2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 3 | 2 |  | APWORKS PHASE2: Meetings, mails, communication, TFS, Interviews
Arslan Khalid | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-09 | 79 | 2 |  | APWORKS PHASE2: Regular bug fixing activity
Arslan Khalid | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-09 | 2 | 2 | 0 | PR-0013: Internal Meetings
Arslan Khalid | PR-0013 | Time Off-Planned | Time Off - Planned | Leave | 2024-09 | 16 | 2 | 0 | PR-0013: Time Off - Planned
Arslan Khalid | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-09 | 4 | 2 | 0 | PR-0013: Time Off - Un Planned
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Bug Fixing | 2024-10 | 13 | 3 |  | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 100 | Apply discount based on Payment terms settings | Bug Fixing | 2024-10 | 4 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Apply discount based on Payment terms settings
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 7 | Associate vendor/stations/sites to multiple pay to | Bug Fixing | 2024-10 | 10 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Associate vendor/stations/sites to multiple pay to
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 7 | Associate vendor/stations/sites to multiple pay to | Development | 2024-10 | 12 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Associate vendor/stations/sites to multiple pay to
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 7 | Associate vendor/stations/sites to multiple pay to | Task/Code Review | 2024-10 | 1 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Associate vendor/stations/sites to multiple pay to
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Development | 2024-10 | 5 | 3 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 10 | Broadcast Invoice: Invoice View UI | Bug Fixing | 2024-10 | 3 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Invoice View UI
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 10 | Broadcast Invoice: Invoice View UI | Development | 2024-10 | 2 | 3 |  | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Invoice View UI
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 25 | Broadcast Invoice: Manage Invoice Documents | Development | 2024-10 | 4 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Manage Invoice Documents
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 28 | Customer Information: Select Client on Vendor Invoice | Analysis | 2024-10 | 2 | 3 | 12 | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 28 | Customer Information: Select Client on Vendor Invoice | Bug Fixing | 2024-10 | 5 | 3 |  | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 28 | Customer Information: Select Client on Vendor Invoice | Design | 2024-10 | 6 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 28 | Customer Information: Select Client on Vendor Invoice | Development | 2024-10 | 25 | 3 |  | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 17 | Master Data: Payment Terms | Development | 2024-10 | 0 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Master Data: Payment Terms
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 29 | Route invoice from one company - company identification | Analysis | 2024-10 | 1 | 3 |  | APWORKS 2024.2 - PHASE 3: Route invoice from one company - company identification
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 29 | Route invoice from one company - company identification | Bug Fixing | 2024-10 | 9 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Route invoice from one company - company identification
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 29 | Route invoice from one company - company identification | Development | 2024-10 | 14 | 3 | 40 | APWORKS 2024.2 - PHASE 3: Route invoice from one company - company identification
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Analysis | 2024-10 | 3 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Bug Fixing | 2024-10 | 4 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Design | 2024-10 | 13 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Development | 2024-10 | 9 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 31 | Vendor/stations/sites associated to multiple pay to. | Bug Fixing | 2024-10 | 2 | 3 |  | APWORKS 2024.2 - PHASE 3: Vendor/stations/sites associated to multiple pay to.
Arslan Khalid | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-10 | 17 | 3 |  | APWORKS PHASE2: Regular bug fixing activity
Arslan Khalid | PR-0013 | Internal Meeting | Internal Meetings | Bug Fixing | 2024-10 | 0 | 3 | 0 | PR-0013: Internal Meetings
Arslan Khalid | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-10 | 14 | 3 | 0 | PR-0013: Internal Meetings
Arslan Khalid | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-10 | 8 | 3 | 0 | PR-0013: Time Off - Un Planned
Arslan Khalid | AP WORKFLOW | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-11 | 3 | 4 | 0 | AP WORKFLOW: Regular bug fixing activity
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Bug Fixing | 2024-11 | 14 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 100 | Apply discount based on Payment terms settings | Bug Fixing | 2024-11 | 8 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Apply discount based on Payment terms settings
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 7 | Associate vendor/stations/sites to multiple pay to | Bug Fixing | 2024-11 | 3 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Associate vendor/stations/sites to multiple pay to
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 27 | Broadcast Invoice: Invoice View UI | Bug Fixing | 2024-11 | 5 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Invoice View UI
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 27 | Broadcast Invoice: Invoice View UI | Development | 2024-11 | 6 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Invoice View UI
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 28 | Customer Information: Select Client on Vendor Invoice | Bug Fixing | 2024-11 | 3 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 102 | Invoice Editing: Make the tax editable | Development | 2024-11 | 10 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Invoice Editing: Make the tax editable
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 102 | Invoice Editing: Make the tax editable | Testing | 2024-11 | 1 | 4 |  | APWORKS 2024.2 - PHASE 3: Invoice Editing: Make the tax editable
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 101 | Remove Site column from vendor lookup | Bug Fixing | 2024-11 | 3 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Remove Site column from vendor lookup
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 101 | Remove Site column from vendor lookup | Development | 2024-11 | 3 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Remove Site column from vendor lookup
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 103 | Vendor Map: Vendor Popup: Remove identifier currency filter | Analysis | 2024-11 | 6 | 4 |  | APWORKS 2024.2 - PHASE 3: Vendor Map: Vendor Popup: Remove identifier currency filter
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 103 | Vendor Map: Vendor Popup: Remove identifier currency filter | Bug Fixing | 2024-11 | 2 | 4 |  | APWORKS 2024.2 - PHASE 3: Vendor Map: Vendor Popup: Remove identifier currency filter
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | 103 | Vendor Map: Vendor Popup: Remove identifier currency filter | Development | 2024-11 | 5 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Vendor Map: Vendor Popup: Remove identifier currency filter
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 102 | Apply variable name for Site in vendor mapping | Development | 2024-11 | 8 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Apply variable name for Site in vendor mapping
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Analysis | 2024-11 | 2 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Approval routing
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Development | 2024-11 | 35 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Approval routing
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Testing | 2024-11 | 0.5 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Approval routing
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 8 | Production: Project should be available on summary as well. | Development | 2024-11 | 8 | 4 |  | APWORKS 2024.2 - PHASE 4: Production: Project should be available on summary as well.
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Meetings | 2024-11 | 3 | 4 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Arslan Khalid | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-11 | 4 | 4 |  | APWORKS PHASE2: Regular bug fixing activity
Arslan Khalid | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-11 | 23.5 | 4 | 0 | PR-0013: Internal Meetings
Arslan Khalid | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-11 | 10 | 4 | 0 | PR-0013: Time Off - Un Planned
Arslan Khalid | AP WORKFLOW | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-12 | 22 | 5 | 0 | AP WORKFLOW: Regular bug fixing activity
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 102 | Apply variable name for Site in vendor mapping | Testing | 2024-12 | 2 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Apply variable name for Site in vendor mapping
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Analysis | 2024-12 | 1 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Approval routing
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Bug Fixing | 2024-12 | 6 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Approval routing
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Development | 2024-12 | 27 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Approval routing
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Testing | 2024-12 | 4 | 5 |  | APWORKS 2024.2 - PHASE 4: Approval routing
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 117 | Report >> Vendor Invoices: we need the discount field to show up | Bug Fixing | 2024-12 | 1 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Report >> Vendor Invoices: we need the discount field to show up
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 117 | Report >> Vendor Invoices: we need the discount field to show up | Development | 2024-12 | 4 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Report >> Vendor Invoices: we need the discount field to show up
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | 113 | Vendor mapping enhancement for Non-media | Development | 2024-12 | 5 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Vendor mapping enhancement for Non-media
Arslan Khalid | APWORKS 2024.2 PHASE 5 | 1 | Google Drive Setup (company configuration UI) | Analysis | 2024-12 | 4 | 5 |  | APWORKS 2024.2 PHASE 5: Google Drive Setup (company configuration UI)
Arslan Khalid | APWORKS 2024.2 PHASE 5 | 1 | Google Drive Setup (company configuration UI) | Development | 2024-12 | 10 | 5 |  | APWORKS 2024.2 PHASE 5: Google Drive Setup (company configuration UI)
Arslan Khalid | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-12 | 1 | 5 |  | APWORKS PHASE2: Regular bug fixing activity
Arslan Khalid | PR-0013 | Client Items | Client Items | Bug Fixing | 2024-12 | 3 | 5 |  | PR-0013: Client Items
Arslan Khalid | PR-0013 | Client Items | Client Items | Client Items | 2024-12 | 12 | 5 |  | PR-0013: Client Items
Arslan Khalid | PR-0013 | In-house Trainin | In-house Training | Meetings | 2024-12 | 2.5 | 5 |  | PR-0013: In-house Training
Arslan Khalid | PR-0013 | In-house Trainin | In-house Training | Training | 2024-12 | 4 | 5 |  | PR-0013: In-house Training
Arslan Khalid | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-12 | 19.5 | 5 |  | PR-0013: Internal Meetings
Asad Mahmood | AP WORKFLOW | Production Issue | Analysis of production issues reported by support team | Other | 2024-08 | 2 | 1 |  | AP WORKFLOW: Analysis of production issues reported by support team
Asad Mahmood | AP WORKFLOW | Analysis | Analysis of the new project/assignment/task | Other | 2024-08 | 10 | 1 |  | AP WORKFLOW: Analysis of the new project/assignment/task
Asad Mahmood | AP WORKFLOW | Development DB | Development of new project/assignment/task | Other | 2024-08 | 12 | 1 |  | AP WORKFLOW: Development of new project/assignment/task
Asad Mahmood | AP WORKFLOW | Development DotN | Development of new project/assignment/task | Other | 2024-08 | 13 | 1 | 0 | AP WORKFLOW: Development of new project/assignment/task
Asad Mahmood | AP WORKFLOW | Internal Meeting | Internal Meetings | Other | 2024-08 | 5 | 1 |  | AP WORKFLOW: Internal Meetings
Asad Mahmood | AP WORKFLOW | National Gazette | National Gazetted Holidays | Other | 2024-08 | 8 | 1 | 0 | AP WORKFLOW: National Gazetted Holidays
Asad Mahmood | AP WORKFLOW | Bug Fixing | Regular bug fixing activity | Other | 2024-08 | 46 | 1 |  | AP WORKFLOW: Regular bug fixing activity
Asad Mahmood | APWORKS PHASE2 | Development DotN | Development of new project/assignment/task | Development | 2024-08 | 4 | 1 |  | APWORKS PHASE2: Development of new project/assignment/task
Asad Mahmood | APWORKS PHASE2 | Development DotN | Development of new project/assignment/task | Other | 2024-08 | 26 | 1 | 0 | APWORKS PHASE2: Development of new project/assignment/task
Asad Mahmood | APWORKS PHASE2 | Internal Meeting | Internal Meetings | Meetings | 2024-08 | 10 | 1 |  | APWORKS PHASE2: Internal Meetings
Asad Mahmood | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-08 | 26 | 1 | 0 | APWORKS PHASE2: Regular bug fixing activity
Asad Mahmood | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Other | 2024-08 | 22 | 1 | 0 | APWORKS PHASE2: Regular bug fixing activity
Asad Mahmood | AP WORKFLOW | National Gazette | National Gazetted Holidays | Leave | 2024-09 | 8 | 2 | 0 | AP WORKFLOW: National Gazetted Holidays
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Development | 2024-09 | 56 | 2 |  | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Meetings | 2024-09 | 5 | 2 |  | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Asad Mahmood | APWORKS PHASE2 | Dev Support | Dev Support | Bug Fixing | 2024-09 | 4 | 2 | 0 | APWORKS PHASE2: Dev Support
Asad Mahmood | APWORKS PHASE2 | Internal Meeting | Internal Meetings | Meetings | 2024-09 | 3 | 2 | 0 | APWORKS PHASE2: Internal Meetings
Asad Mahmood | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-09 | 63 | 2 | 0 | APWORKS PHASE2: Regular bug fixing activity
Asad Mahmood | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Testing | 2024-09 | 21 | 2 | 0 | APWORKS PHASE2: Regular bug fixing activity
Asad Mahmood | PR-0013 | Time Off-Planned | Time Off - Planned | Leave | 2024-09 | 8 | 2 | 0 | PR-0013: Time Off - Planned
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Bug Fixing | 2024-10 | 8 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Development | 2024-10 | 31 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Testing | 2024-10 | 4 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Development | 2024-10 | 2 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Bug Fixing | 2024-10 | 14 | 3 |  | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Development | 2024-10 | 33 | 3 |  | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Bug Fixing | 2024-10 | 8 | 3 |  | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Development | 2024-10 | 20 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Asad Mahmood | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-10 | 40 | 3 | 0 | APWORKS PHASE2: Regular bug fixing activity
Asad Mahmood | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-10 | 24 | 3 | 0 | PR-0013: Time Off - Un Planned
Asad Mahmood | AD-0001 | 1 | Meetings | Meetings | 2024-11 | 13 | 4 |  | AD-0001: Meetings
Asad Mahmood | AP WORKFLOW | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Leave | 2024-11 | 8 | 4 | 0 | AP WORKFLOW: Meetings, mails, communication, TFS, Interviews
Asad Mahmood | AP WORKFLOW | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-11 | 4 | 4 | 0 | AP WORKFLOW: Regular bug fixing activity
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Bug Fixing | 2024-11 | 12 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Development | 2024-11 | 4 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 104 | Google Drive - Split Process and show documents in queue | Bug Fixing | 2024-11 | 6 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Google Drive - Split Process and show documents in queue
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 104 | Google Drive - Split Process and show documents in queue | Development | 2024-11 | 31 | 4 |  | APWORKS 2024.2 - PHASE 3: Google Drive - Split Process and show documents in queue
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 104 | Google Drive - Split Process and show documents in queue | Testing | 2024-11 | 3 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Google Drive - Split Process and show documents in queue
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Post_dep_fixes | 2024-11 | 5 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Project Overhead
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Bug Fixing | 2024-11 | 20 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Testing | 2024-11 | 3 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 10 | Approve upto last level and auto post. | Development | 2024-11 | 8 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Approve upto last level and auto post.
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 10 | Approve upto last level and auto post. | Testing | 2024-11 | 1 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Approve upto last level and auto post.
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 13 | EDI file updating and upload | Analysis | 2024-11 | 1 | 4 | 0 | APWORKS 2024.2 - PHASE 4: EDI file updating and upload
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 13 | EDI file updating and upload | Development | 2024-11 | 11 | 4 |  | APWORKS 2024.2 - PHASE 4: EDI file updating and upload
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 3 | PDF based broadcast invoices - Invoice Scan | Development | 2024-11 | 12 | 4 | 0 | APWORKS 2024.2 - PHASE 4: PDF based broadcast invoices - Invoice Scan
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 3 | PDF based broadcast invoices - Invoice Scan | Testing | 2024-11 | 2 | 4 | 0 | APWORKS 2024.2 - PHASE 4: PDF based broadcast invoices - Invoice Scan
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 100 | Production: Auto populate lines based PO during scanning | Development | 2024-11 | 3 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Production: Auto populate lines based PO during scanning
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 101 | Production: show keyvalue pairs for level2 mapping | Development | 2024-11 | 8 | 4 |  | APWORKS 2024.2 - PHASE 4: Production: show keyvalue pairs for level2 mapping
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Post_dep_fixes | 2024-11 | 6 | 4 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 12 | Stamp multiple approvers. | Bug Fixing | 2024-11 | 1 | 4 |  | APWORKS 2024.2 - PHASE 4: Stamp multiple approvers.
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 12 | Stamp multiple approvers. | Development | 2024-11 | 8 | 4 |  | APWORKS 2024.2 - PHASE 4: Stamp multiple approvers.
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 12 | Stamp multiple approvers. | Testing | 2024-11 | 1 | 4 |  | APWORKS 2024.2 - PHASE 4: Stamp multiple approvers.
Asad Mahmood | AD-0001 | 1 | Meetings | Meetings | 2024-12 | 24 | 5 | 0 | AD-0001: Meetings
Asad Mahmood | AP WORKFLOW | National Gazette | National Gazetted Holidays | Leave | 2024-12 | 8 | 5 |  | AP WORKFLOW: National Gazetted Holidays
Asad Mahmood | AP WORKFLOW | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-12 | 14 | 5 |  | AP WORKFLOW: Regular bug fixing activity
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 105 | PDF based broadcast invoices - Import / Export lines | Development | 2024-12 | 6 | 5 |  | APWORKS 2024.2 - PHASE 4: PDF based broadcast invoices - Import / Export lines
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 3 | PDF based broadcast invoices - Invoice Scan | Development | 2024-12 | 40 | 5 |  | APWORKS 2024.2 - PHASE 4: PDF based broadcast invoices - Invoice Scan
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 4 | PDF based broadcast invoices - Model List | Development | 2024-12 | 4 | 5 |  | APWORKS 2024.2 - PHASE 4: PDF based broadcast invoices - Model List
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Analysis | 2024-12 | 1.5 | 5 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Deployment | 2024-12 | 3 | 5 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Meetings | 2024-12 | 5 | 5 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Post_dep_fixes | 2024-12 | 5 | 5 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Asim Jameel | AD-0001 | TIME | Time | Meetings | 2024-08 | 1 | 1 |  | AD-0001: Time
Asim Jameel | AD-0001 | TIME | Time | Other | 2024-08 | 17.5 | 1 |  | AD-0001: Time
Asim Jameel | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Documentation | 2024-08 | 8 | 1 |  | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Asim Jameel | APWORKS 2024.2 - PHASE 3 | 2 | Add Media Type/Service type/Roles | Documentation | 2024-08 | 8 | 1 |  | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles
Asim Jameel | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Documentation | 2024-08 | 11 | 1 |  | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Asim Jameel | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Analysis | 2024-08 | 8 | 1 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Asim Jameel | NEXELUS 13.0 | Session Meetings | Session with US team | Other | 2024-08 | 9.8 | 1 |  | NEXELUS 13.0: Session with US team
Asim Jameel | NEXELUS 2024.2 | Client Items | Client Items | Other | 2024-08 | 6.5 | 1 |  | NEXELUS 2024.2: Client Items
Asim Jameel | NEXELUS 2024.2 | Development DotN | Development of new project/assignment/task | Other | 2024-08 | 30.5 | 1 |  | NEXELUS 2024.2: Development of new project/assignment/task
Asim Jameel | NEXELUS 2024.2 | Internal Meeting | Internal Meetings | Other | 2024-08 | 7.1 | 1 |  | NEXELUS 2024.2: Internal Meetings
Asim Jameel | NEXELUS 2024.2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 3 | 1 |  | NEXELUS 2024.2: Meetings, mails, communication, TFS, Interviews
Asim Jameel | NEXELUS 2024.2 | Bug Fixing | Regular bug fixing activity | Other | 2024-08 | 1.5 | 1 |  | NEXELUS 2024.2: Regular bug fixing activity
Asim Jameel | NEXELUS 2024.2 | Support Items | Support Items | Other | 2024-08 | 2.5 | 1 |  | NEXELUS 2024.2: Support Items
Asim Jameel | NEXELUS 2024.2 | Time Off-Un Plan | Time Off - Un Planned | Other | 2024-08 | 6.5 | 1 |  | NEXELUS 2024.2: Time Off - Un Planned
Asim Jameel | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-08 | 2.5 | 1 |  | PR-0013: Internal Meetings
Asim Jameel | PR-0013 | Session Meetings | Session with US team | Client Items | 2024-08 | 2.4 | 1 |  | PR-0013: Session with US team
Asim Jameel | PR-0013 | Time Off-Planned | Time Off - Planned | Leave | 2024-08 | 16 | 1 |  | PR-0013: Time Off - Planned
Asim Jameel | Support and Maintenance | TIME | Time | Client Items | 2024-08 | 16 | 1 |  | Support and Maintenance: Time
Asim Jameel | AD-0001 | TIME | Time | Admin | 2024-09 | 3 | 2 |  | AD-0001: Time
Asim Jameel | AD-0001 | TIME | Time | Leave | 2024-09 | 8 | 2 |  | AD-0001: Time
Asim Jameel | AD-0001 | TIME | Time | Meetings | 2024-09 | 24.85 | 2 |  | AD-0001: Time
Asim Jameel | AD-0001 | TIME | Time | Project Mgmt | 2024-09 | 3.5 | 2 |  | AD-0001: Time
Asim Jameel | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Documentation | 2024-09 | 15 | 2 |  | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Asim Jameel | APWORKS PHASE2 | Requirement Writ | Requirement Specifications document writing | Documentation | 2024-09 | 18.5 | 2 | 0 | APWORKS PHASE2: Requirement Specifications document writing
Asim Jameel | NEXELUS 2024.2 | Requirement Anal | Document review/understanding Requirement Specifications | Documentation | 2024-09 | 17 | 2 | 0 | NEXELUS 2024.2: Document review/understanding Requirement Specifications
Asim Jameel | NEXELUS 2024.2 | Requirement Writ | Requirement Specifications document writing | Documentation | 2024-09 | 9 | 2 |  | NEXELUS 2024.2: Requirement Specifications document writing
Asim Jameel | NEXELUS 2024.2 | Support Items | Support Items | Analysis | 2024-09 | 4 | 2 |  | NEXELUS 2024.2: Support Items
Asim Jameel | PR-0013 | Session Meetings | Session with US team | Client Items | 2024-09 | 18.5 | 2 |  | PR-0013: Session with US team
Asim Jameel | PR-0013 | Session Meetings | Session with US team | Meetings | 2024-09 | 5.5 | 2 | 0 | PR-0013: Session with US team
Asim Jameel | Support and Maintenance | TIME | Time | Client Items | 2024-09 | 18 | 2 | 0 | Support and Maintenance: Time
Asim Jameel | AD-0001 | TIME | Time | Meetings | 2024-10 | 22.5 | 3 | 0 | AD-0001: Time
Asim Jameel | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Meetings | 2024-10 | 6 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Project Overhead
Asim Jameel | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Development | 2024-10 | 28 | 3 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Asim Jameel | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Documentation | 2024-10 | 17 | 3 |  | NEXELUS 2024.1 SP2: Project Overhead
Asim Jameel | PR-0013 | Session Meetings | Session with US team | Client Items | 2024-10 | 26.5 | 3 |  | PR-0013: Session with US team
Asim Jameel | AD-0001 | TIME | Time | Meetings | 2024-11 | 38.5 | 4 |  | AD-0001: Time
Asim Jameel | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Meetings | 2024-11 | 11.5 | 4 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Asim Jameel | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Development | 2024-11 | 16 | 4 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Asim Jameel | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Testing | 2024-11 | 5 | 4 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Asim Jameel | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Documentation | 2024-11 | 25 | 4 |  | NEXELUS 2024.1 SP2: Project Overhead
Asim Jameel | NEXELUS 2024.1 SP2 | 10 | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | Meetings | 2024-11 | 4.5 | 4 |  | NEXELUS 2024.1 SP2: UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp)
Asim Jameel | PR-0013 | Production Issue | Analysis of production issues reported by support team | Support Tickets | 2024-11 | 8 | 4 |  | PR-0013: Analysis of production issues reported by support team
Asim Jameel | PR-0013 | Client Items | Client Items | Client Items | 2024-11 | 4 | 4 |  | PR-0013: Client Items
Asim Jameel | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2024-11 | 0.75 | 4 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Asim Jameel | PR-0013 | Session Meetings | Session with US team | Client Items | 2024-11 | 15.5 | 4 |  | PR-0013: Session with US team
Asim Jameel | PR-0013 | Session Meetings | Session with US team | Meetings | 2024-11 | 4 | 4 |  | PR-0013: Session with US team
Asiya Bibi | AD-0001 | HR | HR ad Admin Activities | Admin | 2024-08 | 24 | 1 |  | AD-0001: HR ad Admin Activities
Asiya Bibi | AD-0001 | HR | HR ad Admin Activities | HR Management | 2024-08 | 31 | 1 |  | AD-0001: HR ad Admin Activities
Asiya Bibi | AD-0001 | HR | HR ad Admin Activities | Interview | 2024-08 | 9 | 1 |  | AD-0001: HR ad Admin Activities
Asiya Bibi | AD-0001 | HR | HR ad Admin Activities | Other | 2024-08 | 41 | 1 |  | AD-0001: HR ad Admin Activities
Asiya Bibi | AD-0001 | Network Support | Network and infrastructure Support | Admin | 2024-08 | 21 | 1 |  | AD-0001: Network and infrastructure Support
Asiya Bibi | AD-0001 | Taxes and Bank R | Taxes and Bank Related | Admin | 2024-08 | 7 | 1 |  | AD-0001: Taxes and Bank Related
Asiya Bibi | AD-0001 | Taxes and Bank R | Taxes and Bank Related | Other | 2024-08 | 9.5 | 1 |  | AD-0001: Taxes and Bank Related
Asiya Bibi | AD-0001 | TIME | Time | Other | 2024-08 | 53 | 1 |  | AD-0001: Time
Asiya Bibi | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Leave | 2024-08 | 3 | 1 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Asiya Bibi | AD-0001 | HR | HR ad Admin Activities | HR Management | 2024-09 | 68 | 2 |  | AD-0001: HR ad Admin Activities
Asiya Bibi | AD-0001 | Network Support | Network and infrastructure Support | Admin | 2024-09 | 47 | 2 |  | AD-0001: Network and infrastructure Support
Asiya Bibi | AD-0001 | Taxes and Bank R | Taxes and Bank Related | Admin | 2024-09 | 19 | 2 |  | AD-0001: Taxes and Bank Related
Asiya Bibi | AD-0001 | TIME | Time | Interview | 2024-09 | 3.5 | 2 |  | AD-0001: Time
Asiya Bibi | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 23.5 | 2 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Asiya Bibi | AD-0001 | HR | HR ad Admin Activities | HR Management | 2024-10 | 68 | 3 |  | AD-0001: HR ad Admin Activities
Asiya Bibi | AD-0001 | Network Support | Network and infrastructure Support | Admin | 2024-10 | 71 | 3 |  | AD-0001: Network and infrastructure Support
Asiya Bibi | AD-0001 | Taxes and Bank R | Taxes and Bank Related | Admin | 2024-10 | 15 | 3 |  | AD-0001: Taxes and Bank Related
Asiya Bibi | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-10 | 20 | 3 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Asiya Bibi | AD-0001 | HR | HR ad Admin Activities | Admin | 2024-11 | 20 | 4 |  | AD-0001: HR ad Admin Activities
Asiya Bibi | AD-0001 | HR | HR ad Admin Activities | Admin | 2024-11 | 12 | 4 | 0 | AD-0001: HR ad Admin Activities
Asiya Bibi | AD-0001 | HR | HR ad Admin Activities | Admin | 2024-11 | 57 | 4 |  | AD-0001: HR ad Admin Activities
Asiya Bibi | AD-0001 | HR | HR ad Admin Activities | HR Management | 2024-11 | 40 | 4 |  | AD-0001: HR ad Admin Activities
Asiya Bibi | AD-0001 | HR | HR ad Admin Activities | Interview | 2024-11 | 4 | 4 |  | AD-0001: HR ad Admin Activities
Asiya Bibi | AD-0001 | 1 | Meetings | Meetings | 2024-11 | 5 | 4 |  | AD-0001: Meetings
Asiya Bibi | AD-0001 | Network Support | Network and infrastructure Support | Admin | 2024-11 | 17.5 | 4 |  | AD-0001: Network and infrastructure Support
Asiya Bibi | AD-0001 | Taxes and Bank R | Taxes and Bank Related | HR Management | 2024-11 | 5 | 4 |  | AD-0001: Taxes and Bank Related
Ayesha Qurban | AP WORKFLOW | QA | Regular testing and QA new project/assignment/task | Other | 2024-08 | 116 | 1 |  | AP WORKFLOW: Regular testing and QA new project/assignment/task
Ayesha Qurban | APWORKS PHASE2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-08 | 5 | 1 | 0 | APWORKS PHASE2: Meetings, mails, communication, TFS, Interviews
Ayesha Qurban | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-08 | 35 | 1 |  | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Ayesha Qurban | NEXELUS 2024.2 | Production Issue | Analysis of production issues reported by support team | Other | 2024-08 | 6 | 1 |  | NEXELUS 2024.2: Analysis of production issues reported by support team
Ayesha Qurban | NEXELUS 2024.2 | QA | Regular testing and QA new project/assignment/task | Other | 2024-08 | 20 | 1 |  | NEXELUS 2024.2: Regular testing and QA new project/assignment/task
Ayesha Qurban | AP WORKFLOW | Analysis | Analysis of the new project/assignment/task | Analysis | 2024-09 | 5 | 2 |  | AP WORKFLOW: Analysis of the new project/assignment/task
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Test Case Dev | 2024-09 | 16 | 2 |  | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Test Case Dev | 2024-09 | 16 | 2 | 13.2 | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Ayesha Qurban | APWORKS PHASE2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Documentation | 2024-09 | 1 | 2 |  | APWORKS PHASE2: Meetings, mails, communication, TFS, Interviews
Ayesha Qurban | APWORKS PHASE2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 14 | 2 | 0 | APWORKS PHASE2: Meetings, mails, communication, TFS, Interviews
Ayesha Qurban | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-09 | 76 | 2 |  | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Ayesha Qurban | NEXELUS 2024.2 | Production Issue | Analysis of production issues reported by support team | Client Items | 2024-09 | 6 | 2 | 0 | NEXELUS 2024.2: Analysis of production issues reported by support team
Ayesha Qurban | NEXELUS 2024.2 | Analysis | Analysis of the new project/assignment/task | Analysis | 2024-09 | 22 | 2 | 0 | NEXELUS 2024.2: Analysis of the new project/assignment/task
Ayesha Qurban | PR-0013 | Time Off-Planned | Time Off - Planned | Leave | 2024-09 | 16 | 2 | 0 | PR-0013: Time Off - Planned
Ayesha Qurban | AP WORKFLOW | Internal Meeting | Internal Meetings | Meetings | 2024-10 | 1 | 3 | 0 | AP WORKFLOW: Internal Meetings
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Testing | 2024-10 | 21 | 3 | 8 | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Testing | 2024-10 | 4 | 3 |  | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Meetings | 2024-10 | 2 | 3 | 6.8 | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Test Case Dev | 2024-10 | 28 | 3 |  | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Testing | 2024-10 | 29 | 3 |  | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Testing | 2024-10 | 16 | 3 |  | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 2 | Add Media Type/Service type/Roles | Meetings | 2024-10 | 4 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 2 | Add Media Type/Service type/Roles | Testing | 2024-10 | 3 | 3 |  | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 2 | Add Media Type/Service type/Roles | Testing | 2024-10 | 21 | 3 |  | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 12 | Checkbox to filter discrepant lines | Testing | 2024-10 | 2 | 3 |  | APWORKS 2024.2 - PHASE 3: Checkbox to filter discrepant lines
Ayesha Qurban | APWORKS PHASE2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-10 | 3 | 3 |  | APWORKS PHASE2: Meetings, mails, communication, TFS, Interviews
Ayesha Qurban | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-10 | 11 | 3 | 0 | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Ayesha Qurban | NEXELUS 2024.2 | Analysis | Analysis of the new project/assignment/task | Analysis | 2024-10 | 6 | 3 | 0 | NEXELUS 2024.2: Analysis of the new project/assignment/task
Ayesha Qurban | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-10 | 33 | 3 | 0 | PR-0013: Time Off - Un Planned
Ayesha Qurban | AP WORKFLOW | Requirement Anal | Document review/understanding Requirement Specifications | Documentation | 2024-11 | 3 | 4 | 0 | AP WORKFLOW: Document review/understanding Requirement Specifications
Ayesha Qurban | AP WORKFLOW | Internal Meeting | Internal Meetings | Meetings | 2024-11 | 6 | 4 | 0 | AP WORKFLOW: Internal Meetings
Ayesha Qurban | AP WORKFLOW | QA | Regular testing and QA new project/assignment/task | Testing | 2024-11 | 5 | 4 | 0 | AP WORKFLOW: Regular testing and QA new project/assignment/task
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Testing | 2024-11 | 6 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Testing | 2024-11 | 4 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 2 | Add Media Type/Service type/Roles | Testing | 2024-11 | 2 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 100 | Apply discount based on Payment terms settings | Testing | 2024-11 | 2.5 | 4 |  | APWORKS 2024.2 - PHASE 3: Apply discount based on Payment terms settings
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 100 | Apply discount based on Payment terms settings | Testing | 2024-11 | 10 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Apply discount based on Payment terms settings
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 15 | Forward Inv to user OR select user when invoice is Pending Apr | Testing | 2024-11 | 1 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Forward Inv to user OR select user when invoice is Pending Apr
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 104 | Google Drive - Split Process and show documents in queue | Testing | 2024-11 | 2 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Google Drive - Split Process and show documents in queue
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 104 | Google Drive - Split Process and show documents in queue | Testing | 2024-11 | 2 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Google Drive - Split Process and show documents in queue
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 102 | Invoice Editing: Make the tax editable | Meetings | 2024-11 | 1 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Invoice Editing: Make the tax editable
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 102 | Invoice Editing: Make the tax editable | Testing | 2024-11 | 1 | 4 |  | APWORKS 2024.2 - PHASE 3: Invoice Editing: Make the tax editable
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 102 | Invoice Editing: Make the tax editable | Testing | 2024-11 | 8 | 4 |  | APWORKS 2024.2 - PHASE 3: Invoice Editing: Make the tax editable
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 101 | Remove Site column from vendor lookup | Testing | 2024-11 | 1 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Remove Site column from vendor lookup
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 29 | Route invoice from one company - company identification | Testing | 2024-11 | 2.5 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Route invoice from one company - company identification
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Testing | 2024-11 | 3 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 103 | Vendor Map: Vendor Popup: Remove identifier currency filter | Testing | 2024-11 | 2 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Vendor Map: Vendor Popup: Remove identifier currency filter
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Analysis | 2024-11 | 5 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Approval routing
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Testing | 2024-11 | 1 | 4 |  | APWORKS 2024.2 - PHASE 4: Approval routing
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Testing | 2024-11 | 2 | 4 |  | APWORKS 2024.2 - PHASE 4: Approval routing
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 10 | Approve upto last level and auto post. | Testing | 2024-11 | 3 | 4 |  | APWORKS 2024.2 - PHASE 4: Approve upto last level and auto post.
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Meetings | 2024-11 | 5 | 4 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Ayesha Qurban | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-11 | 12 | 4 |  | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Ayesha Qurban | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-11 | 21 | 4 | 0 | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Ayesha Qurban | Support and Maintenance | 2 | Time | Client Items | 2024-11 | 19 | 4 | 0 | Support and Maintenance: Time
Ayesha Qurban | Support and Maintenance | 2 | Time | Client Items | 2024-11 | 12 | 4 |  | Support and Maintenance: Time
Ayesha Qurban | Support and Maintenance | 2 | Time | Client Items | 2024-11 | 25 | 4 | 0 | Support and Maintenance: Time
Ayesha Qurban | AP WORKFLOW | Analysis | Analysis of the new project/assignment/task | Analysis | 2024-12 | 3 | 5 |  | AP WORKFLOW: Analysis of the new project/assignment/task
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 100 | Apply discount based on Payment terms settings | Testing | 2024-12 | 1 | 5 | 0 | APWORKS 2024.2 - PHASE 3: Apply discount based on Payment terms settings
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Testing | 2024-12 | 1 | 5 | 0 | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 2 | A report to spot check the invoices processed | Testing | 2024-12 | 1 | 5 | 3 | APWORKS 2024.2 - PHASE 4: A report to spot check the invoices processed
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 102 | Apply variable name for Site in vendor mapping | Testing | 2024-12 | 1 | 5 |  | APWORKS 2024.2 - PHASE 4: Apply variable name for Site in vendor mapping
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Test Case Dev | 2024-12 | 8 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Approval routing
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Testing | 2024-12 | 2 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Approval routing
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Testing | 2024-12 | 7 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Approval routing
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 13 | EDI file updating and upload | Analysis | 2024-12 | 3 | 5 |  | APWORKS 2024.2 - PHASE 4: EDI file updating and upload
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 99 | EDI: Generate PDF - Updates | Testing | 2024-12 | 2 | 5 |  | APWORKS 2024.2 - PHASE 4: EDI: Generate PDF - Updates
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 8 | Production: Project should be available on summary as well. | Testing | 2024-12 | 1 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Production: Project should be available on summary as well.
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Meetings | 2024-12 | 3 | 5 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | 117 | Report >> Vendor Invoices: we need the discount field to show up | Testing | 2024-12 | 1 | 5 |  | APWORKS 2024.2 - PHASE 4: Report >> Vendor Invoices: we need the discount field to show up
Ayesha Qurban | APWORKS 2024.2 PHASE 5 | 0 | Project Overhead | Analysis | 2024-12 | 2 | 5 |  | APWORKS 2024.2 PHASE 5: Project Overhead
Ayesha Qurban | APWORKS 2024.2 PHASE 5 | 0 | Project Overhead | Meetings | 2024-12 | 3 | 5 |  | APWORKS 2024.2 PHASE 5: Project Overhead
Ayesha Qurban | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-12 | 4 | 5 |  | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Ayesha Qurban | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2024-12 | 2 | 5 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Ayesha Qurban | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-12 | 8 | 5 |  | PR-0013: Time Off - Un Planned
Ayesha Qurban | Support and Maintenance | 2 | Time | Client Items | 2024-12 | 8 | 5 |  | Support and Maintenance: Time
Ayesha Qurban | Support and Maintenance | 2 | Time | Client Items | 2024-12 | 11 | 5 | 0 | Support and Maintenance: Time
Ayesha Qurban | Support and Maintenance | 2 | Time | Client Items | 2024-12 | 5 | 5 |  | Support and Maintenance: Time
Ayesha Qurban | Support and Maintenance | 1 | Time | Support Tickets | 2024-12 | 3 | 5 |  | Support and Maintenance: Time
Bilal Afzal Raja | AP WORKFLOW | Production Issue | Analysis of production issues reported by support team | Other | 2024-08 | 16 | 1 |  | AP WORKFLOW: Analysis of production issues reported by support team
Bilal Afzal Raja | AP WORKFLOW | Cient UAT Upgrad | Cient UAT Upgrade | Other | 2024-08 | 1 | 1 |  | AP WORKFLOW: Cient UAT Upgrade
Bilal Afzal Raja | AP WORKFLOW | QA Environment U | QA Environment Upgrade | Other | 2024-08 | 40 | 1 |  | AP WORKFLOW: QA Environment Upgrade
Bilal Afzal Raja | AP WORKFLOW | Release Upgrade | Release Environment Upgrade | Other | 2024-08 | 6 | 1 |  | AP WORKFLOW: Release Environment Upgrade
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Meetings | 2024-08 | 3 | 1 | 0 | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Bilal Afzal Raja | APWORKS PHASE2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-08 | 8 | 1 |  | APWORKS PHASE2: Meetings, mails, communication, TFS, Interviews
Bilal Afzal Raja | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-08 | 10 | 1 |  | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Bilal Afzal Raja | NEXELUS 2024.2 | Production Issue | Analysis of production issues reported by support team | Other | 2024-08 | 29 | 1 |  | NEXELUS 2024.2: Analysis of production issues reported by support team
Bilal Afzal Raja | NEXELUS 2024.2 | Cient UAT Upgrad | Cient UAT Upgrade | Other | 2024-08 | 14.5 | 1 | 0 | NEXELUS 2024.2: Cient UAT Upgrade
Bilal Afzal Raja | NEXELUS 2024.2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 26 | 1 |  | NEXELUS 2024.2: Meetings, mails, communication, TFS, Interviews
Bilal Afzal Raja | NEXELUS 2024.2 | National Gazette | National Gazetted Holidays | Other | 2024-08 | 8 | 1 | 0 | NEXELUS 2024.2: National Gazetted Holidays
Bilal Afzal Raja | NEXELUS 2024.2 | QA | Regular testing and QA new project/assignment/task | Other | 2024-08 | 3 | 1 |  | NEXELUS 2024.2: Regular testing and QA new project/assignment/task
Bilal Afzal Raja | PR-0013 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-08 | 10 | 1 | 0 | PR-0013: Analysis of production issues reported by support team
Bilal Afzal Raja | PR-0013 | Production Issue | Analysis of production issues reported by support team | Testing | 2024-08 | 9 | 1 |  | PR-0013: Analysis of production issues reported by support team
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Meetings | 2024-09 | 7 | 2 |  | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Meetings | 2024-09 | 7 | 2 | 0 | APWORKS 2024.2 - PHASE 3: Project Overhead
Bilal Afzal Raja | APWORKS PHASE2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 8 | 2 | 0 | APWORKS PHASE2: Meetings, mails, communication, TFS, Interviews
Bilal Afzal Raja | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-09 | 16 | 2 |  | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Bilal Afzal Raja | NEXELUS 2024.2 | Analysis | Analysis of the new project/assignment/task | Documentation | 2024-09 | 6 | 2 |  | NEXELUS 2024.2: Analysis of the new project/assignment/task
Bilal Afzal Raja | NEXELUS 2024.2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 3 | 2 | 0 | NEXELUS 2024.2: Meetings, mails, communication, TFS, Interviews
Bilal Afzal Raja | NEXELUS 2024.2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Testing | 2024-09 | 24 | 2 |  | NEXELUS 2024.2: Meetings, mails, communication, TFS, Interviews
Bilal Afzal Raja | NEXELUS 2024.2 | Bug Fixing | Regular bug fixing activity | Testing | 2024-09 | 6 | 2 | 0 | NEXELUS 2024.2: Regular bug fixing activity
Bilal Afzal Raja | PR-0013 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-09 | 38 | 2 | 0 | PR-0013: Analysis of production issues reported by support team
Bilal Afzal Raja | PR-0013 | Production Issue | Analysis of production issues reported by support team | Testing | 2024-09 | 4 | 2 |  | PR-0013: Analysis of production issues reported by support team
Bilal Afzal Raja | PR-0013 | Internal Meeting | Internal Meetings | Documentation | 2024-09 | 4 | 2 |  | PR-0013: Internal Meetings
Bilal Afzal Raja | PR-0013 | Production Upgra | Production upgrades | Development | 2024-09 | 5 | 2 | 0 | PR-0013: Production upgrades
Bilal Afzal Raja | PR-0013 | Time Off-Planned | Time Off - Planned | Leave | 2024-09 | 31 | 2 |  | PR-0013: Time Off - Planned
Bilal Afzal Raja | PR-0013 | Time Off-Planned | Time Off - Planned | Meetings | 2024-09 | 6 | 2 | 0 | PR-0013: Time Off - Planned
Bilal Afzal Raja | AP WORKFLOW | Production Issue | Analysis of production issues reported by support team | Testing | 2024-10 | 10 | 3 |  | AP WORKFLOW: Analysis of production issues reported by support team
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Testing | 2024-10 | 4 | 3 |  | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | 1 | Ability to automatically attach additional documents to Invoice | Meetings | 2024-10 | 2 | 3 |  | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | 2 | Add Media Type/Service type/Roles | Testing | 2024-10 | 2 | 3 |  | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Analysis | 2024-10 | 5 | 3 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Meetings | 2024-10 | 9 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Project Overhead
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | 31 | Vendor/stations/sites associated to multiple pay to. | Testing | 2024-10 | 2 | 3 |  | APWORKS 2024.2 - PHASE 3: Vendor/stations/sites associated to multiple pay to.
Bilal Afzal Raja | APWORKS PHASE2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-10 | 3 | 3 |  | APWORKS PHASE2: Meetings, mails, communication, TFS, Interviews
Bilal Afzal Raja | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-10 | 15 | 3 | 0 | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Bilal Afzal Raja | NEXELUS 2024.2 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-10 | 14 | 3 |  | NEXELUS 2024.2: Analysis of production issues reported by support team
Bilal Afzal Raja | NEXELUS 2024.2 | Analysis | Analysis of the new project/assignment/task | Documentation | 2024-10 | 7 | 3 | 0 | NEXELUS 2024.2: Analysis of the new project/assignment/task
Bilal Afzal Raja | NEXELUS 2024.2 | Requirement Anal | Document review/understanding Requirement Specifications | Documentation | 2024-10 | 7 | 3 |  | NEXELUS 2024.2: Document review/understanding Requirement Specifications
Bilal Afzal Raja | NEXELUS 2024.2 | QA | Regular testing and QA new project/assignment/task | Documentation | 2024-10 | 6 | 3 | 0 | NEXELUS 2024.2: Regular testing and QA new project/assignment/task
Bilal Afzal Raja | PR-0013 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-10 | 30 | 3 | 0 | PR-0013: Analysis of production issues reported by support team
Bilal Afzal Raja | PR-0013 | Production Issue | Analysis of production issues reported by support team | Testing | 2024-10 | 16 | 3 | 0 | PR-0013: Analysis of production issues reported by support team
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrad | Cient UAT Upgrade | Analysis | 2024-10 | 7 | 3 | 0 | PR-0013: Cient UAT Upgrade
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrad | Cient UAT Upgrade | Testing | 2024-10 | 15 | 3 | 0 | PR-0013: Cient UAT Upgrade
Bilal Afzal Raja | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-10 | 16 | 3 | 0 | PR-0013: Internal Meetings
Bilal Afzal Raja | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-10 | 12 | 3 |  | PR-0013: Time Off - Un Planned
Bilal Afzal Raja | AP WORKFLOW | Production Issue | Analysis of production issues reported by support team | Testing | 2024-11 | 3 | 4 |  | AP WORKFLOW: Analysis of production issues reported by support team
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | 99 | Documentation | Documentation | 2024-11 | 1.5 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Documentation
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 6 | Backup Table for vendor/client lines relationship | Testing | 2024-11 | 20 | 4 |  | NEXELUS 2024.1 SP2: Backup Table for vendor/client lines relationship
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 7 | Billing by Media Type | Test Case Dev | 2024-11 | 3 | 4 | 0 | NEXELUS 2024.1 SP2: Billing by Media Type
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 50 | Documentation | Documentation | 2024-11 | 2 | 4 |  | NEXELUS 2024.1 SP2: Documentation
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 5 | eConnect shell change to service | Testing | 2024-11 | 7 | 4 |  | NEXELUS 2024.1 SP2: eConnect shell change to service
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Test Case Dev | 2024-11 | 3 | 4 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 10 | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | Test Case Dev | 2024-11 | 6 | 4 | 0 | NEXELUS 2024.1 SP2: UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp)
Bilal Afzal Raja | NEXELUS 2024.2 | Requirement Anal | Document review/understanding Requirement Specifications | Analysis | 2024-11 | 2 | 4 |  | NEXELUS 2024.2: Document review/understanding Requirement Specifications
Bilal Afzal Raja | NEXELUS 2024.2 | Requirement Anal | Document review/understanding Requirement Specifications | Documentation | 2024-11 | 3 | 4 | 0 | NEXELUS 2024.2: Document review/understanding Requirement Specifications
Bilal Afzal Raja | NEXELUS 2024.2 | Requirement Anal | Document review/understanding Requirement Specifications | Testing | 2024-11 | 15 | 4 | 0 | NEXELUS 2024.2: Document review/understanding Requirement Specifications
Bilal Afzal Raja | PR-0013 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-11 | 8 | 4 | 0 | PR-0013: Analysis of production issues reported by support team
Bilal Afzal Raja | PR-0013 | Production Issue | Analysis of production issues reported by support team | Testing | 2024-11 | 5.5 | 4 | 0 | PR-0013: Analysis of production issues reported by support team
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrad | Cient UAT Upgrade | Testing | 2024-11 | 42 | 4 | 0 | PR-0013: Cient UAT Upgrade
Bilal Afzal Raja | PR-0013 | In-house Trainin | In-house Training | Domain Learning | 2024-11 | 6.5 | 4 |  | PR-0013: In-house Training
Bilal Afzal Raja | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-11 | 28 | 4 |  | PR-0013: Internal Meetings
Bilal Afzal Raja | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-11 | 2 | 4 | 0 | PR-0013: Meetings, mails, communication, TFS, Interviews
Bilal Afzal Raja | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-11 | 7.5 | 4 |  | PR-0013: Time Off - Un Planned
Bilal Afzal Raja | AP WORKFLOW | Production Issue | Analysis of production issues reported by support team | Testing | 2024-12 | 1 | 5 |  | AP WORKFLOW: Analysis of production issues reported by support team
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 57 | AdTech Fee commission | Documentation | 2024-12 | 3 | 5 |  | NEXELUS 2024.1 SP2: AdTech Fee commission
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 57 | AdTech Fee commission | Testing | 2024-12 | 7 | 5 | 0 | NEXELUS 2024.1 SP2: AdTech Fee commission
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 7 | Billing by Media Type | Testing | 2024-12 | 14 | 5 | 0 | NEXELUS 2024.1 SP2: Billing by Media Type
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 56 | Enhancement for Visual Indicators and Flighting Details in Place | Testing | 2024-12 | 1 | 5 | 0 | NEXELUS 2024.1 SP2: Enhancement for Visual Indicators and Flighting Details in Place
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Bug Fixing | 2024-12 | 2.5 | 5 | 0 | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Testing | 2024-12 | 32 | 5 | 0 | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | 59 | Media Plan: Import/Export Flighting | Testing | 2024-12 | 2 | 5 | 0 | NEXELUS 2024.1 SP2: Media Plan: Import/Export Flighting
Bilal Afzal Raja | PR-0013 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-12 | 1 | 5 | 0 | PR-0013: Analysis of production issues reported by support team
Bilal Afzal Raja | PR-0013 | Production Issue | Analysis of production issues reported by support team | Testing | 2024-12 | 9 | 5 | 0 | PR-0013: Analysis of production issues reported by support team
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrad | Cient UAT Upgrade | Testing | 2024-12 | 5.5 | 5 | 0 | PR-0013: Cient UAT Upgrade
Bilal Afzal Raja | PR-0013 | Internal Meeting | Internal Meetings | Documentation | 2024-12 | 10 | 5 | 0 | PR-0013: Internal Meetings
Bilal Afzal Raja | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-12 | 21.5 | 5 | 0 | PR-0013: Internal Meetings
Bilal Afzal Raja | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-12 | 6.5 | 5 | 0 | PR-0013: Time Off - Un Planned
Farooq Azam | NEXELUS 13.0 | Development DotN | Development of new project/assignment/task | Other | 2024-08 | 40 | 1 | 0 | NEXELUS 13.0: Development of new project/assignment/task
Fawad Ahmed | AP WORKFLOW | Client Items | Client Items | Client Items | 2024-09 | 0 | 2 | 0 | AP WORKFLOW: Client Items
Fawad Ahmed | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Development | 2024-09 | 106 | 2 | 0 | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Fawad Ahmed | NEXELUS 2024.2 | Bug Fixing | Regular bug fixing activity | Development | 2024-09 | 44 | 2 | 0 | NEXELUS 2024.2: Regular bug fixing activity
Fawad Ahmed | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Bug Fixing | 2024-10 | 0 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Fawad Ahmed | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Development | 2024-10 | 73 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Fawad Ahmed | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Analysis | 2024-10 | 35 | 3 | 0 | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Fawad Ahmed | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Development | 2024-10 | 0 | 3 | 0 | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Fawad Ahmed | NEXELUS 2024.1 SP2 | 8 | UDF & Naming Convention in Vendor Portal - Proposal Import/exp | Development | 2024-10 | 57 | 3 |  | NEXELUS 2024.1 SP2: UDF & Naming Convention in Vendor Portal - Proposal Import/exp
Fawad Ahmed | NEXELUS 2024.1 SP2 | 7 | Billing by Media Type | Development | 2024-11 | 38.5 | 4 | 0 | NEXELUS 2024.1 SP2: Billing by Media Type
Fawad Ahmed | NEXELUS 2024.1 SP2 | 7 | Billing by Media Type | Documentation | 2024-11 | 2 | 4 |  | NEXELUS 2024.1 SP2: Billing by Media Type
Fawad Ahmed | NEXELUS 2024.1 SP2 | 7 | Billing by Media Type | Meetings | 2024-11 | 1.75 | 4 |  | NEXELUS 2024.1 SP2: Billing by Media Type
Fawad Ahmed | NEXELUS 2024.1 SP2 | 7 | Billing by Media Type | Testing | 2024-11 | 4.75 | 4 |  | NEXELUS 2024.1 SP2: Billing by Media Type
Fawad Ahmed | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Bug Fixing | 2024-11 | 0 | 4 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Fawad Ahmed | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Development | 2024-11 | 0 | 4 | 0 | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Fawad Ahmed | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Deployment | 2024-11 | 0.3 | 4 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Fawad Ahmed | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Post_dep_fixes | 2024-11 | 1 | 4 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Fawad Ahmed | NEXELUS 2024.1 SP2 | 9 | UDF & Naming Convention in Nexelus - Export on Proposal | Development | 2024-11 | 24 | 4 | 12 | NEXELUS 2024.1 SP2: UDF & Naming Convention in Nexelus - Export on Proposal
Fawad Ahmed | NEXELUS 2024.1 SP2 | 10 | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | Development | 2024-11 | 13 | 4 | 0 | NEXELUS 2024.1 SP2: UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp)
Fawad Ahmed | NEXELUS 2024.1 SP2 | 10 | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | Testing | 2024-11 | 3.5 | 4 | 0 | NEXELUS 2024.1 SP2: UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp)
Fawad Ahmed | NEXELUS 2024.1 SP2 | 8 | UDF & Naming Convention in Vendor Portal - Proposal Import/exp | Bug Fixing | 2024-11 | 43 | 4 | 0.9 | NEXELUS 2024.1 SP2: UDF & Naming Convention in Vendor Portal - Proposal Import/exp
Fawad Ahmed | NEXELUS 2024.1 SP2 | 8 | UDF & Naming Convention in Vendor Portal - Proposal Import/exp | Development | 2024-11 | 8 | 4 | 0.9 | NEXELUS 2024.1 SP2: UDF & Naming Convention in Vendor Portal - Proposal Import/exp
Fawad Ahmed | NEXELUS 2024.2 | Client Items | Client Items | Development | 2024-11 | 0 | 4 | 0 | NEXELUS 2024.2: Client Items
Fawad Ahmed | NEXELUS 2024.2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-11 | 2 | 4 | 0 | NEXELUS 2024.2: Meetings, mails, communication, TFS, Interviews
Fawad Ahmed | PR-0013 | In-house Trainin | In-house Training | Training | 2024-11 | 5.5 | 4 | 0 | PR-0013: In-house Training
Fawad Ahmed | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-11 | 5.15 | 4 |  | PR-0013: Internal Meetings
Fawad Ahmed | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-11 | 8 | 4 | 0 | PR-0013: Time Off - Un Planned
Fawad Ahmed | APWORKS PHASE2 | In-house Trainin | In-house Training | Meetings | 2024-12 | 5.5 | 5 |  | APWORKS PHASE2: In-house Training
Fawad Ahmed | NEXELUS 2024.1 SP2 | 57 | AdTech Fee commission | Bug Fixing | 2024-12 | 2 | 5 |  | NEXELUS 2024.1 SP2: AdTech Fee commission
Fawad Ahmed | NEXELUS 2024.1 SP2 | 57 | AdTech Fee commission | Development | 2024-12 | 17 | 5 |  | NEXELUS 2024.1 SP2: AdTech Fee commission
Fawad Ahmed | NEXELUS 2024.1 SP2 | 57 | AdTech Fee commission | Documentation | 2024-12 | 1 | 5 | 0 | NEXELUS 2024.1 SP2: AdTech Fee commission
Fawad Ahmed | NEXELUS 2024.1 SP2 | 7 | Billing by Media Type | Bug Fixing | 2024-12 | 1 | 5 | 40 | NEXELUS 2024.1 SP2: Billing by Media Type
Fawad Ahmed | NEXELUS 2024.1 SP2 | 56 | Enhancement for Visual Indicators and Flighting Details in Place | Bug Fixing | 2024-12 | 11 | 5 |  | NEXELUS 2024.1 SP2: Enhancement for Visual Indicators and Flighting Details in Place
Fawad Ahmed | NEXELUS 2024.1 SP2 | 56 | Enhancement for Visual Indicators and Flighting Details in Place | Development | 2024-12 | 30.25 | 5 |  | NEXELUS 2024.1 SP2: Enhancement for Visual Indicators and Flighting Details in Place
Fawad Ahmed | NEXELUS 2024.1 SP2 | 56 | Enhancement for Visual Indicators and Flighting Details in Place | Documentation | 2024-12 | 2 | 5 |  | NEXELUS 2024.1 SP2: Enhancement for Visual Indicators and Flighting Details in Place
Fawad Ahmed | NEXELUS 2024.1 SP2 | 56 | Enhancement for Visual Indicators and Flighting Details in Place | Meetings | 2024-12 | 1 | 5 | 0 | NEXELUS 2024.1 SP2: Enhancement for Visual Indicators and Flighting Details in Place
Fawad Ahmed | NEXELUS 2024.1 SP2 | 56 | Enhancement for Visual Indicators and Flighting Details in Place | Task/Code Review | 2024-12 | 3 | 5 |  | NEXELUS 2024.1 SP2: Enhancement for Visual Indicators and Flighting Details in Place
Fawad Ahmed | NEXELUS 2024.1 SP2 | 56 | Enhancement for Visual Indicators and Flighting Details in Place | Testing | 2024-12 | 15.5 | 5 | 0 | NEXELUS 2024.1 SP2: Enhancement for Visual Indicators and Flighting Details in Place
Fawad Ahmed | NEXELUS 2024.1 SP2 | 0 | Project Overhead | Deployment | 2024-12 | 6.5 | 5 | 0 | NEXELUS 2024.1 SP2: Project Overhead
Fawad Ahmed | PR-0013 | In-house Trainin | In-house Training | Training | 2024-12 | 3 | 5 |  | PR-0013: In-house Training
Fawad Ahmed | PR-0013 | Internal Meeting | Internal Meetings | Bug Fixing | 2024-12 | 1 | 5 |  | PR-0013: Internal Meetings
Fawad Ahmed | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-12 | 13.25 | 5 |  | PR-0013: Internal Meetings
Fawad Ahmed | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-12 | 4 | 5 | 0 | PR-0013: Time Off - Un Planned
Hamza Nouman | AP WORKFLOW | Bug Fixing | Regular bug fixing activity | Other | 2024-08 | 16 | 1 | 0 | AP WORKFLOW: Regular bug fixing activity
Hamza Nouman | AP WORKFLOW | QA | Regular testing and QA new project/assignment/task | Other | 2024-08 | 6 | 1 |  | AP WORKFLOW: Regular testing and QA new project/assignment/task
Hamza Nouman | AP WORKFLOW | QA | Regular testing and QA new project/assignment/task | Testing | 2024-08 | 18 | 1 |  | AP WORKFLOW: Regular testing and QA new project/assignment/task
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 6 | Tolerance by media type | Testing | 2024-08 | 13 | 1 |  | APWORKS 2024.2 - PHASE 3: Tolerance by media type
Hamza Nouman | NEXELUS 14.0 | Internal Meeting | Internal Meetings | Other | 2024-08 | 11 | 1 |  | NEXELUS 14.0: Internal Meetings
Hamza Nouman | NEXELUS 2024.2 | Client Items | Client Items | Other | 2024-08 | 48 | 1 |  | NEXELUS 2024.2: Client Items
Hamza Nouman | NEXELUS 2024.2 | Internal Meeting | Internal Meetings | Meetings | 2024-08 | 11 | 1 | 0 | NEXELUS 2024.2: Internal Meetings
Hamza Nouman | NEXELUS 2024.2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-08 | 49 | 1 | 0 | NEXELUS 2024.2: Regular testing and QA new project/assignment/task
Hamza Nouman | AD-0001 | TIME | Time | Leave | 2024-09 | 8 | 2 |  | AD-0001: Time
Hamza Nouman | AP WORKFLOW | Cient UAT Upgrad | Cient UAT Upgrade | Testing | 2024-09 | 4 | 2 | 0 | AP WORKFLOW: Cient UAT Upgrade
Hamza Nouman | AP WORKFLOW | Bug Fixing | Regular bug fixing activity | Testing | 2024-09 | 13 | 2 | 0 | AP WORKFLOW: Regular bug fixing activity
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 99 | Documentation | Documentation | 2024-09 | 1 | 2 |  | APWORKS 2024.2 - PHASE 3: Documentation
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Test Case Dev | 2024-09 | 39 | 2 | 8 | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Hamza Nouman | APWORKS PHASE2 | Internal Meeting | Internal Meetings | Meetings | 2024-09 | 8 | 2 | 0 | APWORKS PHASE2: Internal Meetings
Hamza Nouman | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-09 | 50.5 | 2 |  | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Hamza Nouman | NEXELUS 2024.2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-09 | 1 | 2 |  | NEXELUS 2024.2: Regular testing and QA new project/assignment/task
Hamza Nouman | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-09 | 6 | 2 |  | PR-0013: Internal Meetings
Hamza Nouman | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 4 | 2 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Hamza Nouman | PR-0013 | Requirement Writ | Requirement Specifications document writing | Analysis | 2024-09 | 14 | 2 |  | PR-0013: Requirement Specifications document writing
Hamza Nouman | PR-0013 | Time Off-Planned | Time Off - Planned | Leave | 2024-09 | 8 | 2 |  | PR-0013: Time Off - Planned
Hamza Nouman | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-09 | 12.5 | 2 |  | PR-0013: Time Off - Un Planned
Hamza Nouman | AP WORKFLOW | Cient UAT Upgrad | Cient UAT Upgrade | Testing | 2024-10 | 18 | 3 | 0 | AP WORKFLOW: Cient UAT Upgrade
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Test Case Dev | 2024-10 | 6 | 3 | 40 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Testing | 2024-10 | 42.5 | 3 | 40 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Testing | 2024-10 | 10 | 3 | 40 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Test Case Dev | 2024-10 | 3 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Testing | 2024-10 | 35 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Testing | 2024-10 | 32.5 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Hamza Nouman | NEXELUS 2024.2 | Cient UAT Upgrad | Cient UAT Upgrade | Testing | 2024-10 | 4 | 3 |  | NEXELUS 2024.2: Cient UAT Upgrade
Hamza Nouman | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-10 | 22 | 3 |  | PR-0013: Internal Meetings
Hamza Nouman | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-10 | 10 | 3 |  | PR-0013: Time Off - Un Planned
Hamza Nouman | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | No Workbench | 2024-10 | 1 | 3 |  | PR-0013: Time Off - Un Planned
Hamza Nouman | AD-0001 | 1 | Meetings | Meetings | 2024-11 | 6 | 4 |  | AD-0001: Meetings
Hamza Nouman | AD-0001 | TIME | Time | Leave | 2024-11 | 8 | 4 | 0 | AD-0001: Time
Hamza Nouman | AD-0001 | TIME | Time | No Workbench | 2024-11 | 1 | 4 |  | AD-0001: Time
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 8 | Broadcast Invoice: EDI File Processing | Testing | 2024-11 | 33 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 4 | Google Drive integration. (Setup and Integration development) | Testing | 2024-11 | 31 | 4 |  | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development)
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 29 | Route invoice from one company - company identification | Testing | 2024-11 | 3 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Route invoice from one company - company identification
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Testing | 2024-11 | 4 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | 6 | Google Drive Setup (company configuration UI) | Testing | 2024-11 | 5 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Google Drive Setup (company configuration UI)
Hamza Nouman | NEXELUS 2024.1 SP2 | 50 | Documentation | Documentation | 2024-11 | 4 | 4 |  | NEXELUS 2024.1 SP2: Documentation
Hamza Nouman | NEXELUS 2024.1 SP2 | 4 | Media Plan Approval | Testing | 2024-11 | 5 | 4 |  | NEXELUS 2024.1 SP2: Media Plan Approval
Hamza Nouman | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-11 | 9 | 4 |  | PR-0013: Internal Meetings
Hamza Nouman | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-11 | 12 | 4 |  | PR-0013: Time Off - Un Planned
Hamza Nouman | Support and Maintenance | 2 | Time | Client Items | 2024-11 | 47 | 4 | 0 | Support and Maintenance: Time
Hamza Nouman | AD-0001 | 1 | Meetings | Meetings | 2024-12 | 8 | 5 |  | AD-0001: Meetings
Hamza Nouman | AD-0001 | TIME | Time | No Workbench | 2024-12 | 1.5 | 5 |  | AD-0001: Time
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Bug Fixing | 2024-12 | 5 | 5 |  | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | 13 | EDI file updating and upload | Testing | 2024-12 | 3 | 5 | 0 | APWORKS 2024.2 - PHASE 4: EDI file updating and upload
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | 6 | Google Drive Setup (company configuration UI) | Testing | 2024-12 | 7 | 5 |  | APWORKS 2024.2 - PHASE 4: Google Drive Setup (company configuration UI)
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Post_dep_fixes | 2024-12 | 7 | 5 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Hamza Nouman | APWORKS 2024.2 PHASE 5 | 0 | Project Overhead | Analysis | 2024-12 | 5 | 5 |  | APWORKS 2024.2 PHASE 5: Project Overhead
Hamza Nouman | NEXELUS 2024.1 SP2 | 57 | AdTech Fee commission | Testing | 2024-12 | 14 | 5 |  | NEXELUS 2024.1 SP2: AdTech Fee commission
Hamza Nouman | NEXELUS 2024.1 SP2 | 50 | Documentation | Documentation | 2024-12 | 10.5 | 5 |  | NEXELUS 2024.1 SP2: Documentation
Hamza Nouman | NEXELUS 2024.1 SP2 | 50 | Documentation | Testing | 2024-12 | 3 | 5 |  | NEXELUS 2024.1 SP2: Documentation
Hamza Nouman | NEXELUS 2024.1 SP2 | 56 | Enhancement for Visual Indicators and Flighting Details in Place | Testing | 2024-12 | 17 | 5 |  | NEXELUS 2024.1 SP2: Enhancement for Visual Indicators and Flighting Details in Place
Hamza Nouman | NEXELUS 2024.1 SP2 | 59 | Media Plan: Import/Export Flighting | Testing | 2024-12 | 14 | 5 | 0 | NEXELUS 2024.1 SP2: Media Plan: Import/Export Flighting
Hamza Nouman | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-12 | 5 | 5 |  | PR-0013: Internal Meetings
Hamza Nouman | PR-0013 | Time Off-Planned | Time Off - Planned | Leave | 2024-12 | 8 | 5 | 0 | PR-0013: Time Off - Planned
Hamza Nouman | Support and Maintenance | 2 | Time | Client Items | 2024-12 | 4 | 5 |  | Support and Maintenance: Time
Imran UL Haq | AP WORKFLOW | Development DB | Development of new project/assignment/task | Other | 2024-08 | 33 | 1 |  | AP WORKFLOW: Development of new project/assignment/task
Imran UL Haq | AP WORKFLOW | Bug Fixing | Regular bug fixing activity | Other | 2024-08 | 13 | 1 |  | AP WORKFLOW: Regular bug fixing activity
Imran UL Haq | APWORKS PHASE1 | Bug Fixing | Regular bug fixing activity | Other | 2024-08 | 1 | 1 | 0 | APWORKS PHASE1: Regular bug fixing activity
Imran UL Haq | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-08 | 1 | 1 | 0 | APWORKS PHASE2: Regular bug fixing activity
Imran UL Haq | NEXELUS 2024.2 | Analysis | Analysis of the new project/assignment/task | Other | 2024-08 | 1 | 1 |  | NEXELUS 2024.2: Analysis of the new project/assignment/task
Imran UL Haq | NEXELUS 2024.2 | Client Items | Client Items | Development | 2024-08 | 36.5 | 1 |  | NEXELUS 2024.2: Client Items
Imran UL Haq | NEXELUS 2024.2 | Client Items | Client Items | Other | 2024-08 | 92 | 1 | 0 | NEXELUS 2024.2: Client Items
Imran UL Haq | NEXELUS 2024.2 | In-house Trainin | In-house Training | Other | 2024-08 | 1 | 1 | 0 | NEXELUS 2024.2: In-house Training
Imran UL Haq | NEXELUS 2024.2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 9 | 1 | 0 | NEXELUS 2024.2: Meetings, mails, communication, TFS, Interviews
Imran UL Haq | NEXELUS 2024.2 | National Gazette | National Gazetted Holidays | Other | 2024-08 | 8 | 1 | 0 | NEXELUS 2024.2: National Gazetted Holidays
Imran UL Haq | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-08 | 2.5 | 1 | 0 | PR-0013: Meetings, mails, communication, TFS, Interviews
Imran UL Haq | AP WORKFLOW | Release Environm | Release Environment Upgrade | Deployment | 2024-09 | 6 | 2 |  | AP WORKFLOW: Release Environment Upgrade
Imran UL Haq | APWORKS PHASE2 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-09 | 11 | 2 |  | APWORKS PHASE2: Analysis of production issues reported by support team
Imran UL Haq | APWORKS PHASE2 | Support Items | Support Items | Meetings | 2024-09 | 1 | 2 |  | APWORKS PHASE2: Support Items
Imran UL Haq | NEXELUS 2024.2 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-09 | 4 | 2 | 0 | NEXELUS 2024.2: Analysis of production issues reported by support team
Imran UL Haq | NEXELUS 2024.2 | Client Items | Client Items | Client Items | 2024-09 | 92 | 2 | 0 | NEXELUS 2024.2: Client Items
Imran UL Haq | NEXELUS 2024.2 | Client Items | Client Items | Development | 2024-09 | 2 | 2 |  | NEXELUS 2024.2: Client Items
Imran UL Haq | NEXELUS 2024.2 | Client Items | Client Items | Meetings | 2024-09 | 1 | 2 |  | NEXELUS 2024.2: Client Items
Imran UL Haq | NEXELUS 2024.2 | Development DB | Development of new project/assignment/task | Development | 2024-09 | 3 | 2 |  | NEXELUS 2024.2: Development of new project/assignment/task
Imran UL Haq | NEXELUS 2024.2 | Internal Meeting | Internal Meetings | Meetings | 2024-09 | 1 | 2 |  | NEXELUS 2024.2: Internal Meetings
Imran UL Haq | NEXELUS 2024.2 | National Gazette | National Gazetted Holidays | Leave | 2024-09 | 8 | 2 |  | NEXELUS 2024.2: National Gazetted Holidays
Imran UL Haq | NEXELUS 2024.2 | Production Upgra | Production upgrades | Development | 2024-09 | 5 | 2 |  | NEXELUS 2024.2: Production upgrades
Imran UL Haq | NEXELUS 2024.2 | Support Items | Support Items | Bug Fixing | 2024-09 | 2 | 2 |  | NEXELUS 2024.2: Support Items
Imran UL Haq | NEXELUS 2024.2 | Time Off-Planned | Time Off - Planned | Leave | 2024-09 | 8 | 2 | 0 | NEXELUS 2024.2: Time Off - Planned
Imran UL Haq | PR-0013 | Development DB | Development of new project/assignment/task | Development | 2024-09 | 28 | 2 | 0 | PR-0013: Development of new project/assignment/task
Imran UL Haq | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 1 | 2 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Imran UL Haq | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Development | 2024-10 | 7 | 3 |  | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Imran UL Haq | APWORKS PHASE2 | Development DB | Development of new project/assignment/task | Development | 2024-10 | 15 | 3 |  | APWORKS PHASE2: Development of new project/assignment/task
Imran UL Haq | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-10 | 8 | 3 |  | APWORKS PHASE2: Regular bug fixing activity
Imran UL Haq | NEXELUS 2024.2 | Production Issue | Analysis of production issues reported by support team | Analysis | 2024-10 | 5 | 3 |  | NEXELUS 2024.2: Analysis of production issues reported by support team
Imran UL Haq | NEXELUS 2024.2 | Production Issue | Analysis of production issues reported by support team | Bug Fixing | 2024-10 | 13 | 3 |  | NEXELUS 2024.2: Analysis of production issues reported by support team
Imran UL Haq | NEXELUS 2024.2 | Client Items | Client Items | Client Items | 2024-10 | 40 | 3 | 0 | NEXELUS 2024.2: Client Items
Imran UL Haq | NEXELUS 2024.2 | In-house Trainin | In-house Training | Meetings | 2024-10 | 1 | 3 | 0 | NEXELUS 2024.2: In-house Training
Imran UL Haq | NEXELUS 2024.2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-10 | 1 | 3 |  | NEXELUS 2024.2: Regular bug fixing activity
Imran UL Haq | NEXELUS 2024.2 | Support Items | Support Items | Bug Fixing | 2024-10 | 5 | 3 | 0 | NEXELUS 2024.2: Support Items
Imran UL Haq | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-10 | 2 | 3 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Imran UL Haq | Support and Maintenance | 1 | Time | Client Items | 2024-10 | 11 | 3 |  | Support and Maintenance: Time
Imran UL Haq | Support and Maintenance | 1 | Time | Client Items | 2024-10 | 14 | 3 |  | Support and Maintenance: Time
Imran UL Haq | Support and Maintenance | 1 | Time | Client Items | 2024-10 | 29 | 3 |  | Support and Maintenance: Time
Imran UL Haq | Support and Maintenance | 1 | Time | Client Items | 2024-10 | 11 | 3 |  | Support and Maintenance: Time
Imran UL Haq | Support and Maintenance | 1 | Time | Client Items | 2024-10 | 24 | 3 |  | Support and Maintenance: Time
Imran UL Haq | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Post_dep_fixes | 2024-11 | 16 | 4 |  | APWORKS 2024.2 - PHASE 4: Project Overhead
Imran UL Haq | APWORKS PHASE2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-11 | 2 | 4 |  | APWORKS PHASE2: Regular bug fixing activity
Imran UL Haq | NEXELUS 2024.2 | Bug Fixing | Regular bug fixing activity | Bug Fixing | 2024-11 | 6 | 4 |  | NEXELUS 2024.2: Regular bug fixing activity
Imran UL Haq | NEXELUS 2024.2 | Support Items | Support Items | Analysis | 2024-11 | 1 | 4 |  | NEXELUS 2024.2: Support Items
Imran UL Haq | Support and Maintenance | 1 | Time | Client Items | 2024-11 | 86 | 4 |  | Support and Maintenance: Time
Imran UL Haq | Support and Maintenance | 1 | Time | Client Items | 2024-11 | 6 | 4 |  | Support and Maintenance: Time
Imran UL Haq | Support and Maintenance | 1 | Time | Client Items | 2024-11 | 10 | 4 |  | Support and Maintenance: Time
Imran UL Haq | Support and Maintenance | 1 | Time | Client Items | 2024-11 | 36 | 4 |  | Support and Maintenance: Time
Imran UL Haq | Support and Maintenance | 1 | Time | Client Items | 2024-11 | 5 | 4 | 0 | Support and Maintenance: Time
Imran UL Haq | APWORKS 2024.2 - PHASE 4 | 98 | Integration Testing | Bug Fixing | 2024-12 | 71 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Integration Testing
Imran UL Haq | NEXELUS 2024.1 SP2 | 7 | Billing by Media Type | Bug Fixing | 2024-12 | 3 | 5 |  | NEXELUS 2024.1 SP2: Billing by Media Type
Imran UL Haq | NEXELUS SUPPORT | 3 | Maintenance Activity | Deployment | 2024-12 | 1 | 5 |  | NEXELUS SUPPORT: Maintenance Activity
Imran UL Haq | PR-0013 | Development DB | Development of new project/assignment/task | Development | 2024-12 | 3 | 5 |  | PR-0013: Development of new project/assignment/task
Imran UL Haq | PR-0013 | QA Environment U | QA Environment Upgrade | Support Tickets | 2024-12 | 12 | 5 |  | PR-0013: QA Environment Upgrade
Imran UL Haq | Support and Maintenance | 2 | Time | Client Items | 2024-12 | 2 | 5 |  | Support and Maintenance: Time
Imran UL Haq | Support and Maintenance | 1 | Time | Client Items | 2024-12 | 2 | 5 |  | Support and Maintenance: Time
Imran UL Haq | Support and Maintenance | 1 | Time | Client Items | 2024-12 | 38 | 5 | 0 | Support and Maintenance: Time
Imran UL Haq | Support and Maintenance | 1 | Time | Support Tickets | 2024-12 | 4 | 5 |  | Support and Maintenance: Time
Kashif Hayat | AP WORKFLOW | Production Issue | Analysis of production issues reported by support team | Other | 2024-08 | 3 | 1 | 0 | AP WORKFLOW: Analysis of production issues reported by support team
Kashif Hayat | AP WORKFLOW | Analysis | Analysis of the new project/assignment/task | Other | 2024-08 | 1 | 1 | 0 | AP WORKFLOW: Analysis of the new project/assignment/task
Kashif Hayat | AP WORKFLOW | Requirement Anal | Document review/understanding Requirement Specifications | Other | 2024-08 | 11 | 1 | 0 | AP WORKFLOW: Document review/understanding Requirement Specifications
Kashif Hayat | AP WORKFLOW | Internal Meeting | Internal Meetings | Other | 2024-08 | 6 | 1 |  | AP WORKFLOW: Internal Meetings
Kashif Hayat | AP WORKFLOW | Planning | Project planning for new project/assignment/task | Other | 2024-08 | 3 | 1 |  | AP WORKFLOW: Project planning for new project/assignment/task
Kashif Hayat | AP WORKFLOW | QA Environment U | QA Environment Upgrade | Other | 2024-08 | 39 | 1 |  | AP WORKFLOW: QA Environment Upgrade
Kashif Hayat | AP WORKFLOW | Bug Fixing | Regular bug fixing activity | Other | 2024-08 | 9 | 1 | 0 | AP WORKFLOW: Regular bug fixing activity
Kashif Hayat | AP WORKFLOW | QA | Regular testing and QA new project/assignment/task | Other | 2024-08 | 46 | 1 |  | AP WORKFLOW: Regular testing and QA new project/assignment/task
Kashif Hayat | AP WORKFLOW | Release Environm | Release Environment Upgrade | Other | 2024-08 | 6 | 1 | 0 | AP WORKFLOW: Release Environment Upgrade
Kashif Hayat | AP WORKFLOW | Requirement Writ | Requirement Specifications document writing | Other | 2024-08 | 11 | 1 |  | AP WORKFLOW: Requirement Specifications document writing
Kashif Hayat | APWORKS PHASE2 | Dev Support | Dev Support | Analysis | 2024-08 | 5 | 1 | 0 | APWORKS PHASE2: Dev Support
Kashif Hayat | APWORKS PHASE2 | QA Environment U | QA Environment Upgrade | Testing | 2024-08 | 22 | 1 | 0 | APWORKS PHASE2: QA Environment Upgrade
Kashif Hayat | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-08 | 10 | 1 |  | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Kashif Hayat | AD-0001 | TIME | Time | Leave | 2024-09 | 8 | 2 | 0 | AD-0001: Time
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Meetings | 2024-09 | 16 | 2 | 0 | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Test Case Dev | 2024-09 | 3 | 2 |  | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 2 | Add Media Type/Service type/Roles | Test Case Dev | 2024-09 | 9 | 2 | 0 | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles
Kashif Hayat | APWORKS PHASE2 | Production Issue | Analysis of production issues reported by support team | Client Items | 2024-09 | 15 | 2 | 0 | APWORKS PHASE2: Analysis of production issues reported by support team
Kashif Hayat | APWORKS PHASE2 | Internal Meeting | Internal Meetings | Meetings | 2024-09 | 7 | 2 |  | APWORKS PHASE2: Internal Meetings
Kashif Hayat | APWORKS PHASE2 | Internal Meeting | Internal Meetings | Meetings | 2024-09 | 8 | 2 |  | APWORKS PHASE2: Internal Meetings
Kashif Hayat | APWORKS PHASE2 | Internal Meeting | Internal Meetings | Testing | 2024-09 | 30 | 2 |  | APWORKS PHASE2: Internal Meetings
Kashif Hayat | APWORKS PHASE2 | QA Environment U | QA Environment Upgrade | Testing | 2024-09 | 4 | 2 | 0 | APWORKS PHASE2: QA Environment Upgrade
Kashif Hayat | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-09 | 41 | 2 | 0 | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Kashif Hayat | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-09 | 11 | 2 | 0 | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Kashif Hayat | PR-0013 | Time Off-Planned | Time Off - Planned | Leave | 2024-09 | 8 | 2 | 0 | PR-0013: Time Off - Planned
Kashif Hayat | AD-0001 | TIME | Time | Leave | 2024-10 | 8 | 3 | 0 | AD-0001: Time
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Test Case Dev | 2024-10 | 3 | 3 | 8 | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Testing | 2024-10 | 33 | 3 |  | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 2 | Add Media Type/Service type/Roles | Test Case Dev | 2024-10 | 2 | 3 |  | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 2 | Add Media Type/Service type/Roles | Testing | 2024-10 | 44 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 28 | Customer Information: Select Client on Vendor Invoice | Testing | 2024-10 | 4 | 3 |  | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 21 | Switch Company on Invoice | Documentation | 2024-10 | 1 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Switch Company on Invoice
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 31 | Vendor/stations/sites associated to multiple pay to. | Testing | 2024-10 | 29 | 3 | 0 | APWORKS 2024.2 - PHASE 3: Vendor/stations/sites associated to multiple pay to.
Kashif Hayat | APWORKS PHASE2 | Cient UAT Upgrad | Cient UAT Upgrade | Client Items | 2024-10 | 11 | 3 | 0 | APWORKS PHASE2: Cient UAT Upgrade
Kashif Hayat | APWORKS PHASE2 | Cient UAT Upgrad | Cient UAT Upgrade | Testing | 2024-10 | 8 | 3 | 0 | APWORKS PHASE2: Cient UAT Upgrade
Kashif Hayat | APWORKS PHASE2 | Client Items | Client Items | Testing | 2024-10 | 13 | 3 | 0 | APWORKS PHASE2: Client Items
Kashif Hayat | APWORKS PHASE2 | Internal Meeting | Internal Meetings | Meetings | 2024-10 | 4 | 3 | 0 | APWORKS PHASE2: Internal Meetings
Kashif Hayat | APWORKS PHASE2 | QA Environment U | QA Environment Upgrade | Testing | 2024-10 | 9 | 3 |  | APWORKS PHASE2: QA Environment Upgrade
Kashif Hayat | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-10 | 8 | 3 |  | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Kashif Hayat | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-10 | 8 | 3 |  | PR-0013: Time Off - Un Planned
Kashif Hayat | AP WORKFLOW | QA | Regular testing and QA new project/assignment/task | Analysis | 2024-11 | 8 | 4 |  | AP WORKFLOW: Regular testing and QA new project/assignment/task
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 3 | Ability to assign Employees to Roles by Media type and by Client | Testing | 2024-11 | 4 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 2 | Add Media Type/Service type/Roles | Testing | 2024-11 | 4 | 4 |  | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 100 | Apply discount based on Payment terms settings | Testing | 2024-11 | 2 | 4 |  | APWORKS 2024.2 - PHASE 3: Apply discount based on Payment terms settings
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 28 | Customer Information: Select Client on Vendor Invoice | Testing | 2024-11 | 6 | 4 |  | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 102 | Invoice Editing: Make the tax editable | Analysis | 2024-11 | 2 | 4 |  | APWORKS 2024.2 - PHASE 3: Invoice Editing: Make the tax editable
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 101 | Remove Site column from vendor lookup | Testing | 2024-11 | 1 | 4 | 0 | APWORKS 2024.2 - PHASE 3: Remove Site column from vendor lookup
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | 31 | Vendor/stations/sites associated to multiple pay to. | Testing | 2024-11 | 2 | 4 |  | APWORKS 2024.2 - PHASE 3: Vendor/stations/sites associated to multiple pay to.
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 10 | Approve upto last level and auto post. | Analysis | 2024-11 | 4 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Approve upto last level and auto post.
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 10 | Approve upto last level and auto post. | Testing | 2024-11 | 6 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Approve upto last level and auto post.
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 11 | Currency Changes on Vendor Map | Analysis | 2024-11 | 2 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Currency Changes on Vendor Map
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 98 | Integration Testing | Bug Fixing | 2024-11 | 12 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Integration Testing
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 100 | Production: Auto populate lines based PO during scanning | Testing | 2024-11 | 3 | 4 | 4 | APWORKS 2024.2 - PHASE 4: Production: Auto populate lines based PO during scanning
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 12 | Stamp multiple approvers. | Testing | 2024-11 | 1 | 4 |  | APWORKS 2024.2 - PHASE 4: Stamp multiple approvers.
Kashif Hayat | APWORKS PHASE2 | QA Environment U | QA Environment Upgrade | Testing | 2024-11 | 16 | 4 | 0 | APWORKS PHASE2: QA Environment Upgrade
Kashif Hayat | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-11 | 7 | 4 | 0 | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Kashif Hayat | APWORKS PHASE2 | QA | Regular testing and QA new project/assignment/task | Testing | 2024-11 | 16 | 4 |  | APWORKS PHASE2: Regular testing and QA new project/assignment/task
Kashif Hayat | PR-0013 | Cient UAT Upgrad | Cient UAT Upgrade | Analysis | 2024-11 | 2 | 4 |  | PR-0013: Cient UAT Upgrade
Kashif Hayat | PR-0013 | In-house Trainin | In-house Training | Training | 2024-11 | 2 | 4 |  | PR-0013: In-house Training
Kashif Hayat | PR-0013 | Internal Meeting | Internal Meetings | Meetings | 2024-11 | 1 | 4 |  | PR-0013: Internal Meetings
Kashif Hayat | PR-0013 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-11 | 1 | 4 |  | PR-0013: Meetings, mails, communication, TFS, Interviews
Kashif Hayat | PR-0013 | QA Environment U | QA Environment Upgrade | Testing | 2024-11 | 4 | 4 |  | PR-0013: QA Environment Upgrade
Kashif Hayat | PR-0013 | Time Off-Planned | Time Off - Planned | Leave | 2024-11 | 32 | 4 |  | PR-0013: Time Off - Planned
Kashif Hayat | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-11 | 24 | 4 |  | PR-0013: Time Off - Un Planned
Kashif Hayat | Support and Maintenance | 2 | Time | Client Items | 2024-11 | 8 | 4 | 0 | Support and Maintenance: Time
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 102 | Apply variable name for Site in vendor mapping | Testing | 2024-12 | 2 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Apply variable name for Site in vendor mapping
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 1 | Approval routing | Testing | 2024-12 | 8 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Approval routing
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 10 | Approve upto last level and auto post. | Testing | 2024-12 | 8 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Approve upto last level and auto post.
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 11 | Currency Changes on Vendor Map | Testing | 2024-12 | 2 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Currency Changes on Vendor Map
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 100 | Production: Auto populate lines based PO during scanning | Testing | 2024-12 | 6 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Production: Auto populate lines based PO during scanning
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 8 | Production: Project should be available on summary as well. | Analysis | 2024-12 | 4 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Production: Project should be available on summary as well.
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 101 | Production: show keyvalue pairs for level2 mapping | Bug Fixing | 2024-12 | 4 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Production: show keyvalue pairs for level2 mapping
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Analysis | 2024-12 | 24 | 5 | 0 | APWORKS 2024.2 - PHASE 4: Project Overhead
Kashif Hayat | APWORKS 2024.2 PHASE 5 | 0 | Project Overhead | Analysis | 2024-12 | 48 | 5 | 0 | APWORKS 2024.2 PHASE 5: Project Overhead
Kashif Hayat | PR-0013 | Time Off-Planned | Time Off - Planned | Leave | 2024-12 | 8 | 5 | 0 | PR-0013: Time Off - Planned
Kashif Hayat | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-12 | 8 | 5 | 0 | PR-0013: Time Off - Un Planned
Kashif Hayat | Support and Maintenance | 2 | Time | Client Items | 2024-12 | 20 | 5 | 0 | Support and Maintenance: Time
Saad Saeed | NEXELUS 2024.1 SP2 | 5 | eConnect shell change to service | Development | 2024-10 | 16 | 3 |  | NEXELUS 2024.1 SP2: eConnect shell change to service
Saad Saeed | NEXELUS 2024.1 SP2 | 5 | eConnect shell change to service | Research | 2024-10 | 16 | 3 |  | NEXELUS 2024.1 SP2: eConnect shell change to service
Saad Saeed | PR-0013 | In-house Trainin | In-house Training | Domain Learning | 2024-10 | 40 | 3 |  | PR-0013: In-house Training
Saad Saeed | AD-0001 | 1 | Meetings | Meetings | 2024-11 | 0.75 | 4 |  | AD-0001: Meetings
Saad Saeed | AD-0001 | 1 | Meetings | Meetings | 2024-11 | 0.3 | 4 |  | AD-0001: Meetings
Saad Saeed | AD-0001 | 1 | Meetings | Training | 2024-11 | 2.3 | 4 | 0 | AD-0001: Meetings
Saad Saeed | AD-0001 | Taxes and Bank R | Taxes and Bank Related | Admin | 2024-11 | 1 | 4 | 0 | AD-0001: Taxes and Bank Related
Saad Saeed | AD-0001 | TIME | Time | No Workbench | 2024-11 | 3.3 | 4 |  | AD-0001: Time
Saad Saeed | AD-0001 | TIME | Time | Research | 2024-11 | 2.6 | 4 |  | AD-0001: Time
Saad Saeed | AP WORKFLOW | In-house Trainin | In-house Training | Analysis | 2024-11 | 1 | 4 |  | AP WORKFLOW: In-house Training
Saad Saeed | NEXELUS 2024.1 SP2 | 7 | Billing by Media Type | Development | 2024-11 | 10.3 | 4 |  | NEXELUS 2024.1 SP2: Billing by Media Type
Saad Saeed | NEXELUS 2024.1 SP2 | 7 | Billing by Media Type | Research | 2024-11 | 2.3 | 4 |  | NEXELUS 2024.1 SP2: Billing by Media Type
Saad Saeed | NEXELUS 2024.1 SP2 | 7 | Billing by Media Type | Testing | 2024-11 | 1 | 4 |  | NEXELUS 2024.1 SP2: Billing by Media Type
Saad Saeed | NEXELUS 2024.1 SP2 | 1 | Client Profile: Media > Flag to make the vendor inactive | Development | 2024-11 | 5 | 4 |  | NEXELUS 2024.1 SP2: Client Profile: Media > Flag to make the vendor inactive
Saad Saeed | NEXELUS 2024.1 SP2 | 1 | Client Profile: Media > Flag to make the vendor inactive | Research | 2024-11 | 3.6 | 4 |  | NEXELUS 2024.1 SP2: Client Profile: Media > Flag to make the vendor inactive
Saad Saeed | NEXELUS 2024.1 SP2 | 5 | eConnect shell change to service | Development | 2024-11 | 21.2 | 4 |  | NEXELUS 2024.1 SP2: eConnect shell change to service
Saad Saeed | NEXELUS 2024.1 SP2 | 5 | eConnect shell change to service | Meetings | 2024-11 | 1 | 4 |  | NEXELUS 2024.1 SP2: eConnect shell change to service
Saad Saeed | NEXELUS 2024.1 SP2 | 5 | eConnect shell change to service | Research | 2024-11 | 8 | 4 |  | NEXELUS 2024.1 SP2: eConnect shell change to service
Saad Saeed | NEXELUS 2024.1 SP2 | 5 | eConnect shell change to service | Testing | 2024-11 | 5.3 | 4 |  | NEXELUS 2024.1 SP2: eConnect shell change to service
Saad Saeed | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Development | 2024-11 | 26.6 | 4 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Saad Saeed | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Meetings | 2024-11 | 3.5 | 4 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Saad Saeed | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Research | 2024-11 | 23.6 | 4 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Saad Saeed | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Testing | 2024-11 | 4.75 | 4 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Saad Saeed | NEXELUS 2024.2 | In-house Trainin | In-house Training | Meetings | 2024-11 | 3 | 4 |  | NEXELUS 2024.2: In-house Training
Saad Saeed | PR-0013 | In-house Trainin | In-house Training | Domain Learning | 2024-11 | 24 | 4 |  | PR-0013: In-house Training
Saad Saeed | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-11 | 8 | 4 |  | PR-0013: Time Off - Un Planned
Saad Saeed | AD-0001 | 1 | Meetings | Meetings | 2024-12 | 1.8 | 5 |  | AD-0001: Meetings
Saad Saeed | AD-0001 | 1 | Meetings | Training | 2024-12 | 3 | 5 |  | AD-0001: Meetings
Saad Saeed | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Development | 2024-12 | 52.4 | 5 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Saad Saeed | NEXELUS 2024.1 SP2 | 3 | Generate Client Schedule Lines based on media type | Testing | 2024-12 | 18.8 | 5 |  | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type
Shafiq Ahmed | AD-0001 | Network Support | Network and infrastructure Support | Admin | 2024-08 | 80 | 1 |  | AD-0001: Network and infrastructure Support
Shafiq Ahmed | AD-0001 | Network Support | Network and infrastructure Support | Other | 2024-08 | 96 | 1 |  | AD-0001: Network and infrastructure Support
Shafiq Ahmed | AD-0001 | Network Support | Network and infrastructure Support | Admin | 2024-09 | 168 | 2 |  | AD-0001: Network and infrastructure Support
Shafiq Ahmed | AD-0001 | Network Support | Network and infrastructure Support | Admin | 2024-10 | 72 | 3 | 0 | AD-0001: Network and infrastructure Support
Shafiq Ahmed | AD-0001 | Network Support | Network and infrastructure Support | No Workbench | 2024-10 | 72 | 3 |  | AD-0001: Network and infrastructure Support
Shafiq Ahmed | AD-0001 | TIME | Time | No Workbench | 2024-10 | 40 | 3 |  | AD-0001: Time
Shafiq Ahmed | AD-0001 | Network Support | Network and infrastructure Support | Admin | 2024-11 | 160 | 4 |  | AD-0001: Network and infrastructure Support
Shafiq Ahmed | AD-0001 | Network Support | Network and infrastructure Support | No Workbench | 2024-11 | 8 | 4 |  | AD-0001: Network and infrastructure Support
Shafiq Ahmed | AD-0001 | Network Support | Network and infrastructure Support | Admin | 2024-12 | 144 | 5 |  | AD-0001: Network and infrastructure Support
Tauseef Shahzad | AD-0001 | HR | HR ad Admin Activities | Interview | 2024-08 | 6 | 1 |  | AD-0001: HR ad Admin Activities
Tauseef Shahzad | AD-0001 | Network Support | Network and infrastructure Support | Admin | 2024-08 | 1 | 1 |  | AD-0001: Network and infrastructure Support
Tauseef Shahzad | AD-0001 | Network Support | Network and infrastructure Support | Other | 2024-08 | 55 | 1 |  | AD-0001: Network and infrastructure Support
Tauseef Shahzad | AD-0001 | TIME | Time | Admin | 2024-08 | 1 | 1 |  | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | Meetings | 2024-08 | 6 | 1 |  | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | Other | 2024-08 | 34.5 | 1 |  | AD-0001: Time
Tauseef Shahzad | AP WORKFLOW | Analysis | Analysis of the new project/assignment/task | Other | 2024-08 | 14 | 1 |  | AP WORKFLOW: Analysis of the new project/assignment/task
Tauseef Shahzad | AP WORKFLOW | Client Items | Client Items | Other | 2024-08 | 2 | 1 |  | AP WORKFLOW: Client Items
Tauseef Shahzad | AP WORKFLOW | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 17 | 1 |  | AP WORKFLOW: Meetings, mails, communication, TFS, Interviews
Tauseef Shahzad | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Meetings | 2024-08 | 4 | 1 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Tauseef Shahzad | APWORKS 2024.2 - PHASE 3 | 5 | Project Overhead | Project Mgmt | 2024-08 | 4 | 1 |  | APWORKS 2024.2 - PHASE 3: Project Overhead
Tauseef Shahzad | NEXELUS 2024.2 | Cient UAT Upgrad | Cient UAT Upgrade | Other | 2024-08 | 3 | 1 |  | NEXELUS 2024.2: Cient UAT Upgrade
Tauseef Shahzad | NEXELUS 2024.2 | Client Items | Client Items | Other | 2024-08 | 3 | 1 |  | NEXELUS 2024.2: Client Items
Tauseef Shahzad | NEXELUS 2024.2 | Admin & Misc. | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 8 | 1 |  | NEXELUS 2024.2: Meetings, mails, communication, TFS, Interviews
Tauseef Shahzad | AD-0001 | HR | HR ad Admin Activities | Admin | 2024-09 | 6 | 2 |  | AD-0001: HR ad Admin Activities
Tauseef Shahzad | AD-0001 | HR | HR ad Admin Activities | HR Management | 2024-09 | 4 | 2 |  | AD-0001: HR ad Admin Activities
Tauseef Shahzad | AD-0001 | HR | HR ad Admin Activities | Interview | 2024-09 | 9 | 2 |  | AD-0001: HR ad Admin Activities
Tauseef Shahzad | AD-0001 | Network Support | Network and infrastructure Support | Development | 2024-09 | 1 | 2 |  | AD-0001: Network and infrastructure Support
Tauseef Shahzad | AD-0001 | TIME | Time | Deployment | 2024-09 | 4 | 2 |  | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | Leave | 2024-09 | 8 | 2 |  | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | Meetings | 2024-09 | 24 | 2 |  | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | PMO | 2024-09 | 27 | 2 |  | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | SOC Compliance | 2024-09 | 58 | 2 |  | AD-0001: Time
Tauseef Shahzad | PR-0013 | Session Meetings | Session with US team | Meetings | 2024-09 | 8 | 2 |  | PR-0013: Session with US team
Tauseef Shahzad | PR-0013 | Time Off-Un Plan | Time Off - Un Planned | Leave | 2024-09 | 8 | 2 |  | PR-0013: Time Off - Un Planned
Tauseef Shahzad | AD-0001 | HR | HR ad Admin Activities | Interview | 2024-10 | 10 | 3 |  | AD-0001: HR ad Admin Activities
Tauseef Shahzad | AD-0001 | TIME | Time | Admin | 2024-10 | 6 | 3 |  | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | Leave | 2024-10 | 3 | 3 | 0 | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | Leave | 2024-10 | 10 | 3 | 0 | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | Meetings | 2024-10 | 26 | 3 | 0 | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | PMO | 2024-10 | 45 | 3 | 0 | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | SOC Compliance | 2024-10 | 34 | 3 | 0 | AD-0001: Time
Tauseef Shahzad | PR-0013 | Session Meetings | Session with US team | Meetings | 2024-10 | 17 | 3 | 0 | PR-0013: Session with US team
Tauseef Shahzad | Support and Maintenance | 1 | Time | Client Items | 2024-10 | 2 | 3 | 0 | Support and Maintenance: Time
Tauseef Shahzad | Support and Maintenance | 1 | Time | Client Items | 2024-10 | 8 | 3 | 0 | Support and Maintenance: Time
Tauseef Shahzad | AD-0001 | HR | HR ad Admin Activities | Interview | 2024-11 | 4 | 4 | 0 | AD-0001: HR ad Admin Activities
Tauseef Shahzad | AD-0001 | TIME | Time | Admin | 2024-11 | 20 | 4 | 0 | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | Leave | 2024-11 | 22 | 4 | 0 | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | Meetings | 2024-11 | 33 | 4 | 0 | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | PMO | 2024-11 | 38 | 4 | 0 | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | SOC Compliance | 2024-11 | 4 | 4 | 0 | AD-0001: Time
Tauseef Shahzad | APWORKS 2024.2 - PHASE 4 | 0 | Project Overhead | Deployment | 2024-11 | 7 | 4 | 0 | APWORKS 2024.2 - PHASE 4: Project Overhead
Tauseef Shahzad | PR-0013 | Session Meetings | Session with US team | Meetings | 2024-11 | 20 | 4 | 0 | PR-0013: Session with US team
Tauseef Shahzad | AD-0001 | HR | HR ad Admin Activities | Interview | 2024-12 | 1 | 5 | 0 | AD-0001: HR ad Admin Activities
Tauseef Shahzad | AD-0001 | TIME | Time | Admin | 2024-12 | 22 | 5 | 0 | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | Leave | 2024-12 | 32 | 5 | 0 | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | Meetings | 2024-12 | 19 | 5 | 0 | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | PMO | 2024-12 | 39 | 5 | 0 | AD-0001: Time
Tauseef Shahzad | AD-0001 | TIME | Time | SOC Compliance | 2024-12 | 4 | 5 | 0 | AD-0001: Time
Tauseef Shahzad | PR-0013 | Session Meetings | Session with US team | Meetings | 2024-12 | 17 | 5 | 0 | PR-0013: Session with US team
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:
:

## Const (hidden)
Item | Value | Start Columns | "=IFERROR(IF(E23="Development",VLOOKUP(F23,'Planned Dev'!$D$4:$M$158,J23-2,FALSE),IF(E23="Testing",VLOOKUP(F23,'Planned QA'!$D$4:$N$217,J23-2,FALSE),0)),0)"
2024-08 | 1 | Development
2024-09 | 2 | QA
2024-10 | 3 | Bug Fixing
2024-11 | 4
2024-12 | 5
2025-01 | 6
2025-02 | 7
2025-03 | 8
2025-04 | 9
2025-05 | 10
2025-06 | 11
2025-07 | 12
2025-08 | 13
2025-09 | 14
2025-10 | 15
2025-11 | 16
2025-12 | 17
2026-01 | 18

## Planned Dev
Development
Plan | Task Name | Planned Activity | Full-Activity | Work | Duration | Start | Finish | August, 2024 | September, 2024 | October, 2024 | November, 2024 | December, 2024
| Sprint 3 - Plus Co Items & Additional items |  |  | 518 | 208.14 | Thu 9/5/24 | Mon 10/14/24 |  | 379.39 | 138.61
APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Add Media Type/Service type/Roles | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles | 4 | 5 | Thu 9/5/24 | Thu 9/5/24 |  | 4
APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Google Drive integration. (Setup and Integration development) | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development) | 44 | 57 | Tue 9/10/24 | Fri 9/20/24 |  | 44
APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents (tear sheets, afidavit) to the invoice | Ability to automatically attach additional documents to Invoice | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice | 30 | 116.64 | Thu 9/5/24 | Thu 9/26/24 |  | 30
APWORKS 2024.2 - PHASE 3 | We need to read the company on the invoice document to route to the right company. If the company is not detected properly we will default to a company and mark it with a status. | Route invoice from one company - company identification | APWORKS 2024.2 - PHASE 3: Route invoice from one company - company identification | 56 | 183.14 | Thu 9/5/24 | Wed 10/9/24 |  | 16 | 40
APWORKS 2024.2 - PHASE 3 | Broadcast invoices |  | APWORKS 2024.2 - PHASE 3: | 178 | 208.14 | Thu 9/5/24 | Mon 10/14/24 |  | 131.73 | 46.27
APWORKS 2024.2 - PHASE 3 | We will need a separate node for "Broadcast Invoices" added at the end of Production Invoices. | separate node for "Broadcast Invoices" | APWORKS 2024.2 - PHASE 3: separate node for "Broadcast Invoices" | 4 | 5.72 | Wed 9/11/24 | Wed 9/11/24 |  | 4
APWORKS 2024.2 - PHASE 3 | User Group management changes | Broadcast Invoice: User Group Management Changes | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: User Group Management Changes | 12 | 46.29 | Thu 9/5/24 | Fri 9/13/24 |  | 12
APWORKS 2024.2 - PHASE 3 | Dashboard |  | APWORKS 2024.2 - PHASE 3: | 16 | 77.14 | Thu 9/5/24 | Thu 9/19/24 |  | 16
APWORKS 2024.2 - PHASE 3 | Manage Invoice Documents | Broadcast Invoice: Manage Invoice Documents | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Manage Invoice Documents | 4 | 82.86 | Thu 9/5/24 | Fri 9/20/24 |  | 4
APWORKS 2024.2 - PHASE 3 | EDI file processing | Broadcast Invoice: EDI File Processing | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing | 62 | 128.48 | Thu 9/5/24 | Mon 9/30/24 |  | 62
APWORKS 2024.2 - PHASE 3 | PDF file generation | Broadcast Invoice: PDF file generation | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: PDF file generation | 50 | 79.67 | Mon 9/30/24 | Mon 10/14/24 |  | 3.73 | 46.27
APWORKS 2024.2 - PHASE 3 | Invoice View UI | Broadcast Invoice: Invoice View UI | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Invoice View UI | 30 | 128.48 | Thu 9/5/24 | Mon 9/30/24 |  | 30
APWORKS 2024.2 - PHASE 3 | Fastrack is maintaining the broadcast calendar dates. We may need to maintain this type of date period. |  | APWORKS 2024.2 - PHASE 3: | 0 | 125.72 | Thu 9/5/24 | Mon 9/30/24 |  | 0
APWORKS 2024.2 - PHASE 3 | Customer Information : Selection of the client on the vendor invoice header level. This will help route the invoice to the appropriate client team. - (Sync and a lookup field on invoice) | Customer Information: Select Client on Vendor Invoice | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice | 16 | 118.29 | Thu 9/12/24 | Fri 10/4/24 |  | 4 | 12
APWORKS 2024.2 - PHASE 3 | Read data from Media Ocean Jobs, IOs (buying), Customer Master, Vendor Master, Currencies, Tax codes, Payment terms, EDI?, payment information |  | APWORKS 2024.2 - PHASE 3: | 80 | 142.86 | Thu 9/5/24 | Wed 10/2/24 |  | 74.56 | 5.44
APWORKS 2024.2 - PHASE 3 | vendor/stations/sites can be associated to multiple pay to. EX: Bell Media is linked to Bill pay to | Vendor/stations/sites associated to multiple pay to. | APWORKS 2024.2 - PHASE 3: Vendor/stations/sites associated to multiple pay to. | 32 | 83 | Fri 9/20/24 | Fri 10/4/24 |  | 15.6 | 16.4
APWORKS 2024.2 - PHASE 3 | Checkbox to filter discrepant lines | Checkbox to filter discrepant lines | APWORKS 2024.2 - PHASE 3: Checkbox to filter discrepant lines | 8 | 11.43 | Fri 10/4/24 | Mon 10/7/24 |  |  | 8
APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Ability to assign Employees to Roles by Media type and by Client | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client | 70 | 110.14 | Thu 9/12/24 | Thu 10/3/24 |  | 59.5 | 10.5
APWORKS 2024.2 - PHASE 3 | Make the tax editable | Invoice Editing: Make the tax editable | APWORKS 2024.2 - PHASE 3: Invoice Editing: Make the tax editable | 0
| Sprint #4 (PlusCo Phase 3) |  |  | 389 | 283.5 | Mon 10/21/24 | Mon 12/9/24 |  |  | 71.26 | 267.54 | 50.2
APWORKS 2024.2 - PHASE 4 | Bug fixing - sprint #3 |  | APWORKS 2024.2 - PHASE 4 : | 60 | 37.5 | Fri 10/25/24 | Thu 10/31/24 |  |  | 60
APWORKS 2024.2 - PHASE 4 | Discount implementation CHANGES |  | APWORKS 2024.2 - PHASE 4 : | 12 | 7 | Thu 10/31/24 | Fri 11/1/24 |  |  | 3.26 | 8.74
APWORKS 2024.2 - PHASE 4 | Approve upto last level and auto post as well based on configuration | Approve upto last level and auto post. | APWORKS 2024.2 - PHASE 4 : Approve upto last level and auto post. | 8 | 10 | Fri 11/1/24 | Mon 11/4/24 |  |  |  | 8
APWORKS 2024.2 - PHASE 4 | Remove currency check while mapping vendor in vendor mapping dailog and apply vendor currency to invoices. | Currency Changes on Vendor Map | APWORKS 2024.2 - PHASE 4 : Currency Changes on Vendor Map | 16 | 20 | Fri 11/1/24 | Wed 11/6/24 |  |  |  | 16
APWORKS 2024.2 - PHASE 4 | Stamp multiple approvers. | Stamp multiple approvers. | APWORKS 2024.2 - PHASE 4 : Stamp multiple approvers. | 12 | 15 | Mon 11/4/24 | Wed 11/6/24 |  |  |  | 12
APWORKS 2024.2 - PHASE 4 | Split Process for Google Drive integration and show documents in queue. |  | APWORKS 2024.2 - PHASE 4 : | 30 | 37.5 | Wed 11/6/24 | Wed 11/13/24 |  |  |  | 30
APWORKS 2024.2 - PHASE 4 | EDI file updating | EDI file updating and upload | APWORKS 2024.2 - PHASE 4 : EDI file updating and upload | 12 | 15 | Wed 11/20/24 | Thu 11/21/24 |  |  |  | 12
APWORKS 2024.2 - PHASE 4 | Remove Site column or show media sites |  | APWORKS 2024.2 - PHASE 4 : | 1 hr | 1.25 | Wed 11/6/24 | Wed 11/6/24 |  |  |  | 1
APWORKS 2024.2 - PHASE 4 | Add Vendor column in Insertion order list |  | APWORKS 2024.2 - PHASE 4 : | 4 | 5 | Wed 11/6/24 | Thu 11/7/24 |  |  |  | 4
APWORKS 2024.2 - PHASE 4 | Production: Project should be available on summary as well. | Production: Project should be available on summary as well. | APWORKS 2024.2 - PHASE 4 : Production: Project should be available on summary as well. | 6 | 7.5 | Mon 11/18/24 | Tue 11/19/24 |  |  |  | 6
APWORKS 2024.2 - PHASE 4 | Production: Auto populate lines based PO during scanning | Production: Auto populate lines based PO during scanning | APWORKS 2024.2 - PHASE 4 : Production: Auto populate lines based PO during scanning | 8 | 6.67 | Tue 11/19/24 | Tue 11/19/24 |  |  |  | 8
APWORKS 2024.2 - PHASE 4 | Production: show keyvalue pairs for level2 mapping | Production: show keyvalue pairs for level2 mapping | APWORKS 2024.2 - PHASE 4 : Production: show keyvalue pairs for level2 mapping | 8 | 178.5 | Mon 10/21/24 | Wed 11/20/24 |  |  | 4 | 4
APWORKS 2024.2 - PHASE 4 | Broadcast Model Fields |  | APWORKS 2024.2 - PHASE 4 : | 0
APWORKS 2024.2 - PHASE 4 | We need a way to forward invoice to user OR select a user when invoice is in Pending Approval queue | Route invoice from one company - company identification | APWORKS 2024.2 - PHASE 4 : Route invoice from one company - company identification | 70 | 50 | Thu 11/21/24 | Fri 11/29/24 |  |  |  | 70
APWORKS 2024.2 - PHASE 4 | A report to spot check the invoices processed (Plusco) | A report to spot check the invoices processed | APWORKS 2024.2 - PHASE 4 : A report to spot check the invoices processed | 30 | 68 | Wed 11/20/24 | Mon 12/2/24 |  |  |  | 27 | 3
APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices (Plusco) |  | APWORKS 2024.2 - PHASE 4 : | 60 | 75 | Tue 11/26/24 | Mon 12/9/24 |  |  |  | 24.8 | 35.2
APWORKS 2024.2 - PHASE 4 | Invoice Scan | PDF based broadcast invoices - Invoice Scan | APWORKS 2024.2 - PHASE 4 : PDF based broadcast invoices - Invoice Scan | 40 | 50 | Tue 11/26/24 | Wed 12/4/24 |  |  |  | 24.8 | 15.2
APWORKS 2024.2 - PHASE 4 | Model updates list |  | APWORKS 2024.2 - PHASE 4 : | 10 | 62.5 | Tue 11/26/24 | Thu 12/5/24 |  |  |  |  | 10
APWORKS 2024.2 - PHASE 4 | Manage non-mapped list |  | APWORKS 2024.2 - PHASE 4 : | 10 | 75 | Tue 11/26/24 | Mon 12/9/24 |  |  |  |  | 10
APWORKS 2024.2 - PHASE 4 | Import / Export lines | PDF based broadcast invoices - Import / Export lines | APWORKS 2024.2 - PHASE 4 : PDF based broadcast invoices - Import / Export lines | 0 | 7 | Tue 11/26/24 | Tue 11/26/24
APWORKS 2024.2 - PHASE 4 | Approvals | Approval routing | APWORKS 2024.2 - PHASE 4 : Approval routing | 0 | 7 | Tue 11/26/24 | Tue 11/26/24
APWORKS 2024.2 - PHASE 4 | Pull Client & Sites, Service types as Media Types from Nexelus |  | APWORKS 2024.2 - PHASE 4 : | 36 | 7 | Wed 11/20/24 | Wed 11/20/24 |  |  |  | 36
APWORKS 2024.2 - PHASE 4 | Notification |  | APWORKS 2024.2 - PHASE 4 : | 0
APWORKS 2024.2 - PHASE 4 | Apply variable name for Site in vendor mapping |  | APWORKS 2024.2 - PHASE 4 : | 12 | 7 | Mon 12/2/24 | Tue 12/3/24 |  |  |  |  | 12
APWORKS 2024.2 - PHASE 4 | Checkbox to show unapproved lines |  | APWORKS 2024.2 - PHASE 4 : | 0 | 0 | Mon 10/21/24 | Mon 10/21/24
APWORKS 2024.2 - PHASE 4 | Vendor mapping enhancement for Non-media | Vendor mapping enhancement for Non-media | APWORKS 2024.2 - PHASE 4 : Vendor mapping enhancement for Non-media | 0 | 7 | Mon 10/21/24 | Mon 10/21/24
APWORKS 2024.2 - PHASE 4 | Filter for discrepenet invoices on client base |  | APWORKS 2024.2 - PHASE 4 : | 4 | 8 | Mon 10/21/24 | Tue 10/22/24 |  |  | 4
APWORKS 2024.2 - PHASE 4 | Validation notifications |  | APWORKS 2024.2 - PHASE 4 : | 0 | 7 | Mon 10/21/24 | Mon 10/21/24
APWORKS 2024.2 - PHASE 4 | Re: APWorks - Data search service |  | APWORKS 2024.2 - PHASE 4 : | 0
| Sprint 5 |  | : Sprint 5 | 40 | 635.24 | Tue 8/27/24 | Wed 12/18/24 |  |  |  |  | 40
APWORKS 2024.2 - PHASE 4 | Google Drive Setup (company configuration UI) | Google Drive Setup (company configuration UI) | APWORKS 2024.2 - PHASE 4 : Google Drive Setup (company configuration UI) | 40 | 50 | Tue 12/10/24 | Wed 12/18/24 |  |  |  |  | 40
APWORKS 2024.2 - PHASE 4 | Vendor invoices report: Add date filters |  | APWORKS 2024.2 - PHASE 4 : | 0 | 7 | Tue 8/27/24 | Tue 8/27/24
| Sprint #6 |  | : Sprint #6 | 0 | 635.24 | Tue 8/27/24 | Wed 12/18/24 | 0 |  |  |  | 0
APWORKS 2024.2 - PHASE 6 | Credit memo |  | APWORKS 2024.2 - PHASE 6: | 0 | 95.24 | Mon 12/2/24 | Wed 12/18/24 |  |  |  |  | 0
APWORKS 2024.2 - PHASE 6 | Refine statuses |  | APWORKS 2024.2 - PHASE 6: | 0 | 0 | Wed 12/18/24 | Wed 12/18/24 |  |  |  |  | 0
APWORKS 2024.2 - PHASE 6 | Labels as Variable names |  | APWORKS 2024.2 - PHASE 6: | 0 | 0 | Wed 8/28/24 | Wed 8/28/24 | 0
APWORKS 2024.2 - PHASE 6 | The filter on the dashboard should have: 'like' date from and to |  | APWORKS 2024.2 - PHASE 6: | 0 | 0 | Wed 8/28/24 | Wed 8/28/24 | 0
APWORKS 2024.2 - PHASE 6 | Add a button on dashboard or invoice document listing to post all good invoices. |  | APWORKS 2024.2 - PHASE 6: | 0 | 8 | Tue 8/27/24 | Wed 8/28/24 | 0
APWORKS 2024.2 - PHASE 6 | Moving invoice between media type (Media to Broadcast or viseversa) |  | APWORKS 2024.2 - PHASE 6: | 0 | 8 | Tue 8/27/24 | Wed 8/28/24 | 0
APWORKS 2024.2 - PHASE 6 | Add a flag "perfered" for email |  | APWORKS 2024.2 - PHASE 6: | 0 | 7 | Tue 8/27/24 | Tue 8/27/24
APWORKS 2024.2 - PHASE 6 | Split/Merge on Production module |  | APWORKS 2024.2 - PHASE 6: | 0
APWORKS 2024.2 - PHASE 6 | Email Ref: APWorks - Not urgent items |  | APWORKS 2024.2 - PHASE 6: | 0 | 7 | Tue 8/27/24 | Tue 8/27/24
APWORKS 2024.2 - PHASE 6 | Global Mappings - Vendor Map |  | APWORKS 2024.2 - PHASE 6: | 0
APWORKS 2024.2 - PHASE 6 | RE: APWorks - Nexelus to APWorks data sync improvements |  | APWORKS 2024.2 - PHASE 6: | 0
APWORKS 2024.2 - PHASE 6 | Review and Management |  | APWORKS 2024.2 - PHASE 6: | 70 | 350 | Tue 8/27/24 | Fri 11/1/24 | 6.2 | 25.6 | 36.8 | 1.4
APWORKS 2024.2 - PHASE 6 | Abid |  | APWORKS 2024.2 - PHASE 6: | 70 |  | Tue 8/27/24 | Fri 11/1/24 | 6.2 | 25.6 | 36.8 | 1.4
APWORKS 2024.2 - PHASE 6 | QA |  | APWORKS 2024.2 - PHASE 6: | 343.4 | 524.02 | Fri 9/20/24 | Fri 12/20/24 |  | 23.2 | 202.8 | 48.3 | 69.1
APWORKS 2024.2 - PHASE 6 | Sprint #3 |  | APWORKS 2024.2 - PHASE 6: | 226 | 184.14 | Fri 9/20/24 | Wed 10/23/24 |  | 23.2 | 202.8
APWORKS 2024.2 - PHASE 6 | QA |  | APWORKS 2024.2 - PHASE 6: | 226 | 184.14 | Fri 9/20/24 | Wed 10/23/24 |  | 23.2 | 202.8
APWORKS 2024.2 - PHASE 6 | Google Drive integration. (Setup and Integration development) | Google Drive integration. (Setup and Integration development) | APWORKS 2024.2 - PHASE 6: Google Drive integration. (Setup and Integration development) | 8 | 10 | Fri 9/20/24 | Mon 9/23/24 |  | 8
APWORKS 2024.2 - PHASE 6 | Ability to automatically attach additional documents (tear sheets, afidavit) to the invoice | Ability to automatically attach additional documents to Invoice | APWORKS 2024.2 - PHASE 6: Ability to automatically attach additional documents to Invoice | 20 | 25 | Thu 9/26/24 | Wed 10/2/24 |  | 13.2 | 6.8
APWORKS 2024.2 - PHASE 6 | We need to read the company on the invoice document to route to the right company. If the company is not detected properly we will default to a company and mark it with a status. |  | APWORKS 2024.2 - PHASE 6: | 20 | 25 | Fri 10/4/24 | Wed 10/9/24 |  |  | 20
APWORKS 2024.2 - PHASE 6 | Broadcast invoices |  | APWORKS 2024.2 - PHASE 6: | 60 | 50 | Wed 10/9/24 | Fri 10/18/24 |  | 2 | 58
APWORKS 2024.2 - PHASE 6 | Invoice List UI | Broadcast Invoice: Manage Invoice Models List | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: Manage Invoice Models List | 8 | 10 | Fri 9/20/24 | Mon 9/23/24 |  | 8
APWORKS 2024.2 - PHASE 6 | User Group management changes | Broadcast Invoice: User Group Management Changes | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: User Group Management Changes | 2 |  |  |  |  | 2
APWORKS 2024.2 - PHASE 6 | Dashboard |  | APWORKS 2024.2 - PHASE 6: | 0
APWORKS 2024.2 - PHASE 6 | Manage Invoice Models |  | APWORKS 2024.2 - PHASE 6: | 0
APWORKS 2024.2 - PHASE 6 | Manage Non-Mapped Production Invoices | Broadcast Invoice: Manage Non-Mapped Broadcast Invoices | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: Manage Non-Mapped Broadcast Invoices | 0
APWORKS 2024.2 - PHASE 6 | EDI file processing | Broadcast Invoice: EDI File Processing | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: EDI File Processing | 40 | 50 | Wed 10/9/24 | Fri 10/18/24 |  |  | 40
APWORKS 2024.2 - PHASE 6 | Invoice View UI | Broadcast Invoice: Invoice View UI | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: Invoice View UI | 12 | 15 | Tue 10/15/24 | Thu 10/17/24 |  |  | 12
APWORKS 2024.2 - PHASE 6 | PDF file generation | Broadcast Invoice: PDF file generation | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: PDF file generation | 6 | 7.5 | Mon 10/14/24 | Tue 10/15/24 |  |  | 6
APWORKS 2024.2 - PHASE 6 | Customer Information : Selection of the client on the vendor invoice header level. This will help route the invoice to the appropriate client team. - (Sync and a lookup field on invoice) | Customer Information: Select Client on Vendor Invoice | APWORKS 2024.2 - PHASE 6: Customer Information: Select Client on Vendor Invoice | 4 | 5 | Fri 10/4/24 | Fri 10/4/24 |  |  | 4
APWORKS 2024.2 - PHASE 6 | Read data from Media Ocean Jobs, IOs (buying), Customer Master, Vendor Master, Currencies, Tax codes, Payment terms, EDI?, payment information |  | APWORKS 2024.2 - PHASE 6: | 40 | 50 | Wed 10/2/24 | Thu 10/10/24 |  |  | 40
APWORKS 2024.2 - PHASE 6 | vendor/stations/sites can be associated to multiple pay to. EX: Bell Media is linked to Bill pay to |  | APWORKS 2024.2 - PHASE 6: | 6 | 7.5 | Fri 10/4/24 | Mon 10/7/24 |  |  | 6
APWORKS 2024.2 - PHASE 6 | Ability to assign Employees to Roles by Media type and by Client |  | APWORKS 2024.2 - PHASE 6: | 8 | 26.67 | Thu 10/3/24 | Tue 10/8/24 |  |  | 8
APWORKS 2024.2 - PHASE 6 | Testing and Review |  | APWORKS 2024.2 - PHASE 6: | 60 | 100 | Fri 10/4/24 | Wed 10/23/24 |  |  | 60
APWORKS 2024.2 - PHASE 6 | Sprint #4 |  | APWORKS 2024.2 - PHASE 6: | 101.4 | 131.45 | Wed 11/20/24 | Thu 12/12/24 |  |  |  | 48.3 | 53.1
APWORKS 2024.2 - PHASE 6 | Production: Auto populate lines based PO during scanning |  | APWORKS 2024.2 - PHASE 6: | 4 | 4.44 | Wed 11/20/24 | Wed 11/20/24 |  |  |  | 4
APWORKS 2024.2 - PHASE 6 | Production: Project should be available on summary as well. |  | APWORKS 2024.2 - PHASE 6: | 4 | 4.45 | Wed 11/20/24 | Thu 11/21/24 |  |  |  | 4
APWORKS 2024.2 - PHASE 6 | Production: show keyvalue pairs for level2 mapping |  | APWORKS 2024.2 - PHASE 6: | 4 | 4.45 | Thu 11/21/24 | Thu 11/21/24 |  |  |  | 4
APWORKS 2024.2 - PHASE 6 | We need a way to forward invoice to user OR select a user when invoice is in Pending Approval queue |  | APWORKS 2024.2 - PHASE 6: | 51.4 | 62.45 | Thu 11/21/24 | Tue 12/3/24 |  |  |  | 28.4 | 23
APWORKS 2024.2 - PHASE 6 | A report to spot check the invoices processed |  | APWORKS 2024.2 - PHASE 6: | 8 | 50.22 | Fri 11/22/24 | Tue 12/3/24 |  |  |  | 4 | 4
APWORKS 2024.2 - PHASE 6 | PDF based broadcast invoices |  | APWORKS 2024.2 - PHASE 6: | 30 | 72.78 | Fri 11/29/24 | Thu 12/12/24 |  |  |  | 3.9 | 26.1
APWORKS 2024.2 - PHASE 6 | Pull Client & Sites from Nexelus |  | APWORKS 2024.2 - PHASE 6: | 0 | 8.89 | Thu 11/21/24 | Fri 11/22/24
APWORKS 2024.2 - PHASE 6 | Sprint #5 |  | APWORKS 2024.2 - PHASE 6: | 16 | 17.78 | Wed 12/18/24 | Fri 12/20/24 |  |  |  |  | 16
APWORKS 2024.2 - PHASE 6 | Bug Fixing |  | APWORKS 2024.2 - PHASE 6: | 138 | 661.91 | Tue 8/27/24 | Mon 12/23/24 |  | 1.87 | 98.13 |  | 38
APWORKS 2024.2 - PHASE 6 | Sprint #3 |  | APWORKS 2024.2 - PHASE 6: | 100 | 117.17 | Mon 9/30/24 | Mon 10/21/24 |  | 1.87 | 98.13
APWORKS 2024.2 - PHASE 6 | Sprint #4 |  | APWORKS 2024.2 - PHASE 6: | 30 | 616.78 | Tue 8/27/24 | Mon 12/16/24 |  |  |  |  | 30
APWORKS 2024.2 - PHASE 6 | We need a way to forward invoice to user OR select a user when invoice is in Pending Approval queue |  | APWORKS 2024.2 - PHASE 6: | 11 | 8.89 | Tue 12/3/24 | Wed 12/4/24 |  |  |  |  | 11
APWORKS 2024.2 - PHASE 6 | A report to spot check the invoices processed |  | APWORKS 2024.2 - PHASE 6: | 3 | 3.33 | Tue 12/3/24 | Tue 12/3/24 |  |  |  |  | 3
APWORKS 2024.2 - PHASE 6 | PDF based broadcast invoices |  | APWORKS 2024.2 - PHASE 6: | 16 | 13.33 | Thu 12/12/24 | Mon 12/16/24 |  |  |  |  | 16
APWORKS 2024.2 - PHASE 6 | Pull Client & Sites from Nexelus |  | APWORKS 2024.2 - PHASE 6: | 0 | 0 | Tue 8/27/24 | Tue 8/27/24
APWORKS 2024.2 - PHASE 6 | Sprint #5 |  | APWORKS 2024.2 - PHASE 6: | 8 | 661.91 | Tue 8/27/24 | Mon 12/23/24 |  |  |  |  | 8
APWORKS 2024.2 - PHASE 6 | QA Iteration #2 |  | APWORKS 2024.2 - PHASE 6: | 160 | 641.78 | Tue 8/27/24 | Thu 12/19/24 | 27.9 | 2.1 | 50 |  | 80
APWORKS 2024.2 - PHASE 6 | Integration Testing |  | APWORKS 2024.2 - PHASE 6: | 66 | 24 | Thu 12/19/24 | Tue 12/24/24 |  |  |  |  | 66
APWORKS 2024.2 - PHASE 6 | Bug fixing for integration testing |  | APWORKS 2024.2 - PHASE 6: | 40 | 28.57 | Thu 12/19/24 | Tue 12/24/24 |  |  |  |  | 40
APWORKS 2024.2 - PHASE 6 | UAT Deployments |  | APWORKS 2024.2 - PHASE 6: | 20 | 7 | Tue 12/24/24 | Wed 12/25/24 |  |  |  |  | 20
|  |  | : | 0
| Nexelus 2024.1 SP2 |  | : Nexelus 2024.1 SP2 | 588 | 405.45 | Mon 10/14/24 | Mon 12/23/24 |  |  | 142.9 | 260.4 | 184.7
NEXELUS 2024.1 SP2 | Development and Testing |  | NEXELUS 2024.1 SP2 : | 484 | 360.95 | Mon 10/14/24 | Mon 12/16/24 |  |  | 132.9 | 260.4 | 90.7
NEXELUS 2024.1 SP2 | Backup Table for vendor/client lines relationship | Backup Table for vendor/client lines relationship | NEXELUS 2024.1 SP2 : Backup Table for vendor/client lines relationship | 58 | 62.86 | Tue 10/29/24 | Thu 11/7/24 |  |  | 24.1 | 33.9
NEXELUS 2024.1 SP2 | Need to support UDF & naming convention fields in RFP (Bulksheet only) |  | NEXELUS 2024.1 SP2 : | 188 | 182.86 | Thu 10/17/24 | Mon 11/18/24 |  |  | 89.8 | 98.2
NEXELUS 2024.1 SP2 | Vendor Portal Proposal | UDF & Naming Convention in Vendor Portal - Proposal Import/exp | NEXELUS 2024.1 SP2 : UDF & Naming Convention in Vendor Portal - Proposal Import/exp | 114 | 120 | Thu 10/17/24 | Thu 11/7/24 |  |  | 77.8 | 36.2
NEXELUS 2024.1 SP2 | Nexelus Export only on Proposal | UDF & Naming Convention in Nexelus - Export on Proposal | NEXELUS 2024.1 SP2 : UDF & Naming Convention in Nexelus - Export on Proposal | 36 | 125.72 | Mon 10/21/24 | Tue 11/12/24 |  |  | 4 | 32
NEXELUS 2024.1 SP2 | Nexelus RFP (Import/Export) | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | NEXELUS 2024.1 SP2 : UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | 38 | 182.86 | Thu 10/17/24 | Mon 11/18/24 |  |  | 8 | 30
NEXELUS 2024.1 SP2 | Nexelus RFP (Import/Export) - Phase 2 (onhold) |  | NEXELUS 2024.1 SP2 : | 68 | 34.29 | Thu 10/17/24 | Wed 10/23/24 |  |  | 68
NEXELUS 2024.1 SP2 | Generate client lines based on media type | Generate Client Schedule Lines based on media type | NEXELUS 2024.1 SP2 : Generate Client Schedule Lines based on media type | 205 | 360.95 | Mon 10/14/24 | Mon 12/16/24 |  |  | 13 | 101.3 | 90.7
NEXELUS 2024.1 SP2 | Client Profile |  | NEXELUS 2024.1 SP2 : | 1 hr | 5 | Thu 10/24/24 | Thu 10/24/24 |  |  | 1
NEXELUS 2024.1 SP2 | Level3 |  | NEXELUS 2024.1 SP2 : | 1 hr | 5 | Thu 10/24/24 | Fri 10/25/24 |  |  | 1
NEXELUS 2024.1 SP2 | Media Plan Vendor lines (new, import/export) |  | NEXELUS 2024.1 SP2 : | 66 | 300.43 | Mon 10/14/24 | Wed 12/4/24 |  |  | 4 | 46 | 16
NEXELUS 2024.1 SP2 | Client Lines (new line, generate schedule) | Billing by Media Type | NEXELUS 2024.1 SP2 : Billing by Media Type | 137 | 276.95 | Mon 10/28/24 | Mon 12/16/24 |  |  | 7 | 55.3 | 14.7
NEXELUS 2024.1 SP2 | DB |  | NEXELUS 2024.1 SP2 : | 7 | 17.5 | Mon 10/28/24 | Wed 10/30/24 |  |  | 7
NEXELUS 2024.1 SP2 | Media Plan approval | Media Plan Approval | NEXELUS 2024.1 SP2 : Media Plan Approval | 14 | 26.67 | Thu 10/31/24 | Tue 11/5/24 |  |  | 2.4 | 11.6
NEXELUS 2024.1 SP2 | Please note that data is based on latest Insertion Order based on most recent approved media plan. Please ensure that Insertion Order(s) are revised as such.” |  | NEXELUS 2024.1 SP2 : | 0 | 7 | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | Client Profile: Media > Flag to make the vendor inactive | Client Profile: Media > Flag to make the vendor inactive | NEXELUS 2024.1 SP2 : Client Profile: Media > Flag to make the vendor inactive | 24 | 105.71 | Thu 10/24/24 | Tue 11/12/24 |  |  | 6 | 8
NEXELUS 2024.1 SP2 | Mngt Fee renamable everywhere | AdTech Fee commission | NEXELUS 2024.1 SP2 : AdTech Fee commission | 9 | 175.43 | Mon 10/14/24 | Wed 11/13/24 |  |  |  | 4
NEXELUS 2024.1 SP2 | Support items |  | NEXELUS 2024.1 SP2 : | 0 | 0 | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | support> Pursuit - Is it possible to make the email address field longer on the client profile page? 17136 |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Client Support Item> The issue is resolved which was due to missing preferred group flag for this user. |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | support item> Please see below, currently we see system only allows 256 characters in the comments box. |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Support item -Person shouldn't be able to approve his own expense report / Timesheet even after switching to his manager / supervisor |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Support item> It is crashing because of “&” character, it requires a DLL change to resolve the issue. |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Support item > Can we add Print label in future release> see attached email for reference |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Support Item >Contract level billing should pick Cus Po # from Contract. Also make sure if we mark it on client profile, it defaults to contract. |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Support item> Why am I getting a duplicate message when trying to delete an expense type, e.g. production_old from below example |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Support Item> Msg on Delivery Override” >Please note that data is based on latest Insertion Order based on most recent approved media plan. Please ensure that Insertion Order(s) are revised as such.” |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Support Item > Rule based Hard Stop or warning if user changes the dates on IO placements after delivery override. |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Client item> Support> At TSY I noticed favorite is not showing on top. The user was on MAC. But it looks like even on Windows, the button doesn’t appear when one is on Billing Setup or Invoice screens. |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Feature Name: Enhanced Filtering for RFP and Proposal List UI |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Restrict Self Approval |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Custom field 3/AdServing able to take formulas (on hold) |  | NEXELUS 2024.1 SP2 : | 0 | 7 | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting |  | NEXELUS 2024.1 SP2 : | 0 | 7 | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | Separate broadcast label rename |  | NEXELUS 2024.1 SP2 : | 0 | 7 | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | CHECK: tiered rate on new lines only or all lines? What happens if spend is added to a billed month. |  | NEXELUS 2024.1 SP2 : | 0 | 7 | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | DV360 API Upgrade |  | NEXELUS 2024.1 SP2 : | 10 | 31 | Mon 10/28/24 | Thu 10/31/24 |  |  | 10
|  |  | : | 0
| Hotfix 2024.1 |  | : Hotfix 2024.1 | 37 | 42.86 | Thu 10/31/24 | Thu 11/7/24 |  |  | 11.9 | 25.1
NEXELUS 2024.1 SP2 | eConnect Shell removal : Develop a web service | eConnect shell change to service | NEXELUS 2024.1 SP2 : eConnect shell change to service | 30 | 42.86 | Thu 10/31/24 | Thu 11/7/24 |  |  | 4.9 | 25.1
NEXELUS 2024.1 SP2 | DotNet changes |  | NEXELUS 2024.1 SP2 : | 30 | 42.86 | Thu 10/31/24 | Thu 11/7/24 |  |  | 4.9 | 25.1
NEXELUS 2024.1 SP2 | Deployments and QA |  | NEXELUS 2024.1 SP2 : | 7 | [5 empty] | 7
NEXELUS 2024.1 SP2 | Bilal |  | NEXELUS 2024.1 SP2 : | 7 |  | Thu 10/31/24 | Thu 10/31/24 |  |  | 7
NEXELUS 2024.1 SP2 | UAT upgrade |  | NEXELUS 2024.1 SP2 : | 0
NEXELUS 2024.1 SP2 | Production upgrade |  | NEXELUS 2024.1 SP2 : | 0

## Planned QA
QA
Plan | Task Name | Planned Activity | Full-Activity | Work | Duration | Start | Finish | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01
| Sprint 3 - Plus Co Items & Additional items |  |  | 518 hrs | 208.14 hrs? | Thu 9/5/24 | Mon 10/14/24
APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Add Media Type/Service type/Roles | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles | 4 hrs | 5 hrs? | Thu 9/5/24 | Thu 9/5/24
APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Google Drive integration. (Setup and Integration development) | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development) | 44 hrs | 57 hrs? | Tue 9/10/24 | Fri 9/20/24 |  | 8
APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents (tear sheets, afidavit) to the invoice | Ability to automatically attach additional documents to Invoice | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice | 30 hrs | 116.64 hrs? | Thu 9/5/24 | Thu 9/26/24 |  | 13.2 | 6.8
APWORKS 2024.2 - PHASE 3 | We need to read the company on the invoice document to route to the right company. If the company is not detected properly we will default to a company and mark it with a status. | Route invoice from one company - company identification | APWORKS 2024.2 - PHASE 3: Route invoice from one company - company identification | 56 hrs | 183.14 hrs? | Thu 9/5/24 | Wed 10/9/24 |  |  | 20
APWORKS 2024.2 - PHASE 3 | Broadcast invoices |  | APWORKS 2024.2 - PHASE 3: | 178 hrs | 208.14 hrs? | Thu 9/5/24 | Mon 10/14/24
APWORKS 2024.2 - PHASE 3 | We will need a separate node for "Broadcast Invoices" added at the end of Production Invoices. | separate node for "Broadcast Invoices" | APWORKS 2024.2 - PHASE 3: separate node for "Broadcast Invoices" | 4 hrs | 5.72 hrs? | Wed 9/11/24 | Wed 9/11/24
APWORKS 2024.2 - PHASE 3 | User Group management changes | Broadcast Invoice: User Group Management Changes | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: User Group Management Changes | 12 hrs | 46.29 hrs? | Thu 9/5/24 | Fri 9/13/24 |  | 2
APWORKS 2024.2 - PHASE 3 | Dashboard |  | APWORKS 2024.2 - PHASE 3: | 16 hrs | 77.14 hrs? | Thu 9/5/24 | Thu 9/19/24
APWORKS 2024.2 - PHASE 3 | Manage Invoice Documents | Broadcast Invoice: Manage Invoice Documents | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Manage Invoice Documents | 4 hrs | 82.86 hrs? | Thu 9/5/24 | Fri 9/20/24
APWORKS 2024.2 - PHASE 3 | EDI file processing | Broadcast Invoice: EDI File Processing | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing | 62 hrs | 128.48 hrs? | Thu 9/5/24 | Mon 9/30/24 |  |  | 40
APWORKS 2024.2 - PHASE 3 | PDF file generation | Broadcast Invoice: PDF file generation | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: PDF file generation | 50 hrs | 79.67 hrs? | Mon 9/30/24 | Mon 10/14/24 |  |  | 6
APWORKS 2024.2 - PHASE 3 | Invoice View UI | Broadcast Invoice: Invoice View UI | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Invoice View UI | 30 hrs | 128.48 hrs? | Thu 9/5/24 | Mon 9/30/24 |  |  | 12
APWORKS 2024.2 - PHASE 3 | Fastrack is maintaining the broadcast calendar dates. We may need to maintain this type of date period. |  | APWORKS 2024.2 - PHASE 3: | 0 hrs | 125.72 hrs? | Thu 9/5/24 | Mon 9/30/24
APWORKS 2024.2 - PHASE 3 | Customer Information : Selection of the client on the vendor invoice header level. This will help route the invoice to the appropriate client team. - (Sync and a lookup field on invoice) | Customer Information: Select Client on Vendor Invoice | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice | 16 hrs | 118.29 hrs? | Thu 9/12/24 | Fri 10/4/24 |  |  | 4
APWORKS 2024.2 - PHASE 3 | Read data from Media Ocean Jobs, IOs (buying), Customer Master, Vendor Master, Currencies, Tax codes, Payment terms, EDI?, payment information |  | APWORKS 2024.2 - PHASE 3: | 80 hrs | 142.86 hrs? | Thu 9/5/24 | Wed 10/2/24 |  |  | 40
APWORKS 2024.2 - PHASE 3 | vendor/stations/sites can be associated to multiple pay to. EX: Bell Media is linked to Bill pay to | Vendor/stations/sites associated to multiple pay to. | APWORKS 2024.2 - PHASE 3: Vendor/stations/sites associated to multiple pay to. | 32 hrs | 83 hrs? | Fri 9/20/24 | Fri 10/4/24 |  |  | 6
APWORKS 2024.2 - PHASE 3 | Checkbox to filter discrepant lines | Checkbox to filter discrepant lines | APWORKS 2024.2 - PHASE 3: Checkbox to filter discrepant lines | 8 hrs | 11.43 hrs? | Fri 10/4/24 | Mon 10/7/24
APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Ability to assign Employees to Roles by Media type and by Client | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client | 70 hrs | 110.14 hrs? | Thu 9/12/24 | Thu 10/3/24 |  |  | 8
APWORKS 2024.2 - PHASE 3 | Make the tax editable | Invoice Editing: Make the tax editable | APWORKS 2024.2 - PHASE 3: Invoice Editing: Make the tax editable | 0 hrs
| Sprint #4 (PlusCo Phase 3) |  |  | 389 hrs | 283.5 hrs? | Mon 10/21/24 | Mon 12/9/24
APWORKS 2024.2 - PHASE 4 | Bug fixing - sprint #3 |  | APWORKS 2024.2 - PHASE 4: | 60 hrs | 37.5 hrs? | Fri 10/25/24 | Thu 10/31/24
APWORKS 2024.2 - PHASE 4 | Discount implementation CHANGES |  | APWORKS 2024.2 - PHASE 4: | 12 hrs | 7 hrs? | Thu 10/31/24 | Fri 11/1/24
APWORKS 2024.2 - PHASE 4 | Approve upto last level and auto post as well based on configuration | Approve upto last level and auto post. | APWORKS 2024.2 - PHASE 4: Approve upto last level and auto post. | 8 hrs | 10 hrs | Fri 11/1/24 | Mon 11/4/24
APWORKS 2024.2 - PHASE 4 | Remove currency check while mapping vendor in vendor mapping dailog and apply vendor currency to invoices. | Currency Changes on Vendor Map | APWORKS 2024.2 - PHASE 4: Currency Changes on Vendor Map | 16 hrs | 20 hrs? | Fri 11/1/24 | Wed 11/6/24
APWORKS 2024.2 - PHASE 4 | Stamp multiple approvers. | Stamp multiple approvers. | APWORKS 2024.2 - PHASE 4: Stamp multiple approvers. | 12 hrs | 15 hrs | Mon 11/4/24 | Wed 11/6/24
APWORKS 2024.2 - PHASE 4 | Split Process for Google Drive integration and show documents in queue. |  | APWORKS 2024.2 - PHASE 4: | 30 hrs | 37.5 hrs? | Wed 11/6/24 | Wed 11/13/24
APWORKS 2024.2 - PHASE 4 | EDI file updating | EDI file updating and upload | APWORKS 2024.2 - PHASE 4: EDI file updating and upload | 12 hrs | 15 hrs? | Wed 11/20/24 | Thu 11/21/24
APWORKS 2024.2 - PHASE 4 | Remove Site column or show media sites |  | APWORKS 2024.2 - PHASE 4: | 1 hr | 1.25 hrs? | Wed 11/6/24 | Wed 11/6/24
APWORKS 2024.2 - PHASE 4 | Add Vendor column in Insertion order list |  | APWORKS 2024.2 - PHASE 4: | 4 hrs | 5 hrs? | Wed 11/6/24 | Thu 11/7/24
APWORKS 2024.2 - PHASE 4 | Production: Project should be available on summary as well. | Production: Project should be available on summary as well. | APWORKS 2024.2 - PHASE 4: Production: Project should be available on summary as well. | 6 hrs | 7.5 hrs? | Mon 11/18/24 | Tue 11/19/24 |  |  |  | 4
APWORKS 2024.2 - PHASE 4 | Production: Auto populate lines based PO during scanning | Production: Auto populate lines based PO during scanning | APWORKS 2024.2 - PHASE 4: Production: Auto populate lines based PO during scanning | 8 hrs | 6.67 hrs? | Tue 11/19/24 | Tue 11/19/24 |  |  |  | 4
APWORKS 2024.2 - PHASE 4 | Production: show keyvalue pairs for level2 mapping | Production: show keyvalue pairs for level2 mapping | APWORKS 2024.2 - PHASE 4: Production: show keyvalue pairs for level2 mapping | 8 hrs | 178.5 hrs? | Mon 10/21/24 | Wed 11/20/24 |  |  |  | 4
APWORKS 2024.2 - PHASE 4 | Broadcast Model Fields |  | APWORKS 2024.2 - PHASE 4: | 0 hrs
APWORKS 2024.2 - PHASE 4 | We need a way to forward invoice to user OR select a user when invoice is in Pending Approval queue | Route invoice from one company - company identification | APWORKS 2024.2 - PHASE 4: Route invoice from one company - company identification | 70 hrs | 50 hrs? | Thu 11/21/24 | Fri 11/29/24 |  |  |  | 28.4 | 23
APWORKS 2024.2 - PHASE 4 | A report to spot check the invoices processed (Plusco) | A report to spot check the invoices processed | APWORKS 2024.2 - PHASE 4: A report to spot check the invoices processed | 30 hrs | 68 hrs? | Wed 11/20/24 | Mon 12/2/24 |  |  |  |  | 3
APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices (Plusco) |  | APWORKS 2024.2 - PHASE 4: | 60 hrs | 75 hrs? | Tue 11/26/24 | Mon 12/9/24 |  |  |  |  | 16
APWORKS 2024.2 - PHASE 4 | Invoice Scan | PDF based broadcast invoices - Invoice Scan | APWORKS 2024.2 - PHASE 4: PDF based broadcast invoices - Invoice Scan | 40 hrs | 50 hrs? | Tue 11/26/24 | Wed 12/4/24
APWORKS 2024.2 - PHASE 4 | Model updates list |  | APWORKS 2024.2 - PHASE 4: | 10 hrs | 62.5 hrs? | Tue 11/26/24 | Thu 12/5/24
APWORKS 2024.2 - PHASE 4 | Manage non-mapped list |  | APWORKS 2024.2 - PHASE 4: | 10 hrs | 75 hrs? | Tue 11/26/24 | Mon 12/9/24
APWORKS 2024.2 - PHASE 4 | Import / Export lines | PDF based broadcast invoices - Import / Export lines | APWORKS 2024.2 - PHASE 4: PDF based broadcast invoices - Import / Export lines | 0 hrs | 7 hrs? | Tue 11/26/24 | Tue 11/26/24
APWORKS 2024.2 - PHASE 4 | Approvals | Approval routing | APWORKS 2024.2 - PHASE 4: Approval routing | 0 hrs | 7 hrs? | Tue 11/26/24 | Tue 11/26/24
APWORKS 2024.2 - PHASE 4 | Pull Client & Sites, Service types as Media Types from Nexelus |  | APWORKS 2024.2 - PHASE 4: | 36 hrs | 7 hrs? | Wed 11/20/24 | Wed 11/20/24
APWORKS 2024.2 - PHASE 4 | Notification |  | APWORKS 2024.2 - PHASE 4: | 0 hrs
APWORKS 2024.2 - PHASE 4 | Apply variable name for Site in vendor mapping |  | APWORKS 2024.2 - PHASE 4: | 12 hrs | 7 hrs? | Mon 12/2/24 | Tue 12/3/24
APWORKS 2024.2 - PHASE 4 | Checkbox to show unapproved lines |  | APWORKS 2024.2 - PHASE 4: | 0 hrs | 0 hrs? | Mon 10/21/24 | Mon 10/21/24
APWORKS 2024.2 - PHASE 4 | Vendor mapping enhancement for Non-media | Vendor mapping enhancement for Non-media | APWORKS 2024.2 - PHASE 4: Vendor mapping enhancement for Non-media | 0 hrs | 7 hrs? | Mon 10/21/24 | Mon 10/21/24
APWORKS 2024.2 - PHASE 4 | Filter for discrepenet invoices on client base |  | APWORKS 2024.2 - PHASE 4: | 4 hrs | 8 hrs | Mon 10/21/24 | Tue 10/22/24
APWORKS 2024.2 - PHASE 4 | Validation notifications |  | APWORKS 2024.2 - PHASE 4: | 0 hrs | 7 hrs? | Mon 10/21/24 | Mon 10/21/24
APWORKS 2024.2 - PHASE 4 | Re: APWorks - Data search service |  | APWORKS 2024.2 - PHASE 4: | 0 hrs
| Sprint 5 |  | : Sprint 5 | 40 hrs | 635.24 hrs? | Tue 8/27/24 | Wed 12/18/24
APWORKS 2024.2 - PHASE 4 | Google Drive Setup (company configuration UI) | Google Drive Setup (company configuration UI) | APWORKS 2024.2 - PHASE 4: Google Drive Setup (company configuration UI) | 40 hrs | 50 hrs? | Tue 12/10/24 | Wed 12/18/24
APWORKS 2024.2 - PHASE 4 | Vendor invoices report: Add date filters |  | APWORKS 2024.2 - PHASE 4: | 0 hrs | 7 hrs? | Tue 8/27/24 | Tue 8/27/24
| Sprint #6 |  | : Sprint #6 | 0 hrs | 635.24 hrs? | Tue 8/27/24 | Wed 12/18/24
APWORKS 2024.2 - PHASE 6 | Credit memo |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 95.24 hrs? | Mon 12/2/24 | Wed 12/18/24
APWORKS 2024.2 - PHASE 6 | Refine statuses |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 0 hrs? | Wed 12/18/24 | Wed 12/18/24
APWORKS 2024.2 - PHASE 6 | Labels as Variable names |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 0 hrs? | Wed 8/28/24 | Wed 8/28/24
APWORKS 2024.2 - PHASE 6 | The filter on the dashboard should have: 'like' date from and to |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 0 hrs? | Wed 8/28/24 | Wed 8/28/24
APWORKS 2024.2 - PHASE 6 | Add a button on dashboard or invoice document listing to post all good invoices. |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 8 hrs? | Tue 8/27/24 | Wed 8/28/24
APWORKS 2024.2 - PHASE 6 | Moving invoice between media type (Media to Broadcast or viseversa) |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 8 hrs? | Tue 8/27/24 | Wed 8/28/24
APWORKS 2024.2 - PHASE 6 | Add a flag "perfered" for email |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 7 hrs? | Tue 8/27/24 | Tue 8/27/24
APWORKS 2024.2 - PHASE 6 | Split/Merge on Production module |  | APWORKS 2024.2 - PHASE 6: | 0 hrs
APWORKS 2024.2 - PHASE 6 | Email Ref: APWorks - Not urgent items |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 7 hrs? | Tue 8/27/24 | Tue 8/27/24
APWORKS 2024.2 - PHASE 6 | Global Mappings - Vendor Map |  | APWORKS 2024.2 - PHASE 6: | 0 hrs
APWORKS 2024.2 - PHASE 6 | RE: APWorks - Nexelus to APWorks data sync improvements |  | APWORKS 2024.2 - PHASE 6: | 0 hrs
APWORKS 2024.2 - PHASE 6 | Review and Management |  | APWORKS 2024.2 - PHASE 6: | 70 hrs | 350 hrs | Tue 8/27/24 | Fri 11/1/24
APWORKS 2024.2 - PHASE 6 | Abid |  | APWORKS 2024.2 - PHASE 6: | 70 hrs |  | Tue 8/27/24 | Fri 11/1/24
APWORKS 2024.2 - PHASE 6 | QA |  | APWORKS 2024.2 - PHASE 6: | 343.4 hrs | 524.02 hrs? | Fri 9/20/24 | Fri 12/20/24
APWORKS 2024.2 - PHASE 6 | Sprint #3 |  | APWORKS 2024.2 - PHASE 6: | 226 hrs | 184.14 hrs? | Fri 9/20/24 | Wed 10/23/24
APWORKS 2024.2 - PHASE 6 | QA |  | APWORKS 2024.2 - PHASE 6: | 226 hrs | 184.14 hrs? | Fri 9/20/24 | Wed 10/23/24
APWORKS 2024.2 - PHASE 6 | Google Drive integration. (Setup and Integration development) | Google Drive integration. (Setup and Integration development) | APWORKS 2024.2 - PHASE 6: Google Drive integration. (Setup and Integration development) | 8 hrs | 10 hrs | Fri 9/20/24 | Mon 9/23/24
APWORKS 2024.2 - PHASE 6 | Ability to automatically attach additional documents (tear sheets, afidavit) to the invoice | Ability to automatically attach additional documents to Invoice | APWORKS 2024.2 - PHASE 6: Ability to automatically attach additional documents to Invoice | 20 hrs | 25 hrs? | Thu 9/26/24 | Wed 10/2/24
APWORKS 2024.2 - PHASE 6 | We need to read the company on the invoice document to route to the right company. If the company is not detected properly we will default to a company and mark it with a status. |  | APWORKS 2024.2 - PHASE 6: | 20 hrs | 25 hrs? | Fri 10/4/24 | Wed 10/9/24
APWORKS 2024.2 - PHASE 6 | Broadcast invoices |  | APWORKS 2024.2 - PHASE 6: | 60 hrs | 50 hrs? | Wed 10/9/24 | Fri 10/18/24
APWORKS 2024.2 - PHASE 6 | Invoice List UI |  | APWORKS 2024.2 - PHASE 6: | 8 hrs | 10 hrs? | Fri 9/20/24 | Mon 9/23/24
APWORKS 2024.2 - PHASE 6 | User Group management changes | Broadcast Invoice: User Group Management Changes | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: User Group Management Changes | 2 hrs
APWORKS 2024.2 - PHASE 6 | Dashboard |  | APWORKS 2024.2 - PHASE 6: | 0 hrs
APWORKS 2024.2 - PHASE 6 | Manage Invoice Models | Broadcast Invoice: Manage Invoice Models List | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: Manage Invoice Models List | 0 hrs
APWORKS 2024.2 - PHASE 6 | Manage Non-Mapped Production Invoices | Broadcast Invoice: Manage Non-Mapped Broadcast Invoices | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: Manage Non-Mapped Broadcast Invoices | 0 hrs
APWORKS 2024.2 - PHASE 6 | EDI file processing | Broadcast Invoice: EDI File Processing | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: EDI File Processing | 40 hrs | 50 hrs? | Wed 10/9/24 | Fri 10/18/24
APWORKS 2024.2 - PHASE 6 | Invoice View UI | Broadcast Invoice: Invoice View UI | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: Invoice View UI | 12 hrs | 15 hrs? | Tue 10/15/24 | Thu 10/17/24
APWORKS 2024.2 - PHASE 6 | PDF file generation | Broadcast Invoice: PDF file generation | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: PDF file generation | 6 hrs | 7.5 hrs? | Mon 10/14/24 | Tue 10/15/24
APWORKS 2024.2 - PHASE 6 | Customer Information : Selection of the client on the vendor invoice header level. This will help route the invoice to the appropriate client team. - (Sync and a lookup field on invoice) | Customer Information: Select Client on Vendor Invoice | APWORKS 2024.2 - PHASE 6: Customer Information: Select Client on Vendor Invoice | 4 hrs | 5 hrs? | Fri 10/4/24 | Fri 10/4/24
APWORKS 2024.2 - PHASE 6 | Read data from Media Ocean Jobs, IOs (buying), Customer Master, Vendor Master, Currencies, Tax codes, Payment terms, EDI?, payment information |  | APWORKS 2024.2 - PHASE 6: | 40 hrs | 50 hrs? | Wed 10/2/24 | Thu 10/10/24
APWORKS 2024.2 - PHASE 6 | vendor/stations/sites can be associated to multiple pay to. EX: Bell Media is linked to Bill pay to |  | APWORKS 2024.2 - PHASE 6: | 6 hrs | 7.5 hrs? | Fri 10/4/24 | Mon 10/7/24
APWORKS 2024.2 - PHASE 6 | Ability to assign Employees to Roles by Media type and by Client |  | APWORKS 2024.2 - PHASE 6: | 8 hrs | 26.67 hrs? | Thu 10/3/24 | Tue 10/8/24
APWORKS 2024.2 - PHASE 6 | Testing and Review |  | APWORKS 2024.2 - PHASE 6: | 60 hrs | 100 hrs | Fri 10/4/24 | Wed 10/23/24
APWORKS 2024.2 - PHASE 6 | Sprint #4 |  | APWORKS 2024.2 - PHASE 6: | 101.4 hrs | 131.45 hrs? | Wed 11/20/24 | Thu 12/12/24
APWORKS 2024.2 - PHASE 6 | Production: Auto populate lines based PO during scanning |  | APWORKS 2024.2 - PHASE 6: | 4 hrs | 4.44 hrs? | Wed 11/20/24 | Wed 11/20/24
APWORKS 2024.2 - PHASE 6 | Production: Project should be available on summary as well. |  | APWORKS 2024.2 - PHASE 6: | 4 hrs | 4.45 hrs? | Wed 11/20/24 | Thu 11/21/24
APWORKS 2024.2 - PHASE 6 | Production: show keyvalue pairs for level2 mapping |  | APWORKS 2024.2 - PHASE 6: | 4 hrs | 4.45 hrs? | Thu 11/21/24 | Thu 11/21/24
APWORKS 2024.2 - PHASE 6 | We need a way to forward invoice to user OR select a user when invoice is in Pending Approval queue |  | APWORKS 2024.2 - PHASE 6: | 51.4 hrs | 62.45 hrs? | Thu 11/21/24 | Tue 12/3/24
APWORKS 2024.2 - PHASE 6 | A report to spot check the invoices processed |  | APWORKS 2024.2 - PHASE 6: | 8 hrs | 50.22 hrs? | Fri 11/22/24 | Tue 12/3/24
APWORKS 2024.2 - PHASE 6 | PDF based broadcast invoices |  | APWORKS 2024.2 - PHASE 6: | 30 hrs | 72.78 hrs? | Fri 11/29/24 | Thu 12/12/24
APWORKS 2024.2 - PHASE 6 | Pull Client & Sites from Nexelus |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 8.89 hrs? | Thu 11/21/24 | Fri 11/22/24
APWORKS 2024.2 - PHASE 6 | Sprint #5 |  | APWORKS 2024.2 - PHASE 6: | 16 hrs | 17.78 hrs? | Wed 12/18/24 | Fri 12/20/24
APWORKS 2024.2 - PHASE 6 | Bug Fixing |  | APWORKS 2024.2 - PHASE 6: | 138 hrs | 661.91 hrs? | Tue 8/27/24 | Mon 12/23/24
APWORKS 2024.2 - PHASE 6 | Sprint #3 |  | APWORKS 2024.2 - PHASE 6: | 100 hrs | 117.17 hrs? | Mon 9/30/24 | Mon 10/21/24
APWORKS 2024.2 - PHASE 6 | Sprint #4 |  | APWORKS 2024.2 - PHASE 6: | 30 hrs | 616.78 hrs? | Tue 8/27/24 | Mon 12/16/24
APWORKS 2024.2 - PHASE 6 | We need a way to forward invoice to user OR select a user when invoice is in Pending Approval queue |  | APWORKS 2024.2 - PHASE 6: | 11 hrs | 8.89 hrs? | Tue 12/3/24 | Wed 12/4/24
APWORKS 2024.2 - PHASE 6 | A report to spot check the invoices processed |  | APWORKS 2024.2 - PHASE 6: | 3 hrs | 3.33 hrs? | Tue 12/3/24 | Tue 12/3/24
APWORKS 2024.2 - PHASE 6 | PDF based broadcast invoices |  | APWORKS 2024.2 - PHASE 6: | 16 hrs | 13.33 hrs? | Thu 12/12/24 | Mon 12/16/24
APWORKS 2024.2 - PHASE 6 | Pull Client & Sites from Nexelus |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 0 hrs | Tue 8/27/24 | Tue 8/27/24
APWORKS 2024.2 - PHASE 6 | Sprint #5 |  | APWORKS 2024.2 - PHASE 6: | 8 hrs | 661.91 hrs? | Tue 8/27/24 | Mon 12/23/24
APWORKS 2024.2 - PHASE 6 | QA Iteration #2 |  | APWORKS 2024.2 - PHASE 6: | 160 hrs | 641.78 hrs? | Tue 8/27/24 | Thu 12/19/24
APWORKS 2024.2 - PHASE 6 | Integration Testing |  | APWORKS 2024.2 - PHASE 6: | 66 hrs | 24 hrs | Thu 12/19/24 | Tue 12/24/24
APWORKS 2024.2 - PHASE 6 | Bug fixing for integration testing |  | APWORKS 2024.2 - PHASE 6: | 40 hrs | 28.57 hrs | Thu 12/19/24 | Tue 12/24/24
APWORKS 2024.2 - PHASE 6 | UAT Deployments |  | APWORKS 2024.2 - PHASE 6: | 20 hrs | 7 hrs | Tue 12/24/24 | Wed 12/25/24
|  |  | : | 0 hrs
| Nexelus 2024.1 SP2 |  | : Nexelus 2024.1 SP2 | 588 hrs | 405.45 hrs? | Mon 10/14/24 | Mon 12/23/24
NEXELUS 2024.1 SP2 | Development and Testing |  | NEXELUS 2024.1 SP2: | 484 hrs | 360.95 hrs? | Mon 10/14/24 | Mon 12/16/24
NEXELUS 2024.1 SP2 | Backup Table for vendor/client lines relationship | Backup Table for vendor/client lines relationship | NEXELUS 2024.1 SP2: Backup Table for vendor/client lines relationship | 58 hrs | 62.86 hrs? | Tue 10/29/24 | Thu 11/7/24 |  |  |  | 12
NEXELUS 2024.1 SP2 | Need to support UDF & naming convention fields in RFP (Bulksheet only) |  | NEXELUS 2024.1 SP2: | 188 hrs | 182.86 hrs? | Thu 10/17/24 | Mon 11/18/24
NEXELUS 2024.1 SP2 | Vendor Portal Proposal | UDF & Naming Convention in Vendor Portal - Proposal Import/exp | NEXELUS 2024.1 SP2: UDF & Naming Convention in Vendor Portal - Proposal Import/exp | 114 hrs | 120 hrs? | Thu 10/17/24 | Thu 11/7/24 |  |  | 0.9 | 23.1
NEXELUS 2024.1 SP2 | Nexelus Export only on Proposal | UDF & Naming Convention in Nexelus - Export on Proposal | NEXELUS 2024.1 SP2: UDF & Naming Convention in Nexelus - Export on Proposal | 36 hrs | 125.72 hrs? | Mon 10/21/24 | Tue 11/12/24 |  |  | 12
NEXELUS 2024.1 SP2 | Nexelus RFP (Import/Export) | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | NEXELUS 2024.1 SP2: UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | 38 hrs | 182.86 hrs? | Thu 10/17/24 | Mon 11/18/24
NEXELUS 2024.1 SP2 | Nexelus RFP (Import/Export) - Phase 2 (onhold) |  | NEXELUS 2024.1 SP2: | 68 hrs | 34.29 hrs? | Thu 10/17/24 | Wed 10/23/24
NEXELUS 2024.1 SP2 | Generate client lines based on media type | Generate Client Schedule Lines based on media type | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type | 205 hrs | 360.95 hrs? | Mon 10/14/24 | Mon 12/16/24
NEXELUS 2024.1 SP2 | Client Profile |  | NEXELUS 2024.1 SP2: | 1 hr | 5 hrs? | Thu 10/24/24 | Thu 10/24/24
NEXELUS 2024.1 SP2 | Level3 |  | NEXELUS 2024.1 SP2: | 1 hr | 5 hrs? | Thu 10/24/24 | Fri 10/25/24
NEXELUS 2024.1 SP2 | Media Plan Vendor lines (new, import/export) |  | NEXELUS 2024.1 SP2: | 66 hrs | 300.43 hrs? | Mon 10/14/24 | Wed 12/4/24 |  |  |  |  | 8
NEXELUS 2024.1 SP2 | Client Lines (new line, generate schedule) | Billing by Media Type | NEXELUS 2024.1 SP2: Billing by Media Type | 137 hrs | 276.95 hrs? | Mon 10/28/24 | Mon 12/16/24 |  |  |  |  | 40
NEXELUS 2024.1 SP2 | DB |  | NEXELUS 2024.1 SP2: | 7 hrs | 17.5 hrs? | Mon 10/28/24 | Wed 10/30/24
NEXELUS 2024.1 SP2 | Media Plan approval | Media Plan Approval | NEXELUS 2024.1 SP2: Media Plan Approval | 14 hrs | 26.67 hrs? | Thu 10/31/24 | Tue 11/5/24
NEXELUS 2024.1 SP2 | Please note that data is based on latest Insertion Order based on most recent approved media plan. Please ensure that Insertion Order(s) are revised as such.” |  | NEXELUS 2024.1 SP2: | 0 hrs | 7 hrs? | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | Client Profile: Media > Flag to make the vendor inactive | Client Profile: Media > Flag to make the vendor inactive | NEXELUS 2024.1 SP2: Client Profile: Media > Flag to make the vendor inactive | 24 hrs | 105.71 hrs? | Thu 10/24/24 | Tue 11/12/24 |  |  |  | 8
NEXELUS 2024.1 SP2 | Mngt Fee renamable everywhere |  | NEXELUS 2024.1 SP2: | 9 hrs | 175.43 hrs? | Mon 10/14/24 | Wed 11/13/24 |  |  |  | 4
NEXELUS 2024.1 SP2 | Support items |  | NEXELUS 2024.1 SP2: | 0 hrs | 0 hrs | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | support> Pursuit - Is it possible to make the email address field longer on the client profile page? 17136 |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Client Support Item> The issue is resolved which was due to missing preferred group flag for this user. |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | support item> Please see below, currently we see system only allows 256 characters in the comments box. |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support item -Person shouldn't be able to approve his own expense report / Timesheet even after switching to his manager / supervisor |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support item> It is crashing because of “&” character, it requires a DLL change to resolve the issue. |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support item > Can we add Print label in future release> see attached email for reference |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support Item >Contract level billing should pick Cus Po # from Contract. Also make sure if we mark it on client profile, it defaults to contract. |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support item> Why am I getting a duplicate message when trying to delete an expense type, e.g. production_old from below example |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support Item> Msg on Delivery Override” >Please note that data is based on latest Insertion Order based on most recent approved media plan. Please ensure that Insertion Order(s) are revised as such.” |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support Item > Rule based Hard Stop or warning if user changes the dates on IO placements after delivery override. |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Client item> Support> At TSY I noticed favorite is not showing on top. The user was on MAC. But it looks like even on Windows, the button doesn’t appear when one is on Billing Setup or Invoice screens. |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Feature Name: Enhanced Filtering for RFP and Proposal List UI |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Restrict Self Approval |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Custom field 3/AdServing able to take formulas (on hold) |  | NEXELUS 2024.1 SP2: | 0 hrs | 7 hrs? | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting |  | NEXELUS 2024.1 SP2: | 0 hrs | 7 hrs? | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | Separate broadcast label rename |  | NEXELUS 2024.1 SP2: | 0 hrs | 7 hrs? | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | CHECK: tiered rate on new lines only or all lines? What happens if spend is added to a billed month. |  | NEXELUS 2024.1 SP2: | 0 hrs | 7 hrs? | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | DV360 API Upgrade |  | NEXELUS 2024.1 SP2: | 10 hrs | 31 hrs | Mon 10/28/24 | Thu 10/31/24
|  |  | : | 0 hrs
| Hotfix 2024.1 |  | : Hotfix 2024.1 | 37 hrs | 42.86 hrs? | Thu 10/31/24 | Thu 11/7/24
NEXELUS 2024.1 SP2 | eConnect Shell removal : Develop a web service | eConnect shell change to service | NEXELUS 2024.1 SP2: eConnect shell change to service | 30 hrs | 42.86 hrs? | Thu 10/31/24 | Thu 11/7/24
NEXELUS 2024.1 SP2 | DotNet changes |  | NEXELUS 2024.1 SP2: | 30 hrs | 42.86 hrs? | Thu 10/31/24 | Thu 11/7/24
NEXELUS 2024.1 SP2 | Deployments and QA |  | NEXELUS 2024.1 SP2: | 7 hrs
NEXELUS 2024.1 SP2 | Bilal |  | NEXELUS 2024.1 SP2: | 7 hrs |  | Thu 10/31/24 | Thu 10/31/24
NEXELUS 2024.1 SP2 | UAT upgrade |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Production upgrade |  | NEXELUS 2024.1 SP2: | 0 hrs

## Planned BugFix
Bug Fixing
| Task Name | Planned Activity | Full-Activity | Work | Duration | Start | Finish | August, 2024 | September, 2024 | October, 2024 | November, 2024 | December, 2024
| Sprint 3 - Plus Co Items & Additional items |  |  | 518 hrs | 208.14 hrs? | Thu 9/5/24 | Mon 10/14/24
APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Add Media Type/Service type/Roles | APWORKS 2024.2 - PHASE 3: Add Media Type/Service type/Roles | 4 hrs | 5 hrs? | Thu 9/5/24 | Thu 9/5/24
APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Google Drive integration. (Setup and Integration development) | APWORKS 2024.2 - PHASE 3: Google Drive integration. (Setup and Integration development) | 44 hrs | 57 hrs? | Tue 9/10/24 | Fri 9/20/24
APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents (tear sheets, afidavit) to the invoice | Ability to automatically attach additional documents to Invoice | APWORKS 2024.2 - PHASE 3: Ability to automatically attach additional documents to Invoice | 30 hrs | 116.64 hrs? | Thu 9/5/24 | Thu 9/26/24
APWORKS 2024.2 - PHASE 3 | We need to read the company on the invoice document to route to the right company. If the company is not detected properly we will default to a company and mark it with a status. | Route invoice from one company - company identification | APWORKS 2024.2 - PHASE 3: Route invoice from one company - company identification | 56 hrs | 183.14 hrs? | Thu 9/5/24 | Wed 10/9/24
APWORKS 2024.2 - PHASE 3 | Broadcast invoices |  | APWORKS 2024.2 - PHASE 3: | 178 hrs | 208.14 hrs? | Thu 9/5/24 | Mon 10/14/24
APWORKS 2024.2 - PHASE 3 | We will need a separate node for "Broadcast Invoices" added at the end of Production Invoices. | separate node for "Broadcast Invoices" | APWORKS 2024.2 - PHASE 3: separate node for "Broadcast Invoices" | 4 hrs | 5.72 hrs? | Wed 9/11/24 | Wed 9/11/24
APWORKS 2024.2 - PHASE 3 | User Group management changes | Broadcast Invoice: User Group Management Changes | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: User Group Management Changes | 12 hrs | 46.29 hrs? | Thu 9/5/24 | Fri 9/13/24
APWORKS 2024.2 - PHASE 3 | Dashboard |  | APWORKS 2024.2 - PHASE 3: | 16 hrs | 77.14 hrs? | Thu 9/5/24 | Thu 9/19/24
APWORKS 2024.2 - PHASE 3 | Manage Invoice Documents | Broadcast Invoice: Manage Invoice Documents | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Manage Invoice Documents | 4 hrs | 82.86 hrs? | Thu 9/5/24 | Fri 9/20/24
APWORKS 2024.2 - PHASE 3 | EDI file processing | Broadcast Invoice: EDI File Processing | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: EDI File Processing | 62 hrs | 128.48 hrs? | Thu 9/5/24 | Mon 9/30/24
APWORKS 2024.2 - PHASE 3 | PDF file generation | Broadcast Invoice: PDF file generation | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: PDF file generation | 50 hrs | 79.67 hrs? | Mon 9/30/24 | Mon 10/14/24
APWORKS 2024.2 - PHASE 3 | Invoice View UI | Broadcast Invoice: Invoice View UI | APWORKS 2024.2 - PHASE 3: Broadcast Invoice: Invoice View UI | 30 hrs | 128.48 hrs? | Thu 9/5/24 | Mon 9/30/24
APWORKS 2024.2 - PHASE 3 | Fastrack is maintaining the broadcast calendar dates. We may need to maintain this type of date period. |  | APWORKS 2024.2 - PHASE 3: | 0 hrs | 125.72 hrs? | Thu 9/5/24 | Mon 9/30/24
APWORKS 2024.2 - PHASE 3 | Customer Information : Selection of the client on the vendor invoice header level. This will help route the invoice to the appropriate client team. - (Sync and a lookup field on invoice) | Customer Information: Select Client on Vendor Invoice | APWORKS 2024.2 - PHASE 3: Customer Information: Select Client on Vendor Invoice | 16 hrs | 118.29 hrs? | Thu 9/12/24 | Fri 10/4/24
APWORKS 2024.2 - PHASE 3 | Read data from Media Ocean Jobs, IOs (buying), Customer Master, Vendor Master, Currencies, Tax codes, Payment terms, EDI?, payment information |  | APWORKS 2024.2 - PHASE 3: | 80 hrs | 142.86 hrs? | Thu 9/5/24 | Wed 10/2/24
APWORKS 2024.2 - PHASE 3 | vendor/stations/sites can be associated to multiple pay to. EX: Bell Media is linked to Bill pay to | Vendor/stations/sites associated to multiple pay to. | APWORKS 2024.2 - PHASE 3: Vendor/stations/sites associated to multiple pay to. | 32 hrs | 83 hrs? | Fri 9/20/24 | Fri 10/4/24
APWORKS 2024.2 - PHASE 3 | Checkbox to filter discrepant lines | Checkbox to filter discrepant lines | APWORKS 2024.2 - PHASE 3: Checkbox to filter discrepant lines | 8 hrs | 11.43 hrs? | Fri 10/4/24 | Mon 10/7/24
APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Ability to assign Employees to Roles by Media type and by Client | APWORKS 2024.2 - PHASE 3: Ability to assign Employees to Roles by Media type and by Client | 70 hrs | 110.14 hrs? | Thu 9/12/24 | Thu 10/3/24
APWORKS 2024.2 - PHASE 3 | Make the tax editable | Invoice Editing: Make the tax editable | APWORKS 2024.2 - PHASE 3: Invoice Editing: Make the tax editable | 0 hrs
| Sprint #4 (PlusCo Phase 3) |  |  | 389 hrs | 283.5 hrs? | Mon 10/21/24 | Mon 12/9/24
APWORKS 2024.2 - PHASE 4 | Bug fixing - sprint #3 |  | APWORKS 2024.2 - PHASE 4: | 60 hrs | 37.5 hrs? | Fri 10/25/24 | Thu 10/31/24
APWORKS 2024.2 - PHASE 4 | Discount implementation CHANGES |  | APWORKS 2024.2 - PHASE 4: | 12 hrs | 7 hrs? | Thu 10/31/24 | Fri 11/1/24
APWORKS 2024.2 - PHASE 4 | Approve upto last level and auto post as well based on configuration | Approve upto last level and auto post. | APWORKS 2024.2 - PHASE 4: Approve upto last level and auto post. | 8 hrs | 10 hrs | Fri 11/1/24 | Mon 11/4/24
APWORKS 2024.2 - PHASE 4 | Remove currency check while mapping vendor in vendor mapping dailog and apply vendor currency to invoices. | Currency Changes on Vendor Map | APWORKS 2024.2 - PHASE 4: Currency Changes on Vendor Map | 16 hrs | 20 hrs? | Fri 11/1/24 | Wed 11/6/24
APWORKS 2024.2 - PHASE 4 | Stamp multiple approvers. | Stamp multiple approvers. | APWORKS 2024.2 - PHASE 4: Stamp multiple approvers. | 12 hrs | 15 hrs | Mon 11/4/24 | Wed 11/6/24
APWORKS 2024.2 - PHASE 4 | Split Process for Google Drive integration and show documents in queue. |  | APWORKS 2024.2 - PHASE 4: | 30 hrs | 37.5 hrs? | Wed 11/6/24 | Wed 11/13/24
APWORKS 2024.2 - PHASE 4 | EDI file updating | EDI file updating and upload | APWORKS 2024.2 - PHASE 4: EDI file updating and upload | 12 hrs | 15 hrs? | Wed 11/20/24 | Thu 11/21/24
APWORKS 2024.2 - PHASE 4 | Remove Site column or show media sites |  | APWORKS 2024.2 - PHASE 4: | 1 hr | 1.25 hrs? | Wed 11/6/24 | Wed 11/6/24
APWORKS 2024.2 - PHASE 4 | Add Vendor column in Insertion order list |  | APWORKS 2024.2 - PHASE 4: | 4 hrs | 5 hrs? | Wed 11/6/24 | Thu 11/7/24
APWORKS 2024.2 - PHASE 4 | Production: Project should be available on summary as well. | Production: Project should be available on summary as well. | APWORKS 2024.2 - PHASE 4: Production: Project should be available on summary as well. | 6 hrs | 7.5 hrs? | Mon 11/18/24 | Tue 11/19/24
APWORKS 2024.2 - PHASE 4 | Production: Auto populate lines based PO during scanning | Production: Auto populate lines based PO during scanning | APWORKS 2024.2 - PHASE 4: Production: Auto populate lines based PO during scanning | 8 hrs | 6.67 hrs? | Tue 11/19/24 | Tue 11/19/24
APWORKS 2024.2 - PHASE 4 | Production: show keyvalue pairs for level2 mapping | Production: show keyvalue pairs for level2 mapping | APWORKS 2024.2 - PHASE 4: Production: show keyvalue pairs for level2 mapping | 8 hrs | 178.5 hrs? | Mon 10/21/24 | Wed 11/20/24
APWORKS 2024.2 - PHASE 4 | Broadcast Model Fields |  | APWORKS 2024.2 - PHASE 4: | 0 hrs
APWORKS 2024.2 - PHASE 4 | We need a way to forward invoice to user OR select a user when invoice is in Pending Approval queue | Route invoice from one company - company identification | APWORKS 2024.2 - PHASE 4: Route invoice from one company - company identification | 70 hrs | 50 hrs? | Thu 11/21/24 | Fri 11/29/24
APWORKS 2024.2 - PHASE 4 | A report to spot check the invoices processed (Plusco) | A report to spot check the invoices processed | APWORKS 2024.2 - PHASE 4: A report to spot check the invoices processed | 30 hrs | 68 hrs? | Wed 11/20/24 | Mon 12/2/24
APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices (Plusco) |  | APWORKS 2024.2 - PHASE 4: | 60 hrs | 75 hrs? | Tue 11/26/24 | Mon 12/9/24
APWORKS 2024.2 - PHASE 4 | Invoice Scan | PDF based broadcast invoices - Invoice Scan | APWORKS 2024.2 - PHASE 4: PDF based broadcast invoices - Invoice Scan | 40 hrs | 50 hrs? | Tue 11/26/24 | Wed 12/4/24
APWORKS 2024.2 - PHASE 4 | Model updates list |  | APWORKS 2024.2 - PHASE 4: | 10 hrs | 62.5 hrs? | Tue 11/26/24 | Thu 12/5/24
APWORKS 2024.2 - PHASE 4 | Manage non-mapped list |  | APWORKS 2024.2 - PHASE 4: | 10 hrs | 75 hrs? | Tue 11/26/24 | Mon 12/9/24
APWORKS 2024.2 - PHASE 4 | Import / Export lines | PDF based broadcast invoices - Import / Export lines | APWORKS 2024.2 - PHASE 4: PDF based broadcast invoices - Import / Export lines | 0 hrs | 7 hrs? | Tue 11/26/24 | Tue 11/26/24
APWORKS 2024.2 - PHASE 4 | Approvals | Approval routing | APWORKS 2024.2 - PHASE 4: Approval routing | 0 hrs | 7 hrs? | Tue 11/26/24 | Tue 11/26/24
APWORKS 2024.2 - PHASE 4 | Pull Client & Sites, Service types as Media Types from Nexelus |  | APWORKS 2024.2 - PHASE 4: | 36 hrs | 7 hrs? | Wed 11/20/24 | Wed 11/20/24
APWORKS 2024.2 - PHASE 4 | Notification |  | APWORKS 2024.2 - PHASE 4: | 0 hrs
APWORKS 2024.2 - PHASE 4 | Apply variable name for Site in vendor mapping |  | APWORKS 2024.2 - PHASE 4: | 12 hrs | 7 hrs? | Mon 12/2/24 | Tue 12/3/24
APWORKS 2024.2 - PHASE 4 | Checkbox to show unapproved lines |  | APWORKS 2024.2 - PHASE 4: | 0 hrs | 0 hrs? | Mon 10/21/24 | Mon 10/21/24
APWORKS 2024.2 - PHASE 4 | Vendor mapping enhancement for Non-media | Vendor mapping enhancement for Non-media | APWORKS 2024.2 - PHASE 4: Vendor mapping enhancement for Non-media | 0 hrs | 7 hrs? | Mon 10/21/24 | Mon 10/21/24
APWORKS 2024.2 - PHASE 4 | Filter for discrepenet invoices on client base |  | APWORKS 2024.2 - PHASE 4: | 4 hrs | 8 hrs | Mon 10/21/24 | Tue 10/22/24
APWORKS 2024.2 - PHASE 4 | Validation notifications |  | APWORKS 2024.2 - PHASE 4: | 0 hrs | 7 hrs? | Mon 10/21/24 | Mon 10/21/24
APWORKS 2024.2 - PHASE 4 | Re: APWorks - Data search service |  | APWORKS 2024.2 - PHASE 4: | 0 hrs
| Sprint 5 |  | : Sprint 5 | 40 hrs | 635.24 hrs? | Tue 8/27/24 | Wed 12/18/24
APWORKS 2024.2 - PHASE 4 | Google Drive Setup (company configuration UI) | Google Drive Setup (company configuration UI) | APWORKS 2024.2 - PHASE 4: Google Drive Setup (company configuration UI) | 40 hrs | 50 hrs? | Tue 12/10/24 | Wed 12/18/24
APWORKS 2024.2 - PHASE 4 | Vendor invoices report: Add date filters |  | APWORKS 2024.2 - PHASE 4: | 0 hrs | 7 hrs? | Tue 8/27/24 | Tue 8/27/24
| Sprint #6 |  | : Sprint #6 | 0 hrs | 635.24 hrs? | Tue 8/27/24 | Wed 12/18/24
APWORKS 2024.2 - PHASE 6 | Credit memo |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 95.24 hrs? | Mon 12/2/24 | Wed 12/18/24
APWORKS 2024.2 - PHASE 6 | Refine statuses |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 0 hrs? | Wed 12/18/24 | Wed 12/18/24
APWORKS 2024.2 - PHASE 6 | Labels as Variable names |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 0 hrs? | Wed 8/28/24 | Wed 8/28/24
APWORKS 2024.2 - PHASE 6 | The filter on the dashboard should have: 'like' date from and to |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 0 hrs? | Wed 8/28/24 | Wed 8/28/24
APWORKS 2024.2 - PHASE 6 | Add a button on dashboard or invoice document listing to post all good invoices. |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 8 hrs? | Tue 8/27/24 | Wed 8/28/24
APWORKS 2024.2 - PHASE 6 | Moving invoice between media type (Media to Broadcast or viseversa) |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 8 hrs? | Tue 8/27/24 | Wed 8/28/24
APWORKS 2024.2 - PHASE 6 | Add a flag "perfered" for email |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 7 hrs? | Tue 8/27/24 | Tue 8/27/24
APWORKS 2024.2 - PHASE 6 | Split/Merge on Production module |  | APWORKS 2024.2 - PHASE 6: | 0 hrs
APWORKS 2024.2 - PHASE 6 | Email Ref: APWorks - Not urgent items |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 7 hrs? | Tue 8/27/24 | Tue 8/27/24
APWORKS 2024.2 - PHASE 6 | Global Mappings - Vendor Map |  | APWORKS 2024.2 - PHASE 6: | 0 hrs
APWORKS 2024.2 - PHASE 6 | RE: APWorks - Nexelus to APWorks data sync improvements |  | APWORKS 2024.2 - PHASE 6: | 0 hrs
APWORKS 2024.2 - PHASE 6 | Review and Management |  | APWORKS 2024.2 - PHASE 6: | 70 hrs | 350 hrs | Tue 8/27/24 | Fri 11/1/24
APWORKS 2024.2 - PHASE 6 | Abid |  | APWORKS 2024.2 - PHASE 6: | 70 hrs |  | Tue 8/27/24 | Fri 11/1/24
APWORKS 2024.2 - PHASE 6 | QA |  | APWORKS 2024.2 - PHASE 6: | 343.4 hrs | 524.02 hrs? | Fri 9/20/24 | Fri 12/20/24
APWORKS 2024.2 - PHASE 6 | Sprint #3 |  | APWORKS 2024.2 - PHASE 6: | 226 hrs | 184.14 hrs? | Fri 9/20/24 | Wed 10/23/24
APWORKS 2024.2 - PHASE 6 | QA |  | APWORKS 2024.2 - PHASE 6: | 226 hrs | 184.14 hrs? | Fri 9/20/24 | Wed 10/23/24
APWORKS 2024.2 - PHASE 6 | Google Drive integration. (Setup and Integration development) | Google Drive integration. (Setup and Integration development) | APWORKS 2024.2 - PHASE 6: Google Drive integration. (Setup and Integration development) | 8 hrs | 10 hrs | Fri 9/20/24 | Mon 9/23/24
APWORKS 2024.2 - PHASE 6 | Ability to automatically attach additional documents (tear sheets, afidavit) to the invoice | Ability to automatically attach additional documents to Invoice | APWORKS 2024.2 - PHASE 6: Ability to automatically attach additional documents to Invoice | 20 hrs | 25 hrs? | Thu 9/26/24 | Wed 10/2/24
APWORKS 2024.2 - PHASE 6 | We need to read the company on the invoice document to route to the right company. If the company is not detected properly we will default to a company and mark it with a status. |  | APWORKS 2024.2 - PHASE 6: | 20 hrs | 25 hrs? | Fri 10/4/24 | Wed 10/9/24
APWORKS 2024.2 - PHASE 6 | Broadcast invoices |  | APWORKS 2024.2 - PHASE 6: | 60 hrs | 50 hrs? | Wed 10/9/24 | Fri 10/18/24
APWORKS 2024.2 - PHASE 6 | Invoice List UI |  | APWORKS 2024.2 - PHASE 6: | 8 hrs | 10 hrs? | Fri 9/20/24 | Mon 9/23/24
APWORKS 2024.2 - PHASE 6 | User Group management changes | Broadcast Invoice: User Group Management Changes | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: User Group Management Changes | 2 hrs
APWORKS 2024.2 - PHASE 6 | Dashboard |  | APWORKS 2024.2 - PHASE 6: | 0 hrs
APWORKS 2024.2 - PHASE 6 | Manage Invoice Models | Broadcast Invoice: Manage Invoice Models List | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: Manage Invoice Models List | 0 hrs
APWORKS 2024.2 - PHASE 6 | Manage Non-Mapped Production Invoices | Broadcast Invoice: Manage Non-Mapped Broadcast Invoices | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: Manage Non-Mapped Broadcast Invoices | 0 hrs
APWORKS 2024.2 - PHASE 6 | EDI file processing | Broadcast Invoice: EDI File Processing | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: EDI File Processing | 40 hrs | 50 hrs? | Wed 10/9/24 | Fri 10/18/24
APWORKS 2024.2 - PHASE 6 | Invoice View UI | Broadcast Invoice: Invoice View UI | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: Invoice View UI | 12 hrs | 15 hrs? | Tue 10/15/24 | Thu 10/17/24
APWORKS 2024.2 - PHASE 6 | PDF file generation | Broadcast Invoice: PDF file generation | APWORKS 2024.2 - PHASE 6: Broadcast Invoice: PDF file generation | 6 hrs | 7.5 hrs? | Mon 10/14/24 | Tue 10/15/24
APWORKS 2024.2 - PHASE 6 | Customer Information : Selection of the client on the vendor invoice header level. This will help route the invoice to the appropriate client team. - (Sync and a lookup field on invoice) | Customer Information: Select Client on Vendor Invoice | APWORKS 2024.2 - PHASE 6: Customer Information: Select Client on Vendor Invoice | 4 hrs | 5 hrs? | Fri 10/4/24 | Fri 10/4/24
APWORKS 2024.2 - PHASE 6 | Read data from Media Ocean Jobs, IOs (buying), Customer Master, Vendor Master, Currencies, Tax codes, Payment terms, EDI?, payment information |  | APWORKS 2024.2 - PHASE 6: | 40 hrs | 50 hrs? | Wed 10/2/24 | Thu 10/10/24
APWORKS 2024.2 - PHASE 6 | vendor/stations/sites can be associated to multiple pay to. EX: Bell Media is linked to Bill pay to |  | APWORKS 2024.2 - PHASE 6: | 6 hrs | 7.5 hrs? | Fri 10/4/24 | Mon 10/7/24
APWORKS 2024.2 - PHASE 6 | Ability to assign Employees to Roles by Media type and by Client |  | APWORKS 2024.2 - PHASE 6: | 8 hrs | 26.67 hrs? | Thu 10/3/24 | Tue 10/8/24
APWORKS 2024.2 - PHASE 6 | Testing and Review |  | APWORKS 2024.2 - PHASE 6: | 60 hrs | 100 hrs | Fri 10/4/24 | Wed 10/23/24
APWORKS 2024.2 - PHASE 6 | Sprint #4 |  | APWORKS 2024.2 - PHASE 6: | 101.4 hrs | 131.45 hrs? | Wed 11/20/24 | Thu 12/12/24
APWORKS 2024.2 - PHASE 6 | Production: Auto populate lines based PO during scanning |  | APWORKS 2024.2 - PHASE 6: | 4 hrs | 4.44 hrs? | Wed 11/20/24 | Wed 11/20/24
APWORKS 2024.2 - PHASE 6 | Production: Project should be available on summary as well. |  | APWORKS 2024.2 - PHASE 6: | 4 hrs | 4.45 hrs? | Wed 11/20/24 | Thu 11/21/24
APWORKS 2024.2 - PHASE 6 | Production: show keyvalue pairs for level2 mapping |  | APWORKS 2024.2 - PHASE 6: | 4 hrs | 4.45 hrs? | Thu 11/21/24 | Thu 11/21/24
APWORKS 2024.2 - PHASE 6 | We need a way to forward invoice to user OR select a user when invoice is in Pending Approval queue |  | APWORKS 2024.2 - PHASE 6: | 51.4 hrs | 62.45 hrs? | Thu 11/21/24 | Tue 12/3/24
APWORKS 2024.2 - PHASE 6 | A report to spot check the invoices processed |  | APWORKS 2024.2 - PHASE 6: | 8 hrs | 50.22 hrs? | Fri 11/22/24 | Tue 12/3/24
APWORKS 2024.2 - PHASE 6 | PDF based broadcast invoices |  | APWORKS 2024.2 - PHASE 6: | 30 hrs | 72.78 hrs? | Fri 11/29/24 | Thu 12/12/24
APWORKS 2024.2 - PHASE 6 | Pull Client & Sites from Nexelus |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 8.89 hrs? | Thu 11/21/24 | Fri 11/22/24
APWORKS 2024.2 - PHASE 6 | Sprint #5 |  | APWORKS 2024.2 - PHASE 6: | 16 hrs | 17.78 hrs? | Wed 12/18/24 | Fri 12/20/24
APWORKS 2024.2 - PHASE 6 | Bug Fixing |  | APWORKS 2024.2 - PHASE 6: | 138 hrs | 661.91 hrs? | Tue 8/27/24 | Mon 12/23/24
APWORKS 2024.2 - PHASE 6 | Sprint #3 |  | APWORKS 2024.2 - PHASE 6: | 100 hrs | 117.17 hrs? | Mon 9/30/24 | Mon 10/21/24
APWORKS 2024.2 - PHASE 6 | Sprint #4 |  | APWORKS 2024.2 - PHASE 6: | 30 hrs | 616.78 hrs? | Tue 8/27/24 | Mon 12/16/24
APWORKS 2024.2 - PHASE 6 | We need a way to forward invoice to user OR select a user when invoice is in Pending Approval queue |  | APWORKS 2024.2 - PHASE 6: | 11 hrs | 8.89 hrs? | Tue 12/3/24 | Wed 12/4/24
APWORKS 2024.2 - PHASE 6 | A report to spot check the invoices processed |  | APWORKS 2024.2 - PHASE 6: | 3 hrs | 3.33 hrs? | Tue 12/3/24 | Tue 12/3/24
APWORKS 2024.2 - PHASE 6 | PDF based broadcast invoices |  | APWORKS 2024.2 - PHASE 6: | 16 hrs | 13.33 hrs? | Thu 12/12/24 | Mon 12/16/24
APWORKS 2024.2 - PHASE 6 | Pull Client & Sites from Nexelus |  | APWORKS 2024.2 - PHASE 6: | 0 hrs | 0 hrs | Tue 8/27/24 | Tue 8/27/24
APWORKS 2024.2 - PHASE 6 | Sprint #5 |  | APWORKS 2024.2 - PHASE 6: | 8 hrs | 661.91 hrs? | Tue 8/27/24 | Mon 12/23/24
APWORKS 2024.2 - PHASE 6 | QA Iteration #2 |  | APWORKS 2024.2 - PHASE 6: | 160 hrs | 641.78 hrs? | Tue 8/27/24 | Thu 12/19/24
APWORKS 2024.2 - PHASE 6 | Integration Testing |  | APWORKS 2024.2 - PHASE 6: | 66 hrs | 24 hrs | Thu 12/19/24 | Tue 12/24/24
APWORKS 2024.2 - PHASE 6 | Bug fixing for integration testing |  | APWORKS 2024.2 - PHASE 6: | 40 hrs | 28.57 hrs | Thu 12/19/24 | Tue 12/24/24
APWORKS 2024.2 - PHASE 6 | UAT Deployments |  | APWORKS 2024.2 - PHASE 6: | 20 hrs | 7 hrs | Tue 12/24/24 | Wed 12/25/24
|  |  | : | 0 hrs
| Nexelus 2024.1 SP2 |  | : Nexelus 2024.1 SP2 | 588 hrs | 405.45 hrs? | Mon 10/14/24 | Mon 12/23/24
NEXELUS 2024.1 SP2 | Development and Testing |  | NEXELUS 2024.1 SP2: | 484 hrs | 360.95 hrs? | Mon 10/14/24 | Mon 12/16/24
NEXELUS 2024.1 SP2 | Backup Table for vendor/client lines relationship | Backup Table for vendor/client lines relationship | NEXELUS 2024.1 SP2: Backup Table for vendor/client lines relationship | 58 hrs | 62.86 hrs? | Tue 10/29/24 | Thu 11/7/24 |  |  |  | 8
NEXELUS 2024.1 SP2 | DB |  | NEXELUS 2024.1 SP2: | 8 hrs | 20 hrs? | Tue 10/29/24 | Thu 10/31/24
NEXELUS 2024.1 SP2 | DotNet |  | NEXELUS 2024.1 SP2: | 30 hrs | 42.86 hrs? | Tue 10/29/24 | Tue 11/5/24
NEXELUS 2024.1 SP2 | Need to support UDF & naming convention fields in RFP (Bulksheet only) |  | NEXELUS 2024.1 SP2: | 188 hrs | 182.86 hrs? | Thu 10/17/24 | Mon 11/18/24
NEXELUS 2024.1 SP2 | Vendor Portal Proposal | UDF & Naming Convention in Vendor Portal - Proposal Import/exp | NEXELUS 2024.1 SP2: UDF & Naming Convention in Vendor Portal - Proposal Import/exp | 114 hrs | 120 hrs? | Thu 10/17/24 | Thu 11/7/24 |  |  | 0.9 | 13.1
NEXELUS 2024.1 SP2 | Nexelus Export only on Proposal | UDF & Naming Convention in Nexelus - Export on Proposal | NEXELUS 2024.1 SP2: UDF & Naming Convention in Nexelus - Export on Proposal | 36 hrs | 125.72 hrs? | Mon 10/21/24 | Tue 11/12/24 |  |  | 12
NEXELUS 2024.1 SP2 | Nexelus RFP (Import/Export) | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | NEXELUS 2024.1 SP2: UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | 38 hrs | 182.86 hrs? | Thu 10/17/24 | Mon 11/18/24
NEXELUS 2024.1 SP2 | Nexelus RFP (Import/Export) - Phase 2 (onhold) |  | NEXELUS 2024.1 SP2: | 68 hrs | 34.29 hrs? | Thu 10/17/24 | Wed 10/23/24
NEXELUS 2024.1 SP2 | Generate client lines based on media type | Generate Client Schedule Lines based on media type | NEXELUS 2024.1 SP2: Generate Client Schedule Lines based on media type | 205 hrs | 360.95 hrs? | Mon 10/14/24 | Mon 12/16/24
NEXELUS 2024.1 SP2 | Client Profile |  | NEXELUS 2024.1 SP2: | 1 hr | 5 hrs? | Thu 10/24/24 | Thu 10/24/24
NEXELUS 2024.1 SP2 | Level3 |  | NEXELUS 2024.1 SP2: | 1 hr | 5 hrs? | Thu 10/24/24 | Fri 10/25/24
NEXELUS 2024.1 SP2 | Media Plan Vendor lines (new, import/export) |  | NEXELUS 2024.1 SP2: | 66 hrs | 300.43 hrs? | Mon 10/14/24 | Wed 12/4/24 |  |  |  |  | 8
NEXELUS 2024.1 SP2 | Client Lines (new line, generate schedule) | Billing by Media Type | NEXELUS 2024.1 SP2: Billing by Media Type | 137 hrs | 276.95 hrs? | Mon 10/28/24 | Mon 12/16/24 |  |  |  |  | 20
NEXELUS 2024.1 SP2 | DB |  | NEXELUS 2024.1 SP2: | 7 hrs | 17.5 hrs? | Mon 10/28/24 | Wed 10/30/24
NEXELUS 2024.1 SP2 | Media Plan approval | Media Plan Approval | NEXELUS 2024.1 SP2: Media Plan Approval | 14 hrs | 26.67 hrs? | Thu 10/31/24 | Tue 11/5/24
NEXELUS 2024.1 SP2 | Please note that data is based on latest Insertion Order based on most recent approved media plan. Please ensure that Insertion Order(s) are revised as such.” |  | NEXELUS 2024.1 SP2: | 0 hrs | 7 hrs? | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | Client Profile: Media > Flag to make the vendor inactive | Client Profile: Media > Flag to make the vendor inactive | NEXELUS 2024.1 SP2: Client Profile: Media > Flag to make the vendor inactive | 24 hrs | 105.71 hrs? | Thu 10/24/24 | Tue 11/12/24 |  |  |  | 2
NEXELUS 2024.1 SP2 | Mngt Fee renamable everywhere |  | NEXELUS 2024.1 SP2: | 9 hrs | 175.43 hrs? | Mon 10/14/24 | Wed 11/13/24 |  |  |  | 1
NEXELUS 2024.1 SP2 | Support items |  | NEXELUS 2024.1 SP2: | 0 hrs | 0 hrs | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | support> Pursuit - Is it possible to make the email address field longer on the client profile page? 17136 |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Client Support Item> The issue is resolved which was due to missing preferred group flag for this user. |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | support item> Please see below, currently we see system only allows 256 characters in the comments box. |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support item -Person shouldn't be able to approve his own expense report / Timesheet even after switching to his manager / supervisor |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support item> It is crashing because of “&” character, it requires a DLL change to resolve the issue. |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support item > Can we add Print label in future release> see attached email for reference |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support Item >Contract level billing should pick Cus Po # from Contract. Also make sure if we mark it on client profile, it defaults to contract. |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support item> Why am I getting a duplicate message when trying to delete an expense type, e.g. production_old from below example |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support Item> Msg on Delivery Override” >Please note that data is based on latest Insertion Order based on most recent approved media plan. Please ensure that Insertion Order(s) are revised as such.” |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Support Item > Rule based Hard Stop or warning if user changes the dates on IO placements after delivery override. |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Client item> Support> At TSY I noticed favorite is not showing on top. The user was on MAC. But it looks like even on Windows, the button doesn’t appear when one is on Billing Setup or Invoice screens. |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Feature Name: Enhanced Filtering for RFP and Proposal List UI |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Restrict Self Approval |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Custom field 3/AdServing able to take formulas (on hold) |  | NEXELUS 2024.1 SP2: | 0 hrs | 7 hrs? | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting |  | NEXELUS 2024.1 SP2: | 0 hrs | 7 hrs? | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | Separate broadcast label rename |  | NEXELUS 2024.1 SP2: | 0 hrs | 7 hrs? | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | CHECK: tiered rate on new lines only or all lines? What happens if spend is added to a billed month. |  | NEXELUS 2024.1 SP2: | 0 hrs | 7 hrs? | Mon 10/14/24 | Mon 10/14/24
NEXELUS 2024.1 SP2 | DV360 API Upgrade |  | NEXELUS 2024.1 SP2: | 10 hrs | 31 hrs | Mon 10/28/24 | Thu 10/31/24
|  |  | : | 0 hrs
| Hotfix 2024.1 |  | : Hotfix 2024.1 | 37 hrs | 42.86 hrs? | Thu 10/31/24 | Thu 11/7/24
NEXELUS 2024.1 SP2 | eConnect Shell removal : Develop a web service | eConnect shell change to service | NEXELUS 2024.1 SP2: eConnect shell change to service | 30 hrs | 42.86 hrs? | Thu 10/31/24 | Thu 11/7/24
NEXELUS 2024.1 SP2 | DotNet changes |  | NEXELUS 2024.1 SP2: | 30 hrs | 42.86 hrs? | Thu 10/31/24 | Thu 11/7/24
NEXELUS 2024.1 SP2 | Deployments and QA |  | NEXELUS 2024.1 SP2: | 7 hrs
NEXELUS 2024.1 SP2 | Bilal |  | NEXELUS 2024.1 SP2: | 7 hrs |  | Thu 10/31/24 | Thu 10/31/24
NEXELUS 2024.1 SP2 | UAT upgrade |  | NEXELUS 2024.1 SP2: | 0 hrs
NEXELUS 2024.1 SP2 | Production upgrade |  | NEXELUS 2024.1 SP2: | 0 hrs

## SQL
use nex_pdm;
select
concat(pdd_resources.name_first,' ',pdd_resources.name_last) employee,
level2_key 'Project',
level3_key 'Activity Code',
(select top 1 level3_description
from pdd_level3
where pdd_level3.level2_key = pld_transactions.level2_key and
PATINDEX (concat(rtrim(pld_transactions.level3_key),'%'),pdd_level3.level3_key)>0 ) 'Activity Desc',
task_code,
units 'Hours',
--Month(applied_date) 'Date'
DateName(Month,applied_date) 'Date'
from pld_transactions
inner join pdd_resources on pdd_resources.resource_id=pld_transactions.resource_id
where applied_date >= '9/01/2024'
--and applied_date < '11/01/2024'
#NAME?