## April-June
| Resources |  |  | Estimate | [5 empty] | Actual | [5 empty] | Management and Meetings |  |  |  | Documentation |  |  |  |  | Totals
Project / Task | Dev | DB | QA | Research | Dev | Review | Test Cases | QA | Bug Fixing | Research | Development | Task/Code Review | QA | Bug Fixing | Admin | Analysis | Planinng | Project Mgmt | Meetings | Design | Documentation | SRS-Review | Task Domain | Deployment | Plan | Actual
APWORKS 2025.2 |  |  |  | 8 | 684 | 54 | 86 | 158 | 184 | 42 | 582.5 | 25 | 1034 | 236.75 |  | 20 | 0 | 49.5 | 55.75 | 0 | 9 | 9.5 | 20.5 | 50.5 | 1174 | 2093
Ability to Approve the invoice when resolving discrepancy | Ali |  | Kashif Hayat |  | 36 | 4 | 4 | 8 | 16 |  | 23 | 0.5 | 64 | 6 | [10 empty] | 68 | 93.5
Ability to create templates across multiple Companies | Arslan | Yasir | Ayesha |  | 120 | 4 | 6 | 26 | 18 |  | 114.75 | 4.5 | 198.5 | 38.75 |  | 2 |  |  | 27 | [5 empty] | 174 | 385.5
Auto populate call letters; media type and band after 1st maping | Arslan | Yasir | Kashif / Ayesha |  | 32 | 4 | 4 | 8 | 11 |  | 25 | 2.5 | 47 | 9 | [10 empty] | 59 | 83.5
Credit Memo | Ali / Asad | Yasir | Kashif |  | 76 | 4 | 12 | 16 | 24 |  | 68 | 5 | 178 | 15.5 |  | 4 |  |  | 9 |  |  | 5 |  |  | 132 | 284.5
Display client #, when inv is linked to IO in all UIs and Report | Arslan | Yasir | Ayesha |  | 8 | 2 | 4 | 4 | 2 |  | 6 | 1 | 46 | 2 |  | 1 | [8 empty] | 20 | 56
Nexelus Email Function for IO |  | Yasir | [8 empty] | 3 |  | 0 | 0 | [10 empty] | 0 | 3
Optimizing data retrieval processes to enhance performance | Aimen, Ali, Arslan, Asad | Yasir | Kashif, Aysha, Hamza | 8 | 158 | 23 | 16 | 30 | 39 |  | 141 | 6.5 | 116 | 60 |  |  |  |  | 6.5 | [5 empty] | 274 | 330
Restriction by user group on which fields can be edited | Ali, Arslan, Asad | Yasir | Aysha, Hamza, Kashif |  | 180 | 10 | 20 | 40 | 52 | 6 | 135.25 | 3 | 152.5 | 27 |  | 7 |  |  | 13.25 |  |  | 1 |  |  | 302 | 339
Separate the financial integration API from the main application | Abid, Asad |  |  |  | 40 |  | 10 | 16 | 12 | 7 | 35 |  | 0 | 0 | [6 empty] | 2 |  |  |  | 78 | 37
Split invoice by MOS - Print / OOH / Digital |  | Arif | Ayesha, Kashif | [8 empty] | 2 | 82 | 0 | [7 empty] | 3 |  |  | 0 | 87
Standardize the Status in Dashboard vs reports | Arslan | Yasir | Ayesha |  | 8 | 2 | 2 | 2 | 2 |  | 2.5 |  | 4 | 2.5 | [10 empty] | 16 | 9
Warren Lamb provided PDF ingestion | Asad | Yasir | Kashif |  | 26 | 1 | 8 | 8 | 8 |  | 29 |  | 146 | 6 |  | 5 | [5 empty] | 0.5 |  |  | 51 | 186.5
Project Overhead | [9 empty] | 29 |  |  | 0 | 70 |  | 1 |  | 49.5 |  |  | 7 |  | 20.5 | 50.5 | 0 | 198.5
APWORKS 2025.2 SP1 |  |  |  | 0 | 69 | 0 | 0 | 8 | 0 | 15 | 93.5 |  | 93 | 30 |  | 7.5 |  | 12 | 6.5 |  |  |  |  | 4.5 | 77 | 247
APWorks amounts - format to 2 decimal places | Ali, Arslan | [9 empty] | 28 |  | 0 | 1 | [10 empty] | 0 | 29
For "No filter' all data not getting shown | Ali | Arif | Kashif |  | 8 | [5 empty] | 13 |  | 42 | 0 | [10 empty] | 8 | 55
Maintenance page creation | Ali | [9 empty] | 13 |  | 0 | 0 | [10 empty] | 0 | 13
Make date fields editable for Broadcast | Arslan | Yasir | kashif |  | 21 | [5 empty] | 8 |  | 36 | 4 | [10 empty] | 21 | 48
Manage invoice list optimization | Ali |  | Kashif | [6 empty] | 8 | 5 |  | 9 | 1 | [10 empty] | 0 | 15
Split functionality enhancement. | Arslan | Yasir |  |  | 40 |  |  | 8 |  |  | 26.5 |  | 6 | 10 |  | 7.5 |  |  | 6.5 | [5 empty] | 48 | 56.5
Project Overhead | [9 empty] | 7 |  |  | 0 | 14 |  |  |  | 12 | [5 empty] | 4.5 | 0 | 30.5
APWORKS 2025.2 SP2 |  |  |  | 24 | 72 | 0 | 0 | 16 | 0 |  | 9 |  | 4 | 0 |  |  |  | 3 | 3 | [5 empty] | 112 | 19
Partial posting in posting process for failed invoices into MO | Asad |  |  | 24 | 72 |  |  | 16 |  |  | 9 |  | 4 | 0 |  |  |  |  | 3 | [5 empty] | 112 | 16
Project Overhead | Abid | [11 empty] | 0 | 0 |  |  |  | 3 | [6 empty] | 0 | 3
NEXELUS - ADDHOC ITEMS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 22.42 | 1.5 | 0 | 0 | [10 empty] | 0 | 23.92
IPC - Upgrade Facebook API version to V22 | Muzammil | [9 empty] | 22.42 | 1.5 | 0 | 0 | [10 empty] | 0 | 23.92
Nexelus Vulnerability Report - 2025 | Aimen | [8 empty] | 18 |  |  | 0 | 0 | [10 empty] | 0 | 0
NEXELUS 2025.2 |  |  |  | 0 | 204 | 11 | 0 | 20 | 0 | 23.5 | 522.5 | 25.5 | 705 | 263.35 | 0 | 14.5 | 0 | 64.5 | 29 | 11 | 33 | 3 | 40.5 | 15.5 | 235 | 1727.35
Add a 'Collapse All Packages/Placements' button on Placement | Aimen, Muzammil |  | Hamza |  | 6 | 1 |  |  |  |  | 30.9 | 0.5 | 23 | 8.5 | [5 empty] | 1 |  |  |  |  | 7 | 63.9
Alerting users when an FX rate is unavailable to prevent the |  | Arif |  |  | 8 | [5 empty] | 17 |  | 0 | 0 |  |  |  |  | 1 | [5 empty] | 8 | 18
Allow manual adjustments for partial billing by the client | Abid Ali Fawad | Yasir | Blal |  | 40 | 6 |  |  |  |  | 36 |  | 32 | 13 |  |  |  |  | 2 |  |  | 1 |  |  | 46 | 84
Allow switching media plan from Media Plan UI | Aimen Arslan |  | Hamza |  | 7 | 1 | [5 empty] | 0.5 | 25 | 7 | [10 empty] | 8 | 32.5
DENTSU CHANGES: Enhance Close Job functionality | Aimen |  | Hamza |  | 4 | [5 empty] | 15 |  | 102 | 0 | [10 empty] | 4 | 117
Display Vendor distribution for individual client line under | Aimen | Arif | Bilal |  | 18 | 1 |  |  |  |  | 31 | 4 | 22 | 8 | [10 empty] | 19 | 65
Exchange rate changes | Fawad | Arif | Bilal | [7 empty] | 62 | 5 | 84 | 26.5 |  | 3 |  |  | 2 |  | 2 |  |  |  | 0 | 184.5
iPC Selfservices: UI optimization | Aimen | [9 empty] | 18 |  | 0 | 0 | [10 empty] | 0 | 18
MC: Apply exchange rate from revision date or IO creation date | Fawad | Arif | Bilal | [7 empty] | 134 | 9.5 | 163 | 12 |  |  |  |  | 6.5 |  | 1 | 1 |  |  | 0 | 327
Net Media + Ad serving Added to Media Spend under Campaign | Aimen |  | Bilal | [8 empty] | 4 | 22 | 1 | [10 empty] | 0 | 27
Nexelus Email Function for IO |  |  | Bilal | [9 empty] | 22 | 0 | [10 empty] | 0 | 22
Provide an option to include AdTech Fee in a separate invoice | Aimen Abid | Arif | [8 empty] | 29 |  | 0 | 2 |  | 1 |  |  |  | 10 |  | 0.5 |  |  | 0 | 42.5
Restrict Consecutive Approvals by the Same | Muzammil Aimen | Arif | Hamza |  | 73 | 2 |  |  |  |  | 99.1 |  | 202 | 63.25 |  | 9.5 |  |  | 1.5 |  |  | 0.5 |  |  | 75 | 375.85
Starred media plans (NEX 17059) |  |  | Hamza Bilal | [9 empty] | 8 | 0 | [10 empty] | 0 | 8
Enhance revise BO to allow consecutive IOs to merge into it | Aimen, Muzammil | Yasir | Ayesha |  | 48 |  |  | 20 |  |  | 50.5 | 2 | 0 | 91.1 | [10 empty] | 68 | 143.6
Project Overhead | [9 empty] | 23.5 |  |  | 0 | 31 |  | 1 |  | 64.5 | 16 |  | 30 |  | 40.5 | 15.5 | 0 | 198.5
APWORKS - TEST AUTOMATION |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 28 |  | 0 | 0 |  | 1 |  |  |  | 8 |  |  |  |  | 0 | 37
Media approval: approve invoices | Kashif | [9 empty] | 24 |  | 0 | 0 | [10 empty] | 0 | 24
Media: Discrepant Invoices - Make Corrections | Kashif | [9 empty] | 4 |  | 0 | 0 | [10 empty] | 0 | 4
Media: Read Data diven excel files for the correspinding data | Kashif | [11 empty] | 0 | 0 | [5 empty] | 8 |  |  |  |  | 0 | 8
Project Overhead | Kashif | [11 empty] | 0 | 0 |  | 1 | [8 empty] | 0 | 1
Grand Total |  |  |  | 32 | 1029 | 65 | 86 | 202 | 184 | 98.5 | 1257.92 | 52 | 1836 | 530.1 | 0 | 43 | 0 | 129 | 94.25 | 19 | 42 | 12.5 | 61 | 70.5 | 1598 | 4147.27

## Data
employee | level2_key | level3_description | task_code | appliedmonth | Hours
Abid Ali | AD-0001 | Meetings | Meetings | 2024-11 | 13.5
Abid Ali | AD-0001 | Meetings | Meetings | 2024-12 | 32
Abid Ali | AD-0001 | Meetings | Meetings | 2025-01 | 40.5
Abid Ali | AD-0001 | Meetings | Meetings | 2025-02 | 24.5
Abid Ali | AD-0001 | Meetings | Meetings | 2025-03 | 28.7
Abid Ali | AD-0001 | Meetings | Meetings | 2025-04 | 26.5
Abid Ali | AD-0001 | Meetings | Meetings | 2025-05 | 35
Abid Ali | AD-0001 | Meetings | Meetings | 2025-06 | 6
Abid Ali | AP WORKFLOW | Analysis of production issues reported by support team | Bug Fixing | 2024-10 | 5
Abid Ali | AP WORKFLOW | Analysis of production issues reported by support team | Development | 2024-08 | 1
Abid Ali | AP WORKFLOW | Analysis of production issues reported by support team | Other | 2024-08 | 1
Abid Ali | AP WORKFLOW | Cient UAT Upgrade | Deployment | 2024-11 | 12
Abid Ali | AP WORKFLOW | Cient UAT Upgrade | Other | 2024-08 | 0.5
Abid Ali | AP WORKFLOW | Development of new project/assignment/task | Bug Fixing | 2024-08 | 3
Abid Ali | AP WORKFLOW | Development of new project/assignment/task | Development | 2024-08 | 2
Abid Ali | AP WORKFLOW | Development of new project/assignment/task | Other | 2024-08 | 20.5
Abid Ali | AP WORKFLOW | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-08 | 3
Abid Ali | AP WORKFLOW | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 1
Abid Ali | AP WORKFLOW | Meetings, mails, communication, TFS, Interviews | Project Mgmt | 2024-11 | 18
Abid Ali | AP WORKFLOW | National Gazetted Holidays | Leave | 2024-09 | 8
Abid Ali | AP WORKFLOW | National Gazetted Holidays | Leave | 2024-12 | 8
Abid Ali | AP WORKFLOW | Project planning for new project/assignment/task | Other | 2024-08 | 20.5
Abid Ali | AP WORKFLOW | QA Environment Upgrade | Deployment | 2024-08 | 3.5
Abid Ali | AP WORKFLOW | QA Environment Upgrade | Deployment | 2024-09 | 1
Abid Ali | AP WORKFLOW | QA Environment Upgrade | Deployment | 2024-11 | 6
Abid Ali | AP WORKFLOW | QA Environment Upgrade | Other | 2024-08 | 10
Abid Ali | AP WORKFLOW | Regular bug fixing activity | Bug Fixing | 2024-10 | 3
Abid Ali | APWORKS - SUPPORT | Maintenance Activity | JustGlobal | 2025-04 | 2
Abid Ali | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Analysis | 2024-09 | 3
Abid Ali | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Task/Code Review | 2024-10 | 3
Abid Ali | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Analysis | 2024-09 | 0.5
Abid Ali | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Analysis | 2024-10 | 1
Abid Ali | APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Analysis | 2024-09 | 2
Abid Ali | APWORKS 2024.2 - PHASE 3 | Associate vendor/stations/sites to multiple pay to | Analysis | 2024-09 | 1
Abid Ali | APWORKS 2024.2 - PHASE 3 | Associate vendor/stations/sites to multiple pay to | Task/Code Review | 2024-10 | 1
Abid Ali | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: EDI File Processing | Analysis | 2024-10 | 2
Abid Ali | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: EDI File Processing | Development | 2024-10 | 7
Abid Ali | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: EDI File Processing | Task/Code Review | 2024-10 | 13
Abid Ali | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: Invoice View UI | Task/Code Review | 2024-09 | 2
Abid Ali | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: Manage Invoice Models List | Analysis | 2024-09 | 2
Abid Ali | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: PDF file generation | Analysis | 2024-09 | 5
Abid Ali | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: PDF file generation | Development | 2024-09 | 5
Abid Ali | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: PDF file generation | Development | 2024-10 | 23
Abid Ali | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: PDF file generation | Testing | 2024-10 | 10.5
Abid Ali | APWORKS 2024.2 - PHASE 3 | Customer Information: Select Client on Vendor Invoice | Analysis | 2024-09 | 0.5
Abid Ali | APWORKS 2024.2 - PHASE 3 | Customer Information: Select Client on Vendor Invoice | Analysis | 2024-10 | 2
Abid Ali | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Bug Fixing | 2024-10 | 9
Abid Ali | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Task/Code Review | 2024-10 | 4
Abid Ali | APWORKS 2024.2 - PHASE 3 | Project Overhead | Analysis | 2024-10 | 4.5
Abid Ali | APWORKS 2024.2 - PHASE 3 | Project Overhead | Deployment | 2024-09 | 2.5
Abid Ali | APWORKS 2024.2 - PHASE 3 | Project Overhead | Deployment | 2024-10 | 24.5
Abid Ali | APWORKS 2024.2 - PHASE 3 | Project Overhead | Deployment | 2024-11 | 5.5
Abid Ali | APWORKS 2024.2 - PHASE 3 | Project Overhead | Meetings | 2024-08 | 9.5
Abid Ali | APWORKS 2024.2 - PHASE 3 | Project Overhead | Meetings | 2024-09 | 13.5
Abid Ali | APWORKS 2024.2 - PHASE 3 | Project Overhead | Meetings | 2024-10 | 13.5
Abid Ali | APWORKS 2024.2 - PHASE 3 | Project Overhead | Project Mgmt | 2024-08 | 3
Abid Ali | APWORKS 2024.2 - PHASE 3 | Project Overhead | Project Mgmt | 2024-09 | 1
Abid Ali | APWORKS 2024.2 - PHASE 3 | Project Overhead | Project Mgmt | 2024-10 | 8
Abid Ali | APWORKS 2024.2 - PHASE 3 | Project Overhead | Project Mgmt | 2024-11 | 17
Abid Ali | APWORKS 2024.2 - PHASE 3 | Route invoice from one company - company identification | Analysis | 2024-09 | 1
Abid Ali | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Analysis | 2024-10 | 1
Abid Ali | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Development | 2024-10 | 2
Abid Ali | APWORKS 2024.2 - PHASE 4 | A report to spot check the invoices processed | Development | 2024-11 | 3
Abid Ali | APWORKS 2024.2 - PHASE 4 | Deadlock issue | Analysis | 2025-01 | 11
Abid Ali | APWORKS 2024.2 - PHASE 4 | EDI: Generate PDF - Updates | Development | 2024-11 | 11.5
Abid Ali | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Import / Export lines | Task/Code Review | 2024-12 | 1
Abid Ali | APWORKS 2024.2 - PHASE 4 | Project Overhead | Analysis | 2024-11 | 1
Abid Ali | APWORKS 2024.2 - PHASE 4 | Project Overhead | Deployment | 2024-11 | 6
Abid Ali | APWORKS 2024.2 - PHASE 4 | Project Overhead | Deployment | 2024-12 | 8
Abid Ali | APWORKS 2024.2 - PHASE 4 | Project Overhead | Deployment | 2025-01 | 15
Abid Ali | APWORKS 2024.2 - PHASE 4 | Project Overhead | Meetings | 2024-12 | 1
Abid Ali | APWORKS 2024.2 - PHASE 4 | Project Overhead | Post_dep_fixes | 2025-01 | 29
Abid Ali | APWORKS 2024.2 - PHASE 4 | Project Overhead | Project Mgmt | 2024-11 | 7
Abid Ali | APWORKS 2024.2 - PHASE 4 | Project Overhead | Project Mgmt | 2024-12 | 16.5
Abid Ali | APWORKS 2024.2 - PHASE 4 | Project Overhead | Project Mgmt | 2025-01 | 17
Abid Ali | APWORKS 2025.1 | Project Overhead | Deployment | 2025-03 | 3.5
Abid Ali | APWORKS 2025.1 | Project Overhead | Meetings | 2025-03 | 1
Abid Ali | APWORKS 2025.1 | Project Overhead | Post_dep_fixes | 2025-03 | 6
Abid Ali | APWORKS 2025.1 | Project Overhead | Project Mgmt | 2025-02 | 7
Abid Ali | APWORKS 2025.2 | Ability to Approve the invoice when resolving discrepancy | Task/Code Review | 2025-04 | 0.5
Abid Ali | APWORKS 2025.2 | Ability to create templates across multiple Companies | Meetings | 2025-04 | 1.5
Abid Ali | APWORKS 2025.2 | Ability to create templates across multiple Companies | Task/Code Review | 2025-04 | 1.5
Abid Ali | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Task/Code Review | 2025-04 | 0.5
Abid Ali | APWORKS 2025.2 | Credit Memo | Analysis | 2025-03 | 1
Abid Ali | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Meetings | 2025-03 | 1.5
Abid Ali | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Task/Code Review | 2025-03 | 1
Abid Ali | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Task/Code Review | 2025-04 | 4.5
Abid Ali | APWORKS 2025.2 | Project Overhead | Deployment | 2025-03 | 1
Abid Ali | APWORKS 2025.2 | Project Overhead | Deployment | 2025-04 | 11
Abid Ali | APWORKS 2025.2 | Project Overhead | Deployment | 2025-05 | 14
Abid Ali | APWORKS 2025.2 | Project Overhead | Deployment | 2025-06 | 3
Abid Ali | APWORKS 2025.2 | Project Overhead | Post_dep_fixes | 2025-04 | 2
Abid Ali | APWORKS 2025.2 | Project Overhead | Post_dep_fixes | 2025-05 | 6
Abid Ali | APWORKS 2025.2 | Project Overhead | Project Mgmt | 2025-03 | 9
Abid Ali | APWORKS 2025.2 | Project Overhead | Project Mgmt | 2025-04 | 3.5
Abid Ali | APWORKS 2025.2 | Project Overhead | Project Mgmt | 2025-05 | 17
Abid Ali | APWORKS 2025.2 | Project Overhead | Project Mgmt | 2025-06 | 24
Abid Ali | APWORKS 2025.2 | Project Overhead | Research | 2025-06 | 3
Abid Ali | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Meetings | 2025-03 | 1
Abid Ali | APWORKS 2025.2 | Restriction by user group on which fields can be edited | SRS-Review | 2025-04 | 1
Abid Ali | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Task/Code Review | 2025-04 | 3
Abid Ali | APWORKS 2025.2 | Separate the financial integration API from the main application | Development | 2025-04 | 9
Abid Ali | APWORKS 2025.2 | Separate the financial integration API from the main application | Documentation | 2025-04 | 2
Abid Ali | APWORKS 2025.2 | Separate the financial integration API from the main application | Research | 2025-04 | 6
Abid Ali | APWORKS 2025.2 | Separate the financial integration API from the main application | Research | 2025-05 | 1
Abid Ali | APWORKS 2025.2 | Warren Lamb provided PDF ingestion | SRS-Review | 2025-04 | 0.5
Abid Ali | APWORKS 2025.2 SP1 | Project Overhead | Deployment | 2025-06 | 3
Abid Ali | APWORKS 2025.2 SP1 | Project Overhead | Project Mgmt | 2025-05 | 2
Abid Ali | APWORKS 2025.2 SP1 | Project Overhead | Project Mgmt | 2025-06 | 10
Abid Ali | APWORKS 2025.2 SP2 | Project Overhead | Project Mgmt | 2025-06 | 3
Abid Ali | APWORKS 2025.3 | Project Overhead | Planinng | 2025-06 | 1
Abid Ali | APWORKS PHASE2 | Cient UAT Upgrade | Deployment | 2024-10 | 10.5
Abid Ali | APWORKS PHASE2 | Dev Support | Meetings | 2024-09 | 1
Abid Ali | APWORKS PHASE2 | Document review/understanding Requirement Specifications | Testing | 2024-09 | 11
Abid Ali | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-09 | 16
Abid Ali | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-10 | 3
Abid Ali | NEXELUS - ADDHOC ITEMS | IPC - Upgrade Facebook API version to V22 | Task/Code Review | 2025-04 | 1.5
Abid Ali | NEXELUS 2024.1 SP2 | AdTech Fee commission | Analysis | 2024-12 | 0.5
Abid Ali | NEXELUS 2024.1 SP2 | AdTech Fee commission | Task/Code Review | 2024-12 | 1.5
Abid Ali | NEXELUS 2024.1 SP2 | eConnect shell change to service | Testing | 2024-11 | 2
Abid Ali | NEXELUS 2024.1 SP2 | eConnect shell change to service | Testing | 2024-12 | 1
Abid Ali | NEXELUS 2024.1 SP2 | Enhancement for Visual Indicators and Flighting Details in Place | Task/Code Review | 2024-12 | 2.5
Abid Ali | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Bug Fixing | 2024-12 | 10.5
Abid Ali | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Bug Fixing | 2025-01 | 1
Abid Ali | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Meetings | 2024-10 | 2.5
Abid Ali | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Task/Code Review | 2024-12 | 3
Abid Ali | NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting | Analysis | 2024-12 | 1
Abid Ali | NEXELUS 2024.1 SP2 | Project Overhead | Analysis | 2024-10 | 4
Abid Ali | NEXELUS 2024.1 SP2 | Project Overhead | Analysis | 2024-11 | 1
Abid Ali | NEXELUS 2024.1 SP2 | Project Overhead | Analysis | 2024-12 | 2
Abid Ali | NEXELUS 2024.1 SP2 | Project Overhead | Bug Fixing | 2024-11 | 10
Abid Ali | NEXELUS 2024.1 SP2 | Project Overhead | Deployment | 2024-11 | 5
Abid Ali | NEXELUS 2024.1 SP2 | Project Overhead | Meetings | 2024-10 | 12
Abid Ali | NEXELUS 2024.1 SP2 | Project Overhead | Meetings | 2024-11 | 10.5
Abid Ali | NEXELUS 2024.1 SP2 | Project Overhead | Meetings | 2025-01 | 1
Abid Ali | NEXELUS 2024.1 SP2 | Project Overhead | Post_dep_fixes | 2024-11 | 9
Abid Ali | NEXELUS 2024.1 SP2 | Project Overhead | Project Mgmt | 2024-11 | 2
Abid Ali | NEXELUS 2024.1 SP2 | Project Overhead | Project Mgmt | 2024-12 | 2
Abid Ali | NEXELUS 2024.1 SP2 | Project Overhead | Project Mgmt | 2025-01 | 4
Abid Ali | NEXELUS 2024.1 SP2 | Restrict Self Approval - Time and expense | Analysis | 2024-12 | 1
Abid Ali | NEXELUS 2024.2 | Analysis of production issues reported by support team | Client Items | 2024-09 | 9
Abid Ali | NEXELUS 2024.2 | Analysis of production issues reported by support team | Development | 2024-08 | 8
Abid Ali | NEXELUS 2024.2 | Analysis of production issues reported by support team | Other | 2024-08 | 9
Abid Ali | NEXELUS 2024.2 | Cient UAT Upgrade | Other | 2024-08 | 3.5
Abid Ali | NEXELUS 2024.2 | Client Items | Other | 2024-08 | 5
Abid Ali | NEXELUS 2024.2 | Dev Support | Other | 2024-08 | 2
Abid Ali | NEXELUS 2024.2 | Internal Meetings | Other | 2024-08 | 17
Abid Ali | NEXELUS 2024.2 | Meetings, mails, communication, TFS, Interviews | Development | 2024-08 | 3
Abid Ali | NEXELUS 2024.2 | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 18.5
Abid Ali | NEXELUS 2024.2 | National Gazetted Holidays | Leave | 2024-09 | 8
Abid Ali | NEXELUS 2024.2 | Session with US team | Other | 2024-08 | 33.5
Abid Ali | NEXELUS 2025.1 | Generate billing schedule - bug fixing | Bug Fixing | 2025-02 | 2
Abid Ali | NEXELUS 2025.1 | Generate billing schedule - bug fixing | Bug Fixing | 2025-03 | 8
Abid Ali | NEXELUS 2025.1 | Import/exports flights | Task/Code Review | 2025-02 | 2
Abid Ali | NEXELUS 2025.1 | Project Overhead | Meetings | 2025-03 | 1
Abid Ali | NEXELUS 2025.1 | Project Overhead | Post_dep_fixes | 2025-03 | 5
Abid Ali | NEXELUS 2025.1 | Project Overhead | Project Mgmt | 2025-03 | 2
Abid Ali | NEXELUS 2025.1 SP1 | Project Overhead | Deployment | 2025-03 | 2.5
Abid Ali | NEXELUS 2025.1 SP1 | Project Overhead | Post_dep_fixes | 2025-03 | 3.5
Abid Ali | NEXELUS 2025.1 SP1 | Project Overhead | Project Mgmt | 2025-03 | 1
Abid Ali | NEXELUS 2025.1 SP1 | Provide end date column in flight import export. | Task/Code Review | 2025-03 | 1
Abid Ali | NEXELUS 2025.1 SP1 | TTD: Generate schedule based on Placement Flights | Meetings | 2025-03 | 2
Abid Ali | NEXELUS 2025.1 SP1 | TTD: Generate schedule based on Placement Flights | Task/Code Review | 2025-03 | 2
Abid Ali | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Design | 2025-04 | 1
Abid Ali | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Meetings | 2025-03 | 0.5
Abid Ali | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Task/Code Review | 2025-04 | 0.5
Abid Ali | NEXELUS 2025.2 | Allow manual adjustments for partial billing by the client | Development | 2025-05 | 10
Abid Ali | NEXELUS 2025.2 | Allow manual adjustments for partial billing by the client | SRS-Review | 2025-04 | 1
Abid Ali | NEXELUS 2025.2 | Allow switching media plan from Media Plan UI | Meetings | 2025-03 | 0.5
Abid Ali | NEXELUS 2025.2 | Allow switching media plan from Media Plan UI | Task/Code Review | 2025-04 | 0.5
Abid Ali | NEXELUS 2025.2 | Exchange rate changes | Task/Code Review | 2025-05 | 1
Abid Ali | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | SRS-Review | 2025-04 | 1
Abid Ali | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Task/Code Review | 2025-04 | 2.5
Abid Ali | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Task/Code Review | 2025-05 | 1
Abid Ali | NEXELUS 2025.2 | Project Overhead | Analysis | 2025-04 | 1
Abid Ali | NEXELUS 2025.2 | Project Overhead | Meetings | 2025-04 | 2
Abid Ali | NEXELUS 2025.2 | Project Overhead | Post_dep_fixes | 2025-04 | 1
Abid Ali | NEXELUS 2025.2 | Project Overhead | Project Mgmt | 2025-03 | 3
Abid Ali | NEXELUS 2025.2 | Project Overhead | Project Mgmt | 2025-05 | 32
Abid Ali | NEXELUS 2025.2 | Project Overhead | Project Mgmt | 2025-06 | 20
Abid Ali | NEXELUS 2025.2 | Provide an option to include AdTech Fee in a separate invoice | Analysis | 2025-04 | 1
Abid Ali | NEXELUS 2025.2 | Provide an option to include AdTech Fee in a separate invoice | Development | 2025-04 | 4
Abid Ali | NEXELUS 2025.2 | Provide an option to include AdTech Fee in a separate invoice | SRS-Review | 2025-04 | 0.5
Abid Ali | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Analysis | 2025-04 | 0.5
Abid Ali | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Meetings | 2025-04 | 1.5
Abid Ali | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | SRS-Review | 2025-04 | 0.5
Abid Ali | NEXELUS 20253 | Project Overhead | Planinng | 2025-06 | 4
Abid Ali | PR-0013 | Analysis of production issues reported by support team | Analysis | 2024-09 | 10
Abid Ali | PR-0013 | Analysis of production issues reported by support team | Analysis | 2024-10 | 1
Abid Ali | PR-0013 | Analysis of production issues reported by support team | Analysis | 2024-11 | 2
Abid Ali | PR-0013 | Analysis of production issues reported by support team | Bug Fixing | 2024-09 | 12
Abid Ali | PR-0013 | Cient UAT Upgrade | Client Items | 2024-09 | 3.5
Abid Ali | PR-0013 | Cient UAT Upgrade | Deployment | 2025-01 | 3
Abid Ali | PR-0013 | Cient UAT Upgrade | Testing | 2025-01 | 6
Abid Ali | PR-0013 | Development of new project/assignment/task | Project Mgmt | 2025-01 | 12
Abid Ali | PR-0013 | Development of new project/assignment/task | Project Mgmt | 2025-02 | 6
Abid Ali | PR-0013 | Gazetted holidays | Leave | 2025-02 | 8
Abid Ali | PR-0013 | Gazetted holidays | Leave | 2025-03 | 8
Abid Ali | PR-0013 | Gazetted holidays | Leave | 2025-04 | 16
Abid Ali | PR-0013 | Gazetted holidays | Leave | 2025-05 | 8
Abid Ali | PR-0013 | Gazetted holidays | Leave | 2025-06 | 16
Abid Ali | PR-0013 | In-house Training | Training | 2025-04 | 4.5
Abid Ali | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 21.5
Abid Ali | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-10 | 13.5
Abid Ali | PR-0013 | Meetings, mails, communication, TFS, Interviews | Project Mgmt | 2024-10 | 5
Abid Ali | PR-0013 | Meetings, mails, communication, TFS, Interviews | Project Mgmt | 2024-11 | 7.5
Abid Ali | PR-0013 | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2024-11 | 7.5
Abid Ali | PR-0013 | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2024-12 | 17
Abid Ali | PR-0013 | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2025-01 | 23.5
Abid Ali | PR-0013 | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2025-02 | 18
Abid Ali | PR-0013 | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2025-03 | 23
Abid Ali | PR-0013 | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2025-04 | 19.5
Abid Ali | PR-0013 | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2025-05 | 21
Abid Ali | PR-0013 | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2025-06 | 7
Abid Ali | PR-0013 | Production upgrades | Deployment | 2024-09 | 3
Abid Ali | PR-0013 | Production upgrades | Deployment | 2025-01 | 37
Abid Ali | PR-0013 | Production upgrades | Deployment | 2025-02 | 5
Abid Ali | PR-0013 | QA Environment Upgrade | Deployment | 2025-03 | 4.5
Abid Ali | PR-0013 | Session with US team | Meetings | 2024-08 | 2
Abid Ali | PR-0013 | Session with US team | Meetings | 2024-09 | 11.2
Abid Ali | PR-0013 | Session with US team | Meetings | 2024-10 | 10
Abid Ali | PR-0013 | Session with US team | Meetings | 2024-11 | 11.5
Abid Ali | PR-0013 | Session with US team | Project Mgmt | 2024-10 | 2.7
Abid Ali | PR-0013 | Time Off - Planned | Leave | 2024-09 | 16
Abid Ali | PR-0013 | Time Off - Planned | Leave | 2024-12 | 16
Abid Ali | PR-0013 | Time Off - Planned | Leave | 2025-02 | 12
Abid Ali | PR-0013 | Time Off - Planned | Leave | 2025-04 | 8
Abid Ali | PR-0013 | Time Off - Un Planned | Leave | 2024-10 | 1.5
Abid Ali | PR-0013 | Time Off - Un Planned | Leave | 2024-12 | 14
Abid Ali | PR-0013 | Time Off - Un Planned | Leave | 2025-04 | 1.5
Abid Ali | PR-0013 | Time Off - Un Planned | Leave | 2025-06 | 24
Abid Ali | Support and Maintenance | Time | Client Items | 2024-10 | 2
Abid Ali | Support and Maintenance | Time | Client Items | 2024-11 | 7
Abid Ali | Support and Maintenance | Time | Client Items | 2024-12 | 36
Abid Ali | Support and Maintenance | Time | Client Items | 2025-01 | 25
Abid Ali | Support and Maintenance | Time | Client Items | 2025-02 | 64.5
Abid Ali | Support and Maintenance | Time | Client Items | 2025-03 | 17.5
Abid Ali | Support and Maintenance | Time | Client Items | 2025-04 | 28
Abid Ali | Support and Maintenance | Time | Client Items | 2025-05 | 15
Abid Ali | Support and Maintenance | Time | Client Items | 2025-06 | 2
Abid Ali | Support and Maintenance | Time | Support Tickets | 2024-11 | 2
Abid Ali | Support and Maintenance | Time | Support Tickets | 2024-12 | 5
Abid Ali | Support and Maintenance | Time | Support Tickets | 2025-01 | 10.5
Abid Ali | Support and Maintenance | Time | Support Tickets | 2025-02 | 10
Abid Ali | Support and Maintenance | Time | Support Tickets | 2025-03 | 9
Abid Ali | Support and Maintenance | Time | Support Tickets | 2025-04 | 1.5
Abid Ali | Support and Maintenance | Time | Support Tickets | 2025-05 | 31
Abid Ali | Support and Maintenance | Time | Support Tickets | 2025-06 | 2
Aimen nasar | AD-0001 | Time | Meetings | 2025-04 | 2.5
Aimen nasar | NEXELUS 2025.2 | Enhance revise BO to allow consecutive IOs to merge into it | Bug Fixing | 2025-05 | 18
Aimen nasar | NEXELUS 2025.2 | Enhance revise BO to allow consecutive IOs to merge into it | Bug Fixing | 2025-06 | 9
Aimen nasar | NEXELUS 2025.2 | Enhance revise BO to allow consecutive IOs to merge into it | Development | 2025-05 | 20
Aimen nasar | NEXELUS 2025.2 | Enhance revise BO to allow consecutive IOs to merge into it | Task/Code Review | 2025-05 | 2
Aimen nasar | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Development | 2025-04 | 38
Aimen nasar | NEXELUS - ADDHOC ITEMS | Nexelus Vulnerability Report - 2025 | Research | 2025-05 | 18
Aimen nasar | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Bug Fixing | 2025-04 | 6
Aimen nasar | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Bug Fixing | 2025-05 | 2.5
Aimen nasar | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Development | 2025-05 | 6
Aimen nasar | NEXELUS 2025.2 | Allow manual adjustments for partial billing by the client | Development | 2025-04 | 0
Aimen nasar | NEXELUS 2025.2 | Allow switching media plan from Media Plan UI | Bug Fixing | 2025-06 | 7
Aimen nasar | NEXELUS 2025.2 | DENTSU CHANGES: Enhance Close Job functionality | Development | 2025-05 | 15
Aimen nasar | NEXELUS 2025.2 | Display Vendor distribution for individual client line under | Bug Fixing | 2025-04 | 7
Aimen nasar | NEXELUS 2025.2 | Display Vendor distribution for individual client line under | Bug Fixing | 2025-05 | 1
Aimen nasar | NEXELUS 2025.2 | Display Vendor distribution for individual client line under | Development | 2025-04 | 30
Aimen nasar | NEXELUS 2025.2 | iPC Selfservices: UI optimization | Development | 2025-04 | 12
Aimen nasar | NEXELUS 2025.2 | iPC Selfservices: UI optimization | Development | 2025-05 | 6
Aimen nasar | NEXELUS 2025.2 | Net Media + Ad serving Added to Media Spend under Campaign | Bug Fixing | 2025-05 | 1
Aimen nasar | NEXELUS 2025.2 | Project Overhead | Research | 2025-05 | 10.5
Aimen nasar | NEXELUS 2025.2 | Project Overhead | Research | 2025-06 | 9
Aimen nasar | NEXELUS 2025.2 | Provide an option to include AdTech Fee in a separate invoice | Bug Fixing | 2025-06 | 2
Aimen nasar | NEXELUS 2025.2 | Provide an option to include AdTech Fee in a separate invoice | Design | 2025-06 | 10
Aimen nasar | NEXELUS 2025.2 | Provide an option to include AdTech Fee in a separate invoice | Development | 2025-06 | 7
Aimen nasar | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Bug Fixing | 2025-05 | 3.5
Aimen nasar | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Bug Fixing | 2025-06 | 20.5
Aimen nasar | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Development | 2025-05 | 14
Aimen nasar | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Testing | 2025-05 | 6
Aimen nasar | PR-0013 | Development of new project/assignment/task | Analysis | 2025-04 | 14
Aimen nasar | PR-0013 | Development of new project/assignment/task | Development | 2025-05 | 6
Aimen nasar | PR-0013 | Document review/understanding Requirement Specifications | Analysis | 2025-04 | 3
Aimen nasar | PR-0013 | In-house Training | Training | 2025-04 | 17.5
Aimen nasar | PR-0013 | In-house Training | Training | 2025-05 | 8
Aimen nasar | PR-0013 | Internal Meetings | Bug Fixing | 2025-06 | 2
Aimen nasar | PR-0013 | Internal Meetings | Meetings | 2025-04 | 1
Aimen nasar | PR-0013 | Internal Meetings | Meetings | 2025-05 | 14.5
Aimen nasar | PR-0013 | Internal Meetings | Meetings | 2025-06 | 7
Aimen nasar | PR-0013 | Time Off - Un Planned | Leave | 2025-04 | 8
Ali Junaid | AD-0001 | Meetings | Meetings | 2025-03 | 1
Ali Junaid | APWORKS 2024.2 PHASE 5 | PlusCo - Change requests | Bug Fixing | 2025-01 | 16
Ali Junaid | APWORKS 2024.2 PHASE 5 | PlusCo - Change requests | Bug Fixing | 2025-02 | 64
Ali Junaid | APWORKS 2024.2 PHASE 5 | PlusCo - Change requests | Development | 2025-02 | 48
Ali Junaid | APWORKS 2025.1 | Don't refresh dashboard on Mapping dialog Close button action | Bug Fixing | 2025-03 | 0
Ali Junaid | APWORKS 2025.1 | Don't refresh dashboard on Mapping dialog Close button action | Development | 2025-03 | 1
Ali Junaid | APWORKS 2025.1 | Invoice UI: Invoice Preview Zoom Feature | Bug Fixing | 2025-03 | 0
Ali Junaid | APWORKS 2025.1 | Invoice UI: Invoice Preview Zoom Feature | Development | 2025-02 | 8
Ali Junaid | APWORKS 2025.1 | Invoice UI: Invoice Preview Zoom Feature | Development | 2025-03 | 7
Ali Junaid | APWORKS 2025.1 | Project Overhead | Project Mgmt | 2025-03 | 7
Ali Junaid | APWORKS 2025.1 | R&D on dashboard optimization. | Research | 2025-03 | 7
Ali Junaid | APWORKS 2025.1 | User Management UI updates | Bug Fixing | 2025-03 | 0
Ali Junaid | APWORKS 2025.1 | User Management UI updates | Development | 2025-03 | 13
Ali Junaid | APWORKS 2025.1 | Vendor Mapping: Allow User to Date Format | Development | 2025-02 | 16
Ali Junaid | APWORKS 2025.1 | Vendor Mapping: Allow User to Date Format | Testing | 2025-02 | 16
Ali Junaid | APWORKS 2025.2 | Ability to Approve the invoice when resolving discrepancy | Bug Fixing | 2025-05 | 6
Ali Junaid | APWORKS 2025.2 | Ability to Approve the invoice when resolving discrepancy | Development | 2025-04 | 20
Ali Junaid | APWORKS 2025.2 | Ability to Approve the invoice when resolving discrepancy | Development | 2025-05 | 3
Ali Junaid | APWORKS 2025.2 | Ability to create templates across multiple Companies | Bug Fixing | 2025-05 | 2
Ali Junaid | APWORKS 2025.2 | Credit Memo | Development | 2025-04 | 22
Ali Junaid | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Analysis | 2025-03 | 12
Ali Junaid | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Bug Fixing | 2025-03 | 0
Ali Junaid | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Bug Fixing | 2025-04 | 4
Ali Junaid | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Bug Fixing | 2025-05 | 37
Ali Junaid | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Development | 2025-03 | 41
Ali Junaid | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Development | 2025-04 | 9
Ali Junaid | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Development | 2025-05 | 54.5
Ali Junaid | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Testing | 2025-03 | 9
Ali Junaid | APWORKS 2025.2 | Project Overhead | Meetings | 2025-03 | 2
Ali Junaid | APWORKS 2025.2 | Project Overhead | No Workbench | 2025-03 | 7
Ali Junaid | APWORKS 2025.2 | Project Overhead | Post_dep_fixes | 2025-05 | 12
Ali Junaid | APWORKS 2025.2 | Project Overhead | Project Mgmt | 2025-03 | 3
Ali Junaid | APWORKS 2025.2 | Project Overhead | Research | 2025-05 | 18
Ali Junaid | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Analysis | 2025-04 | 6
Ali Junaid | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Bug Fixing | 2025-05 | 12
Ali Junaid | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Development | 2025-03 | 7
Ali Junaid | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Development | 2025-04 | 82
Ali Junaid | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Development | 2025-05 | 8
Ali Junaid | APWORKS 2025.2 | Standardize the Status in Dashboard vs reports | Development | 2025-03 | 3
Ali Junaid | APWORKS 2025.2 SP1 | APWorks amounts - format to 2 decimal places | Bug Fixing | 2025-06 | 1
Ali Junaid | APWORKS 2025.2 SP1 | APWorks amounts - format to 2 decimal places | Development | 2025-06 | 24
Ali Junaid | APWORKS 2025.2 SP1 | For "No filter' all data not getting shown | Development | 2025-06 | 9
Ali Junaid | APWORKS 2025.2 SP1 | Maintenance page creation | Development | 2025-05 | 9
Ali Junaid | APWORKS 2025.2 SP1 | Maintenance page creation | Development | 2025-06 | 4
Ali Junaid | APWORKS 2025.2 SP1 | Make date fields editable for Broadcast | Development | 2025-06 | 2
Ali Junaid | APWORKS 2025.2 SP1 | Manage invoice list optimization | Bug Fixing | 2025-06 | 1
Ali Junaid | APWORKS 2025.2 SP1 | Manage invoice list optimization | Development | 2025-05 | 4
Ali Junaid | APWORKS 2025.2 SP1 | Manage invoice list optimization | Research | 2025-06 | 8
Ali Junaid | APWORKS 2025.2 SP1 | Project Overhead | Research | 2025-06 | 7
Ali Junaid | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Development | 2025-06 | 6.5
Ali Junaid | PR-0013 | Gazetted holidays | Leave | 2025-03 | 8
Ali Junaid | PR-0013 | Gazetted holidays | Leave | 2025-04 | 16
Ali Junaid | PR-0013 | Gazetted holidays | Leave | 2025-05 | 8
Ali Junaid | PR-0013 | Gazetted holidays | Leave | 2025-06 | 16
Ali Junaid | PR-0013 | In-house Training | Analysis | 2025-03 | 7
Ali Junaid | PR-0013 | In-house Training | Training | 2025-01 | 72
Ali Junaid | PR-0013 | In-house Training | Training | 2025-03 | 6
Ali Junaid | PR-0013 | In-house Training | Training | 2025-04 | 20
Ali Junaid | PR-0013 | In-house Training | Training | 2025-05 | 5
Ali Junaid | PR-0013 | In-house Training | Training | 2025-06 | 2.5
Ali Junaid | PR-0013 | Internal Meetings | Meetings | 2025-04 | 1
Ali Junaid | Support and Maintenance | Time | Client Items | 2025-05 | 10
Ali Junaid | Support and Maintenance | Time | Client Items | 2025-06 | 17
Anees Rahman | NEXELUS 2024.2 | Support Items | Client Items | 2024-08 | 81
Anees Rahman | NEXELUS 2024.2 | Support Items | Client Items | 2024-09 | 145
Anees Rahman | NEXELUS 2024.2 | Support Items | Client Items | 2024-10 | 148
Anees Rahman | NEXELUS 2024.2 | Support Items | Client Items | 2024-11 | 61
Anees Rahman | NEXELUS 2024.2 | Support Items | Deployment | 2024-08 | 6.5
Anees Rahman | NEXELUS 2024.2 | Support Items | Other | 2024-08 | 36
Anees Rahman | Support and Maintenance | Time | Client Items | 2025-02 | 16
Anees Rahman | Support and Maintenance | Time | Support Tickets | 2024-11 | 88
Anees Rahman | Support and Maintenance | Time | Support Tickets | 2024-12 | 184
Anees Rahman | Support and Maintenance | Time | Support Tickets | 2025-01 | 184
Anees Rahman | Support and Maintenance | Time | Support Tickets | 2025-02 | 144
Anees Rahman | Support and Maintenance | Time | Support Tickets | 2025-03 | 150
Anees Rahman | Support and Maintenance | Time | Support Tickets | 2025-04 | 182
Anees Rahman | Support and Maintenance | Time | Support Tickets | 2025-05 | 56
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Development | 2024-09 | 6
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Associate vendor/stations/sites to multiple pay to | Development | 2024-09 | 2
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Associate vendor/stations/sites to multiple pay to | Development | 2024-11 | 4.5
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: EDI File Processing | Bug Fixing | 2024-11 | 5.5
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: EDI File Processing | Development | 2024-09 | 10.5
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: EDI File Processing | Development | 2024-10 | 13
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Customer Information: Select Client on Vendor Invoice | Development | 2024-10 | 4
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Enhancement in vendor mapping(Parse Table) | Bug Fixing | 2024-10 | 4
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Enhancement in vendor mapping(Parse Table) | Bug Fixing | 2024-12 | 12
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Enhancement in vendor mapping(Parse Table) | Development | 2024-11 | 19
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Enhancement in vendor mapping(Parse Table) | Development | 2024-12 | 13.5
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Development | 2024-09 | 2
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Project Overhead | Analysis | 2024-09 | 4
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Project Overhead | Deployment | 2024-10 | 15
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Vendor/stations/sites associated to multiple pay to. | Bug Fixing | 2024-11 | 3
Arif Khan Arif | APWORKS 2024.2 - PHASE 3 | Vendor/stations/sites associated to multiple pay to. | Development | 2024-10 | 8
Arif Khan Arif | APWORKS 2024.2 - PHASE 4 | Approval routing | Bug Fixing | 2024-12 | 7
Arif Khan Arif | APWORKS 2024.2 - PHASE 4 | Approval routing | Development | 2025-01 | 13.5
Arif Khan Arif | APWORKS 2024.2 - PHASE 4 | Deadlock issue | Development | 2025-01 | 4.5
Arif Khan Arif | APWORKS 2024.2 - PHASE 4 | EDI file updating and upload | Development | 2024-12 | 5
Arif Khan Arif | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Approvals | Development | 2025-01 | 16
Arif Khan Arif | APWORKS 2024.2 - PHASE 4 | Production: Project should be available on summary as well. | Development | 2024-11 | 3.5
Arif Khan Arif | APWORKS 2024.2 - PHASE 4 | Tax implementation(rule)/column for difference | Development | 2025-01 | 4.5
Arif Khan Arif | APWORKS 2025.1 | Vendor Mapping: Allow User to Date Format | Bug Fixing | 2025-03 | 2.5
Arif Khan Arif | APWORKS 2025.1 | Vendor Mapping: Allow User to Date Format | Development | 2025-03 | 11.5
Arif Khan Arif | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Task/Code Review | 2025-04 | 2
Arif Khan Arif | APWORKS 2025.2 | Credit Memo | SRS-Review | 2025-04 | 1.5
Arif Khan Arif | APWORKS 2025.2 | Credit Memo | SRS-Review | 2025-05 | 3.5
Arif Khan Arif | APWORKS 2025.2 | Credit Memo | Task/Code Review | 2025-04 | 1
Arif Khan Arif | APWORKS 2025.2 | Credit Memo | Task/Code Review | 2025-05 | 1
Arif Khan Arif | APWORKS 2025.2 | Display client #, when inv is linked to IO in all UIs and Report | Analysis | 2025-04 | 1
Arif Khan Arif | APWORKS 2025.2 | Display client #, when inv is linked to IO in all UIs and Report | Task/Code Review | 2025-04 | 1
Arif Khan Arif | NEXELUS 2025.2 | Enhance revise BO to allow consecutive IOs to merge into it | Bug Fixing | 2025-05 | 2
Arif Khan Arif | NEXELUS 2025.2 | Enhance revise BO to allow consecutive IOs to merge into it | Bug Fixing | 2025-06 | 4
Arif Khan Arif | NEXELUS 2025.2 | Enhance revise BO to allow consecutive IOs to merge into it | Development | 2025-05 | 11
Arif Khan Arif | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Development | 2025-03 | 2
Arif Khan Arif | APWORKS 2025.2 | Project Overhead | Post_dep_fixes | 2025-04 | 2
Arif Khan Arif | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Development | 2025-04 | 7
Arif Khan Arif | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Development | 2025-05 | 2
Arif Khan Arif | APWORKS 2025.2 | Split invoice by MOS - Print / OOH / Digital | Task/Code Review | 2025-04 | 1
Arif Khan Arif | APWORKS 2025.2 | Split invoice by MOS - Print / OOH / Digital | Task/Code Review | 2025-05 | 1
Arif Khan Arif | APWORKS 2025.2 SP1 | For "No filter' all data not getting shown | Development | 2025-06 | 2
Arif Khan Arif | APWORKS PHASE2 | Internal Meetings | Meetings | 2024-09 | 4
Arif Khan Arif | APWORKS PHASE2 | Meetings, mails, communication, TFS, Interviews | No Workbench | 2024-09 | 4
Arif Khan Arif | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-09 | 22
Arif Khan Arif | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-11 | 4.5
Arif Khan Arif | APWORKS PHASE2 | Session with US team | Analysis | 2025-01 | 1
Arif Khan Arif | APWORKS PHASE2 | Support Items | Development | 2025-01 | 2
Arif Khan Arif | APWORKS PHASE2 | Time Off - Planned | Leave | 2024-09 | 8
Arif Khan Arif | NEXELUS 2024.1 SP2 | AdTech Fee commission | Development | 2024-12 | 20
Arif Khan Arif | NEXELUS 2024.1 SP2 | AdTech Fee commission | Development | 2025-01 | 6
Arif Khan Arif | NEXELUS 2024.1 SP2 | Backup Table for vendor/client lines relationship | Development | 2024-10 | 3
Arif Khan Arif | NEXELUS 2024.1 SP2 | Billing by Media Type | Bug Fixing | 2024-11 | 7.5
Arif Khan Arif | NEXELUS 2024.1 SP2 | Billing by Media Type | Bug Fixing | 2024-12 | 3.5
Arif Khan Arif | NEXELUS 2024.1 SP2 | Billing by Media Type | Development | 2024-12 | 9
Arif Khan Arif | NEXELUS 2024.1 SP2 | Billing by Media Type | Development | 2025-01 | 9
Arif Khan Arif | NEXELUS 2024.1 SP2 | Client Profile: Media > Flag to make the vendor inactive | Development | 2024-11 | 4.5
Arif Khan Arif | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Development | 2024-11 | 3.5
Arif Khan Arif | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Development | 2024-12 | 7
Arif Khan Arif | NEXELUS 2024.1 SP2 | Restrict Self Approval - Time and expense | Development | 2024-12 | 2
Arif Khan Arif | NEXELUS 2024.1 SP2 | Restrict Self Approval - Time and expense | Development | 2025-01 | 3
Arif Khan Arif | NEXELUS 2024.2 | Analysis of production issues reported by support team | Analysis | 2024-09 | 2
Arif Khan Arif | NEXELUS 2024.2 | Analysis of production issues reported by support team | Other | 2024-08 | 12
Arif Khan Arif | NEXELUS 2024.2 | Client Items | Other | 2024-08 | 8
Arif Khan Arif | NEXELUS 2024.2 | Development of new project/assignment/task | Bug Fixing | 2024-08 | 4.5
Arif Khan Arif | NEXELUS 2024.2 | Development of new project/assignment/task | Other | 2024-08 | 32.5
Arif Khan Arif | NEXELUS 2024.2 | Internal Meetings | Leave | 2024-08 | 1
Arif Khan Arif | NEXELUS 2024.2 | Internal Meetings | Other | 2024-08 | 12
Arif Khan Arif | NEXELUS 2024.2 | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 14.5
Arif Khan Arif | NEXELUS 2024.2 | Meetings, mails, communication, TFS, Interviews | Testing | 2024-08 | 1
Arif Khan Arif | NEXELUS 2024.2 | National Gazetted Holidays | Other | 2024-08 | 8
Arif Khan Arif | NEXELUS 2024.2 | Session with US team | Other | 2024-08 | 1
Arif Khan Arif | NEXELUS 2024.2 | Support Items | Documentation | 2024-08 | 2
Arif Khan Arif | NEXELUS 2024.2 | Support Items | Other | 2024-08 | 7.5
Arif Khan Arif | NEXELUS 2025.1 | Import/exports flights | Bug Fixing | 2025-03 | 1
Arif Khan Arif | NEXELUS 2025.1 | Import/exports flights | Development | 2025-03 | 5
Arif Khan Arif | NEXELUS 2025.1 | Margin change for TTD | Bug Fixing | 2025-03 | 4
Arif Khan Arif | NEXELUS 2025.1 | Margin change for TTD | Development | 2025-03 | 16
Arif Khan Arif | NEXELUS 2025.1 SP1 | Project Overhead | Post_dep_fixes | 2025-03 | 2
Arif Khan Arif | NEXELUS 2025.2 | Alerting users when an FX rate is unavailable to prevent the | Development | 2025-04 | 5
Arif Khan Arif | NEXELUS 2025.2 | Alerting users when an FX rate is unavailable to prevent the | Development | 2025-05 | 12
Arif Khan Arif | NEXELUS 2025.2 | Display Vendor distribution for individual client line under | Development | 2025-04 | 1
Arif Khan Arif | NEXELUS 2025.2 | Exchange rate changes | Bug Fixing | 2025-05 | 5.5
Arif Khan Arif | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Bug Fixing | 2025-06 | 12
Arif Khan Arif | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Development | 2025-03 | 12
Arif Khan Arif | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Development | 2025-04 | 4.5
Arif Khan Arif | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Development | 2025-05 | 9.5
Arif Khan Arif | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Development | 2025-06 | 21
Arif Khan Arif | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Testing | 2025-04 | 2.5
Arif Khan Arif | NEXELUS 2025.2 | Project Overhead | Post_dep_fixes | 2025-04 | 9.5
Arif Khan Arif | NEXELUS 2025.2 | Project Overhead | Post_dep_fixes | 2025-05 | 10.5
Arif Khan Arif | NEXELUS 2025.2 | Provide an option to include AdTech Fee in a separate invoice | Development | 2025-04 | 7.5
Arif Khan Arif | NEXELUS 2025.2 | Provide an option to include AdTech Fee in a separate invoice | Development | 2025-05 | 9.5
Arif Khan Arif | NEXELUS 2025.2 | Provide an option to include AdTech Fee in a separate invoice | Development | 2025-06 | 1
Arif Khan Arif | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Analysis | 2025-04 | 3
Arif Khan Arif | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Analysis | 2025-05 | 6
Arif Khan Arif | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Bug Fixing | 2025-05 | 5.5
Arif Khan Arif | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Development | 2025-06 | 5
Arif Khan Arif | NEXELUS SUPPORT | Maintenance Activity | Support Tickets | 2024-12 | 1.5
Arif Khan Arif | PR-0013 | Client Items | Development | 2025-01 | 13.5
Arif Khan Arif | PR-0013 | Development of new project/assignment/task | Bug Fixing | 2024-09 | 35
Arif Khan Arif | PR-0013 | Development of new project/assignment/task | Bug Fixing | 2024-10 | 10
Arif Khan Arif | PR-0013 | Development of new project/assignment/task | Bug Fixing | 2024-11 | 6
Arif Khan Arif | PR-0013 | Development of new project/assignment/task | Client Items | 2024-10 | 63
Arif Khan Arif | PR-0013 | Development of new project/assignment/task | Client Items | 2024-11 | 5
Arif Khan Arif | PR-0013 | Gazetted holidays | Leave | 2025-03 | 8
Arif Khan Arif | PR-0013 | Gazetted holidays | Leave | 2025-04 | 16
Arif Khan Arif | PR-0013 | Gazetted holidays | Leave | 2025-05 | 8
Arif Khan Arif | PR-0013 | Gazetted holidays | Leave | 2025-06 | 16
Arif Khan Arif | PR-0013 | In-house Training | Training | 2025-03 | 17.5
Arif Khan Arif | PR-0013 | In-house Training | Training | 2025-04 | 14.5
Arif Khan Arif | PR-0013 | In-house Training | Training | 2025-05 | 10.5
Arif Khan Arif | PR-0013 | Internal Meetings | Development | 2024-09 | 11
Arif Khan Arif | PR-0013 | Internal Meetings | Development | 2024-10 | 3
Arif Khan Arif | PR-0013 | Internal Meetings | Meetings | 2025-04 | 25
Arif Khan Arif | PR-0013 | Internal Meetings | Meetings | 2025-05 | 29
Arif Khan Arif | PR-0013 | Internal Meetings | Meetings | 2025-06 | 11
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Analysis | 2024-09 | 7.5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Analysis | 2024-10 | 23
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Analysis | 2024-11 | 64
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Analysis | 2024-12 | 18.5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Development | 2024-12 | 55
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Development | 2025-01 | 84.5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Development | 2025-02 | 42.5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-10 | 21.5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-11 | 1.5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2025-02 | 16
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2025-03 | 20
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2025-04 | 15.5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2025-05 | 3.5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2025-06 | 2
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | No Workbench | 2024-10 | 7.5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | No Workbench | 2024-12 | 1.5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Project Mgmt | 2025-03 | 9.5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Project Mgmt | 2025-04 | 9.5
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Project Mgmt | 2025-05 | 13
Arif Khan Arif | PR-0013 | Meetings, mails, communication, TFS, Interviews | Project Mgmt | 2025-06 | 4.5
Arif Khan Arif | PR-0013 | Production upgrades | Deployment | 2025-01 | 6
Arif Khan Arif | PR-0013 | Production upgrades | Development | 2024-09 | 5
Arif Khan Arif | PR-0013 | Session with US team | Analysis | 2024-09 | 3
Arif Khan Arif | PR-0013 | Session with US team | Meetings | 2025-01 | 0.5
Arif Khan Arif | PR-0013 | Session with US team | Meetings | 2025-02 | 1.5
Arif Khan Arif | PR-0013 | Time Off - Planned | Leave | 2024-12 | 8
Arif Khan Arif | PR-0013 | Time Off - Planned | Leave | 2025-02 | 8
Arif Khan Arif | PR-0013 | Time Off - Un Planned | Analysis | 2024-11 | 20.5
Arif Khan Arif | PR-0013 | Time Off - Un Planned | Leave | 2024-12 | 8
Arif Khan Arif | PR-0013 | Time Off - Un Planned | Leave | 2025-02 | 16
Arif Khan Arif | PR-0013 | Time Off - Un Planned | Leave | 2025-03 | 9.5
Arif Khan Arif | PR-0013 | Time Off - Un Planned | Leave | 2025-04 | 13.5
Arif Khan Arif | PR-0013 | Time Off - Un Planned | No Workbench | 2024-09 | 43
Arif Khan Arif | PR-0013 | Time Off - Un Planned | No Workbench | 2024-10 | 8
Arif Khan Arif | Support and Maintenance | Time | Client Items | 2024-10 | 2
Arif Khan Arif | Support and Maintenance | Time | Client Items | 2024-11 | 4.5
Arif Khan Arif | Support and Maintenance | Time | Client Items | 2025-01 | 22
Arif Khan Arif | Support and Maintenance | Time | Client Items | 2025-02 | 87.5
Arif Khan Arif | Support and Maintenance | Time | Client Items | 2025-03 | 15.5
Arif Khan Arif | Support and Maintenance | Time | Client Items | 2025-04 | 22
Arif Khan Arif | Support and Maintenance | Time | Client Items | 2025-05 | 36.5
Arif Khan Arif | Support and Maintenance | Time | Client Items | 2025-06 | 25
Arif Khan Arif | Support and Maintenance | Time | Support Tickets | 2025-01 | 14
Arif Khan Arif | Support and Maintenance | Time | Support Tickets | 2025-03 | 19.75
Arif Khan Arif | Support and Maintenance | Time | Support Tickets | 2025-04 | 12
Arshad Sadal | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: EDI File Processing | Research | 2024-08 | 11
Arslan Khalid | AP WORKFLOW | Analysis of the new project/assignment/task | Other | 2024-08 | 12
Arslan Khalid | AP WORKFLOW | Development of new project/assignment/task | Other | 2024-08 | 67
Arslan Khalid | AP WORKFLOW | Regular bug fixing activity | Bug Fixing | 2024-11 | 3
Arslan Khalid | AP WORKFLOW | Regular bug fixing activity | Bug Fixing | 2024-12 | 22
Arslan Khalid | AP WORKFLOW | Regular bug fixing activity | Other | 2024-08 | 9
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Bug Fixing | 2024-10 | 13
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Bug Fixing | 2024-11 | 14
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Apply discount based on Payment terms settings | Bug Fixing | 2024-10 | 4
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Apply discount based on Payment terms settings | Bug Fixing | 2024-11 | 8
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Associate vendor/stations/sites to multiple pay to | Bug Fixing | 2024-10 | 10
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Associate vendor/stations/sites to multiple pay to | Bug Fixing | 2024-11 | 3
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Associate vendor/stations/sites to multiple pay to | Design | 2024-09 | 3
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Associate vendor/stations/sites to multiple pay to | Development | 2024-09 | 21
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Associate vendor/stations/sites to multiple pay to | Development | 2024-10 | 12
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Associate vendor/stations/sites to multiple pay to | Task/Code Review | 2024-10 | 1
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: EDI File Processing | Development | 2024-10 | 5
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: Invoice View UI | Bug Fixing | 2024-10 | 3
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: Invoice View UI | Bug Fixing | 2024-11 | 5
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: Invoice View UI | Development | 2024-09 | 16
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: Invoice View UI | Development | 2024-10 | 2
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: Invoice View UI | Development | 2024-11 | 6
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: Manage Invoice Documents | Development | 2024-09 | 2
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: Manage Invoice Documents | Development | 2024-10 | 4
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: Manage Invoice Models List | Development | 2024-09 | 2
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: Manage Non-Mapped Broadcast Invoices | Development | 2024-09 | 2
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: User Group Management Changes | Development | 2024-09 | 4
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Customer Information: Select Client on Vendor Invoice | Analysis | 2024-10 | 2
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Customer Information: Select Client on Vendor Invoice | Bug Fixing | 2024-10 | 5
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Customer Information: Select Client on Vendor Invoice | Bug Fixing | 2024-11 | 3
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Customer Information: Select Client on Vendor Invoice | Design | 2024-10 | 6
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Customer Information: Select Client on Vendor Invoice | Development | 2024-10 | 25
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Invoice Editing: Make the tax editable | Development | 2024-11 | 10
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Invoice Editing: Make the tax editable | Testing | 2024-11 | 1
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Master Data: Payment Terms | Development | 2024-10 | 0
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Remove Site column from vendor lookup | Bug Fixing | 2024-11 | 3
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Remove Site column from vendor lookup | Development | 2024-11 | 3
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Route invoice from one company - company identification | Analysis | 2024-10 | 1
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Route invoice from one company - company identification | Bug Fixing | 2024-10 | 9
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Route invoice from one company - company identification | Development | 2024-10 | 14
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | separate node for "Broadcast Invoices" | Development | 2024-09 | 8
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Analysis | 2024-10 | 3
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Bug Fixing | 2024-10 | 4
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Design | 2024-10 | 13
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Development | 2024-10 | 9
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Vendor Map: Vendor Popup: Remove identifier currency filter | Analysis | 2024-11 | 6
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Vendor Map: Vendor Popup: Remove identifier currency filter | Bug Fixing | 2024-11 | 2
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Vendor Map: Vendor Popup: Remove identifier currency filter | Development | 2024-11 | 5
Arslan Khalid | APWORKS 2024.2 - PHASE 3 | Vendor/stations/sites associated to multiple pay to. | Bug Fixing | 2024-10 | 2
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Apply variable name for Site in vendor mapping | Development | 2024-11 | 8
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Apply variable name for Site in vendor mapping | Testing | 2024-12 | 2
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Approval routing | Analysis | 2024-11 | 2
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Approval routing | Analysis | 2024-12 | 1
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Approval routing | Bug Fixing | 2024-12 | 6
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Approval routing | Development | 2024-11 | 35
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Approval routing | Development | 2024-12 | 27
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Approval routing | Testing | 2024-11 | 0.5
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Approval routing | Testing | 2024-12 | 4
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Media Type Identification for IOs. | Analysis | 2025-01 | 4
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Media Type Identification for IOs. | Development | 2025-01 | 14
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Production: Project should be available on summary as well. | Development | 2024-11 | 8
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Project Overhead | Meetings | 2024-11 | 3
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Report >> Vendor Invoices: we need the discount field to show up | Bug Fixing | 2024-12 | 1
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Report >> Vendor Invoices: we need the discount field to show up | Development | 2024-12 | 4
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Tax implementation(rule)/column for difference | Development | 2025-01 | 38
Arslan Khalid | APWORKS 2024.2 - PHASE 4 | Vendor mapping enhancement for Non-media | Development | 2024-12 | 5
Arslan Khalid | APWORKS 2024.2 PHASE 5 | Google Drive Setup (company configuration UI) | Analysis | 2024-12 | 4
Arslan Khalid | APWORKS 2024.2 PHASE 5 | Google Drive Setup (company configuration UI) | Development | 2024-12 | 10
Arslan Khalid | APWORKS 2025.1 | Add client column on Discrepant Gadget | Development | 2025-03 | 3
Arslan Khalid | APWORKS 2025.1 | Vendor Mapping: Allow User to Date Format | Bug Fixing | 2025-03 | 6
Arslan Khalid | APWORKS 2025.1 | Vendor Mapping: Allow User to Date Format | Development | 2025-02 | 20
Arslan Khalid | APWORKS 2025.1 | Vendor Mapping: Allow User to Date Format | Development | 2025-03 | 8
Arslan Khalid | APWORKS 2025.1 | Vendor Mapping: Allow User to Date Format | Testing | 2025-03 | 4
Arslan Khalid | APWORKS 2025.2 | Ability to create templates across multiple Companies | Analysis | 2025-04 | 2
Arslan Khalid | APWORKS 2025.2 | Ability to create templates across multiple Companies | Bug Fixing | 2025-05 | 23.75
Arslan Khalid | APWORKS 2025.2 | Ability to create templates across multiple Companies | Development | 2025-04 | 69.25
Arslan Khalid | APWORKS 2025.2 | Ability to create templates across multiple Companies | Development | 2025-05 | 7.5
Arslan Khalid | APWORKS 2025.2 | Ability to create templates across multiple Companies | Meetings | 2025-04 | 11.5
Arslan Khalid | APWORKS 2025.2 | Ability to create templates across multiple Companies | Meetings | 2025-05 | 12
Arslan Khalid | APWORKS 2025.2 | Ability to create templates across multiple Companies | Task/Code Review | 2025-04 | 3
Arslan Khalid | APWORKS 2025.2 | Ability to create templates across multiple Companies | Testing | 2025-04 | 16.25
Arslan Khalid | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Analysis | 2025-03 | 2
Arslan Khalid | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Bug Fixing | 2025-05 | 7
Arslan Khalid | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Development | 2025-03 | 2
Arslan Khalid | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Development | 2025-04 | 10
Arslan Khalid | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Development | 2025-05 | 5
Arslan Khalid | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Testing | 2025-04 | 6
Arslan Khalid | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Testing | 2025-05 | 2.5
Arslan Khalid | APWORKS 2025.2 | Credit Memo | Task/Code Review | 2025-04 | 3
Arslan Khalid | APWORKS 2025.2 | Display client #, when inv is linked to IO in all UIs and Report | Bug Fixing | 2025-05 | 2
Arslan Khalid | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Bug Fixing | 2025-05 | 7
Arslan Khalid | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Meetings | 2025-05 | 1
Arslan Khalid | APWORKS 2025.2 | Project Overhead | No Workbench | 2025-04 | 1
Arslan Khalid | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Analysis | 2025-05 | 1
Arslan Khalid | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Bug Fixing | 2025-05 | 6
Arslan Khalid | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Development | 2025-05 | 15.25
Arslan Khalid | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Development | 2025-06 | 4
Arslan Khalid | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Meetings | 2025-05 | 11.25
Arslan Khalid | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Testing | 2025-05 | 8.25
Arslan Khalid | APWORKS 2025.2 | Standardize the Status in Dashboard vs reports | Development | 2025-05 | 2.5
Arslan Khalid | APWORKS 2025.2 SP1 | APWorks amounts - format to 2 decimal places | Development | 2025-06 | 4
Arslan Khalid | APWORKS 2025.2 SP1 | Make date fields editable for Broadcast | Bug Fixing | 2025-06 | 4
Arslan Khalid | APWORKS 2025.2 SP1 | Make date fields editable for Broadcast | Development | 2025-06 | 4
Arslan Khalid | APWORKS 2025.2 SP1 | Make date fields editable for Broadcast | Testing | 2025-06 | 6
Arslan Khalid | APWORKS 2025.2 SP1 | Split functionality enhancement. | Analysis | 2025-05 | 4.5
Arslan Khalid | APWORKS 2025.2 SP1 | Split functionality enhancement. | Analysis | 2025-06 | 3
Arslan Khalid | APWORKS 2025.2 SP1 | Split functionality enhancement. | Bug Fixing | 2025-06 | 10
Arslan Khalid | APWORKS 2025.2 SP1 | Split functionality enhancement. | Development | 2025-05 | 14.5
Arslan Khalid | APWORKS 2025.2 SP1 | Split functionality enhancement. | Development | 2025-06 | 7
Arslan Khalid | APWORKS 2025.2 SP1 | Split functionality enhancement. | Meetings | 2025-06 | 6.5
Arslan Khalid | APWORKS 2025.2 SP1 | Split functionality enhancement. | Testing | 2025-05 | 3
Arslan Khalid | APWORKS PHASE2 | Analysis of the new project/assignment/task | Development | 2024-09 | 6
Arslan Khalid | APWORKS PHASE2 | Development of new project/assignment/task | Other | 2024-08 | 46
Arslan Khalid | APWORKS PHASE2 | Meetings, mails, communication, TFS, Interviews | Client Items | 2024-08 | 3
Arslan Khalid | APWORKS PHASE2 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 3
Arslan Khalid | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-08 | 29
Arslan Khalid | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-09 | 79
Arslan Khalid | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-10 | 17
Arslan Khalid | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-11 | 4
Arslan Khalid | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-12 | 28.5
Arslan Khalid | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2025-01 | 46
Arslan Khalid | APWORKS PHASE2 | Regular bug fixing activity | Other | 2024-08 | 10
Arslan Khalid | NEXELUS 2025.1 | Project Overhead | No Workbench | 2025-03 | 6
Arslan Khalid | NEXELUS 2025.1 SP1 | TTD: Generate schedule based on Placement Flights | Development | 2025-03 | 13
Arslan Khalid | NEXELUS 2025.1 SP1 | TTD: Generate schedule based on Placement Flights | Task/Code Review | 2025-03 | 4
Arslan Khalid | NEXELUS 2025.1 SP1 | TTD: Generate schedule based on Placement Flights | Testing | 2025-03 | 3
Arslan Khalid | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Development | 2025-03 | 2
Arslan Khalid | NEXELUS 2025.2 | Allow switching media plan from Media Plan UI | Analysis | 2025-03 | 5
Arslan Khalid | NEXELUS 2025.2 | Allow switching media plan from Media Plan UI | Development | 2025-03 | 8
Arslan Khalid | NEXELUS 2025.2 | Allow switching media plan from Media Plan UI | Testing | 2025-03 | 3
Arslan Khalid | NEXELUS 2025.2 | Project Overhead | No Workbench | 2025-03 | 4
Arslan Khalid | PR-0013 | Client Items | Bug Fixing | 2024-12 | 3
Arslan Khalid | PR-0013 | Client Items | Client Items | 2024-12 | 12
Arslan Khalid | PR-0013 | Gazetted holidays | Leave | 2025-03 | 7
Arslan Khalid | PR-0013 | Gazetted holidays | Leave | 2025-04 | 14
Arslan Khalid | PR-0013 | Gazetted holidays | Leave | 2025-05 | 8
Arslan Khalid | PR-0013 | Gazetted holidays | Leave | 2025-06 | 16
Arslan Khalid | PR-0013 | In-house Training | Meetings | 2024-12 | 2.5
Arslan Khalid | PR-0013 | In-house Training | Training | 2024-12 | 5
Arslan Khalid | PR-0013 | In-house Training | Training | 2025-01 | 1
Arslan Khalid | PR-0013 | In-house Training | Training | 2025-03 | 29
Arslan Khalid | PR-0013 | In-house Training | Training | 2025-04 | 1
Arslan Khalid | PR-0013 | In-house Training | Training | 2025-06 | 1
Arslan Khalid | PR-0013 | Internal Meetings | Bug Fixing | 2024-10 | 0
Arslan Khalid | PR-0013 | Internal Meetings | Meetings | 2024-09 | 2
Arslan Khalid | PR-0013 | Internal Meetings | Meetings | 2024-10 | 14
Arslan Khalid | PR-0013 | Internal Meetings | Meetings | 2024-11 | 23.5
Arslan Khalid | PR-0013 | Internal Meetings | Meetings | 2024-12 | 26
Arslan Khalid | PR-0013 | Internal Meetings | Meetings | 2025-01 | 27.5
Arslan Khalid | PR-0013 | Internal Meetings | Meetings | 2025-02 | 11
Arslan Khalid | PR-0013 | Internal Meetings | Meetings | 2025-03 | 31
Arslan Khalid | PR-0013 | Internal Meetings | Meetings | 2025-04 | 17
Arslan Khalid | PR-0013 | Internal Meetings | Meetings | 2025-05 | 17
Arslan Khalid | PR-0013 | Internal Meetings | Meetings | 2025-06 | 7.95
Arslan Khalid | PR-0013 | Time Off - Planned | Leave | 2024-09 | 16
Arslan Khalid | PR-0013 | Time Off - Planned | Leave | 2024-12 | 8
Arslan Khalid | PR-0013 | Time Off - Planned | Leave | 2025-01 | 40
Arslan Khalid | PR-0013 | Time Off - Planned | Leave | 2025-02 | 88
Arslan Khalid | PR-0013 | Time Off - Planned | Leave | 2025-04 | 16
Arslan Khalid | PR-0013 | Time Off - Un Planned | Leave | 2024-09 | 4
Arslan Khalid | PR-0013 | Time Off - Un Planned | Leave | 2024-10 | 8
Arslan Khalid | PR-0013 | Time Off - Un Planned | Leave | 2024-11 | 10
Arslan Khalid | PR-0013 | Time Off - Un Planned | Leave | 2024-12 | 5
Arslan Khalid | PR-0013 | Time Off - Un Planned | Leave | 2025-03 | 7
Arslan Khalid | Support and Maintenance | Time | Client Items | 2025-02 | 41
Arslan Khalid | Support and Maintenance | Time | Client Items | 2025-04 | 2
Arslan Khalid | Support and Maintenance | Time | Client Items | 2025-05 | 11
Arslan Khalid | Support and Maintenance | Time | Support Tickets | 2025-05 | 4
Arslan Khalid | Support and Maintenance | Time | Support Tickets | 2025-06 | 15
Asad Mahmood | AD-0001 | Meetings | Meetings | 2024-11 | 13
Asad Mahmood | AD-0001 | Meetings | Meetings | 2024-12 | 42
Asad Mahmood | AD-0001 | Meetings | Meetings | 2025-01 | 53
Asad Mahmood | AD-0001 | Meetings | Meetings | 2025-02 | 23
Asad Mahmood | AD-0001 | Meetings | Meetings | 2025-03 | 26.5
Asad Mahmood | AD-0001 | Meetings | Meetings | 2025-04 | 18.5
Asad Mahmood | AD-0001 | Meetings | Meetings | 2025-05 | 23.5
Asad Mahmood | AD-0001 | Meetings | Meetings | 2025-06 | 3
Asad Mahmood | AP WORKFLOW | Analysis of production issues reported by support team | Other | 2024-08 | 2
Asad Mahmood | AP WORKFLOW | Analysis of the new project/assignment/task | Other | 2024-08 | 10
Asad Mahmood | AP WORKFLOW | Development of new project/assignment/task | Other | 2024-08 | 25
Asad Mahmood | AP WORKFLOW | Internal Meetings | Other | 2024-08 | 5
Asad Mahmood | AP WORKFLOW | Meetings, mails, communication, TFS, Interviews | Leave | 2024-11 | 8
Asad Mahmood | AP WORKFLOW | National Gazetted Holidays | Leave | 2024-09 | 8
Asad Mahmood | AP WORKFLOW | National Gazetted Holidays | Leave | 2024-12 | 8
Asad Mahmood | AP WORKFLOW | National Gazetted Holidays | Other | 2024-08 | 8
Asad Mahmood | AP WORKFLOW | Regular bug fixing activity | Bug Fixing | 2024-11 | 4
Asad Mahmood | AP WORKFLOW | Regular bug fixing activity | Bug Fixing | 2024-12 | 14
Asad Mahmood | AP WORKFLOW | Regular bug fixing activity | Other | 2024-08 | 46
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Bug Fixing | 2024-10 | 8
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Bug Fixing | 2024-11 | 12
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Development | 2024-10 | 31
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Development | 2024-11 | 4
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Testing | 2024-10 | 4
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: EDI File Processing | Development | 2024-10 | 2
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Google Drive - Split Process and show documents in queue | Bug Fixing | 2024-11 | 6
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Google Drive - Split Process and show documents in queue | Development | 2024-11 | 31
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Google Drive - Split Process and show documents in queue | Testing | 2024-11 | 3
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Bug Fixing | 2024-10 | 14
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Development | 2024-09 | 56
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Development | 2024-10 | 33
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Meetings | 2024-09 | 5
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Project Overhead | Post_dep_fixes | 2024-11 | 5
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Bug Fixing | 2024-10 | 8
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Bug Fixing | 2024-11 | 20
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Development | 2024-10 | 20
Asad Mahmood | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Testing | 2024-11 | 3
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Approve upto last level and auto post. | Development | 2024-11 | 8
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Approve upto last level and auto post. | Testing | 2024-11 | 1
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | EDI file updating and upload | Analysis | 2024-11 | 1
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | EDI file updating and upload | Development | 2024-11 | 11
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | EDI: Generate PDF - Updates | Development | 2025-01 | 34
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Import / Export lines | Design | 2025-01 | 2
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Import / Export lines | Development | 2024-12 | 6
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Invoice Scan | Development | 2024-11 | 12
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Invoice Scan | Development | 2024-12 | 40
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Invoice Scan | Testing | 2024-11 | 2
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Model List | Development | 2024-12 | 4
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Production: Auto populate lines based PO during scanning | Development | 2024-11 | 3
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Production: show keyvalue pairs for level2 mapping | Development | 2024-11 | 8
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Project Overhead | Analysis | 2024-12 | 2
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Project Overhead | Deployment | 2024-12 | 3
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Project Overhead | Deployment | 2025-01 | 3
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Project Overhead | Meetings | 2024-12 | 5
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Project Overhead | Post_dep_fixes | 2024-11 | 6
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Project Overhead | Post_dep_fixes | 2024-12 | 51
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Project Overhead | Post_dep_fixes | 2025-01 | 18
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Stamp multiple approvers. | Bug Fixing | 2024-11 | 1
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Stamp multiple approvers. | Development | 2024-11 | 8
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Stamp multiple approvers. | Testing | 2024-11 | 1
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Tax implementation(rule)/column for difference | Bug Fixing | 2025-01 | 4
Asad Mahmood | APWORKS 2024.2 - PHASE 4 | Tax implementation(rule)/column for difference | Development | 2025-01 | 8
Asad Mahmood | APWORKS 2024.2 PHASE 5 | Project Overhead | Post_dep_fixes | 2025-01 | 2
Asad Mahmood | APWORKS 2024.2 PHASE 5 | Vendor invoices report: Add date filters | Development | 2025-01 | 2
Asad Mahmood | APWORKS 2025.1 | Google Drive: Allow PDF in Attachment | Bug Fixing | 2025-03 | 5.5
Asad Mahmood | APWORKS 2025.1 | Google Drive: Allow PDF in Attachment | Development | 2025-02 | 6
Asad Mahmood | APWORKS 2025.1 | Google Drive: Allow PDF in Attachment | Development | 2025-03 | 1
Asad Mahmood | APWORKS 2025.1 | Google Drive: Allow PDF in Attachment | Testing | 2025-03 | 1
Asad Mahmood | APWORKS 2025.1 | Invoice UI: Invoice Preview Zoom Feature | Development | 2025-03 | 3
Asad Mahmood | APWORKS 2025.1 | Project Overhead | Deployment | 2025-03 | 1
Asad Mahmood | APWORKS 2025.1 | Project Overhead | No Workbench | 2025-03 | 10
Asad Mahmood | APWORKS 2025.1 | Project Overhead | Post_dep_fixes | 2025-03 | 2
Asad Mahmood | APWORKS 2025.1 | R&D on dashboard optimization. | Analysis | 2025-03 | 2
Asad Mahmood | APWORKS 2025.1 | Vendor Mapping: Allow User to Date Format | Analysis | 2025-03 | 3
Asad Mahmood | APWORKS 2025.1 | Vendor Mapping: Allow User to Date Format | Bug Fixing | 2025-03 | 1
Asad Mahmood | APWORKS 2025.1 | Vendor Mapping: Allow User to Date Format | Development | 2025-03 | 3
Asad Mahmood | APWORKS 2025.2 | Ability to create templates across multiple Companies | Meetings | 2025-04 | 2
Asad Mahmood | APWORKS 2025.2 | Credit Memo | Analysis | 2025-04 | 4
Asad Mahmood | APWORKS 2025.2 | Credit Memo | Bug Fixing | 2025-05 | 5
Asad Mahmood | APWORKS 2025.2 | Credit Memo | Development | 2025-04 | 11.5
Asad Mahmood | APWORKS 2025.2 | Credit Memo | Development | 2025-05 | 9
Asad Mahmood | APWORKS 2025.2 | Credit Memo | Meetings | 2025-04 | 9
Asad Mahmood | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Analysis | 2025-03 | 2
Asad Mahmood | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Bug Fixing | 2025-04 | 7
Asad Mahmood | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Development | 2025-03 | 28
Asad Mahmood | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Development | 2025-04 | 18
Asad Mahmood | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Meetings | 2025-04 | 5.5
Asad Mahmood | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Task/Code Review | 2025-04 | 2
Asad Mahmood | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Testing | 2025-03 | 12
Asad Mahmood | APWORKS 2025.2 | Project Overhead | Analysis | 2025-03 | 4
Asad Mahmood | APWORKS 2025.2 | Project Overhead | Deployment | 2025-04 | 3
Asad Mahmood | APWORKS 2025.2 | Project Overhead | Deployment | 2025-05 | 1
Asad Mahmood | APWORKS 2025.2 | Project Overhead | No Workbench | 2025-03 | 6.5
Asad Mahmood | APWORKS 2025.2 | Project Overhead | No Workbench | 2025-04 | 1
Asad Mahmood | APWORKS 2025.2 | Project Overhead | No Workbench | 2025-05 | 2
Asad Mahmood | APWORKS 2025.2 | Project Overhead | Post_dep_fixes | 2025-03 | 4
Asad Mahmood | APWORKS 2025.2 | Project Overhead | Post_dep_fixes | 2025-04 | 2
Asad Mahmood | APWORKS 2025.2 | Project Overhead | Post_dep_fixes | 2025-05 | 17
Asad Mahmood | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Meetings | 2025-04 | 2
Asad Mahmood | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Research | 2025-04 | 6
Asad Mahmood | APWORKS 2025.2 | Separate the financial integration API from the main application | Development | 2025-05 | 26
Asad Mahmood | APWORKS 2025.2 | Warren Lamb provided PDF ingestion | Analysis | 2025-04 | 5
Asad Mahmood | APWORKS 2025.2 | Warren Lamb provided PDF ingestion | Bug Fixing | 2025-05 | 5
Asad Mahmood | APWORKS 2025.2 | Warren Lamb provided PDF ingestion | Development | 2025-04 | 10
Asad Mahmood | APWORKS 2025.2 | Warren Lamb provided PDF ingestion | Development | 2025-05 | 16
Asad Mahmood | APWORKS 2025.2 | Warren Lamb provided PDF ingestion | Testing | 2025-05 | 13
Asad Mahmood | APWORKS 2025.2 SP2 | Partial posting in posting process for failed invoices into MO | Development | 2025-06 | 9
Asad Mahmood | APWORKS 2025.2 SP2 | Partial posting in posting process for failed invoices into MO | Meetings | 2025-06 | 3
Asad Mahmood | APWORKS 2025.2 SP2 | Partial posting in posting process for failed invoices into MO | Testing | 2025-06 | 2
Asad Mahmood | APWORKS PHASE2 | Analysis of production issues reported by support team | Testing | 2025-02 | 9
Asad Mahmood | APWORKS PHASE2 | Analysis of the new project/assignment/task | Analysis | 2025-01 | 6
Asad Mahmood | APWORKS PHASE2 | Dev Support | Bug Fixing | 2024-09 | 4
Asad Mahmood | APWORKS PHASE2 | Development of new project/assignment/task | Development | 2024-08 | 4
Asad Mahmood | APWORKS PHASE2 | Development of new project/assignment/task | Other | 2024-08 | 26
Asad Mahmood | APWORKS PHASE2 | Internal Meetings | Meetings | 2024-08 | 10
Asad Mahmood | APWORKS PHASE2 | Internal Meetings | Meetings | 2024-09 | 3
Asad Mahmood | APWORKS PHASE2 | National Gazetted Holidays | Leave | 2025-02 | 8
Asad Mahmood | APWORKS PHASE2 | Regular bug fixing activity | Analysis | 2025-01 | 3
Asad Mahmood | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-08 | 26
Asad Mahmood | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-09 | 63
Asad Mahmood | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-10 | 40
Asad Mahmood | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2025-01 | 45
Asad Mahmood | APWORKS PHASE2 | Regular bug fixing activity | Other | 2024-08 | 22
Asad Mahmood | APWORKS PHASE2 | Regular bug fixing activity | Testing | 2024-09 | 21
Asad Mahmood | APWORKS PHASE2 | Time Off - Planned | Leave | 2025-01 | 16
Asad Mahmood | PR-0013 | Gazetted holidays | Leave | 2025-03 | 8
Asad Mahmood | PR-0013 | Gazetted holidays | Leave | 2025-04 | 16
Asad Mahmood | PR-0013 | Gazetted holidays | Leave | 2025-05 | 8
Asad Mahmood | PR-0013 | Gazetted holidays | Leave | 2025-06 | 8
Asad Mahmood | PR-0013 | Time Off - Planned | Leave | 2024-09 | 8
Asad Mahmood | PR-0013 | Time Off - Planned | Leave | 2025-04 | 24
Asad Mahmood | PR-0013 | Time Off - Un Planned | Leave | 2024-10 | 24
Asad Mahmood | PR-0013 | Time Off - Un Planned | Leave | 2025-02 | 8
Asad Mahmood | PR-0013 | Time Off - Un Planned | Leave | 2025-04 | 3
Asad Mahmood | PR-0013 | Time Off - Un Planned | Leave | 2025-05 | 8
Asad Mahmood | PR-0013 | Time Off - Un Planned | Leave | 2025-06 | 24
Asad Mahmood | PR-0013 | Time Off - Un Planned | No Workbench | 2025-04 | 1
Asad Mahmood | Support and Maintenance | Time | Client Items | 2025-02 | 105
Asad Mahmood | Support and Maintenance | Time | Client Items | 2025-03 | 12
Asad Mahmood | Support and Maintenance | Time | Client Items | 2025-04 | 21
Asad Mahmood | Support and Maintenance | Time | Client Items | 2025-05 | 10.5
Asad Mahmood | Support and Maintenance | Time | Client Items | 2025-06 | 3
Asad Mahmood | Support and Maintenance | Time | Support Tickets | 2025-01 | 4
Asad Mahmood | Support and Maintenance | Time | Support Tickets | 2025-02 | 2
Asad Mahmood | Support and Maintenance | Time | Support Tickets | 2025-03 | 11.5
Asad Mahmood | Support and Maintenance | Time | Support Tickets | 2025-04 | 4.5
Asad Mahmood | Support and Maintenance | Time | Support Tickets | 2025-05 | 25
Asim Jameel | AD-0001 | Time | Admin | 2024-09 | 3
Asim Jameel | AD-0001 | Time | Leave | 2024-09 | 8
Asim Jameel | AD-0001 | Time | Meetings | 2024-08 | 1
Asim Jameel | AD-0001 | Time | Meetings | 2024-09 | 24.85
Asim Jameel | AD-0001 | Time | Meetings | 2024-10 | 22.5
Asim Jameel | AD-0001 | Time | Meetings | 2024-11 | 38.5
Asim Jameel | AD-0001 | Time | Meetings | 2025-01 | 8.25
Asim Jameel | AD-0001 | Time | Other | 2024-08 | 17.5
Asim Jameel | AD-0001 | Time | Project Mgmt | 2024-09 | 3.5
Asim Jameel | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Documentation | 2024-08 | 8
Asim Jameel | APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Documentation | 2024-08 | 8
Asim Jameel | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Documentation | 2024-08 | 11
Asim Jameel | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Documentation | 2024-09 | 15
Asim Jameel | APWORKS 2024.2 - PHASE 3 | Project Overhead | Analysis | 2024-08 | 8
Asim Jameel | APWORKS 2024.2 - PHASE 3 | Project Overhead | Meetings | 2024-10 | 6
Asim Jameel | APWORKS 2024.2 - PHASE 3 | Project Overhead | Meetings | 2024-11 | 11.5
Asim Jameel | APWORKS 2024.2 - PHASE 4 | Approval routing | Documentation | 2025-01 | 6
Asim Jameel | APWORKS PHASE2 | Requirement Specifications document writing | Documentation | 2024-09 | 18.5
Asim Jameel | NEXELUS 13.0 | Session with US team | Other | 2024-08 | 9.8
Asim Jameel | NEXELUS 2024.1 SP2 | Backup Table for vendor/client lines relationship | Development | 2025-01 | 4
Asim Jameel | NEXELUS 2024.1 SP2 | Billing by Media Type | Task/Code Review | 2025-01 | 3
Asim Jameel | NEXELUS 2024.1 SP2 | eConnect shell change to service | Testing | 2025-01 | 1.5
Asim Jameel | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Development | 2024-10 | 28
Asim Jameel | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Development | 2024-11 | 16
Asim Jameel | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Testing | 2024-11 | 5
Asim Jameel | NEXELUS 2024.1 SP2 | Project Overhead | Documentation | 2024-10 | 17
Asim Jameel | NEXELUS 2024.1 SP2 | Project Overhead | Documentation | 2024-11 | 25
Asim Jameel | NEXELUS 2024.1 SP2 | Project Overhead | Documentation | 2025-01 | 4
Asim Jameel | NEXELUS 2024.1 SP2 | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | Meetings | 2024-11 | 4.5
Asim Jameel | NEXELUS 2024.2 | Client Items | Other | 2024-08 | 6.5
Asim Jameel | NEXELUS 2024.2 | Development of new project/assignment/task | Other | 2024-08 | 30.5
Asim Jameel | NEXELUS 2024.2 | Document review/understanding Requirement Specifications | Documentation | 2024-09 | 17
Asim Jameel | NEXELUS 2024.2 | Internal Meetings | Other | 2024-08 | 7.1
Asim Jameel | NEXELUS 2024.2 | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 3
Asim Jameel | NEXELUS 2024.2 | Regular bug fixing activity | Other | 2024-08 | 1.5
Asim Jameel | NEXELUS 2024.2 | Requirement Specifications document writing | Documentation | 2024-09 | 9
Asim Jameel | NEXELUS 2024.2 | Support Items | Analysis | 2024-09 | 4
Asim Jameel | NEXELUS 2024.2 | Support Items | Other | 2024-08 | 2.5
Asim Jameel | NEXELUS 2024.2 | Time Off - Un Planned | Other | 2024-08 | 6.5
Asim Jameel | PR-0013 | Analysis of production issues reported by support team | Support Tickets | 2024-11 | 8
Asim Jameel | PR-0013 | Client Items | Client Items | 2024-11 | 4
Asim Jameel | PR-0013 | Client Items | Client Items | 2025-01 | 2
Asim Jameel | PR-0013 | Internal Meetings | Meetings | 2024-08 | 2.5
Asim Jameel | PR-0013 | Meetings, mails, communication, TFS, Interviews | Project Mgmt | 2025-01 | 2
Asim Jameel | PR-0013 | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2024-11 | 0.75
Asim Jameel | PR-0013 | Session with US team | Client Items | 2024-08 | 2.4
Asim Jameel | PR-0013 | Session with US team | Client Items | 2024-09 | 18.5
Asim Jameel | PR-0013 | Session with US team | Client Items | 2024-10 | 26.5
Asim Jameel | PR-0013 | Session with US team | Client Items | 2024-11 | 15.5
Asim Jameel | PR-0013 | Session with US team | Client Items | 2024-12 | 2
Asim Jameel | PR-0013 | Session with US team | Client Items | 2025-01 | 14
Asim Jameel | PR-0013 | Session with US team | Meetings | 2024-09 | 5.5
Asim Jameel | PR-0013 | Session with US team | Meetings | 2024-11 | 4
Asim Jameel | PR-0013 | Time Off - Planned | Leave | 2024-08 | 16
Asim Jameel | Support and Maintenance | Time | Client Items | 2024-08 | 16
Asim Jameel | Support and Maintenance | Time | Client Items | 2024-09 | 18
Asim Jameel | Support and Maintenance | Time | Client Items | 2025-01 | 9
Asiya Bibi | AD-0001 | HR ad Admin Activities | Admin | 2024-08 | 24
Asiya Bibi | AD-0001 | HR ad Admin Activities | Admin | 2024-11 | 89
Asiya Bibi | AD-0001 | HR ad Admin Activities | Admin | 2024-12 | 12
Asiya Bibi | AD-0001 | HR ad Admin Activities | Admin | 2025-01 | 42
Asiya Bibi | AD-0001 | HR ad Admin Activities | Admin | 2025-02 | 37.5
Asiya Bibi | AD-0001 | HR ad Admin Activities | Admin | 2025-03 | 40
Asiya Bibi | AD-0001 | HR ad Admin Activities | Admin | 2025-04 | 57
Asiya Bibi | AD-0001 | HR ad Admin Activities | Admin | 2025-05 | 34
Asiya Bibi | AD-0001 | HR ad Admin Activities | Admin | 2025-06 | 2
Asiya Bibi | AD-0001 | HR ad Admin Activities | HR Management | 2024-08 | 31
Asiya Bibi | AD-0001 | HR ad Admin Activities | HR Management | 2024-09 | 68
Asiya Bibi | AD-0001 | HR ad Admin Activities | HR Management | 2024-10 | 68
Asiya Bibi | AD-0001 | HR ad Admin Activities | HR Management | 2024-11 | 40
Asiya Bibi | AD-0001 | HR ad Admin Activities | HR Management | 2024-12 | 64
Asiya Bibi | AD-0001 | HR ad Admin Activities | HR Management | 2025-01 | 60
Asiya Bibi | AD-0001 | HR ad Admin Activities | HR Management | 2025-02 | 51.5
Asiya Bibi | AD-0001 | HR ad Admin Activities | HR Management | 2025-03 | 42
Asiya Bibi | AD-0001 | HR ad Admin Activities | HR Management | 2025-04 | 54
Asiya Bibi | AD-0001 | HR ad Admin Activities | HR Management | 2025-05 | 37
Asiya Bibi | AD-0001 | HR ad Admin Activities | HR Management | 2025-06 | 2.5
Asiya Bibi | AD-0001 | HR ad Admin Activities | Interview | 2024-08 | 9
Asiya Bibi | AD-0001 | HR ad Admin Activities | Interview | 2024-11 | 4
Asiya Bibi | AD-0001 | HR ad Admin Activities | Other | 2024-08 | 41
Asiya Bibi | AD-0001 | Meetings | Meetings | 2024-11 | 5
Asiya Bibi | AD-0001 | Meetings | Meetings | 2024-12 | 22
Asiya Bibi | AD-0001 | Meetings | Meetings | 2025-01 | 21
Asiya Bibi | AD-0001 | Meetings | Meetings | 2025-02 | 16
Asiya Bibi | AD-0001 | Meetings | Meetings | 2025-03 | 18
Asiya Bibi | AD-0001 | Meetings | Meetings | 2025-04 | 8.5
Asiya Bibi | AD-0001 | Meetings | Meetings | 2025-05 | 10
Asiya Bibi | AD-0001 | Meetings | Meetings | 2025-06 | 0.5
Asiya Bibi | AD-0001 | Network and infrastructure Support | Admin | 2024-08 | 21
Asiya Bibi | AD-0001 | Network and infrastructure Support | Admin | 2024-09 | 47
Asiya Bibi | AD-0001 | Network and infrastructure Support | Admin | 2024-10 | 71
Asiya Bibi | AD-0001 | Network and infrastructure Support | Admin | 2024-11 | 17.5
Asiya Bibi | AD-0001 | Network and infrastructure Support | Admin | 2024-12 | 61
Asiya Bibi | AD-0001 | Network and infrastructure Support | Admin | 2025-01 | 27
Asiya Bibi | AD-0001 | Network and infrastructure Support | Admin | 2025-02 | 16
Asiya Bibi | AD-0001 | Network and infrastructure Support | Admin | 2025-03 | 5
Asiya Bibi | AD-0001 | Network and infrastructure Support | Admin | 2025-04 | 2.5
Asiya Bibi | AD-0001 | Taxes and Bank Related | Admin | 2024-08 | 7
Asiya Bibi | AD-0001 | Taxes and Bank Related | Admin | 2024-09 | 19
Asiya Bibi | AD-0001 | Taxes and Bank Related | Admin | 2024-10 | 15
Asiya Bibi | AD-0001 | Taxes and Bank Related | Admin | 2024-12 | 10
Asiya Bibi | AD-0001 | Taxes and Bank Related | Admin | 2025-01 | 17
Asiya Bibi | AD-0001 | Taxes and Bank Related | Admin | 2025-02 | 17
Asiya Bibi | AD-0001 | Taxes and Bank Related | Admin | 2025-03 | 19
Asiya Bibi | AD-0001 | Taxes and Bank Related | Admin | 2025-04 | 15
Asiya Bibi | AD-0001 | Taxes and Bank Related | Admin | 2025-05 | 17
Asiya Bibi | AD-0001 | Taxes and Bank Related | Admin | 2025-06 | 3
Asiya Bibi | AD-0001 | Taxes and Bank Related | HR Management | 2024-11 | 5
Asiya Bibi | AD-0001 | Taxes and Bank Related | Leave | 2025-02 | 24
Asiya Bibi | AD-0001 | Taxes and Bank Related | Other | 2024-08 | 9.5
Asiya Bibi | AD-0001 | Time | Interview | 2024-09 | 3.5
Asiya Bibi | AD-0001 | Time | Leave | 2025-03 | 28
Asiya Bibi | AD-0001 | Time | Leave | 2025-04 | 12
Asiya Bibi | AD-0001 | Time | Other | 2024-08 | 53
Asiya Bibi | AD-0001 | Time | Research | 2025-05 | 17
Asiya Bibi | PR-0013 | Meetings, mails, communication, TFS, Interviews | Leave | 2024-08 | 3
Asiya Bibi | PR-0013 | Meetings, mails, communication, TFS, Interviews | Leave | 2025-05 | 60
Asiya Bibi | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 23.5
Asiya Bibi | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-10 | 20
Asiya Bibi | PR-0013 | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2024-12 | 1
Ayesha Qurban | AD-0001 | Time | Leave | 2025-05 | 8
Ayesha Qurban | AD-0001 | Time | Research | 2025-04 | 4
Ayesha Qurban | AP WORKFLOW | Analysis of the new project/assignment/task | Analysis | 2024-09 | 5
Ayesha Qurban | AP WORKFLOW | Analysis of the new project/assignment/task | Analysis | 2024-12 | 3
Ayesha Qurban | AP WORKFLOW | Document review/understanding Requirement Specifications | Documentation | 2024-11 | 3
Ayesha Qurban | AP WORKFLOW | Internal Meetings | Meetings | 2024-10 | 1
Ayesha Qurban | AP WORKFLOW | Internal Meetings | Meetings | 2024-11 | 6
Ayesha Qurban | AP WORKFLOW | Regular testing and QA new project/assignment/task | Other | 2024-08 | 116
Ayesha Qurban | AP WORKFLOW | Regular testing and QA new project/assignment/task | Testing | 2024-11 | 5
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Test Case Dev | 2024-09 | 16
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Testing | 2024-10 | 25
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Meetings | 2024-10 | 2
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Test Case Dev | 2024-09 | 16
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Test Case Dev | 2024-10 | 28
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Testing | 2024-10 | 45
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Testing | 2024-11 | 10
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Meetings | 2024-10 | 4
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Testing | 2024-10 | 24
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Testing | 2024-11 | 2
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Apply discount based on Payment terms settings | Testing | 2024-11 | 12.5
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Apply discount based on Payment terms settings | Testing | 2024-12 | 1
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Checkbox to filter discrepant lines | Testing | 2024-10 | 2
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Forward Inv to user OR select user when invoice is Pending Apr | Testing | 2024-11 | 1
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Google Drive - Split Process and show documents in queue | Testing | 2024-11 | 4
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Invoice Editing: Make the tax editable | Meetings | 2024-11 | 1
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Invoice Editing: Make the tax editable | Testing | 2024-11 | 9
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Remove Site column from vendor lookup | Testing | 2024-11 | 1
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Route invoice from one company - company identification | Testing | 2024-11 | 2.5
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Testing | 2024-11 | 3
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Testing | 2024-12 | 1
Ayesha Qurban | APWORKS 2024.2 - PHASE 3 | Vendor Map: Vendor Popup: Remove identifier currency filter | Testing | 2024-11 | 2
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | A report to spot check the invoices processed | Testing | 2024-12 | 1
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Apply variable name for Site in vendor mapping | Testing | 2024-12 | 1
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Apply variable name for Site in vendor mapping | Testing | 2025-02 | 2
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Approval routing | Analysis | 2024-11 | 5
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Approval routing | Test Case Dev | 2024-12 | 8
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Approval routing | Testing | 2024-11 | 3
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Approval routing | Testing | 2024-12 | 18
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Approval routing | Testing | 2025-01 | 9
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Approve upto last level and auto post. | Testing | 2024-11 | 3
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Approve upto last level and auto post. | Testing | 2024-12 | 1
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Discount implementation CHANGES | Testing | 2025-01 | 4
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Discount implementation CHANGES | Testing | 2025-02 | 3
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | EDI file updating and upload | Analysis | 2024-12 | 3
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | EDI file updating and upload | Testing | 2024-12 | 15
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | EDI: Generate PDF - Updates | Testing | 2024-12 | 2
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Google Drive Setup (company configuration UI) | Testing | 2025-01 | 4
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Invoice Scan | Testing | 2024-12 | 2
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Production: Project should be available on summary as well. | Testing | 2024-12 | 1
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Project Overhead | Analysis | 2024-12 | 6
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Project Overhead | Analysis | 2025-01 | 4
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Project Overhead | Meetings | 2024-11 | 5
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Project Overhead | Meetings | 2024-12 | 4
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Pull Client & Sites, Service types as Media Types from Nexelus | Testing | 2025-01 | 4
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Report >> Vendor Invoices: we need the discount field to show up | Testing | 2024-12 | 1
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Tax implementation(rule)/column for difference | Testing | 2025-01 | 25
Ayesha Qurban | APWORKS 2024.2 - PHASE 4 | Tax implementation(rule)/column for difference | Testing | 2025-02 | 4
Ayesha Qurban | APWORKS 2024.2 PHASE 5 | Google Drive Setup (company configuration UI) | Testing | 2024-12 | 2
Ayesha Qurban | APWORKS 2024.2 PHASE 5 | Project Overhead | Analysis | 2024-12 | 29
Ayesha Qurban | APWORKS 2024.2 PHASE 5 | Project Overhead | Analysis | 2025-01 | 2
Ayesha Qurban | APWORKS 2024.2 PHASE 5 | Project Overhead | Meetings | 2024-12 | 5
Ayesha Qurban | APWORKS 2024.2 PHASE 5 | Project Overhead | Support Tickets | 2025-01 | 6
Ayesha Qurban | APWORKS 2025.1 | Project Overhead | Analysis | 2025-03 | 1
Ayesha Qurban | APWORKS 2025.2 | Ability to Approve the invoice when resolving discrepancy | Testing | 2025-05 | 4
Ayesha Qurban | APWORKS 2025.2 | Ability to create templates across multiple Companies | Test Case Dev | 2025-04 | 2
Ayesha Qurban | APWORKS 2025.2 | Ability to create templates across multiple Companies | Testing | 2025-05 | 76
Ayesha Qurban | APWORKS 2025.2 | Ability to create templates across multiple Companies | Testing | 2025-06 | 5
Ayesha Qurban | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Testing | 2025-04 | 7
Ayesha Qurban | APWORKS 2025.2 | Credit Memo | Test Case Dev | 2025-04 | 6
Ayesha Qurban | APWORKS 2025.2 | Display client #, when inv is linked to IO in all UIs and Report | Testing | 2025-04 | 18
Ayesha Qurban | APWORKS 2025.2 | Display client #, when inv is linked to IO in all UIs and Report | Testing | 2025-05 | 5
Ayesha Qurban | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Testing | 2025-05 | 13
Ayesha Qurban | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Testing | 2025-06 | 3
Ayesha Qurban | APWORKS 2025.2 | Project Overhead | Support Tickets | 2025-04 | 3
Ayesha Qurban | APWORKS 2025.2 | Project Overhead | Task Domain | 2025-04 | 3
Ayesha Qurban | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Testing | 2025-04 | 19
Ayesha Qurban | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Testing | 2025-05 | 28
Ayesha Qurban | APWORKS 2025.2 | Split invoice by MOS - Print / OOH / Digital | SRS-Review | 2025-06 | 3
Ayesha Qurban | APWORKS 2025.2 | Split invoice by MOS - Print / OOH / Digital | Testing | 2025-06 | 17
Ayesha Qurban | APWORKS 2025.2 | Standardize the Status in Dashboard vs reports | Testing | 2025-04 | 2
Ayesha Qurban | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Analysis | 2025-06 | 3
Ayesha Qurban | APWORKS PHASE2 | Meetings, mails, communication, TFS, Interviews | Documentation | 2024-09 | 1
Ayesha Qurban | APWORKS PHASE2 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-08 | 5
Ayesha Qurban | APWORKS PHASE2 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 14
Ayesha Qurban | APWORKS PHASE2 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-10 | 3
Ayesha Qurban | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-08 | 35
Ayesha Qurban | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-09 | 76
Ayesha Qurban | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-10 | 11
Ayesha Qurban | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-11 | 33
Ayesha Qurban | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-12 | 4
Ayesha Qurban | NEXELUS 2024.1 SP2 | Level 3 | Testing | 2025-01 | 2
Ayesha Qurban | NEXELUS 2024.2 | Analysis of production issues reported by support team | Client Items | 2024-09 | 6
Ayesha Qurban | NEXELUS 2024.2 | Analysis of production issues reported by support team | Other | 2024-08 | 6
Ayesha Qurban | NEXELUS 2024.2 | Analysis of the new project/assignment/task | Analysis | 2024-09 | 22
Ayesha Qurban | NEXELUS 2024.2 | Analysis of the new project/assignment/task | Analysis | 2024-10 | 6
Ayesha Qurban | NEXELUS 2024.2 | Regular testing and QA new project/assignment/task | Other | 2024-08 | 20
Ayesha Qurban | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Task/Code Review | 2025-04 | 3
Ayesha Qurban | NEXELUS 2025.2 | Project Overhead | Task Domain | 2025-04 | 3
Ayesha Qurban | PR-0013 | Analysis of production issues reported by support team | Analysis | 2025-02 | 3
Ayesha Qurban | PR-0013 | Analysis of production issues reported by support team | Testing | 2025-06 | 4
Ayesha Qurban | PR-0013 | Cient UAT Upgrade | Testing | 2025-01 | 69
Ayesha Qurban | PR-0013 | Cient UAT Upgrade | Testing | 2025-03 | 4
Ayesha Qurban | PR-0013 | Cient UAT Upgrade | Testing | 2025-05 | 11
Ayesha Qurban | PR-0013 | Cient UAT Upgrade | Testing | 2025-06 | 12
Ayesha Qurban | PR-0013 | Client Items | Testing | 2025-03 | 10
Ayesha Qurban | PR-0013 | Document review/understanding Requirement Specifications | Analysis | 2025-03 | 5
Ayesha Qurban | PR-0013 | Document review/understanding Requirement Specifications | Analysis | 2025-04 | 2
Ayesha Qurban | PR-0013 | Gazetted holidays | Leave | 2025-03 | 8
Ayesha Qurban | PR-0013 | Gazetted holidays | Leave | 2025-04 | 16
Ayesha Qurban | PR-0013 | Gazetted holidays | Leave | 2025-06 | 16
Ayesha Qurban | PR-0013 | Internal Meetings | Meetings | 2025-01 | 1
Ayesha Qurban | PR-0013 | Internal Meetings | Meetings | 2025-02 | 1
Ayesha Qurban | PR-0013 | Internal Meetings | Meetings | 2025-03 | 1
Ayesha Qurban | PR-0013 | Internal Meetings | Meetings | 2025-04 | 9
Ayesha Qurban | PR-0013 | Internal Meetings | Meetings | 2025-05 | 5
Ayesha Qurban | PR-0013 | Internal Meetings | Meetings | 2025-06 | 1
Ayesha Qurban | PR-0013 | Internal Meetings | Testing | 2025-05 | 1
Ayesha Qurban | PR-0013 | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2024-12 | 2
Ayesha Qurban | PR-0013 | Production upgrades | Testing | 2025-01 | 5
Ayesha Qurban | PR-0013 | Production upgrades | Testing | 2025-03 | 6
Ayesha Qurban | PR-0013 | Production upgrades | Testing | 2025-05 | 5
Ayesha Qurban | PR-0013 | Production upgrades | Testing | 2025-06 | 2
Ayesha Qurban | PR-0013 | QA Environment Upgrade | Testing | 2025-03 | 8
Ayesha Qurban | PR-0013 | Requirement Specifications document writing | Documentation | 2025-03 | 4
Ayesha Qurban | PR-0013 | Time Off - Planned | Leave | 2024-09 | 16
Ayesha Qurban | PR-0013 | Time Off - Planned | Leave | 2024-12 | 24
Ayesha Qurban | PR-0013 | Time Off - Planned | Leave | 2025-02 | 80
Ayesha Qurban | PR-0013 | Time Off - Planned | Leave | 2025-06 | 8
Ayesha Qurban | PR-0013 | Time Off - Un Planned | Leave | 2024-10 | 33
Ayesha Qurban | PR-0013 | Time Off - Un Planned | Leave | 2024-12 | 8
Ayesha Qurban | PR-0013 | Time Off - Un Planned | Leave | 2025-01 | 8
Ayesha Qurban | PR-0013 | Time Off - Un Planned | Leave | 2025-02 | 8
Ayesha Qurban | PR-0013 | Time Off - Un Planned | Leave | 2025-03 | 7
Ayesha Qurban | PR-0013 | Time Off - Un Planned | Leave | 2025-04 | 24
Ayesha Qurban | PR-0013 | Time Off - Un Planned | Leave | 2025-06 | 8
Ayesha Qurban | Support and Maintenance | Time | Client Items | 2024-11 | 56
Ayesha Qurban | Support and Maintenance | Time | Client Items | 2024-12 | 31
Ayesha Qurban | Support and Maintenance | Time | Client Items | 2025-01 | 60
Ayesha Qurban | Support and Maintenance | Time | Client Items | 2025-02 | 58
Ayesha Qurban | Support and Maintenance | Time | Client Items | 2025-03 | 62.5
Ayesha Qurban | Support and Maintenance | Time | Client Items | 2025-04 | 19
Ayesha Qurban | Support and Maintenance | Time | Client Items | 2025-06 | 7
Ayesha Qurban | Support and Maintenance | Time | Support Tickets | 2024-12 | 3
Ayesha Qurban | Support and Maintenance | Time | Support Tickets | 2025-03 | 33
Ayesha Qurban | Support and Maintenance | Time | Support Tickets | 2025-04 | 33
Ayesha Qurban | Support and Maintenance | Time | Support Tickets | 2025-05 | 21
Ayesha Qurban | Support and Maintenance | Time | Support Tickets | 2025-06 | 5
Bilal Afzal Raja | AP WORKFLOW | Analysis of production issues reported by support team | Other | 2024-08 | 16
Bilal Afzal Raja | AP WORKFLOW | Analysis of production issues reported by support team | Testing | 2024-10 | 10
Bilal Afzal Raja | AP WORKFLOW | Analysis of production issues reported by support team | Testing | 2024-11 | 3
Bilal Afzal Raja | AP WORKFLOW | Analysis of production issues reported by support team | Testing | 2024-12 | 1
Bilal Afzal Raja | AP WORKFLOW | Cient UAT Upgrade | Other | 2024-08 | 1
Bilal Afzal Raja | AP WORKFLOW | QA Environment Upgrade | Other | 2024-08 | 40
Bilal Afzal Raja | AP WORKFLOW | Release Environment Upgrade | Other | 2024-08 | 6
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Testing | 2024-10 | 4
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Meetings | 2024-08 | 3
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Meetings | 2024-09 | 7
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | Meetings | 2024-10 | 2
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Testing | 2024-10 | 2
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | Documentation | Documentation | 2024-11 | 1.5
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | Project Overhead | Analysis | 2024-10 | 5
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | Project Overhead | Meetings | 2024-09 | 7
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | Project Overhead | Meetings | 2024-10 | 9
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 3 | Vendor/stations/sites associated to multiple pay to. | Testing | 2024-10 | 2
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 4 | EDI file updating and upload | Testing | 2025-01 | 6
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 4 | EDI: Generate PDF - Updates | Testing | 2025-01 | 8
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 4 | Integration Testing | Testing | 2025-01 | 8
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Approvals | Testing | 2025-01 | 5
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Import / Export lines | Testing | 2025-01 | 6
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 4 | Project Overhead | Analysis | 2025-01 | 13
Bilal Afzal Raja | APWORKS 2024.2 - PHASE 4 | Tax implementation(rule)/column for difference | Testing | 2025-01 | 4
Bilal Afzal Raja | APWORKS 2025.2 | Project Overhead | Project Mgmt | 2025-05 | 5
Bilal Afzal Raja | APWORKS 2025.2 | Project Overhead | Task Domain | 2025-04 | 17.5
Bilal Afzal Raja | APWORKS 2025.2 | Warren Lamb provided PDF ingestion | Testing | 2025-05 | 5
Bilal Afzal Raja | APWORKS PHASE2 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-08 | 8
Bilal Afzal Raja | APWORKS PHASE2 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 8
Bilal Afzal Raja | APWORKS PHASE2 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-10 | 3
Bilal Afzal Raja | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-08 | 10
Bilal Afzal Raja | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-09 | 16
Bilal Afzal Raja | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-10 | 15
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | AdTech Fee commission | Bug Fixing | 2024-12 | 7
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | AdTech Fee commission | Bug Fixing | 2025-01 | 7
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | AdTech Fee commission | Documentation | 2024-12 | 3
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | AdTech Fee commission | Testing | 2024-12 | 15
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | AdTech Fee commission | Testing | 2025-01 | 3
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Backup Table for vendor/client lines relationship | Testing | 2024-11 | 20
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Billing by Media Type | Bug Fixing | 2024-12 | 4
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Billing by Media Type | Bug Fixing | 2025-01 | 12
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Billing by Media Type | Test Case Dev | 2024-11 | 3
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Billing by Media Type | Testing | 2024-12 | 18
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Billing by Media Type | Testing | 2025-01 | 2
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Client Profile: Media > Flag to make the vendor inactive | Bug Fixing | 2024-12 | 3
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Client Profile: Media > Flag to make the vendor inactive | Bug Fixing | 2025-01 | 10
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Client Profile: Media > Flag to make the vendor inactive | Testing | 2024-12 | 2
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Client Profile: Media > Flag to make the vendor inactive | Testing | 2025-01 | 3
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Documentation | Documentation | 2024-11 | 2
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | eConnect shell change to service | Testing | 2024-11 | 7
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Enhancement for Visual Indicators and Flighting Details in Place | Testing | 2024-12 | 1
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Bug Fixing | 2024-12 | 2.5
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Bug Fixing | 2025-01 | 8
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Test Case Dev | 2024-11 | 3
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Testing | 2024-12 | 32
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Testing | 2025-01 | 1
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Integration Testing | Bug Fixing | 2025-01 | 8
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Level 3 | Bug Fixing | 2025-01 | 1
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Media Plan Approval | Bug Fixing | 2025-01 | 1
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting | Bug Fixing | 2025-01 | 4
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting | Testing | 2024-12 | 2
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Restrict Self Approval - Time and expense | Bug Fixing | 2025-01 | 4
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Restrict Self Approval - Time and expense | Testing | 2024-12 | 5
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | Restrict Self Approval - Time and expense | Testing | 2025-01 | 1
Bilal Afzal Raja | NEXELUS 2024.1 SP2 | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | Test Case Dev | 2024-11 | 6
Bilal Afzal Raja | NEXELUS 2024.2 | Analysis of production issues reported by support team | Analysis | 2024-10 | 14
Bilal Afzal Raja | NEXELUS 2024.2 | Analysis of production issues reported by support team | Other | 2024-08 | 29
Bilal Afzal Raja | NEXELUS 2024.2 | Analysis of the new project/assignment/task | Documentation | 2024-09 | 6
Bilal Afzal Raja | NEXELUS 2024.2 | Analysis of the new project/assignment/task | Documentation | 2024-10 | 7
Bilal Afzal Raja | NEXELUS 2024.2 | Cient UAT Upgrade | Other | 2024-08 | 14.5
Bilal Afzal Raja | NEXELUS 2024.2 | Document review/understanding Requirement Specifications | Analysis | 2024-11 | 2
Bilal Afzal Raja | NEXELUS 2024.2 | Document review/understanding Requirement Specifications | Documentation | 2024-10 | 7
Bilal Afzal Raja | NEXELUS 2024.2 | Document review/understanding Requirement Specifications | Documentation | 2024-11 | 3
Bilal Afzal Raja | NEXELUS 2024.2 | Document review/understanding Requirement Specifications | Testing | 2024-11 | 15
Bilal Afzal Raja | NEXELUS 2024.2 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 3
Bilal Afzal Raja | NEXELUS 2024.2 | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 26
Bilal Afzal Raja | NEXELUS 2024.2 | Meetings, mails, communication, TFS, Interviews | Testing | 2024-09 | 24
Bilal Afzal Raja | NEXELUS 2024.2 | National Gazetted Holidays | Other | 2024-08 | 8
Bilal Afzal Raja | NEXELUS 2024.2 | Regular bug fixing activity | Testing | 2024-09 | 6
Bilal Afzal Raja | NEXELUS 2024.2 | Regular testing and QA new project/assignment/task | Documentation | 2024-10 | 6
Bilal Afzal Raja | NEXELUS 2024.2 | Regular testing and QA new project/assignment/task | Other | 2024-08 | 3
Bilal Afzal Raja | NEXELUS 2025.1 | Generate billing schedule - bug fixing | Testing | 2025-03 | 6
Bilal Afzal Raja | NEXELUS 2025.1 | Import/exports flights | Testing | 2025-03 | 4
Bilal Afzal Raja | NEXELUS 2025.1 | Margin change for TTD | Testing | 2025-03 | 7
Bilal Afzal Raja | NEXELUS 2025.1 | Show PBG Gross up amount on billing reconciliation. | Testing | 2025-03 | 8
Bilal Afzal Raja | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Testing | 2025-04 | 1.5
Bilal Afzal Raja | NEXELUS 2025.2 | Allow manual adjustments for partial billing by the client | Testing | 2025-05 | 16
Bilal Afzal Raja | NEXELUS 2025.2 | Allow switching media plan from Media Plan UI | Testing | 2025-04 | 1.5
Bilal Afzal Raja | NEXELUS 2025.2 | Display Vendor distribution for individual client line under | Task/Code Review | 2025-06 | 4
Bilal Afzal Raja | NEXELUS 2025.2 | Display Vendor distribution for individual client line under | Testing | 2025-04 | 4
Bilal Afzal Raja | NEXELUS 2025.2 | Display Vendor distribution for individual client line under | Testing | 2025-05 | 5
Bilal Afzal Raja | NEXELUS 2025.2 | Display Vendor distribution for individual client line under | Testing | 2025-06 | 2
Bilal Afzal Raja | NEXELUS 2025.2 | Exchange rate changes | Documentation | 2025-05 | 2
Bilal Afzal Raja | NEXELUS 2025.2 | Exchange rate changes | Task/Code Review | 2025-06 | 4
Bilal Afzal Raja | NEXELUS 2025.2 | Exchange rate changes | Testing | 2025-04 | 14
Bilal Afzal Raja | NEXELUS 2025.2 | Exchange rate changes | Testing | 2025-05 | 21
Bilal Afzal Raja | NEXELUS 2025.2 | Exchange rate changes | Testing | 2025-06 | 7
Bilal Afzal Raja | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Testing | 2025-05 | 20
Bilal Afzal Raja | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Testing | 2025-06 | 57
Bilal Afzal Raja | NEXELUS 2025.2 | Net Media + Ad serving Added to Media Spend under Campaign | Task/Code Review | 2025-06 | 4
Bilal Afzal Raja | NEXELUS 2025.2 | Net Media + Ad serving Added to Media Spend under Campaign | Testing | 2025-04 | 5
Bilal Afzal Raja | NEXELUS 2025.2 | Net Media + Ad serving Added to Media Spend under Campaign | Testing | 2025-05 | 4
Bilal Afzal Raja | NEXELUS 2025.2 | Net Media + Ad serving Added to Media Spend under Campaign | Testing | 2025-06 | 2
Bilal Afzal Raja | NEXELUS 2025.2 | Nexelus Email Function for IO | Testing | 2025-04 | 2
Bilal Afzal Raja | NEXELUS 2025.2 | Nexelus Email Function for IO | Testing | 2025-05 | 5
Bilal Afzal Raja | NEXELUS 2025.2 | Nexelus Email Function for IO | Testing | 2025-06 | 4
Bilal Afzal Raja | NEXELUS 2025.2 | Project Overhead | Meetings | 2025-05 | 14
Bilal Afzal Raja | NEXELUS 2025.2 | Project Overhead | Project Mgmt | 2025-04 | 9.5
Bilal Afzal Raja | NEXELUS 2025.2 | Project Overhead | Project Mgmt | 2025-05 | 3
Bilal Afzal Raja | NEXELUS 2025.2 | Project Overhead | Task Domain | 2025-04 | 20.5
Bilal Afzal Raja | NEXELUS 2025.2 | Starred media plans (NEX 17059) | Testing | 2025-04 | 1
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Analysis | 2024-08 | 10
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Analysis | 2024-09 | 38
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Analysis | 2024-10 | 30
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Analysis | 2024-11 | 8
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Analysis | 2024-12 | 2
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Analysis | 2025-03 | 3
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Analysis | 2025-05 | 3.5
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Testing | 2024-08 | 9
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Testing | 2024-09 | 4
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Testing | 2024-10 | 16
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Testing | 2024-11 | 5.5
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Testing | 2024-12 | 14
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Testing | 2025-01 | 31
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Testing | 2025-02 | 2
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Testing | 2025-03 | 9
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Testing | 2025-04 | 3
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Testing | 2025-05 | 24.5
Bilal Afzal Raja | PR-0013 | Analysis of production issues reported by support team | Testing | 2025-06 | 3
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrade | Analysis | 2024-10 | 7
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrade | Testing | 2024-10 | 15
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrade | Testing | 2024-11 | 42
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrade | Testing | 2024-12 | 5.5
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrade | Testing | 2025-01 | 27
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrade | Testing | 2025-03 | 4
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrade | Testing | 2025-04 | 5
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrade | Testing | 2025-05 | 9
Bilal Afzal Raja | PR-0013 | Cient UAT Upgrade | Testing | 2025-06 | 7
Bilal Afzal Raja | PR-0013 | In-house Training | Domain Learning | 2024-11 | 6.5
Bilal Afzal Raja | PR-0013 | Internal Meetings | Documentation | 2024-09 | 4
Bilal Afzal Raja | PR-0013 | Internal Meetings | Documentation | 2024-12 | 10
Bilal Afzal Raja | PR-0013 | Internal Meetings | Meetings | 2024-10 | 16
Bilal Afzal Raja | PR-0013 | Internal Meetings | Meetings | 2024-11 | 28
Bilal Afzal Raja | PR-0013 | Internal Meetings | Meetings | 2024-12 | 30.5
Bilal Afzal Raja | PR-0013 | Internal Meetings | Meetings | 2025-01 | 39.5
Bilal Afzal Raja | PR-0013 | Internal Meetings | Meetings | 2025-02 | 22
Bilal Afzal Raja | PR-0013 | Internal Meetings | Meetings | 2025-03 | 19
Bilal Afzal Raja | PR-0013 | Internal Meetings | Meetings | 2025-04 | 35.5
Bilal Afzal Raja | PR-0013 | Internal Meetings | Meetings | 2025-05 | 17.5
Bilal Afzal Raja | PR-0013 | Internal Meetings | Meetings | 2025-06 | 19.5
Bilal Afzal Raja | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-11 | 2
Bilal Afzal Raja | PR-0013 | Meetings, mails, communication, TFS, Interviews | Testing | 2025-04 | 2
Bilal Afzal Raja | PR-0013 | Production upgrades | Development | 2024-09 | 5
Bilal Afzal Raja | PR-0013 | Production upgrades | Testing | 2025-01 | 29
Bilal Afzal Raja | PR-0013 | Production upgrades | Testing | 2025-03 | 9
Bilal Afzal Raja | PR-0013 | Production upgrades | Testing | 2025-06 | 3
Bilal Afzal Raja | PR-0013 | Time Off - Planned | Leave | 2024-09 | 31
Bilal Afzal Raja | PR-0013 | Time Off - Planned | Leave | 2024-12 | 8
Bilal Afzal Raja | PR-0013 | Time Off - Planned | Leave | 2025-03 | 16
Bilal Afzal Raja | PR-0013 | Time Off - Planned | Leave | 2025-04 | 16
Bilal Afzal Raja | PR-0013 | Time Off - Planned | Leave | 2025-05 | 8
Bilal Afzal Raja | PR-0013 | Time Off - Planned | Leave | 2025-06 | 8
Bilal Afzal Raja | PR-0013 | Time Off - Planned | Meetings | 2024-09 | 6
Bilal Afzal Raja | PR-0013 | Time Off - Un Planned | Leave | 2024-10 | 12
Bilal Afzal Raja | PR-0013 | Time Off - Un Planned | Leave | 2024-11 | 7.5
Bilal Afzal Raja | PR-0013 | Time Off - Un Planned | Leave | 2024-12 | 6.5
Bilal Afzal Raja | PR-0013 | Time Off - Un Planned | Leave | 2025-01 | 16
Bilal Afzal Raja | PR-0013 | Time Off - Un Planned | Leave | 2025-02 | 16
Bilal Afzal Raja | PR-0013 | Time Off - Un Planned | Leave | 2025-03 | 14
Bilal Afzal Raja | PR-0013 | Time Off - Un Planned | Leave | 2025-04 | 12
Bilal Afzal Raja | PR-0013 | Time Off - Un Planned | Leave | 2025-05 | 3
Bilal Afzal Raja | PR-0013 | Time Off - Un Planned | Leave | 2025-06 | 8
Bilal Afzal Raja | Support and Maintenance | Time | Client Items | 2025-02 | 104
Bilal Afzal Raja | Support and Maintenance | Time | Client Items | 2025-03 | 46
Bilal Afzal Raja | Support and Maintenance | Time | Client Items | 2025-04 | 10.5
Bilal Afzal Raja | Support and Maintenance | Time | Client Items | 2025-05 | 9
Bilal Afzal Raja | Support and Maintenance | Time | Client Items | 2025-06 | 2
Bilal Afzal Raja | Support and Maintenance | Time | Support Tickets | 2025-02 | 4
Bilal Afzal Raja | Support and Maintenance | Time | Support Tickets | 2025-04 | 10
Bilal Afzal Raja | Support and Maintenance | Time | Support Tickets | 2025-05 | 6
Bilal Afzal Raja | Support and Maintenance | Time | Support Tickets | 2025-06 | 2
Farooq Azam | NEXELUS 13.0 | Development of new project/assignment/task | Other | 2024-08 | 40
Fawad Ahmed | AP WORKFLOW | Client Items | Client Items | 2024-09 | 0
Fawad Ahmed | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Bug Fixing | 2024-10 | 0
Fawad Ahmed | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Development | 2024-09 | 106
Fawad Ahmed | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Development | 2024-10 | 73
Fawad Ahmed | APWORKS 2024.2 - PHASE 4 | Project Overhead | Post_dep_fixes | 2025-01 | 7
Fawad Ahmed | APWORKS 2024.2 PHASE 5 | Google Drive Setup (company configuration UI) | Development | 2025-01 | 6
Fawad Ahmed | APWORKS 2024.2 PHASE 5 | Google Drive Setup (company configuration UI) | Task/Code Review | 2025-01 | 6
Fawad Ahmed | APWORKS 2024.2 PHASE 5 | Project Overhead | Analysis | 2025-01 | 10
Fawad Ahmed | APWORKS 2024.2 PHASE 5 | Project Overhead | Support Tickets | 2025-01 | 7
Fawad Ahmed | APWORKS PHASE2 | In-house Training | Meetings | 2024-12 | 5.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | AdTech Fee commission | Bug Fixing | 2024-12 | 2
Fawad Ahmed | NEXELUS 2024.1 SP2 | AdTech Fee commission | Bug Fixing | 2025-01 | 6
Fawad Ahmed | NEXELUS 2024.1 SP2 | AdTech Fee commission | Development | 2024-12 | 23
Fawad Ahmed | NEXELUS 2024.1 SP2 | AdTech Fee commission | Documentation | 2024-12 | 1
Fawad Ahmed | NEXELUS 2024.1 SP2 | AdTech Fee commission | Documentation | 2025-02 | 1
Fawad Ahmed | NEXELUS 2024.1 SP2 | AdTech Fee commission | Testing | 2024-12 | 1.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | AdTech Fee commission | Testing | 2025-01 | 3
Fawad Ahmed | NEXELUS 2024.1 SP2 | Billing by Media Type | Bug Fixing | 2024-12 | 6.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | Billing by Media Type | Bug Fixing | 2025-01 | 23.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | Billing by Media Type | Development | 2024-11 | 38.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | Billing by Media Type | Development | 2024-12 | 5.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | Billing by Media Type | Documentation | 2024-11 | 2
Fawad Ahmed | NEXELUS 2024.1 SP2 | Billing by Media Type | Documentation | 2024-12 | 1
Fawad Ahmed | NEXELUS 2024.1 SP2 | Billing by Media Type | Meetings | 2024-11 | 1.75
Fawad Ahmed | NEXELUS 2024.1 SP2 | Billing by Media Type | Task/Code Review | 2024-12 | 2
Fawad Ahmed | NEXELUS 2024.1 SP2 | Billing by Media Type | Testing | 2024-11 | 4.75
Fawad Ahmed | NEXELUS 2024.1 SP2 | Billing by Media Type | Testing | 2024-12 | 1.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | Billing by Media Type | Testing | 2025-01 | 12
Fawad Ahmed | NEXELUS 2024.1 SP2 | Enhancement for Visual Indicators and Flighting Details in Place | Bug Fixing | 2024-12 | 11
Fawad Ahmed | NEXELUS 2024.1 SP2 | Enhancement for Visual Indicators and Flighting Details in Place | Bug Fixing | 2025-01 | 3
Fawad Ahmed | NEXELUS 2024.1 SP2 | Enhancement for Visual Indicators and Flighting Details in Place | Development | 2024-12 | 30.25
Fawad Ahmed | NEXELUS 2024.1 SP2 | Enhancement for Visual Indicators and Flighting Details in Place | Documentation | 2024-12 | 2
Fawad Ahmed | NEXELUS 2024.1 SP2 | Enhancement for Visual Indicators and Flighting Details in Place | Meetings | 2024-12 | 1
Fawad Ahmed | NEXELUS 2024.1 SP2 | Enhancement for Visual Indicators and Flighting Details in Place | Task/Code Review | 2024-12 | 3
Fawad Ahmed | NEXELUS 2024.1 SP2 | Enhancement for Visual Indicators and Flighting Details in Place | Testing | 2024-12 | 15.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | Enhancement for Visual Indicators and Flighting Details in Place | Testing | 2025-01 | 1
Fawad Ahmed | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Analysis | 2024-10 | 35
Fawad Ahmed | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Bug Fixing | 2024-11 | 0
Fawad Ahmed | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Development | 2024-10 | 0
Fawad Ahmed | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Development | 2024-11 | 0
Fawad Ahmed | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Research | 2025-02 | 11
Fawad Ahmed | NEXELUS 2024.1 SP2 | Media Plan Approval | Bug Fixing | 2025-01 | 6
Fawad Ahmed | NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting | Bug Fixing | 2025-01 | 1.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting | Development | 2025-01 | 5
Fawad Ahmed | NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting | Development | 2025-02 | 18
Fawad Ahmed | NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting | Documentation | 2025-02 | 3
Fawad Ahmed | NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting | Testing | 2025-01 | 0.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting | Testing | 2025-02 | 18
Fawad Ahmed | NEXELUS 2024.1 SP2 | Project Overhead | Analysis | 2025-02 | 20
Fawad Ahmed | NEXELUS 2024.1 SP2 | Project Overhead | Deployment | 2024-11 | 0.3
Fawad Ahmed | NEXELUS 2024.1 SP2 | Project Overhead | Deployment | 2024-12 | 6.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | Project Overhead | Deployment | 2025-01 | 9
Fawad Ahmed | NEXELUS 2024.1 SP2 | Project Overhead | Deployment | 2025-02 | 2.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | Project Overhead | Post_dep_fixes | 2024-11 | 1
Fawad Ahmed | NEXELUS 2024.1 SP2 | Project Overhead | Post_dep_fixes | 2025-01 | 4
Fawad Ahmed | NEXELUS 2024.1 SP2 | Project Overhead | Support Tickets | 2025-01 | 7
Fawad Ahmed | NEXELUS 2024.1 SP2 | Project Overhead | Support Tickets | 2025-02 | 5
Fawad Ahmed | NEXELUS 2024.1 SP2 | UDF & Naming Convention in Nexelus - Export on Proposal | Development | 2024-11 | 24
Fawad Ahmed | NEXELUS 2024.1 SP2 | UDF & Naming Convention in Nexelus - Export on Proposal | Development | 2024-12 | 0.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | Development | 2024-11 | 13
Fawad Ahmed | NEXELUS 2024.1 SP2 | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | Testing | 2024-11 | 3.5
Fawad Ahmed | NEXELUS 2024.1 SP2 | UDF & Naming Convention in Vendor Portal - Proposal Import/exp | Bug Fixing | 2024-11 | 43
Fawad Ahmed | NEXELUS 2024.1 SP2 | UDF & Naming Convention in Vendor Portal - Proposal Import/exp | Development | 2024-10 | 57
Fawad Ahmed | NEXELUS 2024.1 SP2 | UDF & Naming Convention in Vendor Portal - Proposal Import/exp | Development | 2024-11 | 8
Fawad Ahmed | NEXELUS 2024.1 SP2 | UDF & Naming Convention in Vendor Portal - Proposal Import/exp | Development | 2024-12 | 0.5
Fawad Ahmed | NEXELUS 2024.2 | Client Items | Development | 2024-11 | 0
Fawad Ahmed | NEXELUS 2024.2 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-11 | 2
Fawad Ahmed | NEXELUS 2024.2 | Regular bug fixing activity | Development | 2024-09 | 44
Fawad Ahmed | NEXELUS 2025.1 | Import/exports flights | Bug Fixing | 2025-02 | 7
Fawad Ahmed | NEXELUS 2025.1 | Import/exports flights | Bug Fixing | 2025-03 | 6.49
Fawad Ahmed | NEXELUS 2025.1 | Import/exports flights | Development | 2025-03 | 12
Fawad Ahmed | NEXELUS 2025.1 | Import/exports flights | Testing | 2025-02 | 6
Fawad Ahmed | NEXELUS 2025.1 | Import/exports flights | Testing | 2025-03 | 13
Fawad Ahmed | NEXELUS 2025.1 | Project Overhead | Deployment | 2025-03 | 6
Fawad Ahmed | NEXELUS 2025.1 | Project Overhead | No Workbench | 2025-03 | 7
Fawad Ahmed | NEXELUS 2025.1 | Project Overhead | Post_dep_fixes | 2025-03 | 4.5
Fawad Ahmed | NEXELUS 2025.1 SP1 | Project Overhead | Post_dep_fixes | 2025-03 | 4
Fawad Ahmed | NEXELUS 2025.1 SP1 | Provide end date column in flight import export. | Development | 2025-03 | 14
Fawad Ahmed | NEXELUS 2025.1 SP1 | Provide end date column in flight import export. | Testing | 2025-03 | 8
Fawad Ahmed | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Development | 2025-03 | 2.5
Fawad Ahmed | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Documentation | 2025-03 | 2
Fawad Ahmed | NEXELUS 2025.2 | Alerting users when an FX rate is unavailable to prevent the | Meetings | 2025-04 | 1
Fawad Ahmed | NEXELUS 2025.2 | Allow manual adjustments for partial billing by the client | Bug Fixing | 2025-05 | 13
Fawad Ahmed | NEXELUS 2025.2 | Allow manual adjustments for partial billing by the client | Development | 2025-05 | 24
Fawad Ahmed | NEXELUS 2025.2 | Allow manual adjustments for partial billing by the client | Meetings | 2025-05 | 2
Fawad Ahmed | NEXELUS 2025.2 | Allow switching media plan from Media Plan UI | Documentation | 2025-03 | 2.5
Fawad Ahmed | NEXELUS 2025.2 | Exchange rate changes | Analysis | 2025-05 | 3
Fawad Ahmed | NEXELUS 2025.2 | Exchange rate changes | Bug Fixing | 2025-05 | 21
Fawad Ahmed | NEXELUS 2025.2 | Exchange rate changes | Development | 2025-05 | 62
Fawad Ahmed | NEXELUS 2025.2 | Exchange rate changes | Meetings | 2025-05 | 2
Fawad Ahmed | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Development | 2025-03 | 5
Fawad Ahmed | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Development | 2025-04 | 95
Fawad Ahmed | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Documentation | 2025-03 | 5
Fawad Ahmed | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Documentation | 2025-04 | 1
Fawad Ahmed | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Meetings | 2025-04 | 6.5
Fawad Ahmed | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Task/Code Review | 2025-04 | 3
Fawad Ahmed | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Test Case Dev | 2025-04 | 2
Fawad Ahmed | NEXELUS 2025.2 | Project Overhead | Documentation | 2025-04 | 2
Fawad Ahmed | NEXELUS 2025.2 | Project Overhead | No Workbench | 2025-03 | 9.5
Fawad Ahmed | NEXELUS 2025.2 | Project Overhead | Post_dep_fixes | 2025-03 | 4
Fawad Ahmed | NEXELUS SUPPORT | Maintenance Activity | Support Tickets | 2025-02 | 18
Fawad Ahmed | NEXELUS SUPPORT | Maintenance Activity | Support Tickets | 2025-03 | 1
Fawad Ahmed | NEXELUS SUPPORT | Maintenance Activity | Support Tickets | 2025-05 | 8
Fawad Ahmed | PR-0013 | Gazetted holidays | Leave | 2025-03 | 8
Fawad Ahmed | PR-0013 | Gazetted holidays | Leave | 2025-04 | 16
Fawad Ahmed | PR-0013 | Gazetted holidays | Leave | 2025-05 | 8
Fawad Ahmed | PR-0013 | In-house Training | Training | 2024-11 | 5.5
Fawad Ahmed | PR-0013 | In-house Training | Training | 2024-12 | 3
Fawad Ahmed | PR-0013 | In-house Training | Training | 2025-01 | 3.5
Fawad Ahmed | PR-0013 | Internal Meetings | Bug Fixing | 2024-12 | 1
Fawad Ahmed | PR-0013 | Internal Meetings | Meetings | 2024-11 | 5.15
Fawad Ahmed | PR-0013 | Internal Meetings | Meetings | 2024-12 | 17.25
Fawad Ahmed | PR-0013 | Internal Meetings | Meetings | 2025-01 | 43
Fawad Ahmed | PR-0013 | Internal Meetings | Meetings | 2025-02 | 25.5
Fawad Ahmed | PR-0013 | Internal Meetings | Meetings | 2025-03 | 32.5
Fawad Ahmed | PR-0013 | Internal Meetings | Meetings | 2025-04 | 22
Fawad Ahmed | PR-0013 | Internal Meetings | Meetings | 2025-05 | 23
Fawad Ahmed | PR-0013 | Time Off - Planned | Leave | 2024-12 | 32
Fawad Ahmed | PR-0013 | Time Off - Planned | Leave | 2025-01 | 8
Fawad Ahmed | PR-0013 | Time Off - Planned | Leave | 2025-02 | 16
Fawad Ahmed | PR-0013 | Time Off - Planned | Leave | 2025-04 | 16
Fawad Ahmed | PR-0013 | Time Off - Un Planned | Leave | 2024-11 | 8
Fawad Ahmed | PR-0013 | Time Off - Un Planned | Leave | 2024-12 | 4
Fawad Ahmed | Support and Maintenance | Time | Client Items | 2025-05 | 3
Fawad Ahmed | Support and Maintenance | Time | Support Tickets | 2025-01 | 9
Fawad Ahmed | Support and Maintenance | Time | Support Tickets | 2025-03 | 1
Fawad Ahmed | Support and Maintenance | Time | Support Tickets | 2025-04 | 5
Fawad Ahmed | Support and Maintenance | Time | Support Tickets | 2025-05 | 3
Hamza Nouman | AD-0001 | Meetings | Meetings | 2024-11 | 6
Hamza Nouman | AD-0001 | Meetings | Meetings | 2024-12 | 8
Hamza Nouman | AD-0001 | Time | Leave | 2024-09 | 8
Hamza Nouman | AD-0001 | Time | Leave | 2024-11 | 8
Hamza Nouman | AD-0001 | Time | Leave | 2024-12 | 8
Hamza Nouman | AD-0001 | Time | Leave | 2025-03 | 8
Hamza Nouman | AD-0001 | Time | Leave | 2025-04 | 16
Hamza Nouman | AD-0001 | Time | Leave | 2025-05 | 54
Hamza Nouman | AD-0001 | Time | No Workbench | 2024-11 | 1
Hamza Nouman | AD-0001 | Time | No Workbench | 2024-12 | 1.5
Hamza Nouman | AD-0001 | Time | No Workbench | 2025-02 | 16
Hamza Nouman | AD-0001 | Time | No Workbench | 2025-03 | 11
Hamza Nouman | AD-0001 | Time | No Workbench | 2025-04 | 6
Hamza Nouman | AP WORKFLOW | Cient UAT Upgrade | Testing | 2024-09 | 4
Hamza Nouman | AP WORKFLOW | Cient UAT Upgrade | Testing | 2024-10 | 18
Hamza Nouman | AP WORKFLOW | Regular bug fixing activity | Other | 2024-08 | 16
Hamza Nouman | AP WORKFLOW | Regular bug fixing activity | Testing | 2024-09 | 13
Hamza Nouman | AP WORKFLOW | Regular testing and QA new project/assignment/task | Other | 2024-08 | 6
Hamza Nouman | AP WORKFLOW | Regular testing and QA new project/assignment/task | Testing | 2024-08 | 18
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: EDI File Processing | Test Case Dev | 2024-10 | 6
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: EDI File Processing | Testing | 2024-10 | 52.5
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | Broadcast Invoice: EDI File Processing | Testing | 2024-11 | 33
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | Documentation | Documentation | 2024-09 | 1
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Test Case Dev | 2024-09 | 39
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Test Case Dev | 2024-10 | 3
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Testing | 2024-10 | 67.5
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | Testing | 2024-11 | 31
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | Route invoice from one company - company identification | Testing | 2024-11 | 3
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Bug Fixing | 2024-12 | 5
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Testing | 2024-11 | 4
Hamza Nouman | APWORKS 2024.2 - PHASE 3 | Tolerance by media type | Testing | 2024-08 | 13
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | Broadcast Model Fields | Testing | 2025-01 | 10
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | EDI file updating and upload | Testing | 2024-12 | 3
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | EDI file updating and upload | Testing | 2025-01 | 8
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | EDI: Generate PDF - Updates | Testing | 2025-01 | 16
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | Google Drive Setup (company configuration UI) | Testing | 2024-11 | 5
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | Google Drive Setup (company configuration UI) | Testing | 2024-12 | 10
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | Google Drive Setup (company configuration UI) | Testing | 2025-01 | 16
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | Google Drive Setup (company configuration UI) | Testing | 2025-02 | 8
Hamza Nouman | APWORKS 2024.2 - PHASE 4 | Project Overhead | Post_dep_fixes | 2024-12 | 7
Hamza Nouman | APWORKS 2024.2 PHASE 5 | Project Overhead | Analysis | 2024-12 | 5
Hamza Nouman | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Testing | 2025-04 | 14
Hamza Nouman | APWORKS 2025.2 | Project Overhead | Post_dep_fixes | 2025-04 | 5
Hamza Nouman | APWORKS 2025.2 | Project Overhead | Research | 2025-04 | 8
Hamza Nouman | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Testing | 2025-04 | 12
Hamza Nouman | APWORKS PHASE2 | Internal Meetings | Meetings | 2024-09 | 8
Hamza Nouman | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-09 | 50.5
Hamza Nouman | APWORKS PHASE2 | User Manual OR Release Notes | Documentation | 2025-02 | 10
Hamza Nouman | NEXELUS 14.0 | Internal Meetings | Other | 2024-08 | 11
Hamza Nouman | NEXELUS 2024.1 SP2 | AdTech Fee commission | Testing | 2024-12 | 32
Hamza Nouman | NEXELUS 2024.1 SP2 | AdTech Fee commission | Testing | 2025-01 | 18
Hamza Nouman | NEXELUS 2024.1 SP2 | Billing by Media Type | Testing | 2024-12 | 14
Hamza Nouman | NEXELUS 2024.1 SP2 | Billing by Media Type | Testing | 2025-01 | 7
Hamza Nouman | NEXELUS 2024.1 SP2 | Client Profile: Media > Flag to make the vendor inactive | Testing | 2025-01 | 6
Hamza Nouman | NEXELUS 2024.1 SP2 | Documentation | Documentation | 2024-11 | 4
Hamza Nouman | NEXELUS 2024.1 SP2 | Documentation | Documentation | 2024-12 | 10.5
Hamza Nouman | NEXELUS 2024.1 SP2 | Documentation | Documentation | 2025-02 | 6
Hamza Nouman | NEXELUS 2024.1 SP2 | Documentation | Testing | 2024-12 | 3
Hamza Nouman | NEXELUS 2024.1 SP2 | Enhancement for Visual Indicators and Flighting Details in Place | Testing | 2024-12 | 17
Hamza Nouman | NEXELUS 2024.1 SP2 | Enhancement for Visual Indicators and Flighting Details in Place | Testing | 2025-01 | 9
Hamza Nouman | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Testing | 2025-02 | 8
Hamza Nouman | NEXELUS 2024.1 SP2 | Media Plan Approval | Testing | 2024-11 | 5
Hamza Nouman | NEXELUS 2024.1 SP2 | Media Plan Approval | Testing | 2025-02 | 6
Hamza Nouman | NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting | Testing | 2024-12 | 14
Hamza Nouman | NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting | Testing | 2025-01 | 32
Hamza Nouman | NEXELUS 2024.1 SP2 | UDF & Naming Convention in Nexelus - Export on Proposal | Testing | 2025-02 | 18
Hamza Nouman | NEXELUS 2024.1 SP2 | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | Testing | 2025-01 | 5
Hamza Nouman | NEXELUS 2024.1 SP2 | UDF & Naming Convention in Vendor Portal - Proposal Import/exp | Testing | 2025-02 | 6
Hamza Nouman | NEXELUS 2024.2 | Cient UAT Upgrade | Testing | 2024-10 | 4
Hamza Nouman | NEXELUS 2024.2 | Client Items | Other | 2024-08 | 48
Hamza Nouman | NEXELUS 2024.2 | Internal Meetings | Meetings | 2024-08 | 11
Hamza Nouman | NEXELUS 2024.2 | Regular testing and QA new project/assignment/task | Testing | 2024-08 | 49
Hamza Nouman | NEXELUS 2024.2 | Regular testing and QA new project/assignment/task | Testing | 2024-09 | 1
Hamza Nouman | NEXELUS 2025.1 | Import/exports flights | Testing | 2025-02 | 16
Hamza Nouman | NEXELUS 2025.1 | Import/exports flights | Testing | 2025-03 | 40
Hamza Nouman | NEXELUS 2025.1 | Margin change for TTD | Documentation | 2025-03 | 2
Hamza Nouman | NEXELUS 2025.1 | Margin change for TTD | Testing | 2025-03 | 2
Hamza Nouman | NEXELUS 2025.1 SP1 | Project Overhead | Analysis | 2025-03 | 5
Hamza Nouman | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Testing | 2025-04 | 8
Hamza Nouman | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Testing | 2025-05 | 2
Hamza Nouman | NEXELUS 2025.2 | Allow switching media plan from Media Plan UI | Testing | 2025-04 | 9
Hamza Nouman | NEXELUS 2025.2 | Allow switching media plan from Media Plan UI | Testing | 2025-05 | 2
Hamza Nouman | NEXELUS 2025.2 | DENTSU CHANGES: Enhance Close Job functionality | Testing | 2025-05 | 35
Hamza Nouman | NEXELUS 2025.2 | DENTSU CHANGES: Enhance Close Job functionality | Testing | 2025-06 | 16
Hamza Nouman | NEXELUS 2025.2 | Project Overhead | Analysis | 2025-03 | 6
Hamza Nouman | NEXELUS 2025.2 | Project Overhead | Deployment | 2025-04 | 1
Hamza Nouman | NEXELUS 2025.2 | Project Overhead | Documentation | 2025-04 | 21
Hamza Nouman | NEXELUS 2025.2 | Project Overhead | Research | 2025-04 | 4
Hamza Nouman | NEXELUS 2025.2 | Project Overhead | Task Domain | 2025-04 | 17
Hamza Nouman | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Testing | 2025-05 | 62
Hamza Nouman | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Testing | 2025-06 | 26
Hamza Nouman | NEXELUS 2025.2 | Starred media plans (NEX 17059) | Testing | 2025-04 | 3
Hamza Nouman | PR-0013 | Cient UAT Upgrade | Testing | 2025-01 | 8
Hamza Nouman | PR-0013 | Cient UAT Upgrade | Testing | 2025-03 | 24
Hamza Nouman | PR-0013 | Client Items | Testing | 2025-01 | 3
Hamza Nouman | PR-0013 | In-house Training | Analysis | 2025-02 | 13
Hamza Nouman | PR-0013 | In-house Training | Training | 2025-02 | 11
Hamza Nouman | PR-0013 | Internal Meetings | Meetings | 2024-09 | 6
Hamza Nouman | PR-0013 | Internal Meetings | Meetings | 2024-10 | 22
Hamza Nouman | PR-0013 | Internal Meetings | Meetings | 2024-11 | 9
Hamza Nouman | PR-0013 | Internal Meetings | Meetings | 2024-12 | 10
Hamza Nouman | PR-0013 | Internal Meetings | Meetings | 2025-01 | 14
Hamza Nouman | PR-0013 | Internal Meetings | Meetings | 2025-02 | 18
Hamza Nouman | PR-0013 | Internal Meetings | Meetings | 2025-03 | 17
Hamza Nouman | PR-0013 | Internal Meetings | Meetings | 2025-04 | 23
Hamza Nouman | PR-0013 | Internal Meetings | Meetings | 2025-05 | 21
Hamza Nouman | PR-0013 | Internal Meetings | Meetings | 2025-06 | 10
Hamza Nouman | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 4
Hamza Nouman | PR-0013 | Production upgrades | Testing | 2025-06 | 12
Hamza Nouman | PR-0013 | Requirement Specifications document writing | Analysis | 2024-09 | 14
Hamza Nouman | PR-0013 | Time Off - Planned | Leave | 2024-09 | 8
Hamza Nouman | PR-0013 | Time Off - Planned | Leave | 2024-12 | 8
Hamza Nouman | PR-0013 | Time Off - Planned | Leave | 2025-01 | 8
Hamza Nouman | PR-0013 | Time Off - Planned | Leave | 2025-04 | 8
Hamza Nouman | PR-0013 | Time Off - Un Planned | Leave | 2024-09 | 12.5
Hamza Nouman | PR-0013 | Time Off - Un Planned | Leave | 2024-10 | 10
Hamza Nouman | PR-0013 | Time Off - Un Planned | Leave | 2024-11 | 12
Hamza Nouman | PR-0013 | Time Off - Un Planned | Leave | 2024-12 | 8
Hamza Nouman | PR-0013 | Time Off - Un Planned | Leave | 2025-01 | 16
Hamza Nouman | PR-0013 | Time Off - Un Planned | Leave | 2025-02 | 8
Hamza Nouman | PR-0013 | Time Off - Un Planned | Leave | 2025-03 | 7
Hamza Nouman | PR-0013 | Time Off - Un Planned | No Workbench | 2024-10 | 1
Hamza Nouman | Support and Maintenance | Time | Client Items | 2024-11 | 47
Hamza Nouman | Support and Maintenance | Time | Client Items | 2024-12 | 4
Hamza Nouman | Support and Maintenance | Time | Client Items | 2025-01 | 9
Hamza Nouman | Support and Maintenance | Time | Client Items | 2025-02 | 8
Hamza Nouman | Support and Maintenance | Time | Client Items | 2025-03 | 12
Hamza Nouman | Support and Maintenance | Time | Client Items | 2025-04 | 21
Hamza Nouman | Support and Maintenance | Time | Support Tickets | 2025-05 | 8
Imran UL Haq | AD-0001 | HR ad Admin Activities | Interview | 2025-04 | 9
Imran UL Haq | AD-0001 | HR ad Admin Activities | Interview | 2025-05 | 1
Imran UL Haq | AD-0001 | Meetings | Training | 2025-06 | 1
Imran UL Haq | AP WORKFLOW | Development of new project/assignment/task | Other | 2024-08 | 33
Imran UL Haq | AP WORKFLOW | Regular bug fixing activity | Other | 2024-08 | 13
Imran UL Haq | AP WORKFLOW | Release Environment Upgrade | Deployment | 2024-09 | 6
Imran UL Haq | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Development | 2024-10 | 7
Imran UL Haq | APWORKS 2024.2 - PHASE 4 | Integration Testing | Bug Fixing | 2024-12 | 85
Imran UL Haq | APWORKS 2024.2 - PHASE 4 | Integration Testing | Bug Fixing | 2025-01 | 16
Imran UL Haq | APWORKS 2024.2 - PHASE 4 | Project Overhead | Post_dep_fixes | 2024-11 | 16
Imran UL Haq | APWORKS 2024.2 - PHASE 4 | Pull Client & Sites, Service types as Media Types from Nexelus | Development | 2024-12 | 4
Imran UL Haq | APWORKS 2024.2 PHASE 5 | Project Overhead | Deployment | 2025-01 | 1
Imran UL Haq | APWORKS 2024.2 PHASE 5 | Project Overhead | Post_dep_fixes | 2025-01 | 7
Imran UL Haq | APWORKS PHASE1 | Regular bug fixing activity | Other | 2024-08 | 1
Imran UL Haq | APWORKS PHASE2 | Analysis of production issues reported by support team | Analysis | 2024-09 | 11
Imran UL Haq | APWORKS PHASE2 | Development of new project/assignment/task | Development | 2024-10 | 15
Imran UL Haq | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-08 | 1
Imran UL Haq | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-10 | 8
Imran UL Haq | APWORKS PHASE2 | Regular bug fixing activity | Bug Fixing | 2024-11 | 2
Imran UL Haq | APWORKS PHASE2 | Support Items | Meetings | 2024-09 | 1
Imran UL Haq | NEXELUS 2024.1 SP2 | Billing by Media Type | Bug Fixing | 2024-12 | 3
Imran UL Haq | NEXELUS 2024.1 SP2 | Project Overhead | Analysis | 2024-12 | 1
Imran UL Haq | NEXELUS 2024.1 SP2 | Project Overhead | Deployment | 2024-12 | 5
Imran UL Haq | NEXELUS 2024.1 SP2 | Project Overhead | Post_dep_fixes | 2025-01 | 1
Imran UL Haq | NEXELUS 2024.2 | Analysis of production issues reported by support team | Analysis | 2024-09 | 4
Imran UL Haq | NEXELUS 2024.2 | Analysis of production issues reported by support team | Analysis | 2024-10 | 5
Imran UL Haq | NEXELUS 2024.2 | Analysis of production issues reported by support team | Bug Fixing | 2024-10 | 13
Imran UL Haq | NEXELUS 2024.2 | Analysis of the new project/assignment/task | Other | 2024-08 | 1
Imran UL Haq | NEXELUS 2024.2 | Client Items | Client Items | 2024-09 | 92
Imran UL Haq | NEXELUS 2024.2 | Client Items | Client Items | 2024-10 | 40
Imran UL Haq | NEXELUS 2024.2 | Client Items | Development | 2024-08 | 36.5
Imran UL Haq | NEXELUS 2024.2 | Client Items | Development | 2024-09 | 2
Imran UL Haq | NEXELUS 2024.2 | Client Items | Meetings | 2024-09 | 1
Imran UL Haq | NEXELUS 2024.2 | Client Items | Other | 2024-08 | 92
Imran UL Haq | NEXELUS 2024.2 | Development of new project/assignment/task | Development | 2024-09 | 3
Imran UL Haq | NEXELUS 2024.2 | In-house Training | Meetings | 2024-10 | 1
Imran UL Haq | NEXELUS 2024.2 | In-house Training | Other | 2024-08 | 1
Imran UL Haq | NEXELUS 2024.2 | Internal Meetings | Meetings | 2024-09 | 1
Imran UL Haq | NEXELUS 2024.2 | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 9
Imran UL Haq | NEXELUS 2024.2 | National Gazetted Holidays | Leave | 2024-09 | 8
Imran UL Haq | NEXELUS 2024.2 | National Gazetted Holidays | Other | 2024-08 | 8
Imran UL Haq | NEXELUS 2024.2 | Production upgrades | Development | 2024-09 | 5
Imran UL Haq | NEXELUS 2024.2 | Regular bug fixing activity | Bug Fixing | 2024-10 | 1
Imran UL Haq | NEXELUS 2024.2 | Regular bug fixing activity | Bug Fixing | 2024-11 | 6
Imran UL Haq | NEXELUS 2024.2 | Support Items | Analysis | 2024-11 | 1
Imran UL Haq | NEXELUS 2024.2 | Support Items | Bug Fixing | 2024-09 | 2
Imran UL Haq | NEXELUS 2024.2 | Support Items | Bug Fixing | 2024-10 | 5
Imran UL Haq | NEXELUS 2024.2 | Time Off - Planned | Leave | 2024-09 | 8
Imran UL Haq | NEXELUS SUPPORT | Maintenance Activity | Deployment | 2024-12 | 1
Imran UL Haq | PR-0013 | Analysis of production issues reported by support team | Bug Fixing | 2025-05 | 4
Imran UL Haq | PR-0013 | Analysis of production issues reported by support team | Support Tickets | 2025-05 | 6
Imran UL Haq | PR-0013 | Cient UAT Upgrade | Bug Fixing | 2025-03 | 3
Imran UL Haq | PR-0013 | Cient UAT Upgrade | Development | 2025-03 | 3
Imran UL Haq | PR-0013 | Development of new project/assignment/task | Deployment | 2025-02 | 3
Imran UL Haq | PR-0013 | Development of new project/assignment/task | Development | 2024-09 | 28
Imran UL Haq | PR-0013 | Development of new project/assignment/task | Development | 2024-12 | 3
Imran UL Haq | PR-0013 | Development of new project/assignment/task | Development | 2025-03 | 10
Imran UL Haq | PR-0013 | Development of new project/assignment/task | Development | 2025-05 | 7
Imran UL Haq | PR-0013 | Gazetted holidays | Leave | 2025-02 | 8
Imran UL Haq | PR-0013 | Gazetted holidays | Leave | 2025-03 | 8
Imran UL Haq | PR-0013 | Gazetted holidays | Leave | 2025-04 | 16
Imran UL Haq | PR-0013 | Gazetted holidays | Leave | 2025-05 | 8
Imran UL Haq | PR-0013 | Gazetted holidays | Leave | 2025-06 | 16
Imran UL Haq | PR-0013 | In-house Training | Training | 2025-02 | 11
Imran UL Haq | PR-0013 | In-house Training | Training | 2025-03 | 12
Imran UL Haq | PR-0013 | In-house Training | Training | 2025-04 | 17
Imran UL Haq | PR-0013 | In-house Training | Training | 2025-05 | 21
Imran UL Haq | PR-0013 | In-house Training | Training | 2025-06 | 5
Imran UL Haq | PR-0013 | Meetings, mails, communication, TFS, Interviews | Documentation | 2025-02 | 11
Imran UL Haq | PR-0013 | Meetings, mails, communication, TFS, Interviews | Leave | 2024-12 | 8
Imran UL Haq | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-08 | 2.5
Imran UL Haq | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-09 | 1
Imran UL Haq | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-10 | 2
Imran UL Haq | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2025-02 | 4
Imran UL Haq | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2025-04 | 2.5
Imran UL Haq | PR-0013 | Meetings, mails, communication, TFS, Interviews | No Workbench | 2025-02 | 8
Imran UL Haq | PR-0013 | Meetings, mails, communication, TFS, Interviews | Support Tickets | 2024-12 | 1
Imran UL Haq | PR-0013 | Production upgrades | Bug Fixing | 2025-01 | 36
Imran UL Haq | PR-0013 | Production upgrades | Deployment | 2025-01 | 18
Imran UL Haq | PR-0013 | QA Environment Upgrade | Support Tickets | 2024-12 | 12
Imran UL Haq | Support and Maintenance | Time | Client Items | 2024-10 | 89
Imran UL Haq | Support and Maintenance | Time | Client Items | 2024-11 | 143
Imran UL Haq | Support and Maintenance | Time | Client Items | 2024-12 | 49
Imran UL Haq | Support and Maintenance | Time | Client Items | 2025-01 | 141
Imran UL Haq | Support and Maintenance | Time | Client Items | 2025-02 | 107
Imran UL Haq | Support and Maintenance | Time | Client Items | 2025-03 | 119
Imran UL Haq | Support and Maintenance | Time | Client Items | 2025-04 | 125
Imran UL Haq | Support and Maintenance | Time | Client Items | 2025-05 | 121
Imran UL Haq | Support and Maintenance | Time | Client Items | 2025-06 | 58
Imran UL Haq | Support and Maintenance | Time | Support Tickets | 2024-12 | 4
Imran UL Haq | Support and Maintenance | Time | Support Tickets | 2025-02 | 4
Imran UL Haq | Support and Maintenance | Time | Support Tickets | 2025-04 | 8
Imran UL Haq | Support and Maintenance | Time | Support Tickets | 2025-05 | 8
Kashif Hayat | AD-0001 | Time | Leave | 2024-09 | 8
Kashif Hayat | AD-0001 | Time | Leave | 2024-10 | 8
Kashif Hayat | AD-0001 | Time | Leave | 2025-02 | 24
Kashif Hayat | AD-0001 | Time | Leave | 2025-03 | 16
Kashif Hayat | AD-0001 | Time | Leave | 2025-04 | 56
Kashif Hayat | AD-0001 | Time | Leave | 2025-05 | 12
Kashif Hayat | AD-0001 | Time | No Workbench | 2025-02 | 9
Kashif Hayat | AP WORKFLOW | Analysis of production issues reported by support team | Other | 2024-08 | 3
Kashif Hayat | AP WORKFLOW | Analysis of the new project/assignment/task | Other | 2024-08 | 1
Kashif Hayat | AP WORKFLOW | Document review/understanding Requirement Specifications | Other | 2024-08 | 11
Kashif Hayat | AP WORKFLOW | Internal Meetings | Other | 2024-08 | 6
Kashif Hayat | AP WORKFLOW | Project planning for new project/assignment/task | Other | 2024-08 | 3
Kashif Hayat | AP WORKFLOW | QA Environment Upgrade | Other | 2024-08 | 39
Kashif Hayat | AP WORKFLOW | Regular bug fixing activity | Other | 2024-08 | 9
Kashif Hayat | AP WORKFLOW | Regular testing and QA new project/assignment/task | Analysis | 2024-11 | 8
Kashif Hayat | AP WORKFLOW | Regular testing and QA new project/assignment/task | Other | 2024-08 | 46
Kashif Hayat | AP WORKFLOW | Release Environment Upgrade | Other | 2024-08 | 6
Kashif Hayat | AP WORKFLOW | Requirement Specifications document writing | Other | 2024-08 | 11
Kashif Hayat | APWORKS - TEST AUTOMATION | Media approval: approve invoices | Development | 2025-04 | 24
Kashif Hayat | APWORKS - TEST AUTOMATION | Media: Discrepant Invoices - Make Corrections | Development | 2025-04 | 4
Kashif Hayat | APWORKS - TEST AUTOMATION | Media: Read Data diven excel files for the correspinding data | Design | 2025-04 | 8
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Meetings | 2024-09 | 16
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Test Case Dev | 2024-09 | 3
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Test Case Dev | 2024-10 | 3
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Testing | 2024-10 | 33
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | Testing | 2024-11 | 4
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Test Case Dev | 2024-09 | 9
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Test Case Dev | 2024-10 | 2
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Testing | 2024-10 | 44
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | Testing | 2024-11 | 4
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Apply discount based on Payment terms settings | Testing | 2024-11 | 2
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Customer Information: Select Client on Vendor Invoice | Testing | 2024-10 | 4
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Customer Information: Select Client on Vendor Invoice | Testing | 2024-11 | 6
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Invoice Editing: Make the tax editable | Analysis | 2024-11 | 2
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Remove Site column from vendor lookup | Testing | 2024-11 | 1
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | Documentation | 2024-10 | 1
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Vendor/stations/sites associated to multiple pay to. | Testing | 2024-10 | 29
Kashif Hayat | APWORKS 2024.2 - PHASE 3 | Vendor/stations/sites associated to multiple pay to. | Testing | 2024-11 | 2
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Apply variable name for Site in vendor mapping | Testing | 2024-12 | 2
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Approval routing | Testing | 2024-12 | 8
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Approve upto last level and auto post. | Analysis | 2024-11 | 4
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Approve upto last level and auto post. | Testing | 2024-11 | 6
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Approve upto last level and auto post. | Testing | 2024-12 | 8
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Broadcast Model Fields | Testing | 2025-01 | 10
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Currency Changes on Vendor Map | Analysis | 2024-11 | 2
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Currency Changes on Vendor Map | Testing | 2024-12 | 2
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Deadlock issue | Testing | 2025-01 | 1
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | EDI file updating and upload | Testing | 2025-01 | 22
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Integration Testing | Bug Fixing | 2024-11 | 12
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Approvals | Testing | 2025-01 | 12
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Import / Export lines | Testing | 2025-01 | 13
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Production: Auto populate lines based PO during scanning | Testing | 2024-11 | 3
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Production: Auto populate lines based PO during scanning | Testing | 2024-12 | 6
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Production: Project should be available on summary as well. | Analysis | 2024-12 | 4
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Production: show keyvalue pairs for level2 mapping | Bug Fixing | 2024-12 | 4
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Project Overhead | Analysis | 2024-12 | 24
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Stamp multiple approvers. | Testing | 2024-11 | 1
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Tax implementation(rule)/column for difference | Testing | 2025-01 | 24
Kashif Hayat | APWORKS 2024.2 - PHASE 4 | Tax implementation(rule)/column for difference | Testing | 2025-02 | 25
Kashif Hayat | APWORKS 2024.2 PHASE 5 | Project Overhead | Analysis | 2024-12 | 80
Kashif Hayat | APWORKS 2024.2 PHASE 5 | Project Overhead | Analysis | 2025-01 | 64
Kashif Hayat | APWORKS 2025.1 | Add client column on Discrepant Gadget | Testing | 2025-03 | 2
Kashif Hayat | APWORKS 2025.1 | Invoice UI: Invoice Preview Zoom Feature | Testing | 2025-03 | 3
Kashif Hayat | APWORKS 2025.1 | Project Overhead | Research | 2025-03 | 112
Kashif Hayat | APWORKS 2025.1 | Vendor Mapping: Allow User to Date Format | Testing | 2025-03 | 2
Kashif Hayat | APWORKS 2025.2 | Ability to Approve the invoice when resolving discrepancy | Testing | 2025-05 | 24
Kashif Hayat | APWORKS 2025.2 | Ability to Approve the invoice when resolving discrepancy | Testing | 2025-06 | 4
Kashif Hayat | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Testing | 2025-05 | 8
Kashif Hayat | APWORKS 2025.2 | Credit Memo | Testing | 2025-05 | 56
Kashif Hayat | APWORKS 2025.2 | Credit Memo | Testing | 2025-06 | 27
Kashif Hayat | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Testing | 2025-05 | 20
Kashif Hayat | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Testing | 2025-06 | 8
Kashif Hayat | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Testing | 2025-06 | 9
Kashif Hayat | APWORKS 2025.2 | Split invoice by MOS - Print / OOH / Digital | Testing | 2025-06 | 24
Kashif Hayat | APWORKS 2025.2 | Warren Lamb provided PDF ingestion | Testing | 2025-05 | 32
Kashif Hayat | APWORKS 2025.2 | Warren Lamb provided PDF ingestion | Testing | 2025-06 | 23
Kashif Hayat | APWORKS 2025.2 SP1 | For "No filter' all data not getting shown | Testing | 2025-06 | 21
Kashif Hayat | APWORKS 2025.2 SP1 | Make date fields editable for Broadcast | Testing | 2025-06 | 12
Kashif Hayat | APWORKS 2025.2 SP1 | Manage invoice list optimization | Testing | 2025-06 | 4.5
Kashif Hayat | APWORKS PHASE2 | Analysis of production issues reported by support team | Client Items | 2024-09 | 15
Kashif Hayat | APWORKS PHASE2 | Cient UAT Upgrade | Client Items | 2024-10 | 11
Kashif Hayat | APWORKS PHASE2 | Cient UAT Upgrade | Testing | 2024-10 | 8
Kashif Hayat | APWORKS PHASE2 | Client Items | Testing | 2024-10 | 13
Kashif Hayat | APWORKS PHASE2 | Dev Support | Analysis | 2024-08 | 5
Kashif Hayat | APWORKS PHASE2 | Internal Meetings | Meetings | 2024-09 | 15
Kashif Hayat | APWORKS PHASE2 | Internal Meetings | Meetings | 2024-10 | 4
Kashif Hayat | APWORKS PHASE2 | Internal Meetings | Testing | 2024-09 | 30
Kashif Hayat | APWORKS PHASE2 | QA Environment Upgrade | Testing | 2024-08 | 22
Kashif Hayat | APWORKS PHASE2 | QA Environment Upgrade | Testing | 2024-09 | 4
Kashif Hayat | APWORKS PHASE2 | QA Environment Upgrade | Testing | 2024-10 | 9
Kashif Hayat | APWORKS PHASE2 | QA Environment Upgrade | Testing | 2024-11 | 16
Kashif Hayat | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-08 | 10
Kashif Hayat | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-09 | 52
Kashif Hayat | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-10 | 8
Kashif Hayat | APWORKS PHASE2 | Regular testing and QA new project/assignment/task | Testing | 2024-11 | 23
Kashif Hayat | PR-0013 | Cient UAT Upgrade | Analysis | 2024-11 | 2
Kashif Hayat | PR-0013 | Cient UAT Upgrade | Testing | 2025-01 | 44
Kashif Hayat | PR-0013 | In-house Training | Training | 2024-11 | 2
Kashif Hayat | PR-0013 | Internal Meetings | Meetings | 2024-11 | 1
Kashif Hayat | PR-0013 | Meetings, mails, communication, TFS, Interviews | Meetings | 2024-11 | 1
Kashif Hayat | PR-0013 | Production upgrades | Testing | 2025-01 | 16
Kashif Hayat | PR-0013 | QA Environment Upgrade | Testing | 2024-11 | 4
Kashif Hayat | PR-0013 | Time Off - Planned | Leave | 2024-09 | 8
Kashif Hayat | PR-0013 | Time Off - Planned | Leave | 2024-11 | 32
Kashif Hayat | PR-0013 | Time Off - Planned | Leave | 2024-12 | 8
Kashif Hayat | PR-0013 | Time Off - Planned | No Workbench | 2025-03 | 8
Kashif Hayat | PR-0013 | Time Off - Un Planned | Leave | 2024-10 | 8
Kashif Hayat | PR-0013 | Time Off - Un Planned | Leave | 2024-11 | 24
Kashif Hayat | PR-0013 | Time Off - Un Planned | Leave | 2024-12 | 8
Kashif Hayat | PR-0013 | Time Off - Un Planned | Leave | 2025-01 | 8
Kashif Hayat | Support and Maintenance | Time | Client Items | 2024-11 | 8
Kashif Hayat | Support and Maintenance | Time | Client Items | 2024-12 | 20
Kashif Hayat | Support and Maintenance | Time | Client Items | 2025-02 | 110
Kashif Hayat | Support and Maintenance | Time | Client Items | 2025-03 | 17
Kashif Hayat | Support and Maintenance | Time | Client Items | 2025-04 | 60
Kashif Hayat | Support and Maintenance | Time | Client Items | 2025-05 | 16
Kashif Hayat | Support and Maintenance | Time | Client Items | 2025-06 | 8
Mohsin Raza | Support and Maintenance | Time | Client Items | 2025-06 | 96
Muhammad Hamayun | AD-0001 | Meetings | Meetings | 2025-05 | 8
Muhammad Hamayun | AD-0001 | Network and infrastructure Support | No Workbench | 2025-04 | 2
Muhammad Hamayun | AD-0001 | Time | Admin | 2025-04 | 4.5
Muhammad Hamayun | AD-0001 | Time | Admin | 2025-05 | 6.5
Muhammad Hamayun | AD-0001 | Time | Admin | 2025-06 | 1
Muhammad Hamayun | AD-0001 | Time | Deployment | 2025-04 | 6.5
Muhammad Hamayun | AD-0001 | Time | Deployment | 2025-05 | 9
Muhammad Hamayun | APWORKS - SUPPORT | Maintenance Activity | General | 2025-06 | 1
Muhammad Hamayun | APWORKS - SUPPORT | Maintenance Activity | JustGlobal | 2025-06 | 2
Muhammad Hamayun | APWORKS - SUPPORT | Maintenance Activity | PlusCo | 2025-05 | 23
Muhammad Hamayun | APWORKS 2025.2 | Project Overhead | Deployment | 2025-04 | 6.5
Muhammad Hamayun | APWORKS 2025.2 | Project Overhead | Deployment | 2025-05 | 8
Muhammad Hamayun | APWORKS 2025.2 | Project Overhead | Deployment | 2025-06 | 4
Muhammad Hamayun | APWORKS 2025.2 | Project Overhead | Support Tickets | 2025-04 | 1
Muhammad Hamayun | APWORKS 2025.2 SP1 | For "No filter' all data not getting shown | Development | 2025-06 | 2
Muhammad Hamayun | APWORKS 2025.2 SP1 | Manage invoice list optimization | Development | 2025-06 | 1
Muhammad Hamayun | APWORKS 2025.2 SP1 | Project Overhead | Deployment | 2025-06 | 1.5
Muhammad Hamayun | NEXELUS 2025.2 | Project Overhead | Deployment | 2025-04 | 2.5
Muhammad Hamayun | NEXELUS 2025.2 | Project Overhead | Deployment | 2025-06 | 12
Muhammad Hamayun | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Development | 2025-05 | 1.5
Muhammad Hamayun | NEXELUS SUPPORT | Maintenance Activity | Deployment | 2025-04 | 1
Muhammad Hamayun | NEXELUS SUPPORT | Maintenance Activity | Deployment | 2025-05 | 5.5
Muhammad Hamayun | PR-0013 | Cient UAT Upgrade | Deployment | 2025-04 | 2
Muhammad Hamayun | PR-0013 | Gazetted holidays | Leave | 2025-03 | 8
Muhammad Hamayun | PR-0013 | Gazetted holidays | Leave | 2025-04 | 16
Muhammad Hamayun | PR-0013 | Gazetted holidays | Leave | 2025-05 | 8
Muhammad Hamayun | PR-0013 | Gazetted holidays | Leave | 2025-06 | 16
Muhammad Hamayun | PR-0013 | In-house Training | Training | 2025-02 | 45
Muhammad Hamayun | PR-0013 | In-house Training | Training | 2025-04 | 62
Muhammad Hamayun | PR-0013 | In-house Training | Training | 2025-05 | 37.5
Muhammad Hamayun | PR-0013 | In-house Training | Training | 2025-06 | 1
Muhammad Hamayun | PR-0013 | Internal Meetings | Deployment | 2025-04 | 1
Muhammad Hamayun | PR-0013 | Internal Meetings | Meetings | 2025-04 | 12
Muhammad Hamayun | PR-0013 | Internal Meetings | Meetings | 2025-05 | 17.5
Muhammad Hamayun | PR-0013 | Internal Meetings | Meetings | 2025-06 | 3
Muhammad Hamayun | PR-0013 | Production upgrades | Deployment | 2025-04 | 3
Muhammad Hamayun | PR-0013 | Release Environment Upgrade | Deployment | 2025-04 | 2
Muhammad Hamayun | PR-0013 | Time Off - Un Planned | Leave | 2025-04 | 8
Muhammad Hamayun | Support and Maintenance | Time | Client Items | 2025-04 | 46
Muhammad Hamayun | Support and Maintenance | Time | Client Items | 2025-05 | 50.5
Muhammad Hamayun | Support and Maintenance | Time | Client Items | 2025-06 | 35.5
Muhammad Hamayun | Support and Maintenance | Time | Support Tickets | 2025-05 | 1
Muhammad Yasir | AD-0001 | Time | Leave | 2025-06 | 4
Muhammad Yasir | APWORKS - SUPPORT | Maintenance Activity | General | 2025-05 | 1
Muhammad Yasir | APWORKS - SUPPORT | Maintenance Activity | General | 2025-06 | 3
Muhammad Yasir | APWORKS - SUPPORT | Maintenance Activity | JustGlobal | 2025-05 | 3
Muhammad Yasir | APWORKS - TEST AUTOMATION | Project Overhead | Analysis | 2025-05 | 1
Muhammad Yasir | APWORKS 2025.2 | Ability to create templates across multiple Companies | Bug Fixing | 2025-05 | 12
Muhammad Yasir | APWORKS 2025.2 | Ability to create templates across multiple Companies | Bug Fixing | 2025-06 | 1
Muhammad Yasir | APWORKS 2025.2 | Ability to create templates across multiple Companies | Development | 2025-04 | 19.5
Muhammad Yasir | APWORKS 2025.2 | Ability to create templates across multiple Companies | Development | 2025-05 | 18.5
Muhammad Yasir | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Bug Fixing | 2025-05 | 2
Muhammad Yasir | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Development | 2025-04 | 8
Muhammad Yasir | APWORKS 2025.2 | Auto populate call letters; media type and band after 1st maping | Development | 2025-05 | 2
Muhammad Yasir | APWORKS 2025.2 | Credit Memo | Bug Fixing | 2025-05 | 10.5
Muhammad Yasir | APWORKS 2025.2 | Credit Memo | Development | 2025-04 | 18.5
Muhammad Yasir | APWORKS 2025.2 | Credit Memo | Development | 2025-05 | 7
Muhammad Yasir | APWORKS 2025.2 | Display client #, when inv is linked to IO in all UIs and Report | Development | 2025-04 | 6
Muhammad Yasir | APWORKS 2025.2 | Nexelus Email Function for IO | Development | 2025-05 | 3
Muhammad Yasir | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Bug Fixing | 2025-05 | 5
Muhammad Yasir | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Development | 2025-04 | 10
Muhammad Yasir | APWORKS 2025.2 | Optimizing data retrieval processes to enhance performance | Development | 2025-05 | 11.5
Muhammad Yasir | APWORKS 2025.2 | Project Overhead | Analysis | 2025-05 | 1
Muhammad Yasir | APWORKS 2025.2 | Project Overhead | Post_dep_fixes | 2025-05 | 23
Muhammad Yasir | APWORKS 2025.2 | Project Overhead | Post_dep_fixes | 2025-06 | 1
Muhammad Yasir | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Bug Fixing | 2025-05 | 9
Muhammad Yasir | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Development | 2025-04 | 12
Muhammad Yasir | APWORKS 2025.2 | Restriction by user group on which fields can be edited | Development | 2025-05 | 5
Muhammad Yasir | APWORKS 2025.2 | Standardize the Status in Dashboard vs reports | Bug Fixing | 2025-05 | 2.5
Muhammad Yasir | APWORKS 2025.2 | Warren Lamb provided PDF ingestion | Bug Fixing | 2025-05 | 1
Muhammad Yasir | APWORKS 2025.2 | Warren Lamb provided PDF ingestion | Development | 2025-05 | 3
Muhammad Yasir | APWORKS 2025.2 SP1 | Make date fields editable for Broadcast | Development | 2025-06 | 2
Muhammad Yasir | APWORKS 2025.2 SP1 | Project Overhead | Post_dep_fixes | 2025-06 | 14
Muhammad Yasir | APWORKS 2025.2 SP1 | Split functionality enhancement. | Development | 2025-06 | 5
Muhammad Yasir | NEXELUS 2025.2 | Allow manual adjustments for partial billing by the client | Development | 2025-05 | 2
Muhammad Yasir | NEXELUS 2025.2 | MC: Apply exchange rate from revision date or IO creation date | Development | 2025-04 | 4
Muhammad Yasir | NEXELUS 2025.2 | Project Overhead | Post_dep_fixes | 2025-05 | 1
Muhammad Yasir | NEXELUS 2025.2 | Project Overhead | Post_dep_fixes | 2025-06 | 9
Muhammad Yasir | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Development | 2025-05 | 11
Muhammad Yasir | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Development | 2025-06 | 1
Muhammad Yasir | PR-0013 | Development of new project/assignment/task | Development | 2025-04 | 1
Muhammad Yasir | PR-0013 | Development of new project/assignment/task | Development | 2025-05 | 4
Muhammad Yasir | PR-0013 | Development of new project/assignment/task | Development | 2025-06 | 2
Muhammad Yasir | PR-0013 | Document review/understanding Requirement Specifications | Meetings | 2025-04 | 1
Muhammad Yasir | PR-0013 | Gazetted holidays | Leave | 2025-03 | 8
Muhammad Yasir | PR-0013 | Gazetted holidays | Leave | 2025-04 | 16
Muhammad Yasir | PR-0013 | Gazetted holidays | Leave | 2025-05 | 8
Muhammad Yasir | PR-0013 | Gazetted holidays | Leave | 2025-06 | 16
Muhammad Yasir | PR-0013 | In-house Training | Meetings | 2025-05 | 2
Muhammad Yasir | PR-0013 | In-house Training | Training | 2025-04 | 31.5
Muhammad Yasir | PR-0013 | In-house Training | Training | 2025-05 | 4
Muhammad Yasir | PR-0013 | Internal Meetings | Meetings | 2025-04 | 19
Muhammad Yasir | PR-0013 | Internal Meetings | Meetings | 2025-05 | 3
Muhammad Yasir | PR-0013 | Time Off - Planned | Leave | 2025-06 | 8
Muhammad Yasir | PR-0013 | Time Off - Un Planned | Leave | 2025-06 | 8
Muhammad Yasir | Support and Maintenance | Time | Client Items | 2025-04 | 28.5
Muhammad Yasir | Support and Maintenance | Time | Client Items | 2025-05 | 10
Muhammad Yasir | Support and Maintenance | Time | Client Items | 2025-06 | 12
Muhammad Yasir | Support and Maintenance | Time | Support Tickets | 2025-05 | 17
Muhammad Yasir | Support and Maintenance | Time | Support Tickets | 2025-06 | 18
Muzammil Shahzad | AD-0001 | Meetings | Meetings | 2025-04 | 7.24
Muzammil Shahzad | AD-0001 | Meetings | Meetings | 2025-05 | 5.55
Muzammil Shahzad | AD-0001 | Meetings | Meetings | 2025-06 | 12.5
Muzammil Shahzad | NEXELUS 2025.2 | Enhance revise BO to allow consecutive IOs to merge into it | Bug Fixing | 2025-05 | 26.5
Muzammil Shahzad | NEXELUS 2025.2 | Enhance revise BO to allow consecutive IOs to merge into it | Bug Fixing | 2025-06 | 31.6
Muzammil Shahzad | NEXELUS 2025.2 | Enhance revise BO to allow consecutive IOs to merge into it | Development | 2025-05 | 19.5
Muzammil Shahzad | NEXELUS - ADDHOC ITEMS | IPC - Upgrade Facebook API version to V22 | Development | 2025-04 | 22.42
Muzammil Shahzad | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Development | 2025-04 | 17.4
Muzammil Shahzad | NEXELUS 2025.2 | Add a 'Collapse All Packages/Placements' button on Placement | Development | 2025-05 | 7.5
Muzammil Shahzad | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Bug Fixing | 2025-05 | 16
Muzammil Shahzad | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Bug Fixing | 2025-06 | 17.75
Muzammil Shahzad | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Development | 2025-05 | 66.6
Muzammil Shahzad | NEXELUS 2025.2 | Restrict Consecutive Approvals by the Same | Testing | 2025-05 | 7
Muzammil Shahzad | PR-0013 | In-house Training | Training | 2025-04 | 17.8
Muzammil Shahzad | PR-0013 | In-house Training | Training | 2025-05 | 6
Muzammil Shahzad | PR-0013 | In-house Training | Training | 2025-06 | 1.25
Muzammil Shahzad | PR-0013 | Internal Meetings | Meetings | 2025-05 | 28.75
Muzammil Shahzad | PR-0013 | Internal Meetings | Meetings | 2025-06 | 17
Saad Saeed | AD-0001 | Meetings | Meetings | 2024-11 | 1.05
Saad Saeed | AD-0001 | Meetings | Meetings | 2024-12 | 1.8
Saad Saeed | AD-0001 | Meetings | Training | 2024-11 | 2.3
Saad Saeed | AD-0001 | Meetings | Training | 2024-12 | 3
Saad Saeed | AD-0001 | Taxes and Bank Related | Admin | 2024-11 | 1
Saad Saeed | AD-0001 | Time | No Workbench | 2024-11 | 3.3
Saad Saeed | AD-0001 | Time | Research | 2024-11 | 2.6
Saad Saeed | AP WORKFLOW | In-house Training | Analysis | 2024-11 | 1
Saad Saeed | NEXELUS 2024.1 SP2 | Billing by Media Type | Development | 2024-11 | 10.3
Saad Saeed | NEXELUS 2024.1 SP2 | Billing by Media Type | Research | 2024-11 | 2.3
Saad Saeed | NEXELUS 2024.1 SP2 | Billing by Media Type | Testing | 2024-11 | 1
Saad Saeed | NEXELUS 2024.1 SP2 | Client Profile: Media > Flag to make the vendor inactive | Development | 2024-11 | 5
Saad Saeed | NEXELUS 2024.1 SP2 | Client Profile: Media > Flag to make the vendor inactive | Research | 2024-11 | 3.6
Saad Saeed | NEXELUS 2024.1 SP2 | eConnect shell change to service | Development | 2024-10 | 16
Saad Saeed | NEXELUS 2024.1 SP2 | eConnect shell change to service | Development | 2024-11 | 21.2
Saad Saeed | NEXELUS 2024.1 SP2 | eConnect shell change to service | Meetings | 2024-11 | 1
Saad Saeed | NEXELUS 2024.1 SP2 | eConnect shell change to service | Research | 2024-10 | 16
Saad Saeed | NEXELUS 2024.1 SP2 | eConnect shell change to service | Research | 2024-11 | 8
Saad Saeed | NEXELUS 2024.1 SP2 | eConnect shell change to service | Testing | 2024-11 | 5.3
Saad Saeed | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Development | 2024-11 | 26.6
Saad Saeed | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Development | 2024-12 | 52.4
Saad Saeed | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Meetings | 2024-11 | 3.5
Saad Saeed | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Research | 2024-11 | 23.6
Saad Saeed | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Testing | 2024-11 | 4.75
Saad Saeed | NEXELUS 2024.1 SP2 | Generate Client Schedule Lines based on media type | Testing | 2024-12 | 18.8
Saad Saeed | NEXELUS 2024.2 | In-house Training | Meetings | 2024-11 | 3
Saad Saeed | PR-0013 | In-house Training | Domain Learning | 2024-10 | 40
Saad Saeed | PR-0013 | In-house Training | Domain Learning | 2024-11 | 24
Saad Saeed | PR-0013 | Time Off - Un Planned | Leave | 2024-11 | 8
Shafiq Ahmed | AD-0001 | Network and infrastructure Support | Admin | 2024-08 | 80
Shafiq Ahmed | AD-0001 | Network and infrastructure Support | Admin | 2024-09 | 168
Shafiq Ahmed | AD-0001 | Network and infrastructure Support | Admin | 2024-10 | 72
Shafiq Ahmed | AD-0001 | Network and infrastructure Support | Admin | 2024-11 | 160
Shafiq Ahmed | AD-0001 | Network and infrastructure Support | Admin | 2024-12 | 176
Shafiq Ahmed | AD-0001 | Network and infrastructure Support | Admin | 2025-01 | 184
Shafiq Ahmed | AD-0001 | Network and infrastructure Support | Admin | 2025-02 | 160
Shafiq Ahmed | AD-0001 | Network and infrastructure Support | Admin | 2025-03 | 168
Shafiq Ahmed | AD-0001 | Network and infrastructure Support | Admin | 2025-04 | 56
Shafiq Ahmed | AD-0001 | Network and infrastructure Support | No Workbench | 2024-10 | 72
Shafiq Ahmed | AD-0001 | Network and infrastructure Support | No Workbench | 2024-11 | 8
Shafiq Ahmed | AD-0001 | Network and infrastructure Support | Other | 2024-08 | 96
Shafiq Ahmed | AD-0001 | Time | No Workbench | 2024-10 | 40
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | Admin | 2024-09 | 6
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | HR Management | 2024-09 | 4
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | Interview | 2024-08 | 6
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | Interview | 2024-09 | 9
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | Interview | 2024-10 | 10
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | Interview | 2024-11 | 4
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | Interview | 2024-12 | 2
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | Interview | 2025-01 | 15
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | Interview | 2025-02 | 9
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | Interview | 2025-03 | 12
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | Interview | 2025-04 | 13
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | Interview | 2025-05 | 3
Tauseef Shahzad | AD-0001 | HR ad Admin Activities | Interview | 2025-06 | 3
Tauseef Shahzad | AD-0001 | Network and infrastructure Support | Admin | 2024-08 | 1
Tauseef Shahzad | AD-0001 | Network and infrastructure Support | Development | 2024-09 | 1
Tauseef Shahzad | AD-0001 | Network and infrastructure Support | Other | 2024-08 | 55
Tauseef Shahzad | AD-0001 | Time | Admin | 2024-08 | 1
Tauseef Shahzad | AD-0001 | Time | Admin | 2024-10 | 6
Tauseef Shahzad | AD-0001 | Time | Admin | 2024-11 | 20
Tauseef Shahzad | AD-0001 | Time | Admin | 2024-12 | 24
Tauseef Shahzad | AD-0001 | Time | Admin | 2025-01 | 32
Tauseef Shahzad | AD-0001 | Time | Admin | 2025-02 | 18
Tauseef Shahzad | AD-0001 | Time | Admin | 2025-03 | 17
Tauseef Shahzad | AD-0001 | Time | Admin | 2025-04 | 9
Tauseef Shahzad | AD-0001 | Time | Admin | 2025-05 | 8
Tauseef Shahzad | AD-0001 | Time | Admin | 2025-06 | 7
Tauseef Shahzad | AD-0001 | Time | Deployment | 2024-09 | 4
Tauseef Shahzad | AD-0001 | Time | Leave | 2024-09 | 8
Tauseef Shahzad | AD-0001 | Time | Leave | 2024-10 | 13
Tauseef Shahzad | AD-0001 | Time | Leave | 2024-11 | 22
Tauseef Shahzad | AD-0001 | Time | Leave | 2024-12 | 32
Tauseef Shahzad | AD-0001 | Time | Leave | 2025-02 | 40
Tauseef Shahzad | AD-0001 | Time | Leave | 2025-03 | 22
Tauseef Shahzad | AD-0001 | Time | Leave | 2025-04 | 20
Tauseef Shahzad | AD-0001 | Time | Leave | 2025-06 | 24
Tauseef Shahzad | AD-0001 | Time | Meetings | 2024-08 | 6
Tauseef Shahzad | AD-0001 | Time | Meetings | 2024-09 | 24
Tauseef Shahzad | AD-0001 | Time | Meetings | 2024-10 | 26
Tauseef Shahzad | AD-0001 | Time | Meetings | 2024-11 | 33
Tauseef Shahzad | AD-0001 | Time | Meetings | 2024-12 | 22
Tauseef Shahzad | AD-0001 | Time | Meetings | 2025-01 | 20
Tauseef Shahzad | AD-0001 | Time | Meetings | 2025-02 | 8
Tauseef Shahzad | AD-0001 | Time | Meetings | 2025-03 | 19
Tauseef Shahzad | AD-0001 | Time | Meetings | 2025-04 | 22
Tauseef Shahzad | AD-0001 | Time | Meetings | 2025-05 | 32
Tauseef Shahzad | AD-0001 | Time | Meetings | 2025-06 | 7
Tauseef Shahzad | AD-0001 | Time | Other | 2024-08 | 34.5
Tauseef Shahzad | AD-0001 | Time | PMO | 2024-09 | 27
Tauseef Shahzad | AD-0001 | Time | PMO | 2024-10 | 45
Tauseef Shahzad | AD-0001 | Time | PMO | 2024-11 | 38
Tauseef Shahzad | AD-0001 | Time | PMO | 2024-12 | 41
Tauseef Shahzad | AD-0001 | Time | PMO | 2025-01 | 21
Tauseef Shahzad | AD-0001 | Time | PMO | 2025-02 | 13
Tauseef Shahzad | AD-0001 | Time | PMO | 2025-03 | 26
Tauseef Shahzad | AD-0001 | Time | PMO | 2025-04 | 24
Tauseef Shahzad | AD-0001 | Time | PMO | 2025-05 | 30
Tauseef Shahzad | AD-0001 | Time | PMO | 2025-06 | 11
Tauseef Shahzad | AD-0001 | Time | SOC Compliance | 2024-09 | 58
Tauseef Shahzad | AD-0001 | Time | SOC Compliance | 2024-10 | 34
Tauseef Shahzad | AD-0001 | Time | SOC Compliance | 2024-11 | 4
Tauseef Shahzad | AD-0001 | Time | SOC Compliance | 2024-12 | 4
Tauseef Shahzad | AD-0001 | Time | SOC Compliance | 2025-01 | 4
Tauseef Shahzad | AD-0001 | Time | SOC Compliance | 2025-02 | 5
Tauseef Shahzad | AD-0001 | Time | SOC Compliance | 2025-03 | 24
Tauseef Shahzad | AD-0001 | Time | SOC Compliance | 2025-04 | 49
Tauseef Shahzad | AD-0001 | Time | SOC Compliance | 2025-05 | 23
Tauseef Shahzad | AD-0001 | Time | SOC Compliance | 2025-06 | 8
Tauseef Shahzad | AP WORKFLOW | Analysis of the new project/assignment/task | Other | 2024-08 | 14
Tauseef Shahzad | AP WORKFLOW | Client Items | Other | 2024-08 | 2
Tauseef Shahzad | AP WORKFLOW | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 17
Tauseef Shahzad | APWORKS 2024.2 - PHASE 3 | Project Overhead | Meetings | 2024-08 | 4
Tauseef Shahzad | APWORKS 2024.2 - PHASE 3 | Project Overhead | Project Mgmt | 2024-08 | 4
Tauseef Shahzad | APWORKS 2024.2 - PHASE 4 | Project Overhead | Deployment | 2024-11 | 7
Tauseef Shahzad | APWORKS 2024.2 - PHASE 4 | Project Overhead | Deployment | 2025-01 | 19
Tauseef Shahzad | APWORKS 2024.2 - PHASE 4 | Project Overhead | Post_dep_fixes | 2024-12 | 2
Tauseef Shahzad | APWORKS 2024.2 - PHASE 4 | Project Overhead | Post_dep_fixes | 2025-01 | 3
Tauseef Shahzad | APWORKS 2025.2 | Project Overhead | Documentation | 2025-05 | 3
Tauseef Shahzad | APWORKS 2025.2 | Project Overhead | Documentation | 2025-06 | 4
Tauseef Shahzad | NEXELUS 2024.1 SP2 | Project Overhead | Deployment | 2025-01 | 20
Tauseef Shahzad | NEXELUS 2024.2 | Cient UAT Upgrade | Other | 2024-08 | 3
Tauseef Shahzad | NEXELUS 2024.2 | Client Items | Other | 2024-08 | 3
Tauseef Shahzad | NEXELUS 2024.2 | Meetings, mails, communication, TFS, Interviews | Other | 2024-08 | 8
Tauseef Shahzad | NEXELUS 2025.2 | Project Overhead | Documentation | 2025-05 | 3
Tauseef Shahzad | NEXELUS 2025.2 | Project Overhead | Documentation | 2025-06 | 4
Tauseef Shahzad | NEXELUS SUPPORT | Maintenance Activity | Deployment | 2025-01 | 22
Tauseef Shahzad | NEXELUS SUPPORT | Maintenance Activity | Deployment | 2025-03 | 12
Tauseef Shahzad | PR-0013 | Client Items | Development | 2025-05 | 21
Tauseef Shahzad | PR-0013 | Production upgrades | Deployment | 2024-12 | 6
Tauseef Shahzad | PR-0013 | Production upgrades | Deployment | 2025-01 | 5
Tauseef Shahzad | PR-0013 | Session with US team | Meetings | 2024-09 | 8
Tauseef Shahzad | PR-0013 | Session with US team | Meetings | 2024-10 | 17
Tauseef Shahzad | PR-0013 | Session with US team | Meetings | 2024-11 | 20
Tauseef Shahzad | PR-0013 | Session with US team | Meetings | 2024-12 | 22
Tauseef Shahzad | PR-0013 | Session with US team | Meetings | 2025-01 | 20
Tauseef Shahzad | PR-0013 | Session with US team | Meetings | 2025-02 | 42
Tauseef Shahzad | PR-0013 | Session with US team | Meetings | 2025-03 | 13
Tauseef Shahzad | PR-0013 | Session with US team | Meetings | 2025-04 | 24
Tauseef Shahzad | PR-0013 | Session with US team | Meetings | 2025-05 | 26
Tauseef Shahzad | PR-0013 | Session with US team | Meetings | 2025-06 | 7
Tauseef Shahzad | PR-0013 | Time Off - Un Planned | Leave | 2024-09 | 8
Tauseef Shahzad | Support and Maintenance | Time | Client Items | 2024-10 | 10

## Working
appliedmonth | (Multiple Items)
Sum of Hours | Column Labels
Row Labels | Admin | Analysis | Bug Fixing | Client Items | Deployment | Design | Development | Documentation | General | HR Management | Interview | JustGlobal | Leave | Meetings | No Workbench | Planinng | PlusCo | PMO | Post_dep_fixes | Project Mgmt | Research | SOC Compliance | SRS-Review | Support Tickets | Task Domain | Task/Code Review | Test Case Dev | Testing | Training | Grand Total
AD-0001 | 720 |  |  |  | 15.5 |  |  |  |  | 187 | 50 |  | 368 | 392.99 | 44 |  |  | 104 |  |  | 21 | 109 | [6 empty] | 1 | 2012.49
HR ad Admin Activities | 170.5 | [8 empty] | 187 | 50 | [18 empty] | 407.5
Meetings | [13 empty] | 302.49 | [14 empty] | 1 | 303.49
Network and infrastructure Support | 407.5 | [13 empty] | 2 | [14 empty] | 409.5
Taxes and Bank Related | 71 | [11 empty] | 24 | [16 empty] | 95
Time | 71 |  |  |  | 15.5 | [7 empty] | 344 | 90.5 | 42 |  |  | 104 |  |  | 21 | 109 | [7 empty] | 797
APWORKS - SUPPORT | [8 empty] | 5 |  |  | 7 |  |  |  |  | 23 | [12 empty] | 35
Maintenance Activity | [8 empty] | 5 |  |  | 7 |  |  |  |  | 23 | [12 empty] | 35
APWORKS - TEST AUTOMATION |  | 1 |  |  |  | 8 | 28 | [22 empty] | 37
Media approval: approve invoices | [6 empty] | 24 | [22 empty] | 24
Media: Discrepant Invoices - Make Corrections | [6 empty] | 4 | [22 empty] | 4
Media: Read Data diven excel files for the correspinding data | [5 empty] | 8 | [23 empty] | 8
Project Overhead |  | 1 | [27 empty] | 1
APWORKS 2024.2 - PHASE 4 | [27 empty] | 42 |  | 42
Apply variable name for Site in vendor mapping | [27 empty] | 2 |  | 2
Discount implementation CHANGES | [27 empty] | 3 |  | 3
Google Drive Setup (company configuration UI) | [27 empty] | 8 |  | 8
Tax implementation(rule)/column for difference | [27 empty] | 29 |  | 29
APWORKS 2024.2 PHASE 5 |  |  | 64 |  |  |  | 48 | [22 empty] | 112
PlusCo - Change requests |  |  | 64 |  |  |  | 48 | [22 empty] | 112
APWORKS 2025.1 |  | 6 | 15 |  | 4.5 |  | 100.5 | [6 empty] | 1 | 10 |  |  |  | 8 | 14 | 119 | [6 empty] | 28 |  | 306
Add client column on Discrepant Gadget | [6 empty] | 3 | [20 empty] | 2 |  | 5
Don't refresh dashboard on Mapping dialog Close button action |  |  | 0 |  |  |  | 1 | [22 empty] | 1
Google Drive: Allow PDF in Attachment |  |  | 5.5 |  |  |  | 7 | [20 empty] | 1 |  | 13.5
Invoice UI: Invoice Preview Zoom Feature |  |  | 0 |  |  |  | 18 | [20 empty] | 3 |  | 21
Project Overhead |  | 1 |  |  | 4.5 | [8 empty] | 1 | 10 |  |  |  | 8 | 14 | 112 | [8 empty] | 150.5
R&D on dashboard optimization. |  | 2 | [18 empty] | 7 | [8 empty] | 9
User Management UI updates |  |  | 0 |  |  |  | 13 | [22 empty] | 13
Vendor Mapping: Allow User to Date Format |  | 3 | 9.5 |  |  |  | 58.5 | [20 empty] | 22 |  | 93
APWORKS 2025.2 |  | 41 | 166.75 |  | 51.5 |  | 665.5 | 9 | [5 empty] | 60.25 | 17.5 |  |  |  | 74 | 61.5 | 42 |  | 9.5 | 4 | 20.5 | 26 | 8 | 530 |  | 1787
Ability to Approve the invoice when resolving discrepancy |  |  | 6 |  |  |  | 23 | [18 empty] | 0.5 |  | 32 |  | 61.5
Ability to create templates across multiple Companies |  | 2 | 38.75 |  |  |  | 114.75 | [6 empty] | 27 | [11 empty] | 4.5 | 2 | 97.25 |  | 286.25
Auto populate call letters; media type and band after 1st maping |  | 2 | 9 |  |  |  | 27 | [18 empty] | 2.5 |  | 23.5 |  | 64
Credit Memo |  | 5 | 15.5 |  |  |  | 68 | [6 empty] | 9 | [8 empty] | 5 |  |  | 5 | 6 | 83 |  | 196.5
Display client #, when inv is linked to IO in all UIs and Report |  | 1 | 2 |  |  |  | 6 | [18 empty] | 1 |  | 23 |  | 33
Nexelus Email Function for IO | [6 empty] | 3 | [22 empty] | 3
Optimizing data retrieval processes to enhance performance |  | 14 | 60 |  |  |  | 212 | [6 empty] | 8 | [11 empty] | 7.5 |  | 79 |  | 380.5
Project Overhead |  | 5 |  |  | 51.5 |  |  | 7 | [5 empty] | 2 | 17.5 |  |  |  | 74 | 61.5 | 29 |  |  | 4 | 20.5 |  |  |  |  | 272
Restriction by user group on which fields can be edited |  | 7 | 27 |  |  |  | 142.25 | [6 empty] | 14.25 | [6 empty] | 6 |  | 1 |  |  | 3 |  | 76.25 |  | 276.75
Separate the financial integration API from the main application | [6 empty] | 35 | 2 | [12 empty] | 7 | [8 empty] | 44
Split invoice by MOS - Print / OOH / Digital | [22 empty] | 3 |  |  | 2 |  | 41 |  | 46
Standardize the Status in Dashboard vs reports |  |  | 2.5 |  |  |  | 5.5 | [20 empty] | 2 |  | 10
Warren Lamb provided PDF ingestion |  | 5 | 6 |  |  |  | 29 | [15 empty] | 0.5 |  |  |  |  | 73 |  | 113.5
APWORKS 2025.2 SP1 |  | 7.5 | 16 |  | 4.5 |  | 93.5 | [6 empty] | 6.5 |  |  |  |  | 14 | 12 | 15 | [6 empty] | 46.5 |  | 215.5
APWorks amounts - format to 2 decimal places |  |  | 1 |  |  |  | 28 | [22 empty] | 29
For "No filter' all data not getting shown | [6 empty] | 13 | [20 empty] | 21 |  | 34
Maintenance page creation | [6 empty] | 13 | [22 empty] | 13
Make date fields editable for Broadcast |  |  | 4 |  |  |  | 8 | [20 empty] | 18 |  | 30
Manage invoice list optimization |  |  | 1 |  |  |  | 5 | [13 empty] | 8 | [6 empty] | 4.5 |  | 18.5
Project Overhead |  |  |  |  | 4.5 | [13 empty] | 14 | 12 | 7 | [8 empty] | 37.5
Split functionality enhancement. |  | 7.5 | 10 |  |  |  | 26.5 | [6 empty] | 6.5 | [13 empty] | 3 |  | 53.5
APWORKS 2025.2 SP2 | [6 empty] | 9 | [6 empty] | 3 | [5 empty] | 3 | [7 empty] | 2 |  | 17
Partial posting in posting process for failed invoices into MO | [6 empty] | 9 | [6 empty] | 3 | [13 empty] | 2 |  | 14
Project Overhead | [19 empty] | 3 | [9 empty] | 3
APWORKS 2025.3 |  | 3 |  |  |  |  | 6.5 | [8 empty] | 1 | [13 empty] | 10.5
Project Overhead | [15 empty] | 1 | [13 empty] | 1
Retain user-specific report views and filter preferences during |  | 3 |  |  |  |  | 6.5 | [22 empty] | 9.5
APWORKS PHASE2 | [7 empty] | 10 |  |  |  |  | 8 | [14 empty] | 9 |  | 27
Analysis of production issues reported by support team | [27 empty] | 9 |  | 9
National Gazetted Holidays | [12 empty] | 8 | [16 empty] | 8
User Manual OR Release Notes | [7 empty] | 10 | [21 empty] | 10
NEXELUS - ADDHOC ITEMS | [6 empty] | 22.42 | [13 empty] | 18 |  |  |  |  | 1.5 |  |  |  | 41.92
IPC - Upgrade Facebook API version to V22 | [6 empty] | 22.42 | [18 empty] | 1.5 |  |  |  | 23.92
Nexelus Vulnerability Report - 2025 | [20 empty] | 18 | [8 empty] | 18
NEXELUS 2024.1 SP2 |  | 20 |  |  | 2.5 |  | 18 | 10 | [12 empty] | 11 |  |  | 5 |  |  |  | 56 |  | 122.5
AdTech Fee commission | [7 empty] | 1 | [21 empty] | 1
Documentation | [7 empty] | 6 | [21 empty] | 6
Generate Client Schedule Lines based on media type | [20 empty] | 11 | [6 empty] | 8 |  | 19
Media Plan Approval | [27 empty] | 6 |  | 6
Media Plan: Import/Export Flighting | [6 empty] | 18 | 3 | [19 empty] | 18 |  | 39
Project Overhead |  | 20 |  |  | 2.5 | [18 empty] | 5 | [5 empty] | 27.5
UDF & Naming Convention in Nexelus - Export on Proposal | [27 empty] | 18 |  | 18
UDF & Naming Convention in Vendor Portal - Proposal Import/exp | [27 empty] | 6 |  | 6
NEXELUS 2025.1 |  |  | 28.49 |  | 6 |  | 33 | 2 | [5 empty] | 1 | 13 |  |  |  | 9.5 | 2 | [5 empty] | 2 |  | 102 |  | 198.99
Generate billing schedule - bug fixing |  |  | 10 | [24 empty] | 6 |  | 16
Import/exports flights |  |  | 14.49 |  |  |  | 17 | [18 empty] | 2 |  | 79 |  | 112.49
Margin change for TTD |  |  | 4 |  |  |  | 16 | 2 | [19 empty] | 9 |  | 31
Project Overhead |  |  |  |  | 6 | [8 empty] | 1 | 13 |  |  |  | 9.5 | 2 | [9 empty] | 31.5
Show PBG Gross up amount on billing reconciliation. | [27 empty] | 8 |  | 8
NEXELUS 2025.1 SP1 |  | 5 |  |  | 2.5 |  | 27 | [6 empty] | 2 |  |  |  |  | 9.5 | 1 | [5 empty] | 7 |  | 11 |  | 65
Project Overhead |  | 5 |  |  | 2.5 | [13 empty] | 9.5 | 1 | [9 empty] | 18
Provide end date column in flight import export. | [6 empty] | 14 | [18 empty] | 1 |  | 8 |  | 23
TTD: Generate schedule based on Placement Flights | [6 empty] | 13 | [6 empty] | 2 | [11 empty] | 6 |  | 3 |  | 24
NEXELUS 2025.2 |  | 25.5 | 141.25 |  | 15.5 | 11 | 501.5 | 42.5 | [5 empty] | 30 | 13.5 |  |  |  | 35 | 67.5 | 23.5 |  | 3 |  | 40.5 | 23.5 | 2 | 353.5 |  | 1329.25
Add a 'Collapse All Packages/Placements' button on Placement |  |  | 8.5 |  |  | 1 | 35.4 | 2 | [5 empty] | 0.5 | [11 empty] | 0.5 |  | 11.5 |  | 59.4
Alerting users when an FX rate is unavailable to prevent the | [6 empty] | 17 | [6 empty] | 1 | [15 empty] | 18
Allow manual adjustments for partial billing by the client |  |  | 13 |  |  |  | 36 | [6 empty] | 2 | [8 empty] | 1 |  |  |  |  | 16 |  | 68
Allow switching media plan from Media Plan UI |  | 5 | 7 |  |  |  | 8 | 2.5 | [5 empty] | 0.5 | [11 empty] | 0.5 |  | 15.5 |  | 39
DENTSU CHANGES: Enhance Close Job functionality | [6 empty] | 15 | [20 empty] | 51 |  | 66
Display Vendor distribution for individual client line under |  |  | 8 |  |  |  | 31 | [18 empty] | 4 |  | 11 |  | 54
Exchange rate changes |  | 3 | 26.5 |  |  |  | 62 | 2 | [5 empty] | 2 | [11 empty] | 5 |  | 42 |  | 142.5
iPC Selfservices: UI optimization | [6 empty] | 18 | [22 empty] | 18
MC: Apply exchange rate from revision date or IO creation date |  |  | 12 |  |  |  | 151 | 6 | [5 empty] | 6.5 | [8 empty] | 1 |  |  | 9.5 | 2 | 79.5 |  | 267.5
Net Media + Ad serving Added to Media Spend under Campaign |  |  | 1 | [22 empty] | 4 |  | 11 |  | 16
Nexelus Email Function for IO | [27 empty] | 11 |  | 11
Project Overhead |  | 7 |  |  | 15.5 |  |  | 30 | [5 empty] | 16 | 13.5 |  |  |  | 35 | 67.5 | 23.5 |  |  |  | 40.5 |  |  |  |  | 248.5
Provide an option to include AdTech Fee in a separate invoice |  | 1 | 2 |  |  | 10 | 29 | [15 empty] | 0.5 | [6 empty] | 42.5
Restrict Consecutive Approvals by the Same |  | 9.5 | 63.25 |  |  |  | 99.1 | [6 empty] | 1.5 | [8 empty] | 0.5 |  |  |  |  | 101 |  | 274.85
Starred media plans (NEX 17059) | [27 empty] | 4 |  | 4
NEXELUS 20253 | [15 empty] | 4 | [13 empty] | 4
Project Overhead | [15 empty] | 4 | [13 empty] | 4
NEXELUS SUPPORT |  |  |  |  | 18.5 | [18 empty] | 27 | [5 empty] | 45.5
Maintenance Activity |  |  |  |  | 18.5 | [18 empty] | 27 | [5 empty] | 45.5
PR-0013 |  | 53.5 | 9 |  | 20.5 |  | 96.5 | 15 |  |  |  |  | 1114.5 | 775.2 | 17 |  |  |  |  | 42.5 |  |  |  | 94.5 |  |  |  | 179.5 | 420.05 | 2837.75
Analysis of production issues reported by support team |  | 9.5 | 4 | [20 empty] | 6 |  |  |  | 45.5 |  | 65
Cient UAT Upgrade |  |  | 3 |  | 2 |  | 3 | [20 empty] | 76 |  | 84
Client Items | [6 empty] | 21 | [20 empty] | 10 |  | 31
Development of new project/assignment/task |  | 14 |  |  | 3 |  | 30 | [12 empty] | 6 | [9 empty] | 53
Document review/understanding Requirement Specifications |  | 10 | [11 empty] | 1 | [15 empty] | 11
Gazetted holidays | [12 empty] | 461 | [16 empty] | 461
In-house Training |  | 20 | [11 empty] | 2 | [14 empty] | 420.05 | 442.05
Internal Meetings |  |  | 2 |  | 1 | [8 empty] | 595.2 | [13 empty] | 1 |  | 599.2
Meetings, mails, communication, TFS, Interviews | [6 empty] | 42.5 | 11 |  |  |  |  | 60 | 63.5 | 8 |  |  |  |  | 36.5 |  |  |  | 88.5 |  |  |  | 2 |  | 312
Production upgrades |  |  |  |  | 8 | [22 empty] | 37 |  | 45
QA Environment Upgrade |  |  |  |  | 4.5 | [22 empty] | 8 |  | 12.5
Release Environment Upgrade |  |  |  |  | 2 | [24 empty] | 2
Requirement Specifications document writing | [7 empty] | 4 | [21 empty] | 4
Session with US team | [13 empty] | 113.5 | [15 empty] | 113.5
Time Off - Planned | [12 empty] | 340 |  | 8 | [14 empty] | 348
Time Off - Un Planned | [12 empty] | 253.5 |  | 1 | [14 empty] | 254.5
Support and Maintenance |  |  |  | 1943.5 | [19 empty] | 866.25 | [5 empty] | 2809.75
Time |  |  |  | 1943.5 | [19 empty] | 866.25 | [5 empty] | 2809.75
NEXELUS 2025.2 |  |  | 91.1 |  |  |  | 50.5 | [18 empty] | 2 |  |  |  | 143.6
Enhance revise BO to allow consecutive IOs to merge into it |  |  | 91.1 |  |  |  | 50.5 | [18 empty] | 2 |  |  |  | 143.6
Grand Total | 720 | 162.5 | 531.59 | 1943.5 | 141.5 | 19 | 1699.92 | 88.5 | 5 | 187 | 50 | 7 | 1490.5 | 1271.94 | 115 | 5 | 23 | 104 | 150 | 203.5 | 249.5 | 109 | 12.5 | 996.75 | 61 | 62 | 10 | 1359.5 | 421.05 | 12199.75

## Working 2 (hidden)
appliedmonth | (Multiple Items)
Row Labels | Sum of Hours
AD-0001 | 2557.24
APWORKS - SUPPORT | 35
APWORKS - TEST AUTOMATION | 37
APWORKS 2024.2 - PHASE 4 | 560.5
Apply variable name for Site in vendor mapping | 2
Ayesha Qurban | 2
Approval routing | 28.5
Arif Khan Arif | 13.5
Asim Jameel | 6
Ayesha Qurban | 9
Broadcast Model Fields | 20
Hamza Nouman | 10
Kashif Hayat | 10
Deadlock issue | 16.5
Abid Ali | 11
Arif Khan Arif | 4.5
Kashif Hayat | 1
Discount implementation CHANGES | 7
Ayesha Qurban | 7
EDI file updating and upload | 36
Bilal Afzal Raja | 6
Hamza Nouman | 8
Kashif Hayat | 22
EDI: Generate PDF - Updates | 58
Asad Mahmood | 34
Bilal Afzal Raja | 8
Hamza Nouman | 16
Google Drive Setup (company configuration UI) | 28
Ayesha Qurban | 4
Hamza Nouman | 24
Integration Testing | 24
Bilal Afzal Raja | 8
Imran UL Haq | 16
Media Type Identification for IOs. | 18
Arslan Khalid | 18
PDF based broadcast invoices - Approvals | 33
Arif Khan Arif | 16
Bilal Afzal Raja | 5
Kashif Hayat | 12
PDF based broadcast invoices - Import / Export lines | 21
Asad Mahmood | 2
Bilal Afzal Raja | 6
Kashif Hayat | 13
Project Overhead | 128
Abid Ali | 61
Asad Mahmood | 21
Ayesha Qurban | 4
Bilal Afzal Raja | 13
Fawad Ahmed | 7
Tauseef Shahzad | 22
Pull Client & Sites, Service types as Media Types from Nexelus | 4
Ayesha Qurban | 4
Tax implementation(rule)/column for difference | 136.5
Arif Khan Arif | 4.5
Arslan Khalid | 38
Asad Mahmood | 12
Ayesha Qurban | 29
Bilal Afzal Raja | 4
Kashif Hayat | 49
APWORKS 2024.2 PHASE 5 | 241
Google Drive Setup (company configuration UI) | 12
Fawad Ahmed | 12
PlusCo - Change requests | 128
Ali Junaid | 128
Project Overhead | 99
Asad Mahmood | 2
Ayesha Qurban | 8
Fawad Ahmed | 17
Imran UL Haq | 8
Kashif Hayat | 64
Vendor invoices report: Add date filters | 2
Asad Mahmood | 2
APWORKS 2025.1 | 306
Add client column on Discrepant Gadget | 5
Arslan Khalid | 3
Kashif Hayat | 2
Don't refresh dashboard on Mapping dialog Close button action | 1
Ali Junaid | 1
Google Drive: Allow PDF in Attachment | 13.5
Asad Mahmood | 13.5
Invoice UI: Invoice Preview Zoom Feature | 21
Ali Junaid | 15
Asad Mahmood | 3
Kashif Hayat | 3
Project Overhead | 150.5
Abid Ali | 17.5
Ali Junaid | 7
Asad Mahmood | 13
Ayesha Qurban | 1
Kashif Hayat | 112
R&D on dashboard optimization. | 9
Ali Junaid | 7
Asad Mahmood | 2
User Management UI updates | 13
Ali Junaid | 13
Vendor Mapping: Allow User to Date Format | 93
Ali Junaid | 32
Arif Khan Arif | 14
Arslan Khalid | 38
Asad Mahmood | 7
Kashif Hayat | 2
APWORKS 2025.2 | 1787
Ability to Approve the invoice when resolving discrepancy | 61.5
Abid Ali | 0.5
Ali Junaid | 29
Ayesha Qurban | 4
Kashif Hayat | 28
Ability to create templates across multiple Companies | 286.25
Abid Ali | 3
Ali Junaid | 2
Arslan Khalid | 145.25
Asad Mahmood | 2
Ayesha Qurban | 83
Muhammad Yasir | 51
Auto populate call letters; media type and band after 1st maping | 64
Abid Ali | 0.5
Arif Khan Arif | 2
Arslan Khalid | 34.5
Ayesha Qurban | 7
Kashif Hayat | 8
Muhammad Yasir | 12
Credit Memo | 196.5
Abid Ali | 1
Ali Junaid | 22
Arif Khan Arif | 7
Arslan Khalid | 3
Asad Mahmood | 38.5
Ayesha Qurban | 6
Kashif Hayat | 83
Muhammad Yasir | 36
Display client #, when inv is linked to IO in all UIs and Report | 33
Arif Khan Arif | 2
Arslan Khalid | 2
Ayesha Qurban | 23
Muhammad Yasir | 6
Nexelus Email Function for IO | 3
Muhammad Yasir | 3
Optimizing data retrieval processes to enhance performance | 380.5
Abid Ali | 7
Aimen nasar | 38
Ali Junaid | 166.5
Arif Khan Arif | 2
Arslan Khalid | 8
Asad Mahmood | 74.5
Ayesha Qurban | 16
Hamza Nouman | 14
Kashif Hayat | 28
Muhammad Yasir | 26.5
Project Overhead | 272
Abid Ali | 93.5
Ali Junaid | 42
Arif Khan Arif | 2
Arslan Khalid | 1
Asad Mahmood | 40.5
Ayesha Qurban | 6
Bilal Afzal Raja | 22.5
Hamza Nouman | 13
Muhammad Hamayun | 19.5
Muhammad Yasir | 25
Tauseef Shahzad | 7
Restriction by user group on which fields can be edited | 276.75
Abid Ali | 5
Ali Junaid | 115
Arif Khan Arif | 9
Arslan Khalid | 45.75
Asad Mahmood | 8
Ayesha Qurban | 47
Hamza Nouman | 12
Kashif Hayat | 9
Muhammad Yasir | 26
Separate the financial integration API from the main application | 44
Abid Ali | 18
Asad Mahmood | 26
Split invoice by MOS - Print / OOH / Digital | 46
Arif Khan Arif | 2
Ayesha Qurban | 20
Kashif Hayat | 24
Standardize the Status in Dashboard vs reports | 10
Ali Junaid | 3
Arslan Khalid | 2.5
Ayesha Qurban | 2
Muhammad Yasir | 2.5
Warren Lamb provided PDF ingestion | 113.5
Abid Ali | 0.5
Asad Mahmood | 49
Bilal Afzal Raja | 5
Kashif Hayat | 55
Muhammad Yasir | 4
APWORKS 2025.2 SP1 | 215.5
APWorks amounts - format to 2 decimal places | 29
Ali Junaid | 25
Arslan Khalid | 4
For "No filter' all data not getting shown | 34
Ali Junaid | 9
Arif Khan Arif | 2
Kashif Hayat | 21
Muhammad Hamayun | 2
Maintenance page creation | 13
Ali Junaid | 13
Make date fields editable for Broadcast | 30
Ali Junaid | 2
Arslan Khalid | 14
Kashif Hayat | 12
Muhammad Yasir | 2
Manage invoice list optimization | 18.5
Ali Junaid | 13
Kashif Hayat | 4.5
Muhammad Hamayun | 1
Project Overhead | 37.5
Abid Ali | 15
Ali Junaid | 7
Muhammad Hamayun | 1.5
Muhammad Yasir | 14
Split functionality enhancement. | 53.5
Arslan Khalid | 48.5
Muhammad Yasir | 5
APWORKS 2025.2 SP2 | 17
Partial posting in posting process for failed invoices into MO | 14
Asad Mahmood | 14
Project Overhead | 3
Abid Ali | 3
APWORKS 2025.3 | 10.5
Project Overhead | 1
Abid Ali | 1
Retain user-specific report views and filter preferences during | 9.5
Ali Junaid | 6.5
Ayesha Qurban | 3
APWORKS PHASE2 | 146
Analysis of production issues reported by support team | 9
Asad Mahmood | 9
Analysis of the new project/assignment/task | 6
Asad Mahmood | 6
National Gazetted Holidays | 8
Asad Mahmood | 8
Regular bug fixing activity | 94
Arslan Khalid | 46
Asad Mahmood | 48
Session with US team | 1
Arif Khan Arif | 1
Support Items | 2
Arif Khan Arif | 2
Time Off - Planned | 16
Asad Mahmood | 16
User Manual OR Release Notes | 10
Hamza Nouman | 10
NEXELUS - ADDHOC ITEMS | 41.92
IPC - Upgrade Facebook API version to V22 | 23.92
Abid Ali | 1.5
Muzammil Shahzad | 22.42
Nexelus Vulnerability Report - 2025 | 18
Aimen nasar | 18
NEXELUS 2024.1 SP2 | 405.5
AdTech Fee commission | 44
Arif Khan Arif | 6
Bilal Afzal Raja | 10
Fawad Ahmed | 10
Hamza Nouman | 18
Backup Table for vendor/client lines relationship | 4
Asim Jameel | 4
Billing by Media Type | 68.5
Arif Khan Arif | 9
Asim Jameel | 3
Bilal Afzal Raja | 14
Fawad Ahmed | 35.5
Hamza Nouman | 7
Client Profile: Media > Flag to make the vendor inactive | 19
Bilal Afzal Raja | 13
Hamza Nouman | 6
Documentation | 6
Hamza Nouman | 6
eConnect shell change to service | 1.5
Asim Jameel | 1.5
Enhancement for Visual Indicators and Flighting Details in Place | 13
Fawad Ahmed | 4
Hamza Nouman | 9
Generate Client Schedule Lines based on media type | 29
Abid Ali | 1
Bilal Afzal Raja | 9
Fawad Ahmed | 11
Hamza Nouman | 8
Integration Testing | 8
Bilal Afzal Raja | 8
Level 3 | 3
Ayesha Qurban | 2
Bilal Afzal Raja | 1
Media Plan Approval | 13
Bilal Afzal Raja | 1
Fawad Ahmed | 6
Hamza Nouman | 6
Media Plan: Import/Export Flighting | 82
Bilal Afzal Raja | 4
Fawad Ahmed | 46
Hamza Nouman | 32
Project Overhead | 77.5
Abid Ali | 5
Asim Jameel | 4
Fawad Ahmed | 47.5
Imran UL Haq | 1
Tauseef Shahzad | 20
Restrict Self Approval - Time and expense | 8
Arif Khan Arif | 3
Bilal Afzal Raja | 5
UDF & Naming Convention in Nexelus - Export on Proposal | 18
Hamza Nouman | 18
UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | 5
Hamza Nouman | 5
UDF & Naming Convention in Vendor Portal - Proposal Import/exp | 6
Hamza Nouman | 6
NEXELUS 2025.1 | 198.99
Generate billing schedule - bug fixing | 16
Abid Ali | 10
Bilal Afzal Raja | 6
Import/exports flights | 112.49
Abid Ali | 2
Arif Khan Arif | 6
Bilal Afzal Raja | 4
Fawad Ahmed | 44.49
Hamza Nouman | 56
Margin change for TTD | 31
Arif Khan Arif | 20
Bilal Afzal Raja | 7
Hamza Nouman | 4
Project Overhead | 31.5
Abid Ali | 8
Arslan Khalid | 6
Fawad Ahmed | 17.5
Show PBG Gross up amount on billing reconciliation. | 8
Bilal Afzal Raja | 8
NEXELUS 2025.1 SP1 | 65
Project Overhead | 18
Abid Ali | 7
Arif Khan Arif | 2
Fawad Ahmed | 4
Hamza Nouman | 5
Provide end date column in flight import export. | 23
Abid Ali | 1
Fawad Ahmed | 22
TTD: Generate schedule based on Placement Flights | 24
Abid Ali | 4
Arslan Khalid | 20
NEXELUS 2025.2 | 1329.25
Add a 'Collapse All Packages/Placements' button on Placement | 59.4
Abid Ali | 2
Aimen nasar | 14.5
Arslan Khalid | 2
Bilal Afzal Raja | 1.5
Fawad Ahmed | 4.5
Hamza Nouman | 10
Muzammil Shahzad | 24.9
Alerting users when an FX rate is unavailable to prevent the | 18
Arif Khan Arif | 17
Fawad Ahmed | 1
Allow manual adjustments for partial billing by the client | 68
Abid Ali | 11
Aimen nasar | 0
Bilal Afzal Raja | 16
Fawad Ahmed | 39
Muhammad Yasir | 2
Allow switching media plan from Media Plan UI | 39
Abid Ali | 1
Aimen nasar | 7
Arslan Khalid | 16
Bilal Afzal Raja | 1.5
Fawad Ahmed | 2.5
Hamza Nouman | 11
DENTSU CHANGES: Enhance Close Job functionality | 66
Aimen nasar | 15
Hamza Nouman | 51
Display Vendor distribution for individual client line under | 54
Aimen nasar | 38
Arif Khan Arif | 1
Bilal Afzal Raja | 15
Exchange rate changes | 142.5
Abid Ali | 1
Arif Khan Arif | 5.5
Bilal Afzal Raja | 48
Fawad Ahmed | 88
iPC Selfservices: UI optimization | 18
Aimen nasar | 18
MC: Apply exchange rate from revision date or IO creation date | 267.5
Abid Ali | 4.5
Arif Khan Arif | 61.5
Ayesha Qurban | 3
Bilal Afzal Raja | 77
Fawad Ahmed | 117.5
Muhammad Yasir | 4
Net Media + Ad serving Added to Media Spend under Campaign | 16
Aimen nasar | 1
Bilal Afzal Raja | 15
Nexelus Email Function for IO | 11
Bilal Afzal Raja | 11
Project Overhead | 248.5
Abid Ali | 59
Aimen nasar | 19.5
Arif Khan Arif | 20
Arslan Khalid | 4
Ayesha Qurban | 3
Bilal Afzal Raja | 47
Fawad Ahmed | 15.5
Hamza Nouman | 49
Muhammad Hamayun | 14.5
Muhammad Yasir | 10
Tauseef Shahzad | 7
Provide an option to include AdTech Fee in a separate invoice | 42.5
Abid Ali | 5.5
Aimen nasar | 19
Arif Khan Arif | 18
Restrict Consecutive Approvals by the Same | 274.85
Abid Ali | 2.5
Aimen nasar | 44
Arif Khan Arif | 19.5
Hamza Nouman | 88
Muhammad Hamayun | 1.5
Muhammad Yasir | 12
Muzammil Shahzad | 107.35
Starred media plans (NEX 17059) | 4
Bilal Afzal Raja | 1
Hamza Nouman | 3
NEXELUS 20253 | 4
NEXELUS SUPPORT | 67.5
PR-0013 | 3658.25
Support and Maintenance | 3297.25
NEXELUS 2025.2 | 143.6
Enhance revise BO to allow consecutive IOs to merge into it | 143.6
Aimen nasar | 49
Arif Khan Arif | 17
Muzammil Shahzad | 77.6
Grand Total | 15124