## Project Performance
Project Performance Report
2025-07-08
|  |  | Dev |  |  | Resources |  |  | Planned Hours | [10 empty] | Accumulated Hours to Date
Key | Project |  | Start Date | End Date | Status | Dev | DB | QA | Design | RS Review | Dev | DB | Review | Bug Fixing | Bug Review | Test Case | QA | QA Review | Total | Design | RS Review | Dev | DB | Review | Bug Fixing | Bug Review | Test Case | QA | QA Review
[9 empty] | 132 | 72 | 470 | 96 | 51 | 78 | 9 | 64 | 111 | 26.5 | 1109.5 | 8 | 59 | 351.75 | 40.5 | 10 | 3 | 0 | 49.5 | 20.5 | 0 | 542.25 | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
| ADHOC-ITEMS | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16 |  |  | 0 |  |  | 0 | 16
ADHOC-ITEMS:Voucher, AP rule flag and 4 sided entry - v3 | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | [16 empty] | 0 |  |  |  | 16 | [6 empty] | 16
| APWORKS - TEST AUTOMATION | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 |  | 28 |  |  |  | 0 |  |  | 0 | 36
APWORKS - TEST AUTOMATION:Media approval: approve invoices | APWORKS - TEST AUTOMATION | Media approval: approve invoices | [16 empty] | 0 |  |  | 24 | [7 empty] | 24
APWORKS - TEST AUTOMATION:Media: Discrepant Invoices - Make Corrections | APWORKS - TEST AUTOMATION | Media: Discrepant Invoices - Make Corrections | [16 empty] | 0 |  |  | 4 | [7 empty] | 4
APWORKS - TEST AUTOMATION:Media: Read Data diven excel files for the correspinding data | APWORKS - TEST AUTOMATION | Media: Read Data diven excel files for the correspinding data | [16 empty] | 0 | 8 | [9 empty] | 8
APWORKS - TEST AUTOMATION:Project Overhead | APWORKS - TEST AUTOMATION | Project Overhead | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0
| APWORKS 2025.3 | [7 empty] | 94 | 30 | 330 | 66 | 35 | 46 | 9 | 38 | 79 | 16.5 | 743.5 |  | 36 | 177 | 18.5 | 10 | 3 | 0 | 38 | 13.5 | 0 | 296
APWORKS 2025.3:Flag an invoice in Discrepant bucket for searching |  | Flag an invoice in Discrepant bucket for searching | 2025-07-09 |  | 100% | Ali | Yasir | Ayesha | 8 | 2 | 36 | 20 | 10 | 8 | 0 | 6 | 10 | 3 | 103 |  | 5 | 16 | 1 |  |  |  | 4 |  |  | 26
APWORKS 2025.3:Hide Favorite button: Does not work ( Fix or hide) |  | Hide Favorite button: Does not work ( Fix or hide) | 2025-06-17 |  | 100% | Arslan | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 4.5 |  |  | 3 | 4 | [6 empty] | 7
APWORKS 2025.3:Manually mark invoice Archived |  | Manually mark invoice Archived | 2025-07-29 |  | 50% | Asad | Yasir | Kashif | 8 | 8 | 48 | 24 | 8 | 16 | 0 | 12 | 30 | 4 | 158 |  | 4 | 9 | 8.5 |  |  |  | 9 |  |  | 30.5
APWORKS 2025.3:Net Amount Total: Add field in header to sum Invoice Net Amount |  | Net Amount Total: Add field in header to sum Invoice Net Amount | 2025-06-17 |  | 100% | Arslan | 0 | Kashif | 4 | 2 | 24 | 6 | 2 | 2 | 1 | 4 | 6 | 1 | 52 |  | 2.5 | 9 | 3 | 3 | 3 |  | 5 | 4 |  | 29.5
APWORKS 2025.3:Project Overhead |  | Project Overhead | 0 |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0
APWORKS 2025.3:Rename Invoice amount to invoice net amount |  | Rename Invoice amount to invoice net amount | 0 |  | 0% | Arslan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0
APWORKS 2025.3:Retain user-specific report views and filter preferences during |  | Retain user-specific report views and filter preferences during | 2025-06-17 |  | 90% | Ali | 0 | Ayesha | 8 | 6 | 72 | 0 | 12 | 12 | 8 | 12 | 24 | 6 | 160 |  | 3.5 | 83 |  | 1.5 |  |  | 13 | 6.5 |  | 107.5
APWORKS 2025.3:Show routing history - Invoice comment log |  | Show routing history - Invoice comment log | 2025-06-17 |  | 100% | Arslan | 0 | Kashif | 6 | 4 | 16 | 8 | 2 | 8 | 0 | 4 | 8 | 2 | 58 |  | 5.5 | 14.5 | 2 | 2.5 |  |  | 7 | 3 |  | 34.5
APWORKS 2025.3:Upgrade ApWorks application to dotnet Core 8.0 from 7.0 |  | Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | 2025-06-24 |  | 100% | Asad | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 |  |  | 13.5 | [7 empty] | 13.5
APWORKS 2025.3:eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) |  | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | 2025-06-17 |  | 0% | Shoaib | Yasir | Ayesha | 60 | 8 | 100 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 176 |  | 15.5 | 29 |  | 3 | [5 empty] | 47.5
| NEXELUS 2025.3 | [7 empty] | 38 | 42 | 140 | 30 | 16 | 32 | 0 | 26 | 32 | 10 | 366 | 0 | 23 | 22.75 | 6 | 0 | 0 | 0 | 11.5 | 7 | 0 | 70.25
NEXELUS 2025.3:DENTSU _ Implementing a custom upload error log in Excel |  | DENTSU _ Implementing a custom upload error log in Excel | 2025-07-28 |  | 0% | Arslan | Arif | Hamza | 8 | 12 | 46 | 20 | 8 | 16 | 0 | 16 | 16 | 8 | 150 |  | 5.75 | [5 empty] | 4 |  |  | 9.75
NEXELUS 2025.3:PO numbers to be appended automatically to campaign names |  | PO numbers to be appended automatically to campaign names | 2025-07-01 |  | 0% | Abid, Muzamal | 0 | 0 | 6 | 6 | 24 | 0 | 6 | 6 | 0 | 4 | 8 | 0 | 60 |  | 6.75 | 9.75 | [7 empty] | 16.5
NEXELUS 2025.3:pre-populate objective field from media plan |  | pre-populate objective field from media plan | 2025-06-30 |  | 0% | Arslan | Arif | Hamza | 8 | 12 | 40 | 10 | 2 | 10 | 0 | 6 | 8 | 2 | 98 |  | 8 | 5 | 6 |  |  |  | 4 |  |  | 23
NEXELUS 2025.3:Project Overhead |  | Project Overhead | 0 |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0
NEXELUS 2025.3:Show old vs. new values on revision screens (Design and Rev) |  | Show old vs. new values on revision screens (Design and Rev) | 2025-06-30 |  | 0% | Abid, Asim | 0 | 0 | 16 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 |  | 2.5 | [5 empty] | 3.5 |  |  | 6
NEXELUS 2025.3:Vulnerability Report |  | Vulnerability Report | 2025-06-23 |  | 0% | Muzamal | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 |  |  | 8 | [5 empty] | 7 |  | 15
| NEXELUSAPP - MAUI | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124
NEXELUSAPP - MAUI:Auth Pages: Key Page |  | Auth Pages: Key Page | 0 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [7 empty] | 18
NEXELUSAPP - MAUI:Auth Pages: Login Page + Flow |  | Auth Pages: Login Page + Flow | 0 |  | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 33 | [7 empty] | 33
NEXELUSAPP - MAUI:Project Overhead |  | Project Overhead | [16 empty] | 0 | [10 empty] | 0
NEXELUSAPP - MAUI:TimeSheet: Add New |  | TimeSheet: Add New | 0 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 16 | [7 empty] | 16
NEXELUSAPP - MAUI:TimeSheet: Chart |  | TimeSheet: Chart | 0 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 13 | [7 empty] | 13
NEXELUSAPP - MAUI:TimeSheet: Edit |  | TimeSheet: Edit | 0 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2 | [7 empty] | 2
NEXELUSAPP - MAUI:TimeSheet: Main Page |  | TimeSheet: Main Page | 0 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 29.75 | [7 empty] | 29.75
NEXELUSAPP - MAUI:TimeSheet: Pending Transaction |  | TimeSheet: Pending Transaction | 0 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12.25 | [7 empty] | 12.25
NEXELUSAPP - MAUI:Expense: Add New |  | Expense: Add New | [16 empty] | 0 |  |  | 2.5 | [7 empty] | 2.5
NEXELUSAPP - MAUI:Expense: Assignment Page |  | Expense: Assignment Page | [16 empty] | 0 |  |  | 3.5 | [7 empty] | 3.5
[19 empty] | 0 | [10 empty] | 0
Formulas:
Dev = IFERROR(VLOOKUP([Key],'Project Estimate'!$A7:S135,5,FALSE),"")

## Working (hidden)
Sum of Hours | Column Labels
Row Labels | Analysis | Design | Development | Documentation | Meetings | Planinng | Post_dep_fixes | Project Mgmt | SRS-Review | Task Domain | Task/Code Review | Test Case Dev | Testing | Bug Fixing | DB Dev | Deployment | No Workbench | Research | Grand Total
ADHOC-ITEMS |  |  |  |  | 2 | [9 empty] | 16 |  |  |  | 18
Voucher, AP rule flag and 4 sided entry - v3 |  |  |  |  | 2 | [9 empty] | 16 |  |  |  | 18
APWORKS - TEST AUTOMATION | 7 | 8 | 28 | [13 empty] | 2 |  | 45
Media approval: approve invoices |  |  | 24 | [15 empty] | 24
Media: Discrepant Invoices - Make Corrections |  |  | 4 | [15 empty] | 4
Media: Read Data diven excel files for the correspinding data |  | 8 | [16 empty] | 8
Project Overhead | 7 | [15 empty] | 2 |  | 9
APWORKS 2025.3 | 37 |  | 177 |  | 47.5 | 17 | 1 | 8 | 36 | 24 | 10 | 38 | 13.5 | 3 | 18.5 | 5 | 2 | 6.5 | 444
Flag an invoice in Discrepant bucket for searching |  |  | 16 |  | 2.5 |  |  |  | 5 |  |  | 4 |  |  | 1 |  |  |  | 28.5
Hide Favorite button: Does not work ( Fix or hide) |  |  | 3 |  | 1.5 | [9 empty] | 4 |  |  |  | 8.5
Manually mark invoice Archived |  |  | 9 |  | 2.5 |  |  |  | 4 |  |  | 9 |  |  | 8.5 |  |  |  | 33
Net Amount Total: Add field in header to sum Invoice Net Amount |  |  | 9 |  | 3.5 |  |  |  | 2.5 |  | 3 | 5 | 4 | 3 | 3 |  |  |  | 33
Project Overhead |  |  |  |  | 29.5 | 17 | 1 | 8 |  | 24 | [5 empty] | 5 | 2 |  | 86.5
Rename Invoice amount to invoice net amount |  |  |  |  | 1 | [13 empty] | 1
Retain user-specific report views and filter preferences during |  |  | 83 |  | 1.5 |  |  |  | 3.5 |  | 1.5 | 13 | 6.5 | [5 empty] | 109
Show routing history - Invoice comment log |  |  | 14.5 |  | 2.5 |  |  |  | 5.5 |  | 2.5 | 7 | 3 |  | 2 |  |  |  | 37
Upgrade ApWorks application to dotnet Core 8.0 from 7.0 |  |  | 13.5 | [15 empty] | 13.5
eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | 37 |  | 29 |  | 3 |  |  |  | 15.5 |  | 3 | [6 empty] | 6.5 | 94
NEXELUS 2025.3 | 4 |  | 22.75 | 6.5 | 2 | 11 | 4 | 7.5 | 23 | 14 |  | 11.5 | 7 |  | 6 | 0.5 |  |  | 119.75
DENTSU _ Implementing a custom upload error log in Excel | [8 empty] | 5.75 |  |  | 4 | [6 empty] | 9.75
PO numbers to be appended automatically to campaign names |  |  | 9.75 | [5 empty] | 6.75 | [9 empty] | 16.5
pre-populate objective field from media plan |  |  | 5 |  | 2 |  |  |  | 8 |  |  | 4 |  |  | 6 |  |  |  | 25
Project Overhead | 4 |  |  | 6.5 |  | 11 | 4 | 7.5 |  | 14 | [5 empty] | 0.5 |  |  | 47.5
Show old vs. new values on revision screens (Design and Rev) | [8 empty] | 2.5 |  |  | 3.5 | [6 empty] | 6
Vulnerability Report |  |  | 8 | [9 empty] | 7 | [5 empty] | 15
NEXELUSAPP - MAUI | 19 |  | 130 | 14.5 | [14 empty] | 163.5
Auth Pages: Key Page |  |  | 18 | [15 empty] | 18
Auth Pages: Login Page + Flow |  |  | 33 | [15 empty] | 33
Project Overhead | 19 |  |  | 14.5 | [14 empty] | 33.5
TimeSheet: Add New |  |  | 16 | [15 empty] | 16
TimeSheet: Chart |  |  | 13 | [15 empty] | 13
TimeSheet: Edit |  |  | 2 | [15 empty] | 2
TimeSheet: Main Page |  |  | 29.75 | [15 empty] | 29.75
TimeSheet: Pending Transaction |  |  | 12.25 | [15 empty] | 12.25
Expense: Add New |  |  | 2.5 | [15 empty] | 2.5
Expense: Assignment Page |  |  | 3.5 | [15 empty] | 3.5
Grand Total | 67 | 8 | 357.75 | 21 | 51.5 | 28 | 5 | 15.5 | 59 | 38 | 10 | 49.5 | 20.5 | 3 | 40.5 | 5.5 | 4 | 6.5 | 790.25

## Project Estimate
|  |  |  | Dev |  | Resources |  |  | Planned Hours
Key | Project |  |  | Start Date | Status | Dev | DB | QA | Design | RS Review | Dev | DB | Review | Bug Fixing | Bug Review | Test Case | QA | QA Review
ADHOC-ITEMS
ADHOC-ITEMS:Flag an invoice in Discrepant bucket for searching | ADHOC-ITEMS | 2 | Troubleshoot RM/PM in Nexelus Timesheet | 2025-01-01 | 50%
ADHOC-ITEMS:Format all amounts to be trwo decimals | ADHOC-ITEMS | 1 | Voucher, AP rule flag and 4 sided entry - v3 | 2025-01-01 | 50%
APWORKS - TEST AUTOMATION
APWORKS - TEST AUTOMATION:Manually mark invoice Archived | APWORKS - TEST AUTOMATION | 15 | Media approval: approve invoices |  | 0%
APWORKS - TEST AUTOMATION:Net Amount Total: Add field in header to sum Invoice Net Amount | APWORKS - TEST AUTOMATION | 13 | Media approval: identify approval access |  | 0%
APWORKS - TEST AUTOMATION:Project Overhead | APWORKS - TEST AUTOMATION | 14 | Media Approval: Re-login from user with access for approval |  | 0%
APWORKS - TEST AUTOMATION:Reintroduce the Invoice Number option in Vendor Mapping | APWORKS - TEST AUTOMATION | 2 | Media: Discrepant Invoices - Make Corrections |  | 0%
APWORKS - TEST AUTOMATION:Rename Invoice amount to invoice net amount | APWORKS - TEST AUTOMATION | 12 | Media: Make Corrections and save- Proceed to approval section |  | 0%
APWORKS - TEST AUTOMATION:Retain user-specific report views and filter preferences during | APWORKS - TEST AUTOMATION | 5 | Media: Read Data diven excel files for the correspinding data |  | 0%
APWORKS - TEST AUTOMATION:Show routing history - Invoice comment log | APWORKS - TEST AUTOMATION | 10 | Media: Replace invoice |  | 0%
APWORKS - TEST AUTOMATION:Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | APWORKS - TEST AUTOMATION | 11 | Media: Route to Employee |  | 0%
APWORKS - TEST AUTOMATION:QA Iteration 2 | APWORKS - TEST AUTOMATION | 4 | Media: Validate and input data details lines and fields |  | 0%
APWORKS - TEST AUTOMATION: | APWORKS - TEST AUTOMATION | 3 | Media: Validate and input data header fields |  | 0%
APWORKS - TEST AUTOMATION:Ability to toggle advantage campaign budget on/off via API | APWORKS - TEST AUTOMATION | 1 | Project Overhead |  | 0%
APWORKS 2025.3
APWORKS 2025.3:Ability to control Email alerts | APWORKS 2025.3 | 7 | Ability to control Email alerts | 2025-07-23 | 100% | Ali |  | Ayesha |  |  | 4 |  | 2 |  |  |  | 2 | 1
APWORKS 2025.3:Flag an invoice in Discrepant bucket for searching | APWORKS 2025.3 | 5 | Flag an invoice in Discrepant bucket for searching | 2025-07-09 | 100% | Ali | Yasir | Ayesha | 8 | 2 | 36 | 20 | 10 | 8 |  | 6 | 10 | 3
APWORKS 2025.3:Format all amounts to be trwo decimals | APWORKS 2025.3 | 10 | Format all amounts to be trwo decimals | 2025-06-17 |  | Ali |  | Ayesha | 2 | 2 | 16 |  | 4 | 2 |  | 4 | 6 | 2
APWORKS 2025.3:Hide Favorite button: Does not work ( Fix or hide) | APWORKS 2025.3 | 6 | Hide Favorite button: Does not work ( Fix or hide) | 2025-06-17 | 100% | Arslan |  |  |  |  | 2 |  | 1 |  |  |  | 1 | 0.5
APWORKS 2025.3:Manually mark invoice Archived | APWORKS 2025.3 | 11 | Manually mark invoice Archived | 2025-07-29 | 50% | Asad | Yasir | Kashif | 8 | 8 | 48 | 24 | 8 | 16 |  | 12 | 30 | 4
APWORKS 2025.3:Net Amount Total: Add field in header to sum Invoice Net Amount | APWORKS 2025.3 | 3 | Net Amount Total: Add field in header to sum Invoice Net Amount | 2025-06-17 | 100% | Arslan |  | Kashif | 4 | 2 | 24 | 6 | 2 | 2 | 1 | 4 | 6 | 1
APWORKS 2025.3:Project Overhead | APWORKS 2025.3 | 1 | Project Overhead
APWORKS 2025.3:Reintroduce the Invoice Number option in Vendor Mapping | APWORKS 2025.3 | 8 | Reintroduce the Invoice Number option in Vendor Mapping |  | 0%
APWORKS 2025.3:Rename Invoice amount to invoice net amount | APWORKS 2025.3 | 9 | Rename Invoice amount to invoice net amount |  | 0% | Arslan
APWORKS 2025.3:Retain user-specific report views and filter preferences during | APWORKS 2025.3 | 2 | Retain user-specific report views and filter preferences during | 2025-06-17 | 90% | Ali |  | Ayesha | 8 | 6 | 72 |  | 12 | 12 | 8 | 12 | 24 | 6
APWORKS 2025.3:Show routing history - Invoice comment log | APWORKS 2025.3 | 4 | Show routing history - Invoice comment log | 2025-06-17 | 100% | Arslan |  | Kashif | 6 | 4 | 16 | 8 | 2 | 8 |  | 4 | 8 | 2
APWORKS 2025.3:Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | APWORKS 2025.3 | 15 | Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | 2025-06-24 | 100% | Asad |  |  |  |  | 32
APWORKS 2025.3:eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) |  |  | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | 2025-06-17 | 0% | Shoaib | Yasir | Ayesha | 60 | 8 | 100 | 8
APWORKS 2025.3:QA Iteration 2 | APWORKS 2025.3 |  | QA Iteration 2 | 2025-08-20 | 0% | Muzamal, Shoaib | Arif | Bilal, Hamza | [5 empty] | 160 | 80
NEXELUS 2025.3
NEXELUS 2025.3:Ability to toggle advantage campaign budget on/off via API | NEXELUS 2025.3 | 8 | Ability to toggle advantage campaign budget on/off via API |  | 0% | Arslan | Arif | Hamza | 8 | 12 | 40 | 10 | 20 | 10 |  | 6 | 6 | 3
NEXELUS 2025.3:Add KPI input fields for all metric types, not just Viewability | NEXELUS 2025.3 | 4 | Add KPI input fields for all metric types, not just Viewability |  | 0% | Muzamal |  | Hamza | 4 | 6 | 16 |  | 2 | 4 |  | 6 | 4
NEXELUS 2025.3:DENTSU _ Implementing a custom upload error log in Excel | NEXELUS 2025.3 | 10 | DENTSU _ Implementing a custom upload error log in Excel | 2025-07-28 | 0% | Arslan | Arif | Hamza | 8 | 12 | 46 | 20 | 8 | 16 |  | 16 | 16 | 8
NEXELUS 2025.3:Enable multiple media plans under one Bing IO | NEXELUS 2025.3 | 9 | Enable multiple media plans under one Bing IO | 2025-07-08 | 0% | Asim | Arif | Bilal | 8 | 8 | 100 | 40 | 20 | 40 |  | 12 | 40
NEXELUS 2025.3:PO numbers to be appended automatically to campaign names | NEXELUS 2025.3 | 3 | PO numbers to be appended automatically to campaign names | 2025-07-01 | 0% | Abid, Muzamal |  |  | 6 | 6 | 24 |  | 6 | 6 |  | 4 | 8
NEXELUS 2025.3:pre-populate objective field from media plan | NEXELUS 2025.3 | 7 | pre-populate objective field from media plan | 2025-06-30 | 0% | Arslan | Arif | Hamza | 8 | 12 | 40 | 10 | 2 | 10 |  | 6 | 8 | 2
NEXELUS 2025.3:Project Overhead | NEXELUS 2025.3 | 1 | Project Overhead
NEXELUS 2025.3:Push Package as Campaign Group | NEXELUS 2025.3 | 2 | Push Package as Campaign Group
NEXELUS 2025.3:Push placements as Meta ad sets | NEXELUS 2025.3 | 6 | Push placements as Meta ad sets
NEXELUS 2025.3:Show old vs. new values on revision screens | NEXELUS 2025.3 |  | Show old vs. new values on revision screens
NEXELUS 2025.3:Show old vs. new values on revision screens (Design and Rev) | NEXELUS 2025.3 | 5 | Show old vs. new values on revision screens (Design and Rev) |  | 0% | Abid, Asim |  |  | 16 | 12
NEXELUS 2025.3:Show old vs. new values on revision screens - DB Tasks | NEXELUS 2025.3 | 23 | Show old vs. new values on revision screens - DB Tasks |  | 0% |  | Arif |  |  |  |  | 20
NEXELUS 2025.3:Show old vs. new values on revision screens - DV360 | NEXELUS 2025.3 | 18 | Show old vs. new values on revision screens - DV360 | 2025-07-28 | 0% | Shoaib | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - TTD | NEXELUS 2025.3 | 15 | Show old vs. new values on revision screens - TTD | 2025-07-18 | 0% | Muzamal | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - Twiter | NEXELUS 2025.3 | 17 | Show old vs. new values on revision screens - Twiter | 2025-07-30 | 0% | Muzamal | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - LinkedIn | NEXELUS 2025.3 | 16 | Show old vs. new values on revision screens - LinkedIn | 2025-07-23 | 0% | Abid | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - Meta | NEXELUS 2025.3 | 19 | Show old vs. new values on revision screens - Meta | 2025-08-06 | 0% | Shoaib | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - IPC BingAd | NEXELUS 2025.3 | 20 | Show old vs. new values on revision screens - IPC BingAd | 2025-07-22 | 0% | Shoaib | [5 empty] | 12
NEXELUS 2025.3:Show old vs. new values on revision screens - IPC DV360 | NEXELUS 2025.3 | 21 | Show old vs. new values on revision screens - IPC DV360 | 2025-07-24 | 0% | Shoaib | [5 empty] | 12
NEXELUS 2025.3:Show old vs. new values on revision screens - IPC Meta | NEXELUS 2025.3 | 22 | Show old vs. new values on revision screens - IPC Meta | 2025-08-04 | 0% | Shoaib | [5 empty] | 12
NEXELUS 2025.3:Show old vs. new values on revision screens - Test Cases | NEXELUS 2025.3 |  | Show old vs. new values on revision screens - Test Cases | 2025-07-03 | 0% |  |  | Hamza | [7 empty] | 24
NEXELUS 2025.3:Show old vs. new values on revision screens - QA Review | NEXELUS 2025.3 | 24 | Show old vs. new values on revision screens - QA Review | 2025-07-30 | 0% |  |  | Bilal | [9 empty] | 40
NEXELUS 2025.3:Show old vs. new values on revision screens - Review and Manage | NEXELUS 2025.3 | 25 | Show old vs. new values on revision screens - Review and Manage | 2025-07-18 | 0% | Abid | [6 empty] | 40
NEXELUS 2025.3:Vulnerability Report | NEXELUS 2025.3 | 14 | Vulnerability Report | 2025-06-23 | 0% | Muzamal |  |  |  |  | 30
NEXELUS 2025.3:MC rates for PBG | NEXELUS 2025.3 |  | MC rates for PBG | 2025-07-07 | 0% | Abid | Arif | Bilal |  |  | 32 | 24 |  | 8 |  |  | 16
NEXELUS 2025.3:QA Iteration 2 | NEXELUS 2025.3 |  | QA Iteration 2 | 2025-08-28 | 0% | Asad |  | Bilal, Kashif | [5 empty] | 40 | 80
NEXELUSAPP - MAUI
NEXELUSAPP - MAUI:Auth Pages: Key Page | NEXELUSAPP - MAUI | 2 | Auth Pages: Key Page |  | 100%
NEXELUSAPP - MAUI:Auth Pages: Login Page + Flow | NEXELUSAPP - MAUI | 3 | Auth Pages: Login Page + Flow |  | 50%
NEXELUSAPP - MAUI:TimeSheet: Main Page | NEXELUSAPP - MAUI | 4 | TimeSheet: Main Page |  | 100%
NEXELUSAPP - MAUI:TimeSheet: Chart | NEXELUSAPP - MAUI | 5 | TimeSheet: Chart |  | 100%
NEXELUSAPP - MAUI:TimeSheet: Add New | NEXELUSAPP - MAUI | 6 | TimeSheet: Add New |  | 100%
NEXELUSAPP - MAUI:TimeSheet: Edit | NEXELUSAPP - MAUI | 7 | TimeSheet: Edit |  | 100%
NEXELUSAPP - MAUI:TimeSheet: Pending Transaction | NEXELUSAPP - MAUI | 8 | TimeSheet: Pending Transaction |  | 100%
NEXELUSAPP - MAUI:Expense: Main Page | NEXELUSAPP - MAUI | 9 | Expense: Main Page |  | 100%
NEXELUSAPP - MAUI:Expense: Add New | NEXELUSAPP - MAUI | 10 | Expense: Add New |  | 80%
NEXELUSAPP - MAUI:Expense: Transactions Page + Nested listing | NEXELUSAPP - MAUI | 11 | Expense: Transactions Page + Nested listing |  | 0%
NEXELUSAPP - MAUI:Expense: Assignment Page | NEXELUSAPP - MAUI | 12 | Expense: Assignment Page
NEXELUSAPP - MAUI:Expense: Storage Functionality | NEXELUSAPP - MAUI | 13 | Expense: Storage Functionality
NEXELUSAPP - MAUI:Expense: Permissions | NEXELUSAPP - MAUI | 14 | Expense: Permissions
NEXELUSAPP - MAUI:Expense: Pending Expense Report | NEXELUSAPP - MAUI | 15 | Expense: Pending Expense Report
NEXELUSAPP - MAUI:Time Approval: Main Page | NEXELUSAPP - MAUI | 16 | Time Approval: Main Page
NEXELUSAPP - MAUI:Time Approval: 1st listing page | NEXELUSAPP - MAUI | 17 | Time Approval: 1st listing page
NEXELUSAPP - MAUI:Time Approval: Transaction details | NEXELUSAPP - MAUI | 18 | Time Approval: Transaction details
NEXELUSAPP - MAUI:Time Approval: Comment Popup | NEXELUSAPP - MAUI | 19 | Time Approval: Comment Popup
NEXELUSAPP - MAUI:Expense Approval: Main Page | NEXELUSAPP - MAUI | 20 | Expense Approval: Main Page
NEXELUSAPP - MAUI:Expense Approval: 1st listing page | NEXELUSAPP - MAUI | 21 | Expense Approval: 1st listing page
NEXELUSAPP - MAUI:Expense Approval: 2nd listing page | NEXELUSAPP - MAUI | 22 | Expense Approval: 2nd listing page
NEXELUSAPP - MAUI:Expense Approval: 3rd listing page | NEXELUSAPP - MAUI | 23 | Expense Approval: 3rd listing page
NEXELUSAPP - MAUI:Expense Approval: Transaction details | NEXELUSAPP - MAUI | 24 | Expense Approval: Transaction details
NEXELUSAPP - MAUI:Expense Approval: Comment Popup | NEXELUSAPP - MAUI | 25 | Expense Approval: Comment Popup
NEXELUSAPP - MAUI:Expense Approval: Pending Expense report | NEXELUSAPP - MAUI | 26 | Expense Approval: Pending Expense report
NEXELUSAPP - MAUI:Common Pages: Notification Page | NEXELUSAPP - MAUI | 27 | Common Pages: Notification Page
NEXELUSAPP - MAUI:Common Pages: Profile Page | NEXELUSAPP - MAUI | 28 | Common Pages: Profile Page
NEXELUSAPP - MAUI:Common Pages: User Settings | NEXELUSAPP - MAUI | 29 | Common Pages: User Settings
NEXELUSAPP - MAUI:Common Pages: Pending Expense Report | NEXELUSAPP - MAUI | 30 | Common Pages: Pending Expense Report
NEXELUSAPP - MAUI:API and Logic : Removal of deprecated Controls + Apis | NEXELUSAPP - MAUI | 31 | API and Logic : Removal of deprecated Controls + Apis
NEXELUSAPP - MAUI:API and Logic : App Icons and Splash Changes | NEXELUSAPP - MAUI | 32 | API and Logic : App Icons and Splash Changes
NEXELUSAPP - MAUI:API and Logic : IOS Related Issues and fixing | NEXELUSAPP - MAUI | 33 | API and Logic : IOS Related Issues and fixing
NEXELUSAPP - MAUI:API and Logic : Notifications Support + Flow | NEXELUSAPP - MAUI | 34 | API and Logic : Notifications Support + Flow
NEXELUSAPP - MAUI:API and Logic : Handlers + Other Services | NEXELUSAPP - MAUI | 35 | API and Logic : Handlers + Other Services
NEXELUSAPP - MAUI:API and Logic : OkTA Login, Tesseract | NEXELUSAPP - MAUI | 36 | API and Logic : OkTA Login, Tesseract
NEXELUSAPP - MAUI

## Data
employee | level2_key | level3_description | task_code | appliedmonth | Hours
Kashif Hayat | APWORKS - TEST AUTOMATION | Media approval: approve invoices | Development | 2025-04 | 24
Kashif Hayat | APWORKS - TEST AUTOMATION | Media: Discrepant Invoices - Make Corrections | Development | 2025-04 | 4
Kashif Hayat | APWORKS - TEST AUTOMATION | Media: Read Data diven excel files for the correspinding data | Design | 2025-04 | 8
Muhammad Yasir | APWORKS - TEST AUTOMATION | Project Overhead | Analysis | 2025-05 | 1
Abid Ali | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Analysis | 2025-06 | 3
Abid Ali | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | SRS-Review | 2025-06 | 1
Abid Ali | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | SRS-Review | 2025-06 | 1
Abid Ali | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Task/Code Review | 2025-06 | 1
Abid Ali | APWORKS 2025.3 | Project Overhead | Planinng | 2025-06 | 11
Abid Ali | APWORKS 2025.3 | Project Overhead | Project Mgmt | 2025-06 | 4
Abid Ali | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | SRS-Review | 2025-06 | 0.5
Abid Ali | APWORKS 2025.3 | Show routing history - Invoice comment log | SRS-Review | 2025-06 | 0.5
Abid Ali | APWORKS 2025.3 | Show routing history - Invoice comment log | Task/Code Review | 2025-06 | 1
Abid Ali | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | SRS-Review | 2025-06 | 1
Abid Ali | NEXELUS 2025.3 | pre-populate objective field from media plan | SRS-Review | 2025-06 | 1
Abid Ali | NEXELUS 2025.3 | Project Overhead | Planinng | 2025-06 | 9
Abid Ali | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | SRS-Review | 2025-06 | 1.5
Aimen nasar | NEXELUSAPP - MAUI | Auth Pages: Key Page | Development | 2025-06 | 13
Aimen nasar | NEXELUSAPP - MAUI | Auth Pages: Login Page + Flow | Development | 2025-06 | 22
Aimen nasar | NEXELUSAPP - MAUI | TimeSheet: Add New | Development | 2025-06 | 10
Aimen nasar | NEXELUSAPP - MAUI | TimeSheet: Edit | Development | 2025-06 | 2
Aimen nasar | NEXELUSAPP - MAUI | TimeSheet: Main Page | Development | 2025-06 | 7
Aimen nasar | NEXELUSAPP - MAUI | TimeSheet: Pending Transaction | Development | 2025-06 | 8
Ali Junaid | APWORKS 2025.3 | Project Overhead | Meetings | 2025-06 | 2.5
Ali Junaid | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Development | 2025-06 | 64
Arif Khan Arif | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | DB Dev | 2025-06 | 3
Arslan Khalid | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | SRS-Review | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | Meetings | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | SRS-Review | 2025-06 | 1.5
Arslan Khalid | APWORKS 2025.3 | Hide Favorite button: Does not work ( Fix or hide) | Development | 2025-06 | 2
Arslan Khalid | APWORKS 2025.3 | Manually mark invoice Archived | SRS-Review | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Development | 2025-06 | 9
Arslan Khalid | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Meetings | 2025-06 | 3
Arslan Khalid | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | SRS-Review | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Task/Code Review | 2025-06 | 2
Arslan Khalid | APWORKS 2025.3 | Rename Invoice amount to invoice net amount | Meetings | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Meetings | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | SRS-Review | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Show routing history - Invoice comment log | Development | 2025-06 | 9
Arslan Khalid | APWORKS 2025.3 | Show routing history - Invoice comment log | Meetings | 2025-06 | 1
Arslan Khalid | APWORKS 2025.3 | Show routing history - Invoice comment log | SRS-Review | 2025-06 | 4
Asad Mahmood | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | SRS-Review | 2025-06 | 5.5
Asad Mahmood | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | Meetings | 2025-06 | 1.5
Asad Mahmood | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | SRS-Review | 2025-06 | 1.5
Asad Mahmood | APWORKS 2025.3 | Hide Favorite button: Does not work ( Fix or hide) | Meetings | 2025-06 | 1.5
Asad Mahmood | APWORKS 2025.3 | Manually mark invoice Archived | Meetings | 2025-06 | 1.5
Asad Mahmood | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Meetings | 2025-06 | 0.5
Asad Mahmood | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | SRS-Review | 2025-06 | 0.5
Asad Mahmood | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Meetings | 2025-06 | 0.5
Asad Mahmood | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | SRS-Review | 2025-06 | 2
Asad Mahmood | APWORKS 2025.3 | Show routing history - Invoice comment log | Meetings | 2025-06 | 0.5
Asad Mahmood | APWORKS 2025.3 | Show routing history - Invoice comment log | SRS-Review | 2025-06 | 1
Asad Mahmood | APWORKS 2025.3 | Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | Development | 2025-06 | 13.5
Ayesha Qurban | APWORKS 2025.3 | Project Overhead | Meetings | 2025-06 | 4
Ayesha Qurban | APWORKS 2025.3 | Project Overhead | Task Domain | 2025-06 | 9
Ayesha Qurban | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Test Case Dev | 2025-06 | 13
Bilal Afzal Raja | APWORKS 2025.3 | Project Overhead | Meetings | 2025-06 | 7
Bilal Afzal Raja | APWORKS 2025.3 | Project Overhead | Task Domain | 2025-06 | 11
Hamza Nouman | APWORKS 2025.3 | Project Overhead | Meetings | 2025-06 | 4
Hamza Nouman | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | Test Case Dev | 2025-06 | 1
Hamza Nouman | NEXELUS 2025.3 | pre-populate objective field from media plan | Test Case Dev | 2025-06 | 1
Hamza Nouman | NEXELUS 2025.3 | Project Overhead | Analysis | 2025-06 | 4
Hamza Nouman | NEXELUS 2025.3 | Project Overhead | Task Domain | 2025-06 | 2
Hamza Nouman | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | Test Case Dev | 2025-06 | 1
Hamza Nouman | NEXELUS 2025.3 | Vulnerability Report | Testing | 2025-06 | 7
Kashif Hayat | APWORKS - TEST AUTOMATION | Project Overhead | Analysis | 2025-06 | 6
Kashif Hayat | APWORKS 2025.3 | Manually mark invoice Archived | Test Case Dev | 2025-06 | 9
Kashif Hayat | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Test Case Dev | 2025-06 | 4
Kashif Hayat | APWORKS 2025.3 | Project Overhead | Meetings | 2025-06 | 8
Kashif Hayat | APWORKS 2025.3 | Project Overhead | Task Domain | 2025-06 | 4
Muhammad Yasir | APWORKS 2025.3 | Hide Favorite button: Does not work ( Fix or hide) | DB Dev | 2025-06 | 4
Muhammad Yasir | APWORKS 2025.3 | Manually mark invoice Archived | DB Dev | 2025-06 | 8
Muhammad Yasir | APWORKS 2025.3 | Manually mark invoice Archived | Meetings | 2025-06 | 1
Muhammad Yasir | APWORKS 2025.3 | Manually mark invoice Archived | SRS-Review | 2025-06 | 1
Muhammad Yasir | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | DB Dev | 2025-06 | 3
Muhammad Yasir | APWORKS 2025.3 | Project Overhead | Post_dep_fixes | 2025-06 | 1
Muhammad Yasir | APWORKS 2025.3 | Show routing history - Invoice comment log | DB Dev | 2025-06 | 2
Muhammad Yasir | APWORKS 2025.3 | Show routing history - Invoice comment log | Meetings | 2025-06 | 1
Muhammad Yasir | NEXELUS 2025.3 | Project Overhead | Post_dep_fixes | 2025-06 | 4
Muzammil Shahzad | NEXELUS 2025.3 | Project Overhead | Documentation | 2025-06 | 3
Muzammil Shahzad | Nexelus 2025.3 | Vulnerability Report | Development | 2025-06 | 8
Muzammil Shahzad | NEXELUSAPP - MAUI | Auth Pages: Key Page | Development | 2025-06 | 5
Muzammil Shahzad | NEXELUSAPP - MAUI | Auth Pages: Login Page + Flow | Development | 2025-06 | 4.5
Muzammil Shahzad | NEXELUSAPP - MAUI | Project Overhead | Analysis | 2025-06 | 19
Muzammil Shahzad | NEXELUSAPP - MAUI | Project Overhead | Documentation | 2025-06 | 14.5
Muzammil Shahzad | NEXELUSAPP - MAUI | TimeSheet: Main Page | Development | 2025-06 | 19.75
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Analysis | 2025-06 | 34
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Development | 2025-06 | 4
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Meetings | 2025-06 | 2
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | SRS-Review | 2025-06 | 3
Abid Ali | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | SRS-Review | 2025-07 | 4
Abid Ali | APWORKS 2025.3 | Project Overhead | Deployment | 2025-07 | 5
Abid Ali | APWORKS 2025.3 | Project Overhead | Planinng | 2025-07 | 6
Abid Ali | APWORKS 2025.3 | Project Overhead | Project Mgmt | 2025-07 | 4
Abid Ali | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Task/Code Review | 2025-07 | 1.5
Abid Ali | APWORKS 2025.3 | Show routing history - Invoice comment log | Task/Code Review | 2025-07 | 1.5
Abid Ali | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | SRS-Review | 2025-07 | 1
Abid Ali | NEXELUS 2025.3 | pre-populate objective field from media plan | SRS-Review | 2025-07 | 1
Abid Ali | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | SRS-Review | 2025-07 | 1
Aimen nasar | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | Development | 2025-07 | 2
Aimen nasar | NEXELUSAPP - MAUI | Auth Pages: Login Page + Flow | Development | 2025-07 | 6.5
Aimen nasar | NEXELUSAPP - MAUI | Expense: Add New | Development | 2025-07 | 2.5
Aimen nasar | NEXELUSAPP - MAUI | Expense: Assignment Page | Development | 2025-07 | 3.5
Aimen nasar | NEXELUSAPP - MAUI | TimeSheet: Add New | Development | 2025-07 | 6
Aimen nasar | NEXELUSAPP - MAUI | TimeSheet: Chart | Development | 2025-07 | 10.5
Ali Junaid | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | Development | 2025-07 | 16
Ali Junaid | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | SRS-Review | 2025-07 | 1
Ali Junaid | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Development | 2025-07 | 19
Arif Khan Arif | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | DB Dev | 2025-07 | 4.5
Arif Khan Arif | NEXELUS 2025.3 | pre-populate objective field from media plan | DB Dev | 2025-07 | 6
Arif Khan Arif | NEXELUS 2025.3 | Project Overhead | Deployment | 2025-07 | 0.5
Arif Khan Arif | NEXELUS 2025.3 | Project Overhead | Planinng | 2025-07 | 2
Arslan Khalid | APWORKS 2025.3 | Hide Favorite button: Does not work ( Fix or hide) | Development | 2025-07 | 1
Arslan Khalid | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Bug Fixing | 2025-07 | 3
Arslan Khalid | APWORKS 2025.3 | Show routing history - Invoice comment log | Development | 2025-07 | 5.5
Arslan Khalid | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | SRS-Review | 2025-07 | 5.75
Arslan Khalid | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | SRS-Review | 2025-07 | 0.5
Arslan Khalid | NEXELUS 2025.3 | pre-populate objective field from media plan | Development | 2025-07 | 5
Arslan Khalid | NEXELUS 2025.3 | pre-populate objective field from media plan | Meetings | 2025-07 | 2
Arslan Khalid | NEXELUS 2025.3 | pre-populate objective field from media plan | SRS-Review | 2025-07 | 6
Asad Mahmood | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | SRS-Review | 2025-07 | 2
Asad Mahmood | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Task/Code Review | 2025-07 | 3
Asad Mahmood | APWORKS 2025.3 | Manually mark invoice Archived | Development | 2025-07 | 9
Asad Mahmood | APWORKS 2025.3 | Manually mark invoice Archived | SRS-Review | 2025-07 | 2
Ayesha Qurban | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | Test Case Dev | 2025-07 | 4
Ayesha Qurban | APWORKS 2025.3 | Project Overhead | Meetings | 2025-07 | 1
Ayesha Qurban | APWORKS 2025.3 | Retain user-specific report views and filter preferences during | Testing | 2025-07 | 6.5
Bilal Afzal Raja | NEXELUS 2025.3 | Project Overhead | Project Mgmt | 2025-07 | 7.5
Bilal Afzal Raja | NEXELUS 2025.3 | Project Overhead | Task Domain | 2025-07 | 8
Hamza Nouman | NEXELUS 2025.3 | DENTSU _ Implementing a custom upload error log in Excel | Test Case Dev | 2025-07 | 3
Hamza Nouman | NEXELUS 2025.3 | pre-populate objective field from media plan | Test Case Dev | 2025-07 | 3
Hamza Nouman | NEXELUS 2025.3 | Project Overhead | Task Domain | 2025-07 | 4
Hamza Nouman | NEXELUS 2025.3 | Show old vs. new values on revision screens (Design and Rev) | Test Case Dev | 2025-07 | 2.5
Kashif Hayat | APWORKS - TEST AUTOMATION | Project Overhead | No Workbench | 2025-07 | 2
Kashif Hayat | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Test Case Dev | 2025-07 | 1
Kashif Hayat | APWORKS 2025.3 | Net Amount Total: Add field in header to sum Invoice Net Amount | Testing | 2025-07 | 4
Kashif Hayat | APWORKS 2025.3 | Project Overhead | Meetings | 2025-07 | 3
Kashif Hayat | APWORKS 2025.3 | Project Overhead | No Workbench | 2025-07 | 2
Kashif Hayat | APWORKS 2025.3 | Show routing history - Invoice comment log | Test Case Dev | 2025-07 | 7
Kashif Hayat | APWORKS 2025.3 | Show routing history - Invoice comment log | Testing | 2025-07 | 3
Muhammad Yasir | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | DB Dev | 2025-07 | 8.5
Muhammad Yasir | ADHOC-ITEMS | Voucher, AP rule flag and 4 sided entry - v3 | Meetings | 2025-07 | 2
Muhammad Yasir | APWORKS 2025.3 | Flag an invoice in Discrepant bucket for searching | DB Dev | 2025-07 | 1
Muhammad Yasir | APWORKS 2025.3 | Manually mark invoice Archived | DB Dev | 2025-07 | 0.5
Muzammil Shahzad | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | Development | 2025-07 | 7.75
Muzammil Shahzad | NEXELUS 2025.3 | PO numbers to be appended automatically to campaign names | SRS-Review | 2025-07 | 4.25
Muzammil Shahzad | NEXELUS 2025.3 | Project Overhead | Documentation | 2025-07 | 3.5
Muzammil Shahzad | NEXELUSAPP - MAUI | TimeSheet: Chart | Development | 2025-07 | 2.5
Muzammil Shahzad | NEXELUSAPP - MAUI | TimeSheet: Main Page | Development | 2025-07 | 3
Muzammil Shahzad | NEXELUSAPP - MAUI | TimeSheet: Pending Transaction | Development | 2025-07 | 4.25
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Development | 2025-07 | 25
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Meetings | 2025-07 | 1
Shoaib Hassan | APWORKS 2025.3 | eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | Research | 2025-07 | 6.5

## SQL
select level2_key,level3_key,level3_description from pdd_level3 where level2_key in ('APWORKS 2025.3','NEXELUS 2025.3','APWORKS - TEST AUTOMATION', 'ADHOC-ITEMS','NEXELUSAPP - MAUI') order by level2_key,level3_key
select employee,level2_key,level3_description,task_code,appliedmonth,sum(Hours) Hours from pdv_timesheet_summary where level2_key in ('APWORKS 2025.3','NEXELUS 2025.3','APWORKS - TEST AUTOMATION', 'ADHOC-ITEMS','NEXELUSAPP - MAUI') group by employee,level2_key,level3_description,task_code,appliedmonth order by employee,level2_key,level3_description,task_code,appliedmonth

## Pivot (hidden)
appliedmonth | (All)
Sum of Hours | Column Labels
Row Labels | Analysis | Design | Development | Documentation | Meetings | Planinng | Post_dep_fixes | Project Mgmt | SRS-Review | Task Domain | Task/Code Review | Test Case Dev | Testing | Bug Fixing | DB Dev | Deployment | No Workbench | Research | Grand Total
ADHOC-ITEMS |  |  |  |  | 2 | [9 empty] | 16 |  |  |  | 18
Voucher, AP rule flag and 4 sided entry - v3 |  |  |  |  | 2 | [9 empty] | 16 |  |  |  | 18
APWORKS - TEST AUTOMATION | 7 | 8 | 28 | [13 empty] | 2 |  | 45
Media approval: approve invoices |  |  | 24 | [15 empty] | 24
Media: Discrepant Invoices - Make Corrections |  |  | 4 | [15 empty] | 4
Media: Read Data diven excel files for the correspinding data |  | 8 | [16 empty] | 8
Project Overhead | 7 | [15 empty] | 2 |  | 9
APWORKS 2025.3 | 37 |  | 177 |  | 47.5 | 17 | 1 | 8 | 36 | 24 | 10 | 38 | 13.5 | 3 | 18.5 | 5 | 2 | 6.5 | 444
Flag an invoice in Discrepant bucket for searching |  |  | 16 |  | 2.5 |  |  |  | 5 |  |  | 4 |  |  | 1 |  |  |  | 28.5
Hide Favorite button: Does not work ( Fix or hide) |  |  | 3 |  | 1.5 | [9 empty] | 4 |  |  |  | 8.5
Manually mark invoice Archived |  |  | 9 |  | 2.5 |  |  |  | 4 |  |  | 9 |  |  | 8.5 |  |  |  | 33
Net Amount Total: Add field in header to sum Invoice Net Amount |  |  | 9 |  | 3.5 |  |  |  | 2.5 |  | 3 | 5 | 4 | 3 | 3 |  |  |  | 33
Project Overhead |  |  |  |  | 29.5 | 17 | 1 | 8 |  | 24 | [5 empty] | 5 | 2 |  | 86.5
Rename Invoice amount to invoice net amount |  |  |  |  | 1 | [13 empty] | 1
Retain user-specific report views and filter preferences during |  |  | 83 |  | 1.5 |  |  |  | 3.5 |  | 1.5 | 13 | 6.5 | [5 empty] | 109
Show routing history - Invoice comment log |  |  | 14.5 |  | 2.5 |  |  |  | 5.5 |  | 2.5 | 7 | 3 |  | 2 |  |  |  | 37
Upgrade ApWorks application to dotnet Core 8.0 from 7.0 |  |  | 13.5 | [15 empty] | 13.5
eInvoices (iPC)(BingAd, DV360,GCM,GoogleAd, Twitter) | 37 |  | 29 |  | 3 |  |  |  | 15.5 |  | 3 | [6 empty] | 6.5 | 94
NEXELUS 2025.3 | 4 |  | 22.75 | 6.5 | 2 | 11 | 4 | 7.5 | 23 | 14 |  | 11.5 | 7 |  | 6 | 0.5 |  |  | 119.75
DENTSU _ Implementing a custom upload error log in Excel | [8 empty] | 5.75 |  |  | 4 | [6 empty] | 9.75
PO numbers to be appended automatically to campaign names |  |  | 9.75 | [5 empty] | 6.75 | [9 empty] | 16.5
pre-populate objective field from media plan |  |  | 5 |  | 2 |  |  |  | 8 |  |  | 4 |  |  | 6 |  |  |  | 25
Project Overhead | 4 |  |  | 6.5 |  | 11 | 4 | 7.5 |  | 14 | [5 empty] | 0.5 |  |  | 47.5
Show old vs. new values on revision screens (Design and Rev) | [8 empty] | 2.5 |  |  | 3.5 | [6 empty] | 6
Vulnerability Report |  |  | 8 | [9 empty] | 7 | [5 empty] | 15
NEXELUSAPP - MAUI | 19 |  | 130 | 14.5 | [14 empty] | 163.5
Auth Pages: Key Page |  |  | 18 | [15 empty] | 18
Auth Pages: Login Page + Flow |  |  | 33 | [15 empty] | 33
Project Overhead | 19 |  |  | 14.5 | [14 empty] | 33.5
TimeSheet: Add New |  |  | 16 | [15 empty] | 16
TimeSheet: Chart |  |  | 13 | [15 empty] | 13
TimeSheet: Edit |  |  | 2 | [15 empty] | 2
TimeSheet: Main Page |  |  | 29.75 | [15 empty] | 29.75
TimeSheet: Pending Transaction |  |  | 12.25 | [15 empty] | 12.25
Expense: Add New |  |  | 2.5 | [15 empty] | 2.5
Expense: Assignment Page |  |  | 3.5 | [15 empty] | 3.5
Grand Total | 67 | 8 | 357.75 | 21 | 51.5 | 28 | 5 | 15.5 | 59 | 38 | 10 | 49.5 | 20.5 | 3 | 40.5 | 5.5 | 4 | 6.5 | 790.25