## Sheet2
Resource Commitment Chart
Projects: Nexelus 2024.3, APWorks 2025.3, Mobile App
Hours Per Day | 7
Over All Resource Allocation (Nexelus, APWorks, Mobile App)
Work Distribution
Resource Name | Dept | Total House / Hour Per Month | June | July | August | September | October | November | December | January
|  |  | 70 | 161 | 147 | 147 | 161 | 140 | 161 | 154
Unassigned |  | 128 hrs | Work Distribution June: 98; Work Distribution July: 30
Abid | Dev | 380.43 hrs | Work Distribution June: 125.27; Work Distribution July: 142.44; Work Distribution August: 112.07; Work Distribution September: 0.65
Asim | Dev | 247.33 hrs | Work Distribution June: 53.73; Work Distribution July: 90.93; Work Distribution August: 102.67
Muzamal | Dev | 429.91 hrs | 24.9 | 144.72 | 105.08 | 75.2 | 36.8 | 32 | 11.2
Shoaib | Dev | 331 hrs | Work Distribution June: 34.5; Work Distribution July: 146.9; Work Distribution August: 109.6; Work Distribution September: 40
Arslan | Dev | 293.69 hrs | Work Distribution June: 35.2; Work Distribution July: 139.03; Work Distribution August: 79.47; Work Distribution September: 40
Asad | Dev | 244 hrs | Work Distribution June: 34.93; Work Distribution July: 147.2; Work Distribution August: 61.87
Ali | Dev | 247.38 hrs | Work Distribution June: 55.53; Work Distribution July: 129.2; Work Distribution August: 62.65
Aimen | Dev | 600 hrs | 64 | 147.2 | 128 | 140.8 | 120
Arif | Dev | 168.48 hrs | Work Distribution June: 7.02; Work Distribution July: 69.09; Work Distribution August: 49.13; Work Distribution September: 43.24
Yasir | DB | 202 hrs | Work Distribution June: 41.6; Work Distribution July: 73.23; Work Distribution August: 87.17
Bilal | DB | 309.47 hrs | 9.5 | 35.5 | 99.62 | 84.86 |  |  | 74.17 | 5.83
Hamza | QA | 238.47 hrs | Work Distribution June: 29.62; Work Distribution July: 68.43; Work Distribution August: 70.42; Work Distribution September: 70
Tao | QA | 42.33 hrs | Work Distribution June: 42.33
Ayesha | QA | 185 hrs | Work Distribution June: 36.53; Work Distribution July: 78.47; Work Distribution August: 40; Work Distribution September: 30
Kashif | QA | 438 hrs | 23.53 | 71.97 | 175.8 | 52.8 | 55.2 | 48 | 10.7
Resource Allocation - Nexelus
Work Distribution
Resource Name | Dept | Total House / Hour Per Month | June | July | August | September | October | November | December | January
|  |  | 70 | 161 | 147 | 147 | 161 | 140 | 161 | 154
Unassigned |  | 52 hrs | Work Distribution June: 44.08; Work Distribution July: 7.92
Abid | Dev | 226.17 hrs | Work Distribution June: 39.79; Work Distribution July: 112.45; Work Distribution August: 73.93
Asim | Dev | 208 hrs | Work Distribution June: 16; Work Distribution July: 114.77; Work Distribution August: 77.23
Muzamal | Dev | 229.91 hrs | Work Distribution June: 21.1; Work Distribution July: 109.96; Work Distribution August: 66.95; Work Distribution September: 31.9
Shoaib | Dev | 176 hrs | Work Distribution June: 64; Work Distribution July: 72; Work Distribution August: 8.1; Work Distribution September: 31.9
Arslan | Dev | 224 hrs | Work Distribution June: 40; Work Distribution July: 120.8; Work Distribution August: 31.3; Work Distribution September: 31.9
Asad | Dev | 0 hrs
Ali | Dev | 0 hrs
Aimen | Dev | 0 hrs
Arif | Dev | 166.48 hrs | Work Distribution June: 7.5; Work Distribution July: 98.67; Work Distribution August: 28.4; Work Distribution September: 31.9
Yasir | DB | 48 hrs | Work Distribution July: 48
Bilal | DB | 185.97 hrs | Work Distribution June: 2.5; Work Distribution July: 33.67; Work Distribution August: 87.91; Work Distribution September: 61.9
Hamza | QA | 238.47 hrs | Work Distribution June: 34; Work Distribution July: 101.54; Work Distribution August: 42.19; Work Distribution September: 60.74
Tao | QA | 0 hrs
Ayesha | QA | 30 hrs | Work Distribution September: 30
Kashif | QA | 0 hrs | Work Distribution June: 0; Work Distribution July: 0; Work Distribution August: 0; Work Distribution September: 0
Resource Allocation - APWorks
Work Distribution
Resource Name | Dept | Total House / Hour Per Month | June | July | August | September | October | November | December | January
|  |  | 70 | 161 | 147 | 147 | 161 | 140 | 161 | 154
Unassigned |  | 76 hrs | Work Distribution June: 76
Abid | Dev | 154.26 hrs | Work Distribution June: 89.54; Work Distribution July: 54.55; Work Distribution August: 10.16
Asim | Dev | 39.33 hrs | Work Distribution June: 39.33
Muzamal | Dev | 0 hrs
Shoaib | Dev | 155 hrs | Work Distribution June: 34.5; Work Distribution July: 120.5
Arslan | Dev | 69.69 hrs | Work Distribution June: 35.2; Work Distribution July: 34.49
Asad | Dev | 244 hrs | Work Distribution June: 34.93; Work Distribution July: 147.2; Work Distribution August: 61.87
Ali | Dev | 247.38 hrs | Work Distribution June: 55.53; Work Distribution July: 129.2; Work Distribution August: 62.65
Aimen | Dev | 0 hrs
Arif | Dev | 2 hrs | Work Distribution July: 2
Yasir | DB | 154 hrs | Work Distribution June: 41.6; Work Distribution July: 60.33; Work Distribution August: 52.07
Bilal | DB | 43.5 hrs | Work Distribution June: 7; Work Distribution July: 12.5; Work Distribution August: 24
Hamza | QA | 0 hrs
Tao | QA | 42.33 hrs | Work Distribution June: 42.33
Ayesha | QA | 155 hrs | Work Distribution June: 36.53; Work Distribution July: 78.47; Work Distribution August: 40
Kashif | QA | 158 hrs | Work Distribution June: 23.53; Work Distribution July: 16.47; Work Distribution August: 118
Resource Allocation on Mobile App
Work Distribution
Resource Name | Dept | Total House / Hour Per Month | June | July | August | September | October | November | December | January
|  |  | 70 | 161 | 147 | 147 | 161 | 140 | 161 | 154
Unassigned |  | 0 hrs
Abid | Dev | 0 hrs
Asim | Dev | 0 hrs
Muzamal | Dev | 200 hrs | 16 | 36.8 | 32 | 35.2 | 36.8 | 32 | 11.2
Shoaib | Dev | 0 hrs
Arslan | Dev | 0 hrs
Asad | Dev | 0 hrs
Ali | Dev | 0 hrs
Aimen | Dev | 600 hrs | 64 | 147.2 | 128 | 140.8 | 120
Arif | Dev | 0 hrs
Yasir | DB | 0 hrs
Bilal | DB | 80 hrs | Work Distribution December: 74.17; Work Distribution January: 5.83
Hamza | QA | 0 hrs
Tao | QA | 0 hrs
Ayesha | QA | 0 hrs
Kashif | QA | 280 hrs |  | 55.5 | 57.8 | 52.8 | 55.2 | 48 | 10.7