## Sheet1
|  |  |  | Dev |  | Resources |  |  | Planned Hours
Key | Project |  |  | Start Date | Status | Dev | DB | QA | Design | RS Review | Dev | DB | Review | Bug Fixing | Bug Review | Test Case | QA | QA Review
ADHOC-ITEMS
ADHOC-ITEMS:Flag an invoice in Discrepant bucket for searching |  | 2 | Troubleshoot RM/PM in Nexelus Timesheet | 2025-01-01
ADHOC-ITEMS:Format all amounts to be trwo decimals |  | 1 | Voucher, AP rule flag and 4 sided entry - v3 | 2025-01-01
APWORKS - TEST AUTOMATION
APWORKS - TEST AUTOMATION:Manually mark invoice Archived |  | 15 | Media approval: approve invoices
APWORKS - TEST AUTOMATION:Net Amount Total: Add field in header to sum Invoice Net Amount |  | 13 | Media approval: identify approval access
APWORKS - TEST AUTOMATION:Project Overhead |  | 14 | Media Approval: Re-login from user with access for approval
APWORKS - TEST AUTOMATION:Reintroduce the Invoice Number option in Vendor Mapping |  | 2 | Media: Discrepant Invoices - Make Corrections
APWORKS - TEST AUTOMATION:Rename Invoice amount to invoice net amount |  | 12 | Media: Make Corrections and save- Proceed to approval section
APWORKS - TEST AUTOMATION:Retain user-specific report views and filter preferences during |  | 5 | Media: Read Data diven excel files for the correspinding data
APWORKS - TEST AUTOMATION:Show routing history - Invoice comment log |  | 10 | Media: Replace invoice
APWORKS - TEST AUTOMATION:Upgrade ApWorks application to dotnet Core 8.0 from 7.0 |  | 11 | Media: Route to Employee
APWORKS - TEST AUTOMATION:QA Iteration 2 |  | 4 | Media: Validate and input data details lines and fields
APWORKS - TEST AUTOMATION: |  | 3 | Media: Validate and input data header fields
APWORKS - TEST AUTOMATION:Ability to toggle advantage campaign budget on/off via API |  | 1 | Project Overhead
APWORKS 2025.3
APWORKS 2025.3:Ability to control Email alerts | APWORKS 2025.3 | 7 | Ability to control Email alerts | 2025-07-23 |  | Ali |  | Ayesha |  |  | 4 |  | 2 |  |  |  | 2 | 1
APWORKS 2025.3:Flag an invoice in Discrepant bucket for searching | APWORKS 2025.3 | 5 | Flag an invoice in Discrepant bucket for searching | 2025-07-09 |  | Ali | Yasir | Ayesha | 8 | 2 | 36 | 20 | 10 | 8 |  | 6 | 10 | 3
APWORKS 2025.3:Format all amounts to be trwo decimals | APWORKS 2025.3 | 10 | Format all amounts to be trwo decimals | 2025-06-17 |  | Ali |  | Ayesha | 2 | 2 | 16 |  | 4 | 2 |  | 4 | 6 | 2
APWORKS 2025.3:Hide Favorite button: Does not work ( Fix or hide) | APWORKS 2025.3 | 6 | Hide Favorite button: Does not work ( Fix or hide) | 2025-06-17 |  | Ali |  |  |  |  | 2 |  | 1 |  |  |  | 1 | 0.5
APWORKS 2025.3:Manually mark invoice Archived | APWORKS 2025.3 | 11 | Manually mark invoice Archived | 2025-07-29 |  | Ali | Yasir | Kashif | 8 | 8 | 48 | 24 | 8 | 16 |  | 12 | 30 | 4
APWORKS 2025.3:Net Amount Total: Add field in header to sum Invoice Net Amount | APWORKS 2025.3 | 3 | Net Amount Total: Add field in header to sum Invoice Net Amount | 2025-06-17 |  | Arslan |  | Kashif | 4 | 2 | 24 | 6 | 2 | 2 | 1 | 4 | 6 | 1
APWORKS 2025.3:Project Overhead | APWORKS 2025.3 | 1 | Project Overhead
APWORKS 2025.3:Reintroduce the Invoice Number option in Vendor Mapping | APWORKS 2025.3 | 8 | Reintroduce the Invoice Number option in Vendor Mapping
APWORKS 2025.3:Rename Invoice amount to invoice net amount | APWORKS 2025.3 | 9 | Rename Invoice amount to invoice net amount
APWORKS 2025.3:Retain user-specific report views and filter preferences during | APWORKS 2025.3 | 2 | Retain user-specific report views and filter preferences during | 2025-06-17 | 0% | Ali |  | Ayesha | 8 | 6 | 72 |  | 12 | 12 | 8 | 12 | 24 | 6
APWORKS 2025.3:Show routing history - Invoice comment log | APWORKS 2025.3 | 4 | Show routing history - Invoice comment log | 2025-06-17 |  | Arslan |  | Kashif | 6 | 4 | 16 | 8 | 2 | 8 |  | 4 | 8 | 2
APWORKS 2025.3:Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | APWORKS 2025.3 | 15 | Upgrade ApWorks application to dotnet Core 8.0 from 7.0 | 2025-06-24 |  | Asad |  |  |  |  | 32
APWORKS 2025.3:QA Iteration 2 | APWORKS 2025.3 |  | QA Iteration 2 | 2025-08-20 |  | Muzamal, Shoaib | Arif | Bilal, Hamza | [5 empty] | 160 | 80
NEXELUS 2025.3
NEXELUS 2025.3:Ability to toggle advantage campaign budget on/off via API |  | 8 | Ability to toggle advantage campaign budget on/off via API |  |  | Arslan | Arif | Hamza | 8 | 12 | 40 | 10 | 20 | 10 |  | 6 | 6 | 3
NEXELUS 2025.3:Add KPI input fields for all metric types, not just Viewability |  | 4 | Add KPI input fields for all metric types, not just Viewability |  |  | Muzamal |  | Hamza | 4 | 6 | 16 |  | 2 | 4 |  | 6 | 4
NEXELUS 2025.3:DENTSU _ Implementing a custom upload error log in Excel |  | 10 | DENTSU _ Implementing a custom upload error log in Excel | 2025-07-28 |  | Arslan | Arif | Hamza | 8 | 12 | 46 | 20 | 8 | 16 |  | 16 | 16 | 8
NEXELUS 2025.3:Enable multiple media plans under one Bing IO |  | 9 | Enable multiple media plans under one Bing IO | 2025-07-08 |  | Asim | Arif | Bilal | 8 | 8 | 100 | 40 | 20 | 40 |  | 12 | 40
NEXELUS 2025.3:PO numbers to be appended automatically to campaign names |  | 3 | PO numbers to be appended automatically to campaign names | 2025-07-01 |  | Abid, Muzamal |  |  | 6 | 6 | 24 |  | 6 | 6 |  | 4 | 8
NEXELUS 2025.3:pre-populate objective field from media plan |  | 7 | pre-populate objective field from media plan |  |  | Arslan | Arif | Hamza | 8 | 12 | 40 | 10 | 2 | 10 |  | 6 | 8 | 2
NEXELUS 2025.3:Project Overhead |  | 1 | Project Overhead
NEXELUS 2025.3:Push Package as Campaign Group |  | 2 | Push Package as Campaign Group
NEXELUS 2025.3:Push placements as Meta ad sets |  | 6 | Push placements as Meta ad sets
NEXELUS 2025.3:Show old vs. new values on revision screens |  |  | Show old vs. new values on revision screens
NEXELUS 2025.3:Show old vs. new values on revision screens (Design and Rev) |  | 5 | Show old vs. new values on revision screens (Design and Rev) |  |  | Abid, Asim |  |  | 16 | 12
NEXELUS 2025.3:Show old vs. new values on revision screens - DB Tasks |  | 23 | Show old vs. new values on revision screens - DB Tasks |  |  |  | Arif |  |  |  |  | 20
NEXELUS 2025.3:Show old vs. new values on revision screens - DV360 |  | 18 | Show old vs. new values on revision screens - DV360 | 2025-07-28 |  | Shoaib | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - TTD |  | 15 | Show old vs. new values on revision screens - TTD | 2025-07-18 |  | Muzamal | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - Twiter |  | 17 | Show old vs. new values on revision screens - Twiter | 2025-07-30 |  | Muzamal | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - LinkedIn |  | 16 | Show old vs. new values on revision screens - LinkedIn | 2025-07-23 |  | Abid | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - Meta |  | 19 | Show old vs. new values on revision screens - Meta | 2025-08-06 |  | Shoaib | [5 empty] | 36 |  | 6 |  |  | 8
NEXELUS 2025.3:Show old vs. new values on revision screens - IPC BingAd |  | 20 | Show old vs. new values on revision screens - IPC BingAd | 2025-07-22 |  | Shoaib | [5 empty] | 12
NEXELUS 2025.3:Show old vs. new values on revision screens - IPC DV360 |  | 21 | Show old vs. new values on revision screens - IPC DV360 | 2025-07-24 |  | Shoaib | [5 empty] | 12
NEXELUS 2025.3:Show old vs. new values on revision screens - IPC Meta |  | 22 | Show old vs. new values on revision screens - IPC Meta | 2025-08-04 |  | Shoaib | [5 empty] | 12
NEXELUS 2025.3:Show old vs. new values on revision screens - Test Cases |  |  | Show old vs. new values on revision screens - Test Cases | 2025-07-03 |  |  |  | Hamza | [7 empty] | 24
NEXELUS 2025.3:Show old vs. new values on revision screens - QA Review |  | 24 | Show old vs. new values on revision screens - QA Review | 2025-07-30 |  |  |  | Bilal | [9 empty] | 40
NEXELUS 2025.3:Show old vs. new values on revision screens - Review and Manage |  | 25 | Show old vs. new values on revision screens - Review and Manage | 2025-07-18 |  | Abid | [6 empty] | 40
NEXELUS 2025.3:Vulnerability Report |  | 14 | Vulnerability Report | 2025-06-23 |  | Muzamal |  |  |  |  | 30
NEXELUS 2025.3:MC rates for PBG |  |  | MC rates for PBG | 2025-07-07 |  | Abid | Arif | Bilal |  |  | 32 | 24 |  | 8 |  |  | 16
NEXELUS 2025.3:QA Iteration 2 |  |  | QA Iteration 2 | 2025-08-28 |  | Asad |  | Bilal, Kashif | [5 empty] | 40 | 80
NEXELUSAPP - MAUI
NEXELUSAPP - MAUI:Auth Pages: Key Page |  | 2 | Auth Pages: Key Page
NEXELUSAPP - MAUI:Auth Pages: Login Page + Flow |  | 3 | Auth Pages: Login Page + Flow
NEXELUSAPP - MAUI:TimeSheet: Main Page |  | 4 | TimeSheet: Main Page
NEXELUSAPP - MAUI:TimeSheet: Chart |  | 5 | TimeSheet: Chart
NEXELUSAPP - MAUI:TimeSheet: Add New |  | 6 | TimeSheet: Add New
NEXELUSAPP - MAUI:TimeSheet: Edit |  | 7 | TimeSheet: Edit
NEXELUSAPP - MAUI:TimeSheet: Pending Transaction |  | 8 | TimeSheet: Pending Transaction
NEXELUSAPP - MAUI:Expense: Main Page |  | 9 | Expense: Main Page
NEXELUSAPP - MAUI:Expense: Add New |  | 10 | Expense: Add New
NEXELUSAPP - MAUI:Expense: Transactions Page + Nested listing |  | 11 | Expense: Transactions Page + Nested listing
NEXELUSAPP - MAUI:Expense: Assignment Page |  | 12 | Expense: Assignment Page
NEXELUSAPP - MAUI:Expense: Storage Functionality |  | 13 | Expense: Storage Functionality
NEXELUSAPP - MAUI:Expense: Permissions |  | 14 | Expense: Permissions
NEXELUSAPP - MAUI:Expense: Pending Expense Report |  | 15 | Expense: Pending Expense Report
NEXELUSAPP - MAUI:Time Approval: Main Page |  | 16 | Time Approval: Main Page
NEXELUSAPP - MAUI:Time Approval: 1st listing page |  | 17 | Time Approval: 1st listing page
NEXELUSAPP - MAUI:Time Approval: Transaction details |  | 18 | Time Approval: Transaction details
NEXELUSAPP - MAUI:Time Approval: Comment Popup |  | 19 | Time Approval: Comment Popup
NEXELUSAPP - MAUI:Expense Approval: Main Page |  | 20 | Expense Approval: Main Page
NEXELUSAPP - MAUI:Expense Approval: 1st listing page |  | 21 | Expense Approval: 1st listing page
NEXELUSAPP - MAUI:Expense Approval: 2nd listing page |  | 22 | Expense Approval: 2nd listing page
NEXELUSAPP - MAUI:Expense Approval: 3rd listing page |  | 23 | Expense Approval: 3rd listing page
NEXELUSAPP - MAUI:Expense Approval: Transaction details |  | 24 | Expense Approval: Transaction details
NEXELUSAPP - MAUI:Expense Approval: Comment Popup |  | 25 | Expense Approval: Comment Popup
NEXELUSAPP - MAUI:Expense Approval: Pending Expense report |  | 26 | Expense Approval: Pending Expense report
NEXELUSAPP - MAUI:Common Pages: Notification Page |  | 27 | Common Pages: Notification Page
NEXELUSAPP - MAUI:Common Pages: Profile Page |  | 28 | Common Pages: Profile Page
NEXELUSAPP - MAUI:Common Pages: User Settings |  | 29 | Common Pages: User Settings
NEXELUSAPP - MAUI:Common Pages: Pending Expense Report |  | 30 | Common Pages: Pending Expense Report
NEXELUSAPP - MAUI:API and Logic : Removal of deprecated Controls + Apis |  | 31 | API and Logic : Removal of deprecated Controls + Apis
NEXELUSAPP - MAUI:API and Logic : App Icons and Splash Changes |  | 32 | API and Logic : App Icons and Splash Changes
NEXELUSAPP - MAUI:API and Logic : IOS Related Issues and fixing |  | 33 | API and Logic : IOS Related Issues and fixing
NEXELUSAPP - MAUI:API and Logic : Notifications Support + Flow |  | 34 | API and Logic : Notifications Support + Flow
NEXELUSAPP - MAUI:API and Logic : Handlers + Other Services |  | 35 | API and Logic : Handlers + Other Services
NEXELUSAPP - MAUI:API and Logic : OkTA Login, Tesseract |  | 36 | API and Logic : OkTA Login, Tesseract