## Sheet2
Resource Commitment Chart
Projects: Nexelus 2024.3, APWorks 2025.3, Mobile App (Plan V7)
Hours Per Day | 7
Over All Resource Allocation (Nexelus, APWorks, Mobile App)
Work Distribution
Resource Name | Dept | Total House / Hour Per Month | June | July | August | September | October | November | December | January
|  |  | 70 | 161 | 147 | 147 | 161 | 140 | 161 | 154
Unassigned |  | 46 hrs | Work Distribution June: 30; Work Distribution July: 16
Abid | Dev | 397.56 hrs | Work Distribution June: 111.7; Work Distribution July: 176.47; Work Distribution August: 109.39
Asim | Dev | 223.33 hrs | Work Distribution June: 44.67; Work Distribution July: 104.93; Work Distribution August: 73.73
Muzamal | Dev | 448.57 hrs | 44.2 | 143.45 | 117.32 | 63.6 | 36.8 | 32 | 11.2
Shoaib | Dev | 341 hrs | Work Distribution June: 34.5; Work Distribution July: 146.9; Work Distribution August: 124.7; Work Distribution September: 34.9
Arslan | Dev | 287.69 hrs | Work Distribution June: 28.8; Work Distribution July: 137.83; Work Distribution August: 92.67; Work Distribution September: 28.4
Asad | Dev | 306 hrs | Work Distribution June: 35.2; Work Distribution July: 147.2; Work Distribution August: 112; Work Distribution September: 11.6
Ali | Dev | 306.58 hrs | Work Distribution June: 55.53; Work Distribution July: 141.73; Work Distribution August: 97.72; Work Distribution September: 11.6
Aimen | Dev | 600 hrs | 64 | 147.2 | 128 | 140.8 | 120
Arif | Dev | 191.54 hrs | Work Distribution June: 2.5; Work Distribution July: 122.28; Work Distribution August: 38.37; Work Distribution September: 28.4
Yasir | DB | 180 hrs | Work Distribution June: 14.4; Work Distribution July: 91.39; Work Distribution August: 74.21
Bilal | DB | 315.54 hrs | 8.5 | 45.04 | 117.8 | 64.2 |  |  | 74.17 | 5.83
Hamza | QA | 234.54 hrs | Work Distribution July: 97.48; Work Distribution August: 80.32; Work Distribution September: 56.74
Tao | QA | 54.33 hrs | Work Distribution June: 54.33
Ayesha | QA | 185 hrs | Work Distribution June: 21.87; Work Distribution July: 93.13; Work Distribution August: 40; Work Distribution September: 30
Kashif | QA | 438 hrs | 22.1 | 73.4 | 152.6 | 76 | 55.2 | 48 | 10.7
Resource Allocation - Nexelus
Work Distribution
Resource Name | Dept | Total House / Hour Per Month | June | July | August | September | October | November | December | January
|  |  | 70 | 161 | 147 | 147 | 161 | 140 | 161 | 154
Unassigned |  | 16 hrs | Work Distribution July: 16
Abid | Dev | 243.31 hrs | Work Distribution June: 32.5; Work Distribution July: 117.04; Work Distribution August: 93.76
Asim | Dev | 184 hrs | Work Distribution June: 5.33; Work Distribution July: 104.93; Work Distribution August: 73.73
Muzamal | Dev | 248.57 hrs | Work Distribution June: 28.2; Work Distribution July: 106.65; Work Distribution August: 85.32; Work Distribution September: 28.4
Shoaib | Dev | 186 hrs | Work Distribution July: 26.4; Work Distribution August: 124.7; Work Distribution September: 34.9
Arslan | Dev | 222 hrs | Work Distribution July: 100.93; Work Distribution August: 92.67; Work Distribution September: 28.4
Asad | Dev | 0 hrs
Ali | Dev | 0 hrs
Aimen | Dev | 0 hrs
Arif | Dev | 189.54 hrs | Work Distribution June: 2.5; Work Distribution July: 120.28; Work Distribution August: 38.37; Work Distribution September: 28.4
Yasir | DB | 26 hrs | Work Distribution July: 9.7; Work Distribution August: 16.3
Bilal | DB | 192.04 hrs | Work Distribution June: 2.5; Work Distribution July: 31.54; Work Distribution August: 99.6; Work Distribution September: 58.4
Hamza | QA | 234.54 hrs | Work Distribution July: 97.48; Work Distribution August: 80.32; Work Distribution September: 56.74
Tao | QA | 0 hrs
Ayesha | QA | 30 hrs | Work Distribution September: 30
Kashif | QA | 0 hrs | Work Distribution June: 0; Work Distribution July: 0; Work Distribution August: 0; Work Distribution September: 0
Resource Allocation - APWorks
Work Distribution
Resource Name | Dept | Total House / Hour Per Month | June | July | August | September | October | November | December | January
|  |  | 70 | 161 | 147 | 147 | 161 | 140 | 161 | 154
Unassigned |  | 30 hrs | Work Distribution June: 30
Abid | Dev | 154.26 hrs | Work Distribution June: 79.2; Work Distribution July: 59.42; Work Distribution August: 15.63
Asim | Dev | 39.33 hrs | Work Distribution June: 39.33
Muzamal | Dev | 0 hrs
Shoaib | Dev | 155 hrs | Work Distribution June: 34.5; Work Distribution July: 120.5
Arslan | Dev | 65.69 hrs | Work Distribution June: 28.8; Work Distribution July: 36.89
Asad | Dev | 306 hrs | Work Distribution June: 35.2; Work Distribution July: 147.2; Work Distribution August: 112; Work Distribution September: 11.6
Ali | Dev | 306.58 hrs | Work Distribution June: 55.53; Work Distribution July: 141.73; Work Distribution August: 97.72; Work Distribution September: 11.6
Aimen | Dev | 0 hrs
Arif | Dev | 2 hrs | Work Distribution July: 2
Yasir | DB | 154 hrs | Work Distribution June: 14.4; Work Distribution July: 81.69; Work Distribution August: 57.91
Bilal | DB | 43.5 hrs | Work Distribution June: 6; Work Distribution July: 13.5; Work Distribution August: 18.2; Work Distribution September: 5.8
Hamza | QA | 0 hrs
Tao | QA | 54.33 hrs | Work Distribution June: 54.33
Ayesha | QA | 155 hrs | Work Distribution June: 21.87; Work Distribution July: 93.13; Work Distribution August: 40
Kashif | QA | 158 hrs | Work Distribution June: 22.1; Work Distribution July: 17.9; Work Distribution August: 94.8; Work Distribution September: 23.2
Resource Allocation on Mobile App
Work Distribution
Resource Name | Dept | Total House / Hour Per Month | June | July | August | September | October | November | December | January
|  |  | 70 | 161 | 147 | 147 | 161 | 140 | 161 | 154
Unassigned |  | 0 hrs
Abid | Dev | 0 hrs
Asim | Dev | 0 hrs
Muzamal | Dev | 200 hrs | 16 | 36.8 | 32 | 35.2 | 36.8 | 32 | 11.2
Shoaib | Dev | 0 hrs
Arslan | Dev | 0 hrs
Asad | Dev | 0 hrs
Ali | Dev | 0 hrs
Aimen | Dev | 600 hrs | 64 | 147.2 | 128 | 140.8 | 120
Arif | Dev | 0 hrs
Yasir | DB | 0 hrs
Bilal | DB | 80 hrs | Work Distribution December: 74.17; Work Distribution January: 5.83
Hamza | QA | 0 hrs
Tao | QA | 0 hrs
Ayesha | QA | 0 hrs
Kashif | QA | 280 hrs |  | 55.5 | 57.8 | 52.8 | 55.2 | 48 | 10.7