## January 16,2025
L:\Asif Work\DeploymentApp-Pointing2Prod
|  | Feb 17, 2024 (Saturday) | Feb 17, 2024 (Saturday)
Steps | Clients | JustGlobal | TSY
1 | Web Application Backup | √ | √
1.1 | Core Application backup | √ | √
2 | Update login.aspx with offline settings | √ | √
2.1 | Apply Maintenance/Offline Page
3 | Web Build Deployment on Both Web Servers
4 | Update the Build Version under
8 | Take DB Backup from utility and execute the UPGRADE SCRIPT | √
Close the deployment utility
Start the deployment utility
Select the required databases and fill in the all required fields Select check box ; turn off SQL jobs and click on "Turn off SQL jobs" button and note its time
Click the "backup database" button for Golden backup
8.2 | Execute DB Build Customization on HY only | N/A | N/A
10 | Turn Off SQL Notification Jobs | √ | √
10.1 | GOLDEN Backup | √ | √
11 | Update eMAIL and Integration Code=0 | use nex_jg --use NEX_jg_aus --use Nex_jg_sgp --use nex_jg_uk Go select * into pdd_resources_20250116 from pdd_resources update pdd_resources set mail_flag=0 select distinct mail_flag from pdd_resources select * into pdm_company_20250116 from pdm_company update pdm_company set integration_code=0 select integration_code from pdm_company | use nex_tsy --use NEX_helm Go select * into pdd_resources_Feb172024 from pdd_resources update pdd_resources set mail_flag=0 select distinct mail_flag from pdd_resources select * into pdm_company_Feb172024 from pdm_company update pdm_company set integration_code=0 select integration_code from pdm_company
13 | Process Testing | √ | √
14 | Restore Golden Back up | √ | √
| Turn no SQL notification Jobs | √ | √
20 | Remove Maintenance Page
DentsuX | https://dentsux.nexelus.net/web/login_2023.aspx?querymode=on
DentsuCSL | https://dentsuCreative.nexelus.net/web/login_2023.aspx?querymode=on
Wpool | https://whirlpool.nexelus.net/web/login_2023.aspx

## January 17,2025
L:\Asif Work\DeploymentApp-Pointing2Prod
Steps | Clients | HS | HY | PS
| eMail Reference for PS: RE: Invoice Posting error (NEX 14832) We have deployed the backup version of RestSharp.dll to make Quick book integration/posting work. Below is the required version. | N/A | N/A | Version of RestSharp.dll to make Quick book integration/posting work.
1 | Web Application Backup | √ | √ | √
1.1 | Core Application backup | √ | √ | √
1.2 | take backup of rapidshare.dll for PS only | N/A | N/A | √
2 | DownLoad Web package and Update login.aspx with offline settings | √ | √ | √
2.1 | Apply Maintenance/Offline Page | √ | √ | √
3 | Web Build Deployment on Both Web Servers 1. Deploy 13.20240206.1 2. 13.1.1.0029U- Web and DB only- Fix included level2 reference and budget colunms data issue | √ | √ | √
3.1 | Restore the backup of rapidshare.dll for PS only | N/A | N/A | √
4 | Update the Build Version under appsetting.json (core) and web.config (web) 13.20240206.1 | √ | √ | √
4.1 | NOTE: Configuration Changes needs to be done on Web config and appsettings.json | N/A | N/A | N/A
| CreateFolders for Budget and PO formats company wise | N/A | N/A | N/A
| Recycle Application Pool | N/A | N/A | N/A
6 | Web Customization deployment on both Web Servers | N/A | N/A | N/A
7 | Template Deployment on Prod File Server - Replication - PDM HY - Document - PlanExpertFormat | N/A | N/A | N/A
| Switch the script remove mirroring remove logshipping make it simple shrink logfile | N/A | N/A | N/A
| Take DB Backup of HY and DYNHY before deployment | N/A | N/A | N/A
8 | Take DB Backup from utility and execute the following builds 1. 2024-1.1.0.0.028 [DB] | √ | √ | √
| Close the deployment utility |  |  | √
| Start the deployment utility |  |  | √
| Select the required databases and fill in the all required fields Select check box ; turn off SQL jobs and click on "Turn off SQL jobs" button and note its time | √ | √ | √
| Click the "backup database" button for Golden backup | √ | √ | √
8.1 | Take DB Backup from utility and execute the following builds 2. Build 13.1.0.0064H [DB] | 12.31 P< | 12.31
8.2 | Execute DB Build 28R Customization on HY and WF only | N/A | √ | N/A
8 | Manually Execute the cutomized view under DB Build 13.0.0.0103R | N/A | N/A | N/A
8.1 | DB Customized Build 13.0.0.0102R | N/A | N/A | N/A
8.2 | Manually Execute the cutomized view under DB Build 13.0.0.0104U | N/A | N/A | N/A
10 | Turn Off SQL Notification Jobs | √ | √ | √
10.1 | GOLDEN Backup | √ | √ | √
11 | Update eMAIL and Integration Code=0 | For hainc Only use eSM_Hainc use eSM_SCS Go select * into pdd_resources_Feb242023 from pdd_resources update pdd_resources set mail_flag=0 select distinct mail_flag from pdd_resources select * into pdm_company_Feb242023 from pdm_company update pdm_company set integration_code=0 select integration_code from pdm_company | select * into pdd_resources_Feb232023 from pdd_resources update pdd_resources set mail_flag=0 select distinct mail_flag from pdd_resources select * into pdm_company_Feb232023 from pdm_company update pdm_company set integration_code=0 select integration_code from pdm_company | select * into pdd_resources_Feb232023 from pdd_resources update pdd_resources set mail_flag=0 select distinct mail_flag from pdd_resources select * into pdm_company_Feb232023 from pdm_company update pdm_company set integration_code=0 select integration_code from pdm_company
12 | Rename D365 folder as __D365_ before Process Testing on Production SQL server | N/A | N/A | N/A
13 | Process Testing | Performed on Hainc and SCS Only | √ | √
14 | Restore Golden Back up | √ | √ | √
| Turn no SQL notification Jobs | √ | N/A | N/A
16 | Rename __D365_ folder back to its original name after Restore Golden backup on Production SQL server | N/A | N/A | N/A
18 | Post Deployment Script (if Any) | N/A | N/A | N/A
19 | Notification Jobs Execution [Only those that were schedule between the time to turn off and turn on] | N/A | N/A | N/A
20 | Remove Maintenance Page | √

## January 20, 2025
L:\Asif Work\DeploymentApp-Pointing2Prod
Feb 16 2024 (Friday)
Steps | Clients | WF | TA | DenstuCreative | Whirlpool
1 | Web Application Backup | √ | √ | √ | √
1.1 | Core Application backup | √ | √ | √ | √
1.2 | take backup of rapidshare.dll for PS only | N/A | N/A | N/A | N/A
2 | DownLoad Web package and Update login.aspx with offline settings | √ | √ | √ | √
2.1 | Apply Maintenance/Offline Page | √ | √ | √ | √
3 | Web Build Deployment on Both Web Servers 1. Deploy 13.20240206.1 2. 13.1.1.0029U- Web and DB only- Fix included level2 reference and budget colunms data issue | √ | √ | √ | √
3.1 | Restore the backup of rapidshare.dll for PS only | N/A | N/A | N/A | N/A
4 | Update the Build Version under appsetting.json (core) and web.config (web) 13.20240206.1 | √ | √ | √ | √
4.1 | NOTE: Configuration Changes needs to be done on Web config and appsettings.json | N/A | N/A | N/A | N/A
| CreateFolders for Budget and PO formats company wise | N/A | N/A | N/A | N/A
| Recycle Application Pool | N/A | N/A | N/A | N/A
6 | Web Customization deployment on both Web Servers | N/A | N/A | N/A | N/A
7 | Template Deployment on Prod File Server - Replication - PDM HY - Document - PlanExpertFormat | N/A | N/A | N/A | N/A
8 | Take DB Backup from utility and execute the following builds 1. 2024.1.2.024 [DB] |  |  | √ | √
| Close the deployment utility |  |  | √ | √
| Start the deployment utility |  |  | √ | √
| Select the required databases and fill in the all required fields Select check box ; turn off SQL jobs and click on "Turn off SQL jobs" button and note its time |  |  | √
| Click the "backup database" button for Golden backup | √ | √ | √ | √
8.1 | Take DB Backup from utility and execute the following builds 2. Build 13.1.0.0064H [DB]
8.2 | Execute DB Build 28R Customization on HY and WF only |  | N/A | N/A | N/A
8 | Manually Execute the cutomized view under DB Build 13.0.0.0103R | N/A | N/A | N/A | N/A
8.1 | DB Customized Build 13.0.0.0102R | N/A | N/A | N/A | N/A
8.2 | Manually Execute the cutomized view under DB Build 13.0.0.0104U | N/A | N/A | N/A | N/A
10 | Turn Off SQL Notification Jobs | √ | √ | √ | √
10.1 | GOLDEN Backup | √ | √ | √ | √
11 | Update eMAIL and Integration Code=0 | use eSM_WF GO select * into pdd_resources_20250116 from pdd_resources update pdd_resources set mail_flag=0 select distinct mail_flag from pdd_resources select * into pdm_company_20250116 from pdm_company update pdm_company set integration_code=0 select integration_code from pdm_companyy | use Nex_TA GO select * into pdd_resources_20250116 from pdd_resources update pdd_resources set mail_flag=0 select distinct mail_flag from pdd_resources select * into pdm_company_20250116 from pdm_company update pdm_company set integration_code=0 select integration_code from pdm_company | use Nex_MGB Go select * into pdd_resources_20250116 from pdd_resources update pdd_resources set mail_flag=0 select distinct mail_flag from pdd_resources select * into pdm_company_20250116 from pdm_company update pdm_company set integration_code=0 select integration_code from pdm_company | use Nex_WPool Go select * into pdd_resources_20250116 from pdd_resources update pdd_resources set mail_flag=0 select distinct mail_flag from pdd_resources select * into pdm_company_20250116 from pdm_company update pdm_company set integration_code=0 select integration_code from pdm_company
12 | Rename D365 folder as __D365_ before Process Testing on Production SQL server | N/A | N/A | Rename D365 folder as __D365_ before Process Testing on Production SQL server | Rename D365 folder as __D365_ before Process Testing on Production SQL server
13 | Process Testing | √ | √ | √ | √
14 | Restore Golden Back up | √ | √ | √ | √
| Turn no SQL notification Jobs | √ | √ | √ | √
16 | Rename __D365_ folder back to its original name after Restore Golden backup on Production SQL server | N/A | N/A | Rename __D365_ folder back to its original name after Restore Golden backup on Production SQL server | Rename __D365_ folder back to its original name after Restore Golden backup on Production SQL server
18 | Post Deployment Script (if Any) | N/A | N/A | N/A | N/A
19 | Notification Jobs Execution [Only those that were schedule between the time to turn off and turn on] | N/A | N/A | √ | N/A
20 | Remove Maintenance Page | √ | √