## Summary
Development Activity Breakup (By Month)
HiQu Systems
Forecasted Annual Reported (September 2024 - August 2025)

## SummaryData (hidden)
Monthly Timesheet breakup
Month | Mgmt | Training | Meetings | Deployments | Document | Client Items | Post Dep Fixes | TestCases | Code Review | Analysis | Design | Development | Testing | Bug Fix | Total
2024-09-30 | 1 |  | 183.2 | 12.5 | 38.5 | 133 | 0 | 83 | 2 | 113.5 | 10 | 334.5 | 512.5 | 217 | 1640.7
2024-10-31 | 10.7 | 40 | 157 | 50 | 31 | 391.5 | 0 | 42 | 22 | 114.5 | 67 | 386 | 454.5 | 205 | 1971.2
2024-11-30 | 51.5 | 41 | 163.4 | 35.8 | 35.5 | 432 | 12 | 12 | 2 | 162 | 0 | 334.5 | 512.5 | 217 | 2011.2
Total | 63.2 | 81 | 503.6 | 98.3 | 105 | 956.5 | 12 | 137 | 26 | 390 | 77 | 1055 | 1479.5 | 639 | 5623.1
Month | Mgmt | Training | Meetings | Deployments | Document | Client Items | Post Dep Fixes | TestCases | Code Review | Analysis | Design | Development | Testing | Bug Fix | Total
2024-09-30 | 1 |  | 183.2 | 12.5 | 38.5 | 133 | 0 | 83 | 2 | 113.5 | 10 | 334.5 | 512.5 | 217 | 1640.7
2024-10-31 | 10.7 | 40 | 157 | 50 | 31 | 391.5 | 0 | 42 | 22 | 114.5 | 67 | 386 | 454.5 | 205 | 1971.2
2024-11-30 | 51.5 | 41 | 163.4 | 35.8 | 35.5 | 432 | 12 | 12 | 2 | 162 | 0 | 334.5 | 512.5 | 217 | 2011.2
2024-12-31 | 73.5066 | 42.0323 | 148.927 | 54.5715 | 32.3859 | 614.7669 | 16.6278 | 0 | 7.2191 | 180.965 | 0 | 347.9393 | 497.3645 | 213.8685 | 2230.1745
2025-01-31 | 98.5242 | 43.0442 | 138.7427 | 66.668 | 30.7836 | 766.2617 | 22.5339 | 0 | 7.5545 | 204.8523 | 0 | 348.8027 | 496.3921 | 213.6673 | 2437.8272
2025-02-28 | 121.7299 | 43.9618 | 129.3742 | 77.7729 | 29.3216 | 894.8854 | 28.0204 | 0 | 7.7956 | 227.0388 | 0 | 349.4235 | 495.6929 | 213.5227 | 2618.5396
2025-03-31 | 158.393 | 45.0783 | 126.5761 | 77.6186 | 30.7224 | 1042.6215 | 37.9238 | 0 | 0 | 266.5482 | 0 | 322.8037 | 525.6726 | 219.7254 | 2853.6835
2025-04-30 | 179.7508 | 46.0177 | 115.2615 | 91.8088 | 28.5446 | 1187.2428 | 42.6963 | 0 | 1.649 | 285.9684 | 0 | 329.5654 | 518.0574 | 218.1498 | 3044.7125
2025-05-31 | 214.1441 | 47.084 | 109.6176 | 96.3552 | 28.7986 | 1335.2911 | 52.0143 | 0 | 0 | 323.1318 | 0 | 313.3853 | 536.2797 | 221.9199 | 3278.0215
2025-06-30 | 236.2798 | 48.037 | 99.6861 | 108.2937 | 27.1607 | 1472.2595 | 56.9735 | 0 | 0 | 343.3056 | 0 | 315.3261 | 534.0939 | 221.4677 | 3462.8835
2025-07-31 | 270.8752 | 49.1165 | 95.5305 | 110.5085 | 27.9474 | 1623.9616 | 66.2991 | 0 | 0 | 380.5173 | 0 | 294.6656 | 557.3621 | 226.2818 | 3703.0656
2025-08-31 | 295.2342 | 50.0687 | 85.3463 | 122.6626 | 26.3145 | 1765.507 | 72.0124 | 0 | 0 | 403.6412 | 0 | 295.976 | 555.8862 | 225.9765 | 3898.6256
Total | 1711.6377 | 495.4404 | 1552.6621 | 904.5599 | 366.9792 | 11659.2974 | 407.1015 | 137 | 50.2182 | 3005.9686 | 77 | 3972.8876 | 6196.3013 | 2613.5796 | 33150.6335
Month | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 |  | Total
Mgmt | 1 | 10.7 | 51.5 | 73.5066 | 98.5242 | 121.7299 | 158.393 | 179.7508 | 214.1441 | 236.2798 | 270.8752 | 295.2342 |  | 1711.6377
Training |  | 40 | 41 | 42.0323 | 43.0442 | 43.9618 | 45.0783 | 46.0177 | 47.084 | 48.037 | 49.1165 | 50.0687 |  | 495.4404
Meetings | 183.2 | 157 | 163.4 | 148.927 | 138.7427 | 129.3742 | 126.5761 | 115.2615 | 109.6176 | 99.6861 | 95.5305 | 85.3463 |  | 1552.6621
Deployments | 12.5 | 50 | 35.8 | 54.5715 | 66.668 | 77.7729 | 77.6186 | 91.8088 | 96.3552 | 108.2937 | 110.5085 | 122.6626 |  | 904.5599
Document | 38.5 | 31 | 35.5 | 32.3859 | 30.7836 | 29.3216 | 30.7224 | 28.5446 | 28.7986 | 27.1607 | 27.9474 | 26.3145 |  | 366.9792
Client Items | 133 | 391.5 | 432 | 350 | 370 | 429.5735 | 325 | 400 | 350 | 410 | 390 | 400 |  | 4381.0735
Post Dep Fixes | 0 | 0 | 12 | 16.6278 | 22.5339 | 28.0204 | 37.9238 | 42.6963 | 52.0143 | 56.9735 | 66.2991 | 72.0124 |  | 407.1015
TestCases | 83 | 42 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 137
Code Review | 2 | 22 | 2 | 7.2191 | 7.5545 | 7.7956 | 0 | 1.649 | 0 | 0 | 0 | 0 |  | 50.2182
Analysis | 113.5 | 114.5 | 162 | 180.965 | 204.8523 | 227.0388 | 266.5482 | 285.9684 | 323.1318 | 343.3056 | 380.5173 | 403.6412 |  | 3005.9686
Design | 10 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 77
Development | 334.5 | 386 | 334.5 | 347.9393 | 348.8027 | 349.4235 | 322.8037 | 329.5654 | 313.3853 | 315.3261 | 294.6656 | 295.976 |  | 3972.8876
Testing | 512.5 | 454.5 | 512.5 | 497.3645 | 496.3921 | 495.6929 | 525.6726 | 518.0574 | 536.2797 | 534.0939 | 557.3621 | 555.8862 |  | 6196.3013
Bug Fix | 217 | 205 | 217 | 213.8685 | 213.6673 | 213.5227 | 219.7254 | 218.1498 | 221.9199 | 221.4677 | 226.2818 | 225.9765 |  | 2613.5796
Total | 1640.7 | 1971.2 | 2011.2 | 1965.4076 | 2041.5655 | 2153.2277 | 2136.0619 | 2257.4697 | 2292.7304 | 2400.6241 | 2469.104 | 2533.1186 |  | 25872.4096
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In House Meetings, Project meetings Offshore Meetings
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From November onwards, it also includes tasks directly sent by US Team
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Post Deployment fixes are tracked from November 2024
Note on E26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In House Meetings, Project meetings Offshore Meetings
Note on H26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From November onwards, it also includes tasks directly sent by US Team
Note on I26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Post Deployment fixes are tracked from November 2024
Note on B46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In House Meetings, Project meetings Offshore Meetings
Note on B49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From November onwards, it also includes tasks directly sent by US Team
Note on B50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Post Deployment fixes are tracked from November 2024

## Consolidated
Project Profile
Period: September 2024 - June 2025
Project / | Task | Planned |  |  | Project Overhead | [10 empty] | Development |  |  | Testing |  |  | Bug Fixing |  |  | Total | Total
Release |  | Development | QA | Bug Fixing | Mgmt | Training | Meetings | Deployments | Document | Client Items | Post Dep Fixes | TestCases | Code Review | Analysis | Design | Estimate | Actual | Difference | Planned | Actual | Difference | Planned | Actual | Difference | Planned | Hours
AP WORKFLOW | [18 empty] | 0 |  |  | 0 |  | 0 |  | 0
AP WORKFLOW | Meetings, mails, communication, TFS, Interviews |  |  |  | 18 | [13 empty] | 0 |  |  | 0 |  | 0 | 0 | 18
AP WORKFLOW | Analysis of the new project/assignment/task | [12 empty] | 5 |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 | 5
AP WORKFLOW | Regular bug fixing activity | [17 empty] | 0 | 23 |  | 0 | 10 | 0 | 0 | 33
AP WORKFLOW | Cient UAT Upgrade | [6 empty] | 12 | [10 empty] | 0 |  |  | 0 | 22 | 0 | 0 | 34
AP WORKFLOW | Client Items | [17 empty] | 0 |  |  | 0 |  | 0 | 0 | 0
AP WORKFLOW | In-house Training | [12 empty] | 1 |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 | 1
AP WORKFLOW | Internal Meetings | [5 empty] | 7 | [14 empty] | 0 |  | 0 |  | 7
AP WORKFLOW | National Gazetted Holidays | [20 empty] | 0 |  | 0 |  | 0
AP WORKFLOW | Analysis of production issues reported by support team | [17 empty] | 0 | 13 |  | 0 | 5 | 0 |  | 18
AP WORKFLOW | Regular testing and QA new project/assignment/task | [12 empty] | 8 | [8 empty] | 5 | 0 |  | 13
AP WORKFLOW | QA Environment Upgrade | [6 empty] | 7 | [15 empty] | 0 |  | 7
AP WORKFLOW | Release Environment Upgrade | [6 empty] | 6 | [15 empty] | 0 |  | 6
AP WORKFLOW | Document review/understanding Requirement Specifications | [7 empty] | 3 | [14 empty] | 0 |  | 3
APWORKS PHASE2 | [18 empty] | 0 |  |  | 0 |  | 0 | 0 | 0
APWORKS PHASE2 | Meetings, mails, communication, TFS, Interviews |  |  |  | 31 |  |  |  | 1 | [9 empty] | 0 |  |  | 0 |  | 0 |  | 32
APWORKS PHASE2 | Analysis of the new project/assignment/task | [15 empty] | 6 |  | 0 |  |  | 0 |  | 0 | 0 | 6
APWORKS PHASE2 | Regular bug fixing activity | [17 empty] | 0 | 8 |  | 0 | 258.5 | 0 | 0 | 266.5
APWORKS PHASE2 | Cient UAT Upgrade | [6 empty] | 10.5 |  | 11 | [8 empty] | 0 | 13 |  | 0 |  | 0 |  | 34.5
APWORKS PHASE2 | Client Items |  |  |  | 1 | [16 empty] | 0 | 4 | 0 |  | 5
APWORKS PHASE2 | Dev Support | [17 empty] | 0 |  |  | 0 |  | 0 | 0 | 0
APWORKS PHASE2 | Development of new project/assignment/task | [15 empty] | 15 |  | 0 |  |  | 0 |  | 0 |  | 15
APWORKS PHASE2 | Internal Meetings | [5 empty] | 34 | [11 empty] | 0 | 30 |  | 0 |  | 0 |  | 64
APWORKS PHASE2 | Analysis of production issues reported by support team | [8 empty] | 15 |  |  |  | 11 |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 | 26
APWORKS PHASE2 | Regular testing and QA new project/assignment/task | [17 empty] | 0 | 284.5 |  | 0 |  | 0 | 0 | 284.5
APWORKS PHASE2 | QA Environment Upgrade | [17 empty] | 0 | 29 |  | 0 |  | 0 | 0 | 29
APWORKS PHASE2 | Document review/understanding Requirement Specifications | [18 empty] | 11 |  |  |  | 0 |  | 11
APWORKS PHASE2 | Requirement Specifications document writing | [7 empty] | 18.5 | [14 empty] | 0 |  | 18.5
APWORKS PHASE2 | Support Items | [5 empty] | 1 | [16 empty] | 0 |  | 1
APWORKS PHASE2 | Time Off - Planned | [22 empty] | 0 |  | 0
APWORKS 2024.2 - PHASE 3 | [18 empty] | 0 |  |  | 0 |  | 0 |  | 0
APWORKS 2024.2 - PHASE 3 | Add Media Type/Service type/Roles | 4 | 8 |  |  |  | 4 |  |  |  |  | 11 |  | 2 |  | 4 |  |  | 8 | 76 | -68 | 0 |  | 0 | 12 | 93
APWORKS 2024.2 - PHASE 3 | Google Drive integration. (Setup and Integration development) | 44 | 8 |  |  |  | 5 |  | 15 |  |  | 42 | 4 |  |  | 44 | 91 | -47 | 8 | 97 | -89 | 0 | 23 | 0 | 52 | 277
APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents (tear sheets, afidavit) to the invoice | 30 | 20 |  |  |  | 11 |  |  |  |  | 44 |  | 1.5 |  | 30 | 35 | -5 | 20 | 59 | -39 | 0 | 20 | 0 | 50 | 170.5
APWORKS 2024.2 - PHASE 3 | We need to read the company on the invoice document to route to the right company. If the company is not detected properly we will default to a company and mark it with a status. | 56 | 20 | [12 empty] | 56 |  |  | 20 |  |  | 0 |  | 0 | 76 | 0
APWORKS 2024.2 - PHASE 3 | Broadcast Invoices | [14 empty] | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0
APWORKS 2024.2 - PHASE 3 | We will need a separate node for "Broadcast Invoices" added at the end of Production Invoices. | 4 | [13 empty] | 4 | 8 | -4 | 0 |  |  | 0 |  | 0 | 4 | 8
APWORKS 2024.2 - PHASE 3 | User Group management changes | 12 | [13 empty] | 12 | 4 | 8 | 0 |  |  | 0 |  | 0 | 12 | 4
APWORKS 2024.2 - PHASE 3 | Dashboard | 16 | [13 empty] | 16 |  |  | 0 |  |  | 0 |  | 0 | 16 | 0
APWORKS 2024.2 - PHASE 3 | Manage Invoice Documents | 4 | [11 empty] | 2 |  | 4 | 2 | 2 | 0 |  |  | 0 |  | 0 | 4 | 4
APWORKS 2024.2 - PHASE 3 | Invoice List UI | 32 | [13 empty] | 32 |  |  | 0 |  |  | 0 |  | 0 | 32 | 0
APWORKS 2024.2 - PHASE 3 | EDI file processing | 62 | 40 | [8 empty] | 6 | 13 | 2 |  | 62 | 37.5 | 24.5 | 40 | 85.5 | -45.5 | 0 | 5.5 | 0 | 102 | 149.5
APWORKS 2024.2 - PHASE 3 | PDF file generation | 50 | 6 | [10 empty] | 5 |  | 50 | 28 | 22 | 6 | 10.5 | -4.5 | 0 |  | 0 | 56 | 43.5
APWORKS 2024.2 - PHASE 3 | Invoice View UI | 30 | 12 | [9 empty] | 2 |  |  | 30 | 18 | 12 | 12 |  |  | 0 | 3 | 0 | 42 | 23
APWORKS 2024.2 - PHASE 3 | Customer Information : Selection of the client on the vendor invoice header level. This will help route the invoice to the appropriate client team. - (Sync and a lookup field on invoice) | 16 | 4 | [10 empty] | 4.5 | 6 | 16 | 29 | -13 | 4 | 10 | -6 | 0 | 8 | 0 | 20 | 57.5
APWORKS 2024.2 - PHASE 3 | We will need to introduce tolerance by media type. | 20 | [13 empty] | 20 |  |  | 0 |  |  | 0 |  | 0 | 20 | 0
APWORKS 2024.2 - PHASE 3 | Read data from Media Ocean Jobs, IOs (buying), Customer Master, Vendor Master, Currencies, Tax codes, Payment terms, EDI?, payment information | 80 | 40 | [12 empty] | 80 |  |  | 40 |  |  | 0 |  | 0 | 120 | 0
APWORKS 2024.2 - PHASE 3 | vendor/stations/sites can be associated to multiple pay to. EX: Bell Media is linked to Bill pay to | 32 | [13 empty] | 32 |  |  | 0 |  |  | 0 |  | 0 | 32 | 0
APWORKS 2024.2 - PHASE 3 | Checkbox to filter discrepant lines | 8 | [13 empty] | 8 |  |  | 0 | 2 |  | 0 |  | 0 | 8 | 2
APWORKS 2024.2 - PHASE 3 | Ability to assign Employees to Roles by Media type and by Client | 70 | 8 |  |  |  | 16 |  |  |  |  | 22 | 3 | 3 |  | 70 | 192 | -122 | 8 | 64 | -56 | 0 | 27 | 0 | 78 | 327
APWORKS 2024.2 - PHASE 3 | Ability to automatically attach additional documents to Invoice | 30 | [13 empty] | 30 |  |  | 0 |  |  | 0 |  | 0 | 30 | 0
APWORKS 2024.2 - PHASE 3 | Associate vendor/stations/sites to multiple pay to | 32 | [10 empty] | 2 | 1 | 3 | 32 | 39.5 | -7.5 | 0 | 13 |  | 0 |  | 0 | 32 | 58.5
APWORKS 2024.2 - PHASE 3 | Enhancement in vendor mapping(Parse Table) | [14 empty] | 0 | 19 |  | 0 | 4 |  | 0 |  | 0 |  | 23
APWORKS 2024.2 - PHASE 3 | Master Data: Payment Terms | [14 empty] | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 0
APWORKS 2024.2 - PHASE 3 | Switch Company on Invoice | [7 empty] | 1 |  |  |  |  | 4 | 13 | 0 | 31 |  | 0 | 10 |  | 0 | 32 | 0 | 0 | 91
APWORKS 2024.2 - PHASE 3 | Route invoice from one company to another | 56 | [11 empty] | 2 |  | 56 | 14 | 42 | 0 | 5.5 |  | 0 | 9 | 0 | 56 | 30.5
APWORKS 2024.2 - PHASE 3 | Vendor/stations/sites associated to multiple pay to. | 32 | [13 empty] | 32 | 8 | 24 | 33 |  |  | 0 | 5 | 0 | 65 | 13
APWORKS 2024.2 - PHASE 3 | Apply discount based on Payment Terms Setting | [14 empty] | 0 |  |  |  | 14.5 |  | 0 | 12 | 0 |  | 26.5
APWORKS 2024.2 - PHASE 3 | Project Overhead |  |  |  | 26 |  | 60.5 | 47.5 | 2.5 |  | 5 |  |  | 13.5 |  | 0 |  |  | 0 |  |  | 0 |  | 0 | 0 | 155
APWORKS 2024.2 - PHASE 3 | Forward Inv to user OR select user when invoice is Pending Apr | [14 empty] | 0 |  |  |  | 1 |  |  |  | 0 |  | 1
APWORKS 2024.2 - PHASE 3 | Remove Site column from vendor lookup | 1 | [13 empty] | 1 | 3 | -2 |  | 2 |  |  | 3 | 0 |  | 8
APWORKS 2024.2 - PHASE 3 | Invoice Editing: Make the tax editable | [5 empty] | 1 | [6 empty] | 2 |  | 0 | 10 |  |  | 10 |  |  |  | 0 |  | 23
APWORKS 2024.2 - PHASE 3 | Vendor Map: Vendor Popup: Remove identifier currency filter | [12 empty] | 6 |  | 0 | 5 |  |  | 2 |  |  | 2 | 0 |  | 15
APWORKS 2024.2 - PHASE 3 | Google Drive - Split Process and show documents in queue | [14 empty] | 0 | 31 |  |  | 7 |  |  | 6 | 0 |  | 44
APWORKS 2024.2 - PHASE 4 | [15 empty] | 0 | [7 empty] | 0
APWORKS 2024.2 - PHASE 4 | Project Overhead |  |  |  | 7 |  | 8 | 13 |  |  | 22 |  |  | 1 |  | 0 |  |  | 0 |  |  |  |  | 0 |  | 51
APWORKS 2024.2 - PHASE 4 | Discount implementation CHANGES | 12 | [13 empty] | 12 |  |  | 0 |  |  |  |  | 0 |  | 0
APWORKS 2024.2 - PHASE 4 | Approval routing | [12 empty] | 7 |  | 0 | 35 |  | 0 | 3.5 |  |  |  | 0 |  | 45.5
APWORKS 2024.2 - PHASE 4 | A report to spot check the invoices processed | 30 | 8 | [12 empty] | 30 | 2 | 28 | 8 |  |  |  |  | 0 |  | 2
APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Invoice Scan | 40 | 30 | [12 empty] | 40 | 1 | 39 | 30 |  |  |  |  | 0 |  | 1
APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Model updates list | 10 | [16 empty] | 0 |  |  |  |  | 0 |  | 0
APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Manage non-mapped list | 10 | [16 empty] | 0 |  |  |  |  | 0 |  | 0
APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Import / Export lines | 0 | [16 empty] | 0 |  |  |  |  | 0 |  | 0
APWORKS 2024.2 - PHASE 4 | PDF based broadcast invoices - Approvals | 0 | [16 empty] | 0 |  |  |  |  | 0 |  | 0
APWORKS 2024.2 - PHASE 4 | Google Drive Setup (company configuration UI) | 40 | 16 | [12 empty] | 40 |  |  | 16 | 5 | 11 |  |  | 0 |  | 5
APWORKS 2024.2 - PHASE 4 | Production: Project should be available on summary as well. | 6 | 4 | [12 empty] | 6 | 11.5 | -5.5 | 4 |  |  |  |  | 0 |  | 11.5
APWORKS 2024.2 - PHASE 4 | Approve upto last level and auto post. | 8 | [11 empty] | 4 |  | 8 | 8 | 0 | 0 | 10 |  |  |  | 0 |  | 22
APWORKS 2024.2 - PHASE 4 | Currency Changes on Vendor Map | 16 | [11 empty] | 2 |  | 16 |  |  | 0 |  |  |  |  | 0 |  | 2
APWORKS 2024.2 - PHASE 4 | Stamp multiple approvers. | 12 | [13 empty] | 12 | 8 | 4 | 0 | 2 |  |  | 1 | 0 |  | 11
APWORKS 2024.2 - PHASE 4 | EDI file updating and upload | 12 | [11 empty] | 1 |  | 12 | 11 | 1 | 0 |  |  |  |  | 0 |  | 12
APWORKS 2024.2 - PHASE 4 | Integration Testing | [14 empty] | 0 |  |  | 0 | 12 |  |  |  | 0 |  | 12
APWORKS 2024.2 - PHASE 4 | EDI: Generate PDF - Updates | 12 | [13 empty] | 12 | 11.5 | 0.5 | 0 |  |  |  |  | 0 |  | 11.5
APWORKS 2024.2 - PHASE 4 | Production: Auto populate lines based PO during scanning | 8 | 4 | [12 empty] | 8 | 3 | 5 | 4 | 3 | 1 |  |  | 0 |  | 6
APWORKS 2024.2 - PHASE 4 | Production: show keyvalue pairs for level2 mapping | 8 | 4 | [12 empty] | 8 | 8 | 0 | 4 |  |  |  |  | 0 |  | 8
APWORKS 2024.2 - PHASE 4 | Apply variable name for Site in vendor mapping | 12 | [13 empty] | 12 | 8 | 4 | 0 |  |  |  |  | 0 |  | 8
APWORKS 2024.2 - PHASE 4 | Add Vendor column in Insertion order list | 4 | [13 empty] | 4 |  |  | 0 |  |  |  |  | 0 |  | 0
APWORKS 2024.2 - PHASE 4 | Checkbox to show unapproved lines | 0 | [13 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0
APWORKS 2024.2 - PHASE 4 | Vendor mapping enhancement for Non-media | 0 | [13 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0
APWORKS 2024.2 - PHASE 4 | Filter for discrepenet invoices on client base | 4 | [16 empty] | 0 |  |  |  |  | 0 |  | 0
APWORKS 2024.2 - PHASE 4 | Validation notifications | 0 | [16 empty] | 0 |  |  |  |  | 0 |  | 0
APWORKS 2024.2 - PHASE 4 | Re: APWorks - Data search service | 0 | [16 empty] | 0 |  |  |  |  | 0 |  | 0
APWORKS 2024.2 - PHASE 4 | Forward invoice to user OR select a user when invoice is in Pending | 70 | 51.4 | [15 empty] | 51.4 |  |  |  |  | 0 |  | 0
APWORKS 2024.2 - PHASE 4 | [23 empty] | 0 |  | 0
APWORKS - SUPPORT | [23 empty] | 0 |  | 0
APWORKS - SUPPORT | Support Tickets - Just Global | [22 empty] | 0 |  | 0
APWORKS - SUPPORT | Tasks by US Team - Demo | [8 empty] | 12 | [13 empty] | 0 |  | 12
APWORKS - SUPPORT | Tasks by US Team - Just Gobal | [8 empty] | 80 | [13 empty] | 0 |  | 80
APWORKS - SUPPORT | Tasks by US Team - The Shipyard | [8 empty] | 19 | [13 empty] | 0 |  | 19
NEXELUS 2024.1 SP2 | [18 empty] | 0 |  |  | 0 |  | 0 |  | 0
NEXELUS 2024.1 SP2 | Project Overhead |  |  |  | 2 |  | 10.5 | 5.3 | 31 |  | 10 |  |  | 1 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 59.8
NEXELUS 2024.1 SP2 | Client Lines (New Lines, Generate Schedule) | 67 | 40 | 20 |  |  | 6 |  |  |  |  | 3 |  | 58.6 |  |  | 74.1 |  | 40 | 9.75 | 30.25 | 20 |  | 20 |  | 151.45
NEXELUS 2024.1 SP2 | eConnect shell change to service | [5 empty] | 1 | [6 empty] | 24 |  | 0 | 37.2 |  | 0 | 14.3 |  | 0 |  | 0 |  | 76.5
NEXELUS 2024.1 SP2 | Backup Table for vendor/client lines relationship | 38 | 12 | 8 | [11 empty] | 38 | 3 | 35 | 12 | 20 | -8 | 8 |  | 8 |  | 23
NEXELUS 2024.1 SP2 | Generate client lines based on media type | [14 empty] | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0
NEXELUS 2024.1 SP2 | Client Profile | 1 | [13 empty] | 1 |  |  | 0 |  |  | 0 |  | 0 |  | 0
NEXELUS 2024.1 SP2 | Level3 | 1 | [13 empty] | 1 |  |  | 0 |  |  | 0 |  | 0 |  | 0
NEXELUS 2024.1 SP2 | Media Plan Vendor lines (new, import/export) | 34 | 8 | 8 | [11 empty] | 34 |  |  | 8 |  |  | 8 |  | 8 |  | 0
NEXELUS 2024.1 SP2 | Client Lines (new line, generate schedule) | 67 | 40 | 20 | [11 empty] | 67 |  |  | 40 |  |  | 20 |  | 20 |  | 0
NEXELUS 2024.1 SP2 | Media Plan approval | 8 | 4 | 2 | [11 empty] | 8 |  |  | 4 | 5 | -1 | 2 |  | 2 |  | 5
NEXELUS 2024.1 SP2 | Media Plan: Import/Export Flighting | [14 empty] | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0
NEXELUS 2024.1 SP2 | Client Profile: Media > Flag to make the vendor inactive | 24 | 8 | 2 | [9 empty] | 3.6 |  | 24 | 9.5 | 14.5 | 8 |  |  | 2 |  | 2 |  | 13.1
NEXELUS 2024.1 SP2 | Custom field 3/AdServing able to take formulas (on hold) | [14 empty] | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0
NEXELUS 2024.1 SP2 | Mngt Fee renamable everywhere | 4 | 4 | 1 | [11 empty] | 4 |  |  | 4 |  |  | 1 |  | 1 |  | 0
NEXELUS 2024.1 SP2 | Separate broadcast label rename | [14 empty] | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0
NEXELUS 2024.1 SP2 | CHECK: tiered rate on new lines only or all lines? What happens if spend is added to a billed month. | [14 empty] | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0
NEXELUS 2024.1 SP2 | Billing by Media Type | [5 empty] | 1.75 |  |  |  |  | 3 | 2 | 2.3 |  | 0 | 48.8 |  | 0 | 5.75 |  |  |  | 0 |  | 63.6
NEXELUS 2024.1 SP2 | UDF & Naming Convention in Vendor Portal - Proposal Import/exp | 76 |  | 24 | [11 empty] | 76 | 65 | 11 | 0 | 43 |  |  | 43 | 0 |  | 151
NEXELUS 2024.1 SP2 | UDF & Naming Convention in Nexelus - Export on Proposal | 24 | 8 | 4 | [11 empty] | 24 | 24 | 0 | 8 |  |  |  |  | 0 |  | 24
NEXELUS 2024.1 SP2 | UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | 68 | 24 | 16 |  |  | 4.5 |  |  |  |  | 6 |  |  |  | 68 | 13 | 55 | 24 | 3.5 | 20.5 |  |  | 0 |  | 27
NEXELUS 2024.1 SP2 | [15 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0
NEXELUS 2024.2 | [15 empty] | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0
NEXELUS 2024.2 | Meetings, mails, communication, TFS, Interviews | [5 empty] | 5 | [8 empty] | 0 |  |  | 0 | 24 |  | 0 |  | 0 |  | 29
NEXELUS 2024.2 | Analysis of the new project/assignment/task | [7 empty] | 13 |  |  |  |  | 28 |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 41
NEXELUS 2024.2 | Regular bug fixing activity | [14 empty] | 0 | 44 |  | 0 | 6 |  | 0 | 7 | 0 |  | 57
NEXELUS 2024.2 | Cient UAT Upgrade | [14 empty] | 0 |  |  | 0 | 4 |  | 0 |  | 0 |  | 4
NEXELUS 2024.2 | Client Items | [5 empty] | 1 |  |  | 132 | [5 empty] | 0 | 2 |  | 0 |  |  | 0 |  | 0 |  | 135
NEXELUS 2024.2 | Development of new project/assignment/task | [14 empty] | 0 | 3 |  | 0 |  |  | 0 |  | 0 |  | 3
NEXELUS 2024.2 | In-house Training | [5 empty] | 4 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 4
NEXELUS 2024.2 | Internal Meetings | [5 empty] | 1 | [11 empty] | 0 |  |  | 0 |  | 0 |  | 1
NEXELUS 2024.2 | Analysis of production issues reported by support team | [8 empty] | 15 |  |  |  | 25 |  |  |  |  | 0 | 13 |  | 0 |  | 0 |  | 53
NEXELUS 2024.2 | Production upgrades | [15 empty] | 5 |  | 0 |  |  | 0 |  | 0 |  | 5
NEXELUS 2024.2 | Regular testing and QA new project/assignment/task | [7 empty] | 6 | [9 empty] | 0 | 1 |  | 0 |  | 0 |  | 7
NEXELUS 2024.2 | Document review/understanding Requirement Specifications | [7 empty] | 27 |  |  |  |  | 2 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 29
NEXELUS 2024.2 | Requirement Specifications document writing | [7 empty] | 9 | [9 empty] | 0 |  |  | 0 |  | 0 |  | 9
NEXELUS 2024.2 | Support Items | [8 empty] | 354 |  |  |  | 5 |  |  |  |  | 0 | 7 |  | 0 |  | 0 |  | 366
NEXELUS 2024.2 | [18 empty] | 0 |  |  |  |  | 0 |  | 0
NEXELUS SUPPORT | [18 empty] | 0 |  |  |  |  | 0 |  | 0
NEXELUS SUPPORT | Support Tickets - Demo | [8 empty] | 80 | [8 empty] | 0 |  |  |  |  | 0 |  | 80
NEXELUS SUPPORT | Support Tickets - Just Global | [8 empty] | 1 | [8 empty] | 0 |  |  |  |  | 0 |  | 1
NEXELUS SUPPORT | Tasks by US Team - Just Gobal | [8 empty] | 4.5 | [8 empty] | 0 |  |  |  |  | 0 |  | 4.5
PR-0013 | [18 empty] | 0 |  |  | 0 |  | 0 |  | 0
PR-0013 | Meetings, mails, communication, TFS, Interviews |  |  |  | 12.5 |  | 116.5 |  |  |  | 8.25 |  |  | 94.5 |  |  |  |  | 0 |  |  | 0 |  | 0 |  | 231.75
PR-0013 | Cient UAT Upgrade | [8 empty] | 3.5 |  |  |  | 9 |  |  |  |  | 0 | 57 |  | 0 |  | 0 |  | 69.5
PR-0013 | Client Items | [8 empty] | 4 | [8 empty] | 0 |  |  | 0 |  | 0 |  | 4
PR-0013 | Development of new project/assignment/task | [15 empty] | 28 |  | 0 | 68 |  | 0 | 51 | 0 |  | 147
PR-0013 | In-house Training |  |  |  |  | 78 | [12 empty] | 0 |  |  | 0 |  | 0 |  | 78
PR-0013 | Internal Meetings | [5 empty] | 126.65 |  | 4 | [7 empty] | 14 |  | 0 |  |  | 0 |  | 0 |  | 144.65
PR-0013 | Analysis of production issues reported by support team | [9 empty] | 8 |  |  | 89 |  |  |  |  | 0 | 27.5 |  | 0 |  | 0 |  | 124.5
PR-0013 | Production upgrades | [6 empty] | 3 | [8 empty] | 10 |  | 0 |  |  |  |  | 0 |  | 13
PR-0013 | QA Environment Upgrade | [17 empty] | 0 | 4 |  |  |  | 0 |  | 4
PR-0013 | Requirement Specifications document writing | [8 empty] | 20.5 |  |  |  | 14 |  |  |  |  | 0 |  |  |  |  | 0 |  | 34.5
PR-0013 | Session with US team |  |  |  | 2.7 |  | 8.2 |  |  | 60.5 |  |  |  | 3 |  |  |  |  | 0 |  |  |  |  | 0 |  | 74.4
PR-0013 | [18 empty] | 0 |  |  |  |  | 0 |  | 0
PR-0013 | [18 empty] | 0 |  |  |  |  | 0 |  | 0
Client Items | [18 empty] | 0 |  |  | 0 |  | 0 |  | 0
Client Items | CI-DentsuCreativ | [8 empty] | 39 | [8 empty] | 0 |  |  | 0 |  | 0 |  | 39
Client Items | CI-HY | [8 empty] | 11 | [8 empty] | 0 |  |  | 0 |  | 0 |  | 11
Client Items | CI-JustGlobal | [8 empty] | 52 | [8 empty] | 0 |  |  | 0 |  | 0 |  | 52
Client Items | CI-PlusCo | [8 empty] | 5 | [8 empty] | 0 |  |  | 0 |  | 0 |  | 5
Client Items | CI-PropelHealth | [8 empty] | 17 | [8 empty] | 0 |  |  | 0 |  | 0 |  | 17
Client Items | CI-TheShipyard | [8 empty] | 129 | [8 empty] | 0 |  |  |  |  | 0 |  | 129
[19 empty] | 0 |  |  |  |  | 0 |  | 0
[19 empty] | 0 |  |  | 0 |  | 0 |  | 0
[19 empty] | 0 |  |  | 0 |  | 0 |  | 0
[19 empty] | 0 |  |  | 0 |  | 0 |  | 0
Overall Performance |  | 1447 | 431.4 | 105 | 50.2 | 78 | 391.6 | 68.8 | 108.5 | 1039 | 53.25 | 137 | 26 | 422.5 | 22 | 1286 | 1092.6 | 125.5 | 464.4 | 821.3 | -254.25 | 61 | 257.5 | 61 | 919 | 4568.25
Score Card of planned Activities (For Activities with both Planned and Actual Data)
[16 empty] | Plan - Actual (Development) |  |  | Plan - Actual (Testing) |  |  | Plan - Actual (Bug Fix) |  |  | Plan - Actual (Total)
[16 empty] | Planned | Actual | Diff | Planned | Actual | Diff | Planned | Actual | Diff | Planned | Actual | Diff
[16 empty] | 821 | 695.5 | 125.5 | 194 | 448.25 | -254.25 | 0 | 0 | 0 | 593 | 1261 | -668
[18 empty] | 15.29% |  |  | -131.1% |  |  | 100% |  |  | -112.6%
Note on U172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is difference for tasks where estimate is provided and Actual Work is performed

## November 2024
Project Profile
Period: November 2024
Project / | Task | Planned |  |  | Project Overhead | [5 empty] | Test | Code | Analysis | Design | Development Time |  |  | Testing |  |  | Bug Fixing Time |  |  | Post Deployment Fixes |  |  | Total | Total
Release |  | Development | QA | Bug Fixing | Mgmt | Training | Meetings | Deployments | Document | Client Items | Cases | Review |  |  | Estimate | Actual | Difference | Planned | Actual | Variance | Planned | Actual | Variance | Planned | Actual | Variance | Planned | Hours
APWORKS 2024.2 - PHASE 3 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| Ability to automatically attach additional documents to Invoice | 30 | 20 | [11 empty] | 30 | 4 |  | 20 | 10 |  | 0 | 12 |  |  |  |  | 50 | 26
| Add Media Type/Service type/Roles | 4 | 8 | [11 empty] | 4 |  |  | 8 | 6 |  | 0 | [5 empty] | 12 | 6
| Ability to assign Employees to Roles by Media type and by Client | 70 | 8 | [11 empty] | 70 |  |  | 8 | 14 |  | 0 | 4 |  |  |  |  | 78 | 18
| Google Drive integration. (Setup and Integration development) | 44 | 8 | [11 empty] | 44 |  |  | 8 |  |  | 0 | 31 |  |  |  |  | 52 | 31
| Project Overhead |  |  |  | 17 |  | 11.5 | 5.5 | 1.5 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 5 |  |  |  |  | 0 | 40.5
| Associate vendor/stations/sites to multiple pay to | 32 | [12 empty] | 32 |  |  | 0 | 4.5 |  | 0 | 3 |  |  |  |  | 32 | 7.5
| Broadcast Invoice | [13 empty] | 0 |  |  | 0 |  |  | 0 | [6 empty] | 0
| EDI File Processing | 62 | 40 | [11 empty] | 62 |  |  | 40 | 33 |  | 0 | 5.5 |  |  |  |  | 102 | 38.5
| Invoice View UI | 30 | 12 | [11 empty] | 30 | 6 |  | 12 |  |  | 0 | 5 |  |  |  |  | 42 | 11
| PDF file generation | 50 | 6 | [11 empty] | 50 |  |  | 6 |  |  | 0 | [5 empty] | 56 | 0
| Manage Invoice Documents | 4 | [12 empty] | 4 |  |  | 0 |  |  | 0 | [5 empty] | 4 | 0
| Checkbox to filter discrepant lines | 8 | [12 empty] | 8 |  |  | 0 |  |  | 0 | [5 empty] | 8 | 0
| Enhancement in vendor mapping(Parse Table) | [13 empty] | 0 | 19 |  | 0 |  |  | 0 | [6 empty] | 19
| Master Data: Payment Terms | [13 empty] | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 | 0
| Switch Company on Invoice | [13 empty] | 0 |  |  | 0 | 20 |  | 0 | 10 |  |  |  |  | 0 | 30
| Vendor Inv: Select Client on Header | [13 empty] | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 | 0
| Customer Information: Select Client on Vendor Invoice | 16.4 | [12 empty] | 16.4 |  |  | 0 | 6 |  | 0 | 3 |  |  |  |  | 16.4 | 9
| Route invoice from one company to another | 56 | [12 empty] | 56 |  |  | 0 | 5.5 |  | 0 | [5 empty] | 56 | 5.5
| Vendor/stations/sites associated to multiple pay to. | 32 | [12 empty] | 32 | 2 |  | 0 | 3 |  | 0 | [5 empty] | 32 | 5
| Apply discount based on Payment terms settings | [17 empty] | 14.5 |  |  | 8 | [5 empty] | 22.5
| Forward Inv to user OR select user when invoice is Pending Apr | [17 empty] | 1 | [8 empty] | 1
| Remove Site column from vendor lookup | [14 empty] | 3 |  |  | 2 |  |  | 3 | [5 empty] | 8
| Invoice Editing: Make the tax editable | [5 empty] | 1 | [5 empty] | 2 |  |  | 10 |  |  | 10 | [8 empty] | 23
| Vendor Map: Vendor Popup: Remove identifier currency filter | [11 empty] | 6 |  |  | 5 |  |  | 2 |  |  | 2 | [5 empty] | 15
| Google Drive - Split Process and show documents in queue | [14 empty] | 31 |  |  | 7 |  |  | 6 | [5 empty] | 44
APWORKS 2024.2 - PHASE 4 | [27 empty] | 0
| Project Overhead |  |  |  | 7 |  | 8 | 13 |  |  |  |  | 1 | [11 empty] | 22 |  |  | 29
| Approval routing | [11 empty] | 7 |  |  | 35 |  |  | 3.5 | [8 empty] | 45.5
| A report to spot check the invoices processed | [14 empty] | 2 | [11 empty] | 2
| PDF based broadcast invoices - Invoice Scan | [14 empty] | 1 | [11 empty] | 1
| Google Drive Setup (company configuration UI) | [17 empty] | 5 | [8 empty] | 5
| Production: Project should be available on summary as well. | [14 empty] | 11.5 | [11 empty] | 11.5
| Approve upto last level and auto post. | [11 empty] | 4 |  |  | 8 |  |  | 10 | [8 empty] | 22
| Currency Changes on Vendor Map | [11 empty] | 2 | [14 empty] | 2
| Stamp multiple approvers. | [14 empty] | 8 |  |  | 2 |  |  | 1 | [5 empty] | 11
| EDI file updating and upload | [11 empty] | 1 |  |  | 11 | [11 empty] | 12
| Integration Testing | [17 empty] | 12 | [8 empty] | 12
| EDI: Generate PDF - Updates | [14 empty] | 11.5 | [11 empty] | 11.5
| Production: Auto populate lines based PO during scanning | [14 empty] | 3 |  |  | 3 | [8 empty] | 6
| Production: show keyvalue pairs for level2 mapping | [14 empty] | 8 | [11 empty] | 8
| Apply variable name for Site in vendor mapping | [14 empty] | 8 | [11 empty] | 8
APWORKS PHASE2 | [14 empty] | 0 |  |  | 0 |  |  | 0 | [6 empty] | 0
| Meetings, mails, communication, TFS, Interviews | [13 empty] | 0 |  |  | 0 |  |  | 0 | [6 empty] | 0
| Regular bug fixing activity | [13 empty] | 0 |  |  | 0 | 56 |  | 0 | 10.5 | [5 empty] | 66.5
| Cient UAT Upgrade | [13 empty] | 0 |  |  | 0 |  |  | 0 | [6 empty] | 0
| Client Items | [13 empty] | 0 |  |  | 0 |  |  | 0 | [6 empty] | 0
| Development of new project/assignment/task | [13 empty] | 0 |  |  | 0 |  |  | 0 | [6 empty] | 0
| Internal Meetings | [13 empty] | 0 |  |  | 0 |  |  | 0 | [6 empty] | 0
| Regular testing and QA new project/assignment/task | [13 empty] | 0 |  |  | 0 |  |  | 0 | [6 empty] | 0
| QA Environment Upgrade | [13 empty] | 0 |  |  | 0 | 16 |  | 0 | [6 empty] | 16
AP WORKFLOW | [14 empty] | 0 |  |  | 0 |  |  | 0 | [5 empty] | 0 | 0
| Meetings, mails, communication, TFS, Interviews |  |  |  | 18 | [22 empty] | 18
| Regular bug fixing activity | [17 empty] | 7 |  | 0 | [5 empty] | 0 | 7
| Internal Meetings | [16 empty] | 0 |  |  | 0 | [5 empty] | 0 | 0
| Analysis of production issues reported by support team | [16 empty] | 0 | 3 |  | 0 | [5 empty] | 0 | 3
| Cient UAT Upgrade | [6 empty] | 12 | [19 empty] | 12
| In-house Training |  |  |  |  | 1 | 6 | [20 empty] | 7
| Regular testing and QA new project/assignment/task | [11 empty] | 8 | [5 empty] | 5 | [8 empty] | 13
| QA Environment Upgrade | [5 empty] | 6 |  | 3 | [18 empty] | 9
| Document review/understanding Requirement Specifications | [26 empty] | 0
NEXELUS 2024.1 SP2 | [17 empty] | 0 |  |  | 0 | [6 empty] | 0
| Project Overhead |  |  |  | 2 |  | 10.5 | 5.3 | 31 |  |  |  | 1 |  |  |  |  | 0 | 10 |  | 0 |  |  |  | 10 |  |  | 59.8
| Client Lines (New Lines, Generate Schedule) | 67 | 40 | 20 | [13 empty] | 40 |  |  | 20 | [6 empty] | 0
| eConnect shell change to service | [16 empty] | 0 |  |  | 0 | [6 empty] | 0
| Backup Table | 38 | 12 | 8 | [13 empty] | 12 |  |  | 8 | [6 empty] | 0
| Client Profile: Media > Flag to make the vendor inactive | [26 empty] | 0
| Generate Client Schedule Lines based on media type | [5 empty] | 3.5 |  |  |  | 3 |  | 23.6 |  |  | 46.1 |  |  | 9.75 | [8 empty] | 85.95
| Media Plan Approval | [17 empty] | 5 | [8 empty] | 5
| eConnect shell change to service | [5 empty] | 1 | [5 empty] | 8 |  |  | 21.2 |  |  | 14.3 | [8 empty] | 44.5
| Backup Table for vendor/client lines relationship | [17 empty] | 20 | [8 empty] | 20
| Billing by Media Type | [5 empty] | 1.75 |  |  |  | 3 | 2 | 2.3 |  |  | 48.8 |  |  | 5.75 | [8 empty] | 63.6
| UDF & Naming Convention in Vendor Portal - Proposal Import/exp | [14 empty] | 8 | [5 empty] | 43 | [5 empty] | 51
| UDF & Naming Convention in Nexelus - Export on Proposal | [14 empty] | 24 | [11 empty] | 24
| UDF & Naming Convention in RFP - Nexelus RFP(Exp and Imp) | [5 empty] | 4.5 |  |  |  | 6 |  |  |  |  | 13 |  |  | 3.5 | [8 empty] | 27
NEXELUS 2024.2 | [17 empty] | 0 |  |  | 0 | [6 empty] | 0
| Meetings, mails, communication, TFS, Interviews | [5 empty] | 2 | [20 empty] | 2
| Analysis of the new project/assignment/task | [16 empty] | 0 |  |  | 0 | [6 empty] | 0
| Regular bug fixing activity | [16 empty] | 0 | 6 |  | 0 | [6 empty] | 6
| Client Items | [16 empty] | 0 |  |  | 0 | [6 empty] | 0
| Cient UAT Upgrade | [26 empty] | 0
| In-house Training | [5 empty] | 3 | [10 empty] | 0 |  |  | 0 | [6 empty] | 3
| Analysis of production issues reported by support team | [16 empty] | 0 |  |  | 0 | [6 empty] | 0
| Regular testing and QA new project/assignment/task | [16 empty] | 0 |  |  | 0 | [6 empty] | 0
| Document review/understanding Requirement Specifications | [16 empty] | 0 | 15 |  | 0 | [6 empty] | 15
| Support Items | [8 empty] | 61 | [7 empty] | 0 |  |  | 0 | [6 empty] | 61
PR-0013 | [17 empty] | 0 |  |  | 0 | [6 empty] | 0
| Meetings, mails, communication, TFS, Interviews |  |  |  | 7.5 | 2 | 2.5 | [5 empty] | 64 | [11 empty] | 6.25 |  |  | 76
| Cient UAT Upgrade | [11 empty] | 2 |  |  |  |  | 0 | 42 |  | 0 | [6 empty] | 44
| Client Items | [8 empty] | 4 | [7 empty] | 0 |  |  | 0 | [6 empty] | 4
| Development of new project/assignment/task | [8 empty] | 5 | [7 empty] | 0 |  |  | 0 | 6 | [5 empty] | 11
| In-house Training |  |  |  |  | 38 | [11 empty] | 0 |  |  | 0 | [6 empty] | 38
| Internal Meetings | [5 empty] | 66.65 | [20 empty] | 66.65
| Analysis of production issues reported by support team | [11 empty] | 10 |  |  |  |  | 0 | 5.5 |  | 0 |  |  |  | 8 |  |  | 15.5
| QA Environment Upgrade | [16 empty] | 0 | 4 |  | 0 | [6 empty] | 4
| Session with US team | [5 empty] | 35.5 |  |  | 15.5 | [17 empty] | 51
| Time Off - Planned | [26 empty] | 0
| Time Off - Un Planned | [11 empty] | 20.5 | [14 empty] | 20.5
Client Items | [17 empty] | 0 |  |  | 0 | [6 empty] | 0
| CI-DentsuCreativ | [8 empty] | 10 | [7 empty] | 0 |  |  | 0 | [6 empty] | 10
| CI-HY | [16 empty] | 0 |  |  | 0 | [6 empty] | 0
| CI-JustGlobal | [8 empty] | 36 | [7 empty] | 0 |  |  | 0 | [6 empty] | 36
| CI-PropelHealth | [8 empty] | 6 | [7 empty] | 0 |  |  | 0 | [6 empty] | 6
| CI-TheShipyard | [8 empty] | 93 | [7 empty] | 0 |  |  | 0 | [6 empty] | 93
| CI-PlusCo | [8 empty] | 5 | [17 empty] | 5
APWORKS - SUPPORT | [27 empty] | 0
| Support Tickets | [26 empty] | 0
| Tasks by US Team - Demo | [8 empty] | 12 | [17 empty] | 12
| Tasks by US Team - JustGlobal | [8 empty] | 80 | [17 empty] | 80
| Tasks by US Team - TheShipyard | [8 empty] | 19 | [17 empty] | 19
Nexelus - Support | [27 empty] | 0
| Support Tickets - Demo | [8 empty] | 80 | [17 empty] | 80
| Support Tickets - Just Global | [8 empty] | 1 | [17 empty] | 1
| Tasks by US Team - Just Global | [8 empty] | 4.5 | [17 empty] | 4.5
0
0
0
0
0
[18 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
Overall Performance |  | 543.4 | 154 | 28 | 51.5 | 41 | 163.4 | 35.8 | 35.5 | 432 | 12 | 2 | 162.4 | 0 | 438.4 | 348.1 | 0 | 154 | 401.8 | 0 | 28 | 158 | 0 | 0 | 46.25 | 0 | 540.4 | 1843.5
Note on T128: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is difference for tasks where estimate is provided and Actual Work is performed

## AI Usage
AI Usage by Developers
(Scale 1 - 10)
Resource | Area | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01
Asad | Backend | 2024-11-01: 2; 2024-12-01: 2
Frontend
Documentation
DB
Fawad | Backend | 2024-11-01: 2; 2024-12-01: 2
| Frontend | 2024-11-01: 2; 2024-12-01: 2
Documentation
| DB | 2024-11-01: 2
Arslan | Backend
| Frontend | 2024-11-01: 5; 2024-12-01: 5
Documentation
| DB | 2024-11-01: 4; 2024-12-01: 4
Arif Khan | Backend
Frontend
Documentation
DB
Imran Haq | Backend
Frontend
Documentation
DB

## October 2024
Project Profile
Period: October 2024
Project / | Task | Planned |  |  | Project Overhead | [5 empty] | Test | Code | Analysis | Design | Development Time |  |  | Testing |  |  | Bug Fixing Time |  |  | Total | Total
Release |  | Development | QA | Bug Fixing | Mgmt | Training | Meetings | Deployments | Document | Client Items | Cases | Review |  |  | Estimate | Actual | Difference | Planned | Actual | Variance | Planned | Actual | Variance | Planned | Hours
APWORKS 2024.2 - PHASE 3 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| Ability to automatically attach additional documents to Invoice | 30 | 20 |  |  |  | 4 |  |  |  | 28 |  | 1 |  | 30 | 31 |  | 20 | 49 |  | 0 | 8 |  | 50 | 121
| Add Media Type/Service type/Roles | 4 | 8 |  |  |  | 4 |  |  |  | 2 |  |  |  | 4 |  |  | 8 | 70 |  | 0 |  |  | 12 | 76
| Ability to assign Employees to Roles by Media type and by Client | 70 | 8 | [7 empty] | 3 | 3 |  |  | 70 | 80 |  | 8 | 62 |  | 0 | 13 |  | 78 | 161
| Google Drive integration. (Setup and Integration development) | 44 | 8 |  |  |  | 15 |  |  |  | 3 | 4 | 7 |  | 44 | 33 |  | 8 | 67.5 |  | 0 | 23 |  | 52 | 152.5
| Project Overhead |  |  |  | 8 |  | 28.5 | 39.5 |  |  |  |  | 9.5 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 85.5
| Associate vendor/stations/sites to multiple pay to | 32 | [9 empty] | 2 |  |  | 32 | 12 |  | 0 |  |  | 0 | 10 |  | 32 | 24
| Broadcast Invoice | [13 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| EDI File Processing | 62 | 40 | [7 empty] | 6 | 13 | 2 |  | 62 | 27 |  | 40 | 52.5 |  | 0 |  |  | 102 | 100.5
| Invoice View UI | 30 | 12 | [11 empty] | 30 | 2 |  | 12 |  |  | 0 | 3 |  | 42 | 5
| PDF file generation | 50 | 6 | [11 empty] | 50 | 23 |  | 6 | 10.5 |  | 0 |  |  | 56 | 33.5
| Manage Invoice Documents | 4 | [12 empty] | 4 | 4 |  | 0 |  |  | 0 |  |  | 4 | 4
| Checkbox to filter discrepant lines | 8 | [12 empty] | 8 |  |  | 0 | 2 |  | 0 |  |  | 8 | 2
| Enhancement in vendor mapping(Parse Table) | [13 empty] | 0 |  |  | 0 |  |  | 0 | 4 |  |  | 4
| Master Data: Payment Terms | [13 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| Switch Company on Invoice | [7 empty] | 1 |  |  |  | 4 | 13 | 0 | 31 |  | 0 |  |  | 0 | 12 |  | 0 | 61
| Vendor Inv: Select Client on Header | [11 empty] | 3 | 6 | 0 | 25 |  | 0 |  |  | 0 | 2 |  | 0 | 36
| Customer Information: Select Client on Vendor Invoice | 16.4 | [10 empty] | 4 | 6 | 16.4 | 29 |  | 0 | 4 |  | 0 | 5 |  | 16.4 | 48
| Route invoice from one company to another | 56 | [10 empty] | 1 |  | 56 | 14 |  | 0 |  |  | 0 | 9 |  | 56 | 24
| Vendor/stations/sites associated to multiple pay to. | 32 | [12 empty] | 32 | 8 |  | 0 | 31 |  | 0 | 2 |  | 32 | 41
| Apply discount based on Payment terms settings | [17 empty] | 4
APWORKS PHASE2 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| Meetings, mails, communication, TFS, Interviews | [5 empty] | 6 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 6
| Regular bug fixing activity | [13 empty] | 0 |  |  | 0 |  |  | 0 | 68 |  |  | 68
| Cient UAT Upgrade | [6 empty] | 10.5 |  | 11 |  |  |  |  | 0 |  |  | 0 | 8 |  | 0 |  |  |  | 29.5
| Client Items | [13 empty] | 0 |  |  | 0 | 13 |  | 0 |  |  |  | 13
| Development of new project/assignment/task | [13 empty] | 0 | 15 |  | 0 |  |  | 0 |  |  |  | 15
| Internal Meetings | [5 empty] | 4 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 4
| Regular testing and QA new project/assignment/task | [13 empty] | 0 |  |  | 0 | 34 |  | 0 |  |  |  | 34
| QA Environment Upgrade | [13 empty] | 0 |  |  | 0 | 9 |  | 0 |  |  |  | 9
AP WORKFLOW | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
| Regular bug fixing activity | [13 empty] | 0 |  |  | 0 | 3 |  | 0 |  |  | 0 | 3
| Internal Meetings | [5 empty] | 1 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1
| Analysis of production issues reported by support team | [13 empty] | 0 |  |  | 0 |  |  | 0 | 15 |  | 0 | 15
NEXELUS 2024.1 SP2 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| Project Overhead | [5 empty] | 12 |  | 17 |  |  |  | 4 |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 33
| Client Lines (New Lines, Generate Schedule) | 67 | 40 | 20 |  |  | 2.5 | [6 empty] | 35 | 67 | 30 |  | 40 |  |  | 20 |  |  |  | 67.5
| eConnect shell change to service | [11 empty] | 16 |  | 0 | 16 |  | 0 |  |  | 0 |  |  |  | 32
| Backup Table | 38 | 12 | 8 | [10 empty] | 38 | 3 |  | 12 |  |  | 8 |  |  |  | 3
NEXELUS 2024.2 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| Analysis of the new project/assignment/task | [11 empty] | 6 | 7 | 0 |  |  | 0 |  |  | 0 |  |  |  | 13
| Regular bug fixing activity | [13 empty] | 0 |  |  | 0 |  |  | 0 | 1 |  |  | 1
| Client Items | [8 empty] | 40 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 40
| Cient UAT Upgrade | [17 empty] | 4
| In-house Training | [5 empty] | 1 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 1
| Analysis of production issues reported by support team | [11 empty] | 19 |  | 0 |  |  | 0 |  |  | 0 | 13 |  |  | 32
| Regular testing and QA new project/assignment/task | [7 empty] | 6 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 6
| Document review/understanding Requirement Specifications | [7 empty] | 7 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 7
| Support Items | [8 empty] | 148 |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 5 |  |  | 153
PR-0013 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| Cient UAT Upgrade | [11 empty] | 7 |  | 0 |  |  | 0 | 15 |  | 0 |  |  |  | 22
| Development of new project/assignment/task | [8 empty] | 63 |  |  |  |  | 0 |  |  | 0 |  |  | 0 | 10 |  |  | 73
| In-house Training |  |  |  |  | 40 | [8 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 40
| Internal Meetings | [5 empty] | 52 | [7 empty] | 0 | 3 |  | 0 |  |  | 0 | 2 |  |  | 57
| Analysis of production issues reported by support team | [11 empty] | 31 |  | 0 |  |  | 0 | 16 |  | 0 |  |  |  | 47
| Session with US team |  |  |  | 2.7 |  | 27 |  |  | 26.5 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 56.2
PR-0014 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| CI-DentsuCreativ | [8 empty] | 29 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 29
| CI-HY | [8 empty] | 11 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 11
| CI-JustGlobal | [8 empty] | 16 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 16
| CI-PropelHealth | [8 empty] | 11 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 11
| CI-TheShipyard | [8 empty] | 36 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 36
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
Overall Performance |  | 543.4 | 154 | 28 | 10.7 | 40 | 157 | 50 | 31 | 391.5 | 42 | 22 | 114.5 | 67 | 543.4 | 386 | 0 | 154 | 454.5 | 0 | 28 | 205 | 0 | 540.4 | 1963.2

## September 2024
Project Profile
Period: September 2024
Project / Release | Task | Planned |  |  | Project Overhead | [9 empty] | Development Time |  |  | Testing |  |  | Bug Fixing Time |  |  | Total | Total
|  | Development | QA | Bug Fixing | Mgmt | Training | Meetings | Deployments | Document | Client Items | Test Cases | CodeReview | Analysis | Design | Estimate | Actual | Difference | Planned | Actual | Variance | Planned | Actual | Variance | Planned | Hours
APWORKS 2024.2 - PHASE 3 | [24 empty] | 0
| Add Media Type/Service type/Roles | 4 | 8 | [7 empty] | 9 |  | 2 |  | 4 |  |  | 8 | [5 empty] | 12 | 11
| Google Drive integration. (Setup and Integration development) | 44 | 8 |  |  |  | 5 |  | 15 |  | 39 |  |  |  | 44 | 58 | -14 | 8 | [5 empty] | 52 | 117
| Ability to automatically attach additional documents (tear sheets, afidavit) to the invoice | 30 | 20 |  |  |  | 7 |  |  |  | 16 |  | 0.5 |  | 30 |  |  | 20 | [5 empty] | 50 | 23.5
| We need to read the company on the invoice document to route to the right company. If the company is not detected properly we will default to a company and mark it with a status. | 56 | 20 | [11 empty] | 56 |  |  | 20 | [5 empty] | 76 | 0
| Broadcast Invoices | [13 empty] | 0 |  |  | 0 | [5 empty] | 0 | 0
| We will need a separate node for "Broadcast Invoices" added at the end of Production Invoices. | 4 | [12 empty] | 4 | 8 | -4 | 0 | [5 empty] | 4 | 8
| User Group management changes | 12 | [12 empty] | 12 | 4 | 8 | 0 | [5 empty] | 12 | 4
| Dashboard | 16 | [12 empty] | 16 |  |  | 0 | [5 empty] | 16 | 0
| Manage Invoice Documents | 4 | [12 empty] | 4 | 2 | 2 | 0 | [5 empty] | 4 | 2
| Invoice List UI | 32 | [12 empty] | 32 |  |  | 0 | [5 empty] | 32 | 0
| EDI file processing | 62 | 40 | [11 empty] | 62 | 10.5 | 51.5 | 40 | [5 empty] | 102 | 10.5
| PDF file generation | 50 | 6 | [9 empty] | 5 |  | 50 | 5 | 45 | 6 | [5 empty] | 56 | 10
| Invoice View UI | 30 | 12 | [8 empty] | 2 |  |  | 30 | 16 | 14 | 12 | [5 empty] | 42 | 18
| Manage Non-Mapped Broadcast Invoices | [14 empty] | 2 | [8 empty] | 2
| Customer Information : Selection of the client on the vendor invoice header level. This will help route the invoice to the appropriate client team. - (Sync and a lookup field on invoice) | 16 | 4 | [9 empty] | 0.5 |  | 16 |  |  | 4 | [5 empty] | 20 | 0.5
| We will need to introduce tolerance by media type. | 20 | [12 empty] | 20 |  |  | 0 | [5 empty] | 20 | 0
| Read data from Media Ocean Jobs, IOs (buying), Customer Master, Vendor Master, Currencies, Tax codes, Payment terms, EDI?, payment information | 80 | 40 | [11 empty] | 80 |  |  | 40 | [5 empty] | 120 | 0
| vendor/stations/sites can be associated to multiple pay to. EX: Bell Media is linked to Bill pay to | 32 | [12 empty] | 32 |  |  | 0 | [5 empty] | 32 | 0
| Checkbox to filter discrepant lines | 8 | [12 empty] | 8 |  |  | 0 | [5 empty] | 8 | 0
| Ability to assign Employees to Roles by Media type and by Client | 70 | 8 |  |  |  | 16 |  |  |  | 19 |  | 3 |  | 70 | 112 | -42 | 8 | [5 empty] | 78 | 150
| Ability to automatically attach additional documents to Invoice | 30 | [12 empty] | 30 |  |  | 0 | [5 empty] | 30 | 0
| Associate vendor/stations/sites to multiple pay to | 32 | [10 empty] | 1 | 3 | 32 | 23 | 9 | 0 | [5 empty] | 32 | 27
| Enhancement in vendor mapping(Parse Table) | [13 empty] | 0 |  |  | 0 | [5 empty] | 0 | 0
| Master Data: Payment Terms | [13 empty] | 0 |  |  | 0 | [6 empty] | 0
| Switch Company on Invoice | [13 empty] | 0 |  |  | 0 | [6 empty] | 0
| Route invoice from one company to another | 56 | [10 empty] | 1 |  | 56 |  |  | 0 | [6 empty] | 1
| Vendor/stations/sites associated to multiple pay to. | 32 | [12 empty] | 32 |  |  | 0 | [6 empty] | 0
| Project Overhead |  |  |  | 1 |  | 20.5 | 2.5 | 1 |  |  |  | 4 |  | 0 |  |  | 0 | [6 empty] | 29
AP WORKFLOW | [14 empty] | 0 |  |  | 0 | [6 empty] | 0
| Analysis of the new project/assignment/task | [11 empty] | 5 |  | 0 |  |  | 0 | [5 empty] | 0 | 5
| Regular bug fixing activity | [13 empty] | 0 |  |  | 0 | 13 |  |  |  |  | 0 | 13
| Cient UAT Upgrade | [13 empty] | 0 |  |  | 0 | 4 |  |  |  |  | 0 | 4
| QA Environment Upgrade | [6 empty] | 1 | [6 empty] | 0 |  |  | 0 | [6 empty] | 1
| Release Environment Upgrade | [6 empty] | 6 | [6 empty] | 0 |  |  | 0 | [6 empty] | 6
APWORKS PHASE2 | [14 empty] | 0 |  |  | 0 | [5 empty] | 0 | 0
| Analysis of the new project/assignment/task | [13 empty] | 0 | 6 | -6 | 0 | [5 empty] | 0 | 6
| Dev Support | [5 empty] | 1 |  |  | 4 |  |  |  |  | 0 |  |  | 0 | [5 empty] | 0 | 5
| Meetings, mails, communication, TFS, Interviews | [5 empty] | 25 | [6 empty] | 1 | 0 |  |  | 0 | [5 empty] | 0 | 26
| Regular bug fixing activity | [13 empty] | 0 |  |  | 0 | 180 | -180 |  | 21 | -21 | 0 | 201
| Regular testing and QA new project/assignment/task | [13 empty] | 0 |  |  | 0 | 21 | -21 | 0 | 184 | -184 | 0 | 205
| Support Items | [5 empty] | 1 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 1
NEXELUS 2024.2 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| Analysis of the new project/assignment/task | [11 empty] | 22 | 6 | 0 |  |  | 0 |  |  | 0 |  |  |  | 28
| Client Items | [5 empty] | 1 |  |  | 92 |  |  |  |  | 0 | 2 | -2 | 0 |  |  | 0 |  |  |  | 95
| Development of new project/assignment/task | [13 empty] | 0 | 3 | -3 | 0 |  |  | 0 |  |  |  | 3
| Meetings, mails, communication, TFS, Interviews | [5 empty] | 30 | [7 empty] | 0 |  |  | 0 | 30 | -30 | 0 |  |  |  | 60
| Regular bug fixing activity | [13 empty] | 0 | 44 | -44 | 0 | 6 | -6 | 0 |  |  |  | 50
| Regular testing and QA new project/assignment/task | [13 empty] | 0 |  |  | 0 | 194.5 | -194.5 | 0 |  |  |  | 194.5
| Analysis of production issues reported by support team | [8 empty] | 15 |  |  | 11
| QA Environment Upgrade | [17 empty] | 4 | -4
| Document review/understanding Requirement Specifications | [17 empty] | 11 | -11
| Requirement Specifications document writing | [7 empty] | 18.5
| Support Items | [5 empty] | 1 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 1
| Time Off - Planned | [13 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
PR-0013 | [14 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
| Meetings, mails, communication, TFS, Interviews | [5 empty] | 51 | [5 empty] | 7.5 |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 58.5
| Cient UAT Upgrade | [8 empty] | 3.5 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 3.5
| Development of new project/assignment/task | [13 empty] | 0 | 28 |  | 0 | 35 | -35 | 0 |  |  |  | 63
| Internal Meetings | [7 empty] | 4 | [5 empty] | 0 | 11 |  | 0 |  |  | 0 |  |  |  | 15
| Analysis of production issues reported by support team | [11 empty] | 48 |  | 0 |  |  | 0 | 4 | -4 | 0 | 12 |  |  | 64
| Production upgrades | [6 empty] | 3 | [6 empty] | 0 |  |  | 0 | 10 | -10 | 0 |  |  |  | 13
| Session with US team | [5 empty] | 24.7 |  |  | 18.5 |  |  | 3 |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 46.2
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
[15 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0
[15 empty] | 0 |  |  | 0 | [6 empty] | 0
Overall Performance |  | 720 | 166 | 0 | 1 | 0 | 183.2 | 12.5 | 38.5 | 133 | 83 | 2 | 113.5 | 10 | 720 | 334.5 | 14.5 | 166 | 512.5 | -495.5 | 0 | 217 | -205 | 798 | 1581.2
Score Card of planned Activities (For Activities with Active Data)
[15 empty] | Plan - Actual (Development) |  |  | Plan - Actual (Testing) |  |  | Plan - Actual (Bug Fix) |  |  | Plan - Actual (Bug Fix)
[15 empty] | Planned | Actual | Diff | Planned | Actual | Diff | Planned | Actual | Diff | Planned | Actual | Diff
[15 empty] | 1028 | 573 | 455 | 166 | 512.5 | -346.5 | 0 | 0 | 0 | 1262 | 1962.7 | -700.7
Note on T75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is difference for tasks where estimate is provided and Actual Work is performed