## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | apWorks.ai Enhancements | 234 hrs | September 26, 2022 11:00 AM | November 17, 2022 6:00 PM |  | 0
1 | Yes | Auto Scheduled | Tax | 132 hrs | September 26, 2022 11:00 AM | October 25, 2022 6:00 PM |  | 1
2 | Yes | Auto Scheduled | Development | 78 hrs | September 26, 2022 11:00 AM | October 12, 2022 6:00 PM |  | 2
3 | Yes | Auto Scheduled | DB Changes for Tax Settings From Nexelus | 12 hrs | September 26, 2022 11:00 AM | September 27, 2022 6:00 PM |  | 3
4 | Yes | Auto Scheduled | Data Fetching from Nexelus API | 24 hrs | September 28, 2022 11:00 AM | October 3, 2022 6:00 PM | 3 | 3
5 | Yes | Auto Scheduled | DB Changes in Invoice Details Table | 6 hrs | September 26, 2022 11:00 AM | September 26, 2022 6:00 PM |  | 3
6 | Yes | Auto Scheduled | UI Updates in Invoice Screen | 24 hrs | September 27, 2022 11:00 AM | September 30, 2022 6:00 PM | 5 | 3
7 | Yes | Auto Scheduled | Updates in Invoice Posting | 30 hrs | October 4, 2022 11:00 AM | October 10, 2022 6:00 PM | 4 | 3
8 | Yes | Auto Scheduled | Build Release | 12 hrs | October 11, 2022 11:00 AM | October 12, 2022 6:00 PM | 6,7 | 3
9 | Yes | Auto Scheduled | Quality Assurance | 120 hrs | September 26, 2022 11:00 AM | October 21, 2022 6:00 PM |  | 2
10 | Yes | Auto Scheduled | Test Case Writing | 20 hrs | September 26, 2022 11:00 AM | September 29, 2022 1:00 PM |  | 3
11 | Yes | Auto Scheduled | Testing | 33.33 hrs | October 13, 2022 11:00 AM | October 20, 2022 3:20 PM | 8,10 | 3
12 | Yes | Auto Scheduled | Bug Fixing on UI Side | 18 hrs | October 13, 2022 11:00 AM | October 17, 2022 6:00 PM | 6,11SS | 3
13 | Yes | Auto Scheduled | Bug Fixing Data Fetching & Posting | 42 hrs | October 13, 2022 11:00 AM | October 21, 2022 6:00 PM | 11SS | 3
14 | Yes | Auto Scheduled | Build Creation & Application Deployment For Tax | 12 hrs | October 24, 2022 11:00 AM | October 25, 2022 6:00 PM | 9 | 2
15 | Yes | Auto Scheduled | Invoice Splitting | 138 hrs | October 18, 2022 11:00 AM | November 17, 2022 6:00 PM |  | 1
16 | Yes | Auto Scheduled | Development | 126 hrs | October 18, 2022 11:00 AM | November 15, 2022 6:00 PM |  | 2
17 | Yes | Auto Scheduled | Invoice Model Screen Updates | 24 hrs | October 18, 2022 11:00 AM | October 21, 2022 6:00 PM | 12 | 3
18 | Yes | Auto Scheduled | Updates in Invoice Scanner | 60 hrs | October 24, 2022 11:00 AM | November 4, 2022 6:00 PM |  | 3
19 | Yes | Auto Scheduled | Invoice File cloning based on number of line items | 18 hrs | October 24, 2022 11:00 AM | October 26, 2022 6:00 PM | 17 | 4
20 | Yes | Auto Scheduled | Stamping on lineitem on PDF | 18 hrs | October 27, 2022 11:00 AM | October 31, 2022 6:00 PM | 19 | 4
21 | Yes | Auto Scheduled | Picking specific lines for creation of separate invoice documents in DB | 48 hrs | October 26, 2022 11:00 AM | November 4, 2022 6:00 PM | 1 | 4
22 | Yes | Auto Scheduled | Updates in Invice Screen | 18 hrs | November 1, 2022 11:00 AM | November 3, 2022 6:00 PM | 20 | 3
23 | Yes | Auto Scheduled | Bug Fixing for Scanner Process | 36 hrs | November 7, 2022 11:00 AM | November 14, 2022 6:00 PM | 21 | 3
24 | Yes | Auto Scheduled | Bug Fixing for file stamping, cloning, and Invoice Screen | 18 hrs | November 4, 2022 11:00 AM | November 8, 2022 6:00 PM | 22 | 3
25 | Yes | Auto Scheduled | Build release | 6 hrs | November 15, 2022 11:00 AM | November 15, 2022 6:00 PM | 23,24 | 3
26 | Yes | Auto Scheduled | Quality Assurance | 80 hrs | October 26, 2022 11:00 AM | November 14, 2022 1:00 PM |  | 2
27 | Yes | Auto Scheduled | Test Case Writing | 20 hrs | October 26, 2022 11:00 AM | October 31, 2022 1:00 PM | 1 | 3
28 | Yes | Auto Scheduled | Testing | 60 hrs | October 31, 2022 2:00 PM | November 14, 2022 1:00 PM | 27 | 3
29 | Yes | Auto Scheduled | Bug Fixing | 18 hrs | November 9, 2022 11:00 AM | November 11, 2022 6:00 PM | 28SS,24 | 3
30 | Yes | Auto Scheduled | Build Creation & Application Deployment For Invoice Splitting | 12 hrs | November 16, 2022 11:00 AM | November 17, 2022 6:00 PM | 25,26 | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Faisal Ahmed Farooqui | FAF | Work |  | Manager, Dev | faisalf@nexelus.net | faisalf@nexelus.net | 100% | $0.00/h | 0
2 | Zeeshan Akhter | ZA | Work |  | Dev |  |  | 100% | $0.00/h | 0
3 | MN | MN | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
DB Changes for Tax Settings From Nexelus | Faisal Ahmed Farooqui | 0 | 6h | 50%
Data Fetching from Nexelus API | Faisal Ahmed Farooqui | 0 | 12h | 50%
DB Changes in Invoice Details Table | Zeeshan Akhter | 0 | 6h | 100%
UI Updates in Invoice Screen | Zeeshan Akhter | 0 | 24h | 100%
Updates in Invoice Posting | Faisal Ahmed Farooqui | 0 | 15h | 50%
Build Release | Faisal Ahmed Farooqui | 0 | 6h | 50%
Test Case Writing | MN | 0 | 6h | 30%
Testing | MN | 0 | 10h | 30%
Bug Fixing on UI Side | Zeeshan Akhter | 0 | 18h | 100%
Bug Fixing Data Fetching & Posting | Faisal Ahmed Farooqui | 0 | 21h | 50%
Build Creation & Application Deployment For Tax | Faisal Ahmed Farooqui | 0 | 6h | 50%
Invoice Model Screen Updates | Zeeshan Akhter | 0 | 24h | 100%
Invoice File cloning based on number of line items | Zeeshan Akhter | 0 | 18h | 100%
Stamping on lineitem on PDF | Zeeshan Akhter | 0 | 18h | 100%
Picking specific lines for creation of separate invoice documents in DB | Faisal Ahmed Farooqui | 0 | 24h | 50%
Updates in Invice Screen | Zeeshan Akhter | 0 | 18h | 100%
Bug Fixing for Scanner Process | Faisal Ahmed Farooqui | 0 | 18h | 50%
Bug Fixing for file stamping, cloning, and Invoice Screen | Zeeshan Akhter | 0 | 18h | 100%
Build release | Faisal Ahmed Farooqui | 0 | 6h | 100%
Test Case Writing | MN | 0 | 6h | 30%
Testing | MN | 0 | 18h | 30%
Bug Fixing | Zeeshan Akhter | 0 | 18h | 100%
Build Creation & Application Deployment For Invoice Splitting | Faisal Ahmed Farooqui | 0 | 6h | 50%