## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | AP Automation Phase 2 | 896 hrs | January 21, 2021 8:00 AM | June 25, 2021 5:00 PM |  | 0
1 | Yes | Auto Scheduled | Analysis/Software Requirements | 24 hrs | January 21, 2021 8:00 AM | January 25, 2021 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Document Review | 8 hrs | January 21, 2021 8:00 AM | January 21, 2021 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Understanding of Existing App | 16 hrs | January 22, 2021 8:00 AM | January 25, 2021 5:00 PM | 2 | 2
4 | Yes | Auto Scheduled | Design | 40 hrs | January 26, 2021 8:00 AM | February 1, 2021 5:00 PM | 1 | 1
5 | Yes | Auto Scheduled | DB Design Review | 16 hrs | January 26, 2021 8:00 AM | January 27, 2021 5:00 PM |  | 2
6 | Yes | Auto Scheduled | Architecture Design Review | 16 hrs | January 28, 2021 8:00 AM | January 29, 2021 5:00 PM | 5 | 2
7 | Yes | Auto Scheduled | UI Components Structure Setup | 16 hrs | January 28, 2021 8:00 AM | January 29, 2021 5:00 PM | 5 | 2
8 | Yes | Auto Scheduled | Overall Design Review | 8 hrs | February 1, 2021 8:00 AM | February 1, 2021 5:00 PM | 7,6 | 2
9 | Yes | Auto Scheduled | Development Sprints | 304 hrs | February 2, 2021 8:00 AM | March 25, 2021 5:00 PM | 4 | 1
10 | Yes | Auto Scheduled | Development of Version V1.1 | 304 hrs | February 2, 2021 8:00 AM | March 25, 2021 5:00 PM | 4 | 2
11 | Yes | Auto Scheduled | Version 1.1.1 | 136 hrs | February 2, 2021 8:00 AM | February 24, 2021 5:00 PM |  | 3
12 | Yes | Auto Scheduled | Production Invoices Cloud Infrastructure Updates | 32 hrs | February 2, 2021 8:00 AM | February 5, 2021 5:00 PM |  | 4
13 | Yes | Auto Scheduled | DB Design Implementation | 32 hrs | February 2, 2021 8:00 AM | February 5, 2021 5:00 PM |  | 4
14 | Yes | Auto Scheduled | Code Refactoring | 16 hrs | February 8, 2021 8:00 AM | February 9, 2021 5:00 PM | 13 | 4
15 | Yes | Auto Scheduled | Company Configuration UI | 24 hrs | February 10, 2021 8:00 AM | February 12, 2021 5:00 PM | 14 | 4
16 | Yes | Auto Scheduled | Routing Configuration | 16 hrs | February 8, 2021 8:00 AM | February 9, 2021 5:00 PM | 12 | 4
17 | Yes | Auto Scheduled | Menu & Authorization | 24 hrs | February 10, 2021 8:00 AM | February 12, 2021 5:00 PM | 16 | 4
18 | Yes | Auto Scheduled | Build Version 1.1.1 Release | 16 hrs | February 15, 2021 8:00 AM | February 16, 2021 5:00 PM | 15,17 | 4
19 | Yes | Auto Scheduled | Testing | 32 hrs | February 17, 2021 8:00 AM | February 22, 2021 5:00 PM | 18 | 4
20 | Yes | Auto Scheduled | Bug Fixing | 16 hrs | February 23, 2021 8:00 AM | February 24, 2021 5:00 PM | 19 | 4
21 | Yes | Auto Scheduled | Version 1.1.2 | 168 hrs | February 25, 2021 8:00 AM | March 25, 2021 5:00 PM |  | 3
22 | Yes | Auto Scheduled | Roles Management | 24 hrs | February 25, 2021 8:00 AM | March 1, 2021 5:00 PM | 20 | 4
23 | Yes | Auto Scheduled | Data Sync Function updates | 24 hrs | February 25, 2021 8:00 AM | March 1, 2021 5:00 PM | 20 | 4
24 | Yes | Auto Scheduled | Updates in Model creation screen | 24 hrs | March 2, 2021 8:00 AM | March 4, 2021 5:00 PM | 22 | 4
25 | Yes | Auto Scheduled | Updates in Scanner function | 32 hrs | March 2, 2021 8:00 AM | March 5, 2021 5:00 PM | 23 | 4
26 | Yes | Auto Scheduled | Non-Media/Production Invoice Screen | 24 hrs | March 5, 2021 8:00 AM | March 9, 2021 5:00 PM | 24 | 4
27 | Yes | Auto Scheduled | Invoice Routing | 32 hrs | March 8, 2021 8:00 AM | March 11, 2021 5:00 PM | 25 | 4
28 | Yes | Auto Scheduled | Production Invoices Dashboard | 32 hrs | March 10, 2021 8:00 AM | March 15, 2021 5:00 PM | 26 | 4
29 | Yes | Auto Scheduled | Build Version 1.1.2 Release | 24 hrs | March 16, 2021 8:00 AM | March 18, 2021 5:00 PM | 27,28 | 4
30 | Yes | Auto Scheduled | Bug fixing | 40 hrs | March 19, 2021 8:00 AM | March 25, 2021 5:00 PM | 29 | 4
31 | Yes | Auto Scheduled | QA Training on Product | 40 hrs | March 1, 2021 8:00 AM | March 5, 2021 5:00 PM |  | 4
32 | Yes | Auto Scheduled | Testcase Creation | 40 hrs | March 8, 2021 8:00 AM | March 12, 2021 5:00 PM | 31 | 4
33 | Yes | Auto Scheduled | QA of Build 1.1.2 | 40 hrs | March 19, 2021 8:00 AM | March 25, 2021 5:00 PM | 29,32 | 4
34 | Yes | Auto Scheduled | AI based Development of Version V1.2 | 760 hrs | February 15, 2021 8:00 AM | June 25, 2021 5:00 PM |  | 1
35 | Yes | Auto Scheduled | Resource Allocation | 8 hrs | February 15, 2021 8:00 AM | February 15, 2021 5:00 PM |  | 2
36 | Yes | Auto Scheduled | Model Creation V 0.1 | 472 hrs | February 16, 2021 8:00 AM | May 7, 2021 5:00 PM | 35 | 2
37 | Yes | Auto Scheduled | Requirement Analysis | 64 hrs | March 26, 2021 8:00 AM | April 6, 2021 5:00 PM | 19,30 | 3
38 | Yes | Auto Scheduled | R&D on ML Frameworks | 64 hrs | April 7, 2021 8:00 AM | April 16, 2021 5:00 PM | 37 | 3
39 | Yes | Auto Scheduled | Data Collection-DataSet-1 & DataSet-2 | 40 hrs | February 16, 2021 8:00 AM | March 1, 2021 5:00 PM | 35 | 3
40 | Yes | Auto Scheduled | Data Filteration & Purification | 40 hrs | April 19, 2021 8:00 AM | April 23, 2021 5:00 PM | 39,38,44 | 3
41 | Yes | Auto Scheduled | ML-Model selection/creation on current filtered DataSet-1 | 40 hrs | April 26, 2021 8:00 AM | April 30, 2021 5:00 PM | 40 | 3
42 | Yes | Auto Scheduled | Testing of ML-Model on DataSet-2 | 40 hrs | May 3, 2021 8:00 AM | May 7, 2021 5:00 PM | 41,39 | 3
43 | Yes | Auto Scheduled | Model Creation V 0.2 | 512 hrs | March 2, 2021 8:00 AM | May 28, 2021 5:00 PM |  | 2
44 | Yes | Auto Scheduled | Data Collection-DataSet-3 & DataSet-4 | 40 hrs | March 2, 2021 8:00 AM | March 8, 2021 5:00 PM | 39 | 3
45 | Yes | Auto Scheduled | Data Filteration & Purification | 40 hrs | May 10, 2021 8:00 AM | May 14, 2021 5:00 PM | 44,42 | 3
46 | Yes | Auto Scheduled | ML-Model selection/creation on current filtered DataSet-3 | 40 hrs | May 17, 2021 8:00 AM | May 21, 2021 5:00 PM | 45 | 3
47 | Yes | Auto Scheduled | Testing of ML-Model on DataSet-4 | 40 hrs | May 24, 2021 8:00 AM | May 28, 2021 5:00 PM | 36,46 | 3
48 | Yes | Auto Scheduled | ML-Integrated Version 1.2.1 | 472 hrs | March 26, 2021 8:00 AM | June 16, 2021 5:00 PM |  | 2
49 | Yes | Auto Scheduled | Model Deployment on Dev Env on AWS | 24 hrs | May 31, 2021 8:00 AM | June 2, 2021 5:00 PM | 47 | 3
50 | Yes | Auto Scheduled | Changes in APA for integration & features | 80 hrs | March 26, 2021 8:00 AM | April 8, 2021 5:00 PM | 30 | 3
51 | Yes | Auto Scheduled | ML-Model Integration with scanner | 32 hrs | June 3, 2021 8:00 AM | June 8, 2021 5:00 PM | 50,49 | 3
52 | Yes | Auto Scheduled | Testcase creation for Integration testing | 24 hrs | June 9, 2021 8:00 AM | June 11, 2021 5:00 PM | 51 | 3
53 | Yes | Auto Scheduled | Integration Testing on Dev Environment | 24 hrs | June 14, 2021 8:00 AM | June 16, 2021 5:00 PM | 52,49,51 | 3
54 | Yes | Auto Scheduled | Bug Fixing on Application Side | 24 hrs | June 9, 2021 8:00 AM | June 11, 2021 5:00 PM | 51 | 3
55 | Yes | Auto Scheduled | Model Training | 80 hrs | May 31, 2021 8:00 AM | June 11, 2021 5:00 PM | 43 | 3
56 | Yes | Auto Scheduled | Build Version 1.2.1 Release | 24 hrs | June 14, 2021 8:00 AM | June 16, 2021 5:00 PM | 54,55 | 3
57 | Yes | Auto Scheduled | ML-Integrated Version 1.2.2 | 56 hrs | June 17, 2021 8:00 AM | June 25, 2021 5:00 PM | 48 | 2
58 | Yes | Auto Scheduled | ML-Model-Training Ver 0.3 | 40 hrs | June 17, 2021 8:00 AM | June 23, 2021 5:00 PM | 48 | 3
59 | Yes | Auto Scheduled | Updates in APA | 40 hrs | June 17, 2021 8:00 AM | June 23, 2021 5:00 PM | 48 | 3
60 | Yes | Auto Scheduled | ML-Model-Deployment | 40 hrs | June 17, 2021 8:00 AM | June 23, 2021 5:00 PM | 48 | 3
61 | Yes | Auto Scheduled | Creation of Build Version 1.2.2 | 16 hrs | June 24, 2021 8:00 AM | June 25, 2021 5:00 PM | 60 | 3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Faisal Ahmed Farooqui | FAF | Work |  | Manager, Dev | faisalf@nexelus.net | faisalf@nexelus.net | 100% | $0.00/h | 0
2 | Zeeshan Akhtar | ZA | Work |  | Dev | zeeshana@nexelus.net | zeeshana@nexelus.net | 100% | $0.00/h | 0
3 | AI-Dev | AIDev1 | Work |  | Dev |  |  | 100% | $0.00/h | 0
4 | Tao Lin | TL | Work |  | QA | taol@nexelus.net | taol@nexelus.net | 100% | $0.00/h | 0
5 | QA1 | QA1 | Work |  | QA |  |  | 100% | $0.00/h | 0
6 | [9 empty] | 0
7 | [9 empty] | 0
8 | [9 empty] | 0
9 | [9 empty] | 0
10 | [9 empty] | 0
11 | [9 empty] | 0
12 | [9 empty] | 0
13 | [9 empty] | 0
14 | [9 empty] | 0
15 | [9 empty] | 0
16 | [9 empty] | 0
17 | [9 empty] | 0
18 | [9 empty] | 0
19 | [9 empty] | 0
20 | [9 empty] | 0
21 | [9 empty] | 0
22 | [9 empty] | 0
23 | [9 empty] | 0
24 | [9 empty] | 0
25 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Document Review | Faisal Ahmed Farooqui | 0 | 8h | 100%
Document Review | Zeeshan Akhtar | 0 | 8h | 100%
Understanding of Existing App | Zeeshan Akhtar | 0 | 16h | 100%
DB Design Review | Faisal Ahmed Farooqui | 0 | 16h | 100%
DB Design Review | Zeeshan Akhtar | 0 | 16h | 100%
Architecture Design Review | Faisal Ahmed Farooqui | 0 | 16h | 100%
UI Components Structure Setup | Zeeshan Akhtar | 0 | 16h | 100%
Overall Design Review | Faisal Ahmed Farooqui | 0 | 8h | 100%
Overall Design Review | Zeeshan Akhtar | 0 | 8h | 100%
Production Invoices Cloud Infrastructure Updates | Faisal Ahmed Farooqui | 0 | 32h | 100%
DB Design Implementation | Zeeshan Akhtar | 0 | 32h | 100%
Code Refactoring | Zeeshan Akhtar | 0 | 16h | 100%
Company Configuration UI | Zeeshan Akhtar | 0 | 24h | 100%
Routing Configuration | Faisal Ahmed Farooqui | 0 | 16h | 100%
Menu & Authorization | Faisal Ahmed Farooqui | 0 | 24h | 100%
Build Version 1.1.1 Release | Faisal Ahmed Farooqui | 0 | 12h | 100%
Build Version 1.1.1 Release | Zeeshan Akhtar | 0 | 16h | 100%
Testing | Tao Lin | 0 | 32h | 100%
Bug Fixing | Faisal Ahmed Farooqui | 0 | 12h | 75%
Bug Fixing | Zeeshan Akhtar | 0 | 16h | 100%
Roles Management | Zeeshan Akhtar | 0 | 24h | 100%
Data Sync Function updates | Faisal Ahmed Farooqui | 0 | 18h | 100%
Updates in Model creation screen | Zeeshan Akhtar | 0 | 24h | 100%
Updates in Scanner function | Faisal Ahmed Farooqui | 0 | 24h | 60%
Non-Media/Production Invoice Screen | Zeeshan Akhtar | 0 | 24h | 100%
Invoice Routing | Faisal Ahmed Farooqui | 0 | 24h | 100%
Production Invoices Dashboard | Zeeshan Akhtar | 0 | 32h | 100%
Build Version 1.1.2 Release | Zeeshan Akhtar | 0 | 24h | 100%
Build Version 1.1.2 Release | Faisal Ahmed Farooqui | 0 | 20h | 100%
Bug fixing | Zeeshan Akhtar | 0 | 40h | 100%
Bug fixing | Faisal Ahmed Farooqui | 0 | 40h | 100%
QA Training on Product | QA1 | 0 | 40h | 100%
Testcase Creation | QA1 | 0 | 40h | 100%
QA of Build 1.1.2 | QA1 | 0 | 40h | 100%
Requirement Analysis | AI-Dev | 0 | 32h | 100%
Requirement Analysis | Faisal Ahmed Farooqui | 0 | 16h | 50%
R&D on ML Frameworks | AI-Dev | 0 | 20h | 100%
R&D on ML Frameworks | Faisal Ahmed Farooqui | 0 | 16h | 50%
Data Collection-DataSet-1 & DataSet-2 | Tao Lin | 0 | 40h | 100%
Data Filteration & Purification | AI-Dev | 0 | 40h | 100%
ML-Model selection/creation on current filtered DataSet-1 | AI-Dev | 0 | 40h | 100%
Testing of ML-Model on DataSet-2 | AI-Dev | 0 | 40h | 100%
Testing of ML-Model on DataSet-2 | Faisal Ahmed Farooqui | 0 | 40h | 100%
Data Collection-DataSet-3 & DataSet-4 | Tao Lin | 0 | 40h | 100%
Data Filteration & Purification | AI-Dev | 0 | 40h | 100%
ML-Model selection/creation on current filtered DataSet-3 | AI-Dev | 0 | 40h | 100%
Testing of ML-Model on DataSet-4 | AI-Dev | 0 | 40h | 100%
Testing of ML-Model on DataSet-4 | Faisal Ahmed Farooqui | 0 | 40h | 100%
Model Deployment on Dev Env on AWS | Faisal Ahmed Farooqui | 0 | 24h | 100%
Changes in APA for integration & features | Zeeshan Akhtar | 0 | 80h | 100%
ML-Model Integration with scanner | Zeeshan Akhtar | 0 | 32h | 100%
ML-Model Integration with scanner | Faisal Ahmed Farooqui | 0 | 32h | 100%
Testcase creation for Integration testing | QA1 | 0 | 24h | 100%
Integration Testing on Dev Environment | QA1 | 0 | 24h | 100%
Bug Fixing on Application Side | Zeeshan Akhtar | 0 | 24h | 100%
Model Training | AI-Dev | 0 | 80h | 100%
Build Version 1.2.1 Release | Zeeshan Akhtar | 0 | 24h | 100%
Build Version 1.2.1 Release | AI-Dev | 0 | 24h | 100%
Build Version 1.2.1 Release | Faisal Ahmed Farooqui | 0 | 24h | 100%
ML-Model-Training Ver 0.3 | AI-Dev | 0 | 40h | 100%
Updates in APA | Zeeshan Akhtar | 0 | 40h | 100%
ML-Model-Deployment | Faisal Ahmed Farooqui | 0 | 40h | 100%
Creation of Build Version 1.2.2 | Zeeshan Akhtar | 0 | 16h | 100%
Creation of Build Version 1.2.2 | AI-Dev | 0 | 16h | 100%
Creation of Build Version 1.2.2 | Faisal Ahmed Farooqui | 0 | 16h | 100%