## Info
Internal Audit for SOC Compliance
Audit Conducted On: |  | 2023-06-09
Auditors:
| 1 | Imran Rahman
| 2 | Tauseef Shahzad
| 3 | Tao Lin
| 4 | Peter Platkowski
| 5 | Fayaz Khan

## Audit Findings
Internal Audit for SOC Compliance
Findings - June 9, 2023
Item | Control ID | Control Description | Non Compliance / Findings | Assigned to | ETA | Corrective Action | Status | Completion Date
1 | DCF-002 | Least-Privileged Policy for Customer Data Access | Policy exists. But no evidence of implementaion is provided as screenshot or link | Imran | 2023-06-24 | Tauseef: Excel sheet for Named user acecess added as evidence on Drata. | Complete | 2023-06-24
2 | DCF-011 | Annual Access Control Review | Evidence of Nexelus Access Control are not updated as evidence on Drata | Tauseef |  | Tauseef: Following documents are uploaded as evidence. 1. Minutes of Meeting 2. RACI Spreadsheet 3. Access Control Sheet | Complete | 2023-07-18
2 | DCF-012 | Hardening Standards in Place | Document of Hardening Standards | Peter | 2023-06-30 | Peter will create document on this | Complete | 2023-06-30
3 | DCF-014 | Organizational Chart Maintained | Drata does not show the control as satisfied | Imran | 2023-06-30 | Uploaded evidence for hardening standard checklist | Complete | 2023-07-14
4 | DCF-019 | Annual Penetration Tests Conduct independent 3rd party penetration testing on systems and web application | Penetration Test is not Performed | Tauseef | 2023-06-30 | Tauseef 6/9/2023: Penetration test is in progress. We will get Initial finding report next week Tauseef 6/26/2023: Penetration Test is performed. All identified critical and high vulnerabilities have been resolved. | Complete | 2023-06-26
5 | DCF-038 | Annual Performance Evaluations | Provide evidence of Annual Performance Evaluation | Imran | 2023-06-30 | Tauseef 6/9/2023: Imran to send Performance Evaluation for atleast three employees to Auditor Tauseef 6/30/2023: Imran sent Performance evaluation process and three evaluations to Auditor | Complete | 2023-06-30
6 | DCF-061 | Customer Data Segregation | Application DB Users have access to other client databases | Arif Khan | 2023-06-30 | Tauseef 6/9/2023: Data for each client is maintained in their own respected database and is never shared between clients | Complete | 2023-06-09
7 | DCF-064 | Commitments Explained to Customers | Does the organization communicate its security commitments to external users? | Imran | 2023-06-30 | SaaS Agreement sent via the email Imran: 6/22/2023: Email confirmation received from Moiz that SaaS agreement sent satisfy the control evidence | Complete | 2023-06-22
8 | DCF-065 | Maintains a Privacy Policy | Privacy Policy not publically available | Imran | 2023-06-30 | [Tauseef] 1. Imran to provide a copy of SaaS agreement to Auditor 2. Information Security Policy that covers this control is accessible on Drata for all employees [Imran] Email confirmation received from Moiz that SaaS agreement sent satisfy the control evidence | Complete | 2023-06-22
9 | DCF-066 | Maintains a Terms of Service | Terms of Service not publically available | Imran | 2023-06-30 | [Imran] Email confirmation received from Moiz that SaaS agreement sent satisfy the control evidence | Complete | 2023-06-22
10 | DCF-067 | MFA on Accounts | Drata does not show the control as satisfied | Tao | 2023-06-30 | Tauseef 6/30/2023: Issue resolved onn Drata | Complete
11 | DCF-144 | Board Charter Documented | Does the organization have a documented charter that outlines oversight responsibilities for internal control? | Imran | 2023-06-30 | Tauseef 6/9/2023: As discussed with Moiz, we are Management run board, hence this control is not applicable | Out of Scope | 2023-06-22
12 | DCF-151 | FIM (File Integrity Monitoring) Software in Place | A File Integrity Monitor (FIM) or similar change-detection technology is not implemented on critical assets to generate alerts for unauthorized modifications? | Peter | 2023-06-30 | Tauseef 7/11/2023: Microsoft Defender for Cloud is configured for FIM | Complete | 2023-07-11
13 | DCF-153 | Conduct Control Self-Assessments | 1. Conduct annual self-assessment of controls 2. Corrective Action and responsibilities defined for identified risks | Tauseef | 2023-06-09 | Control Self Assessment is complete. | Complete | 2023-06-09
14 | DCF-157 | Cybersecurity Insurance Maintained | 1. Cybersecurity insurance policy maintained by management | Imran | 2023-06-30 | Mark as out of scope | Out of Scope | 2023-06-02

## Lookups
Status
To Do
In Progress
Complete
On Hold
Out of Scope
Question?