## Nexelus
Sr. # | Steps | Tables Involved | Responsibility | ETA | Status
Database Setup
1 | Take backup of existing database from TSY Database - Nex_TSY |  | Imran | 2024-10-28
2 | Restore backup from step above with new name - Nex_Helm |  | Imran | 2024-10-28
3 | Update Enterprise Database - Nex_Enterprise_TSY |  | Imran | 2024-10-28
3 | Views and Sps Poining if DB name is different on test and production |  | Imran | 2024-10-28
4 | Set mail flag=0 in pdd_resources from "EMPL" | pdd_resources | Imran | 2024-10-28
5 | IPC configuration pointing if any | pdd_lookup_ipc_entities_header | Imran | 2024-10-28
5.1 |  | pdd_customer_profile_ipc_ad_tool | Imran | 2024-10-28
5.2 |  | pdm_company_ipc | Imran | 2024-10-28
5.3 |  | pdd_lookup_ipc_entities_detail | Imran | 2024-10-28
5.4 |  | pdd_invoice_detail_ipc_ad_tool | Imran | 2024-10-28
5.5 |  | pdm_company_ipc_ad_tool | Imran | 2024-10-28
5.6 |  | pdd_delivery_search_ad_tools_campaign | Imran | 2024-10-28
5.7 |  | pdd_level3_ipc_ad_tool | Imran | 2024-10-28
5.8 |  | pdd_ipc_cache_adwords_accounts_for_budget_orders | Imran | 2024-10-28
5.9 |  | pdd_invoice_header_ipc_ad_tool | Imran | 2024-10-28
6 | Set Integration code=0 if UAT instance of Financial ERP is not available, otherwise as required: - 16 = NetSuite | Pdm_company | Imran | 2024-10-28
6.3 | NetSuite | pdd_Netsuite_configuration pdd_netsuite_item_mapping | Tao | 2024-10-28
7 | Update email profile setting | Nex_Enterprise_TSY..ent_email_profile | Imran | 2024-10-28
8 | Insert a record in enterprise for new company with next company code | Nex_Enterprise_TSY..pdi_site | Imran | 2024-10-28
8.1 | - voucher_doc_path - web_app_path - nex_vp_url - report_server_path - database_server_esmte - database_name_esmte - database_server_esm - database_name_esm |  | Imran | 2024-10-28
9 | Reset application pool for step 8 |  | Tauseef Shahzad | 2024-10-28
10 | Clean transactional data | Clear scripts | Imran | 2024-10-28
11 | Clean/reset setup data | As per requirement | Imran | 2024-10-28
12 | Change company code | Company code scripts | Imran | 2024-10-28
Web Deployment
1 | Deploy Web Application |  | Tauseef Shahzad
2 | Deploy Core Applications |  | Tauseef Shahzad
Verificartion
1 | Process Verification |  | Bilal, Tao | 10/29/2024-10-30-2024
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not required

## APWorks
Item | Assigned To | Responsibility | ETA | Status
1 | Company DNS Setup tsy-uat.apworks.ai | Tao
2 | Create S3 Buckets and execute setup scripts helm-uat-apautomation | Tao | 2024-10-25
3 | Create Company Database from JustGlobal UAT Backup uat_apautomation_tsy | Arif Khan / Imran Haq
4 | Enter Helm information in Common Database - ent_client - ent_domain | Arif Khan / Imran Haq | 2024-10-29
5 | Update apam_company table in TSY database | Arif Khan / Imran Haq | 2024-10-29
6 | Cleanup Database - transactional Data - Model Data - Master Data | Arif Khan / Imran Haq | 2024-10-29
7 | Generate Nexelus API Key and update Database | Tao / Imran Haq | 2024-10-25
8 | Verify APWorks (Media and Production) | Bilal / Tao | 10/29/2024-10/30/2024
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not required

## VendorPortal
Item | Assigned To | Responsibility | ETA | Status
1 | Create Database Nex_vendorportal_tsy | Arif Khan /Imran Haq | 2024-10-25
2 | Clean Database | Arif Khan /Imran Haq | 2024-10-25
3 | Update following tables 1. pdi_companies | Arif Khan /Imran Haq | 2024-10-25
4 | Update vendorportal url in PDM_ENTERPRISE_TSY.pdi_site | Arif Khan /Imran Haq | 2024-10-25
5 | Deploy Vendor Portal Application | Tauseef Shahzad | 2024-10-25
6 | Validation/Verification | Bilal / Tao | 10/25/2024 - 10/29/2024