## Info
Internal Audit for SOC Compliance
Audit Conducted On: |  | 2025-04-23
Auditors:
| 1 | Imran Rahman
| 2 | Tauseef Shahzad
| 3 | Tao Lin
| 4 | Peter Platkowski

## Audit Findings
Internal Audit for SOC Compliance
Findings - April 23, 2025
Item | Evidence Description | Non Compliance / Findings | Assigned to | ETA | Corrective Action | Status | Completion Date
Update Policies in Drata
1 | Vulnerability Management Policy | AntiVirus Tool List is not correct | Tauseef Shahzad | 2025-04-30 | Update Anti-virus and Malware List in Policy | In Progress | 2025-05-02
2 | Physical Security Policy | Upload / Download Areas are not defined in Nexelus. Remove this section | Tauseef Shahzad | 2025-04-30 | Remove this segment | In Progress | 2025-05-02
Update Evidence against Controls in Drata
1 | Risk Assessment Report | Risk Assessment Report for 2025 | Imran Rahman | 2025-05-02 |  | In Progress
2 | Org Chart | Org Chart needs to be updated | Imran Rahman | 2025-05-02 | Updated Org Chart | Complete
3 | [SOC1] Control 1.6 - Internal and External edit or testing | Review by April 30, 2025 | Tauseef | 2025-05-02 | Latest Audit Report uploaded in Drata | Complete
4 | QA Environment Screenshot | Review by May 1, 2025 | Tauseef | 2025-05-01 | Update Latest Screenshot with Date Stamp | Complete | 2025-04-23
5 | security deficiency tracking system that shows deficiencies ... | Review by May 1, 2025 | Tao | 2025-05-01 | Update Latest Screenshot with Date Stamp
6 | DLP - 2023-05-19 | Review by May 2, 2025 | Tao | 2025-05-01 | Update Latest Screenshot with Date Stamp
7 | Authentication Protocol | Review by May 3, 2025 | Tao | 2025-05-01 | Update Latest Screenshot with Date Stamp
8 | Database Daily Backup Schedule | Review by May 8, 2025 | Tauseef | 2025-05-01 | Update Latest Screenshot with Date Stamp | Complete | 2025-04-23
9 | AD user for remote VM is unique | Review by May 15, 2025 | Tao | 2025-05-15 | Update Latest Screenshot with Date Stamp | Complete | 2025-04-23
10 | Application Gateway | Review by May 15, 2025 | Tao | 2025-05-15
11 | Background Check | Review by May 15, 2025 | Tauseef | 2025-05-15 |  | Complete | 2026-04-23
12 | Email Evidence | Review by May 15, 2025 | Tao | 2025-05-15
13 | Internal Audit Report | Review by May 15, 2025 | Tauseef | 2025-05-15 | Latest Audit Report uploaded in Drata | Complete | 2025-04-23
15 | Load Balancer 2023-05-19 | Review by May 15, 2025 | Tao | 2025-05-15
16 | Minutes of Meeting for SOC Compliance | Review by May 15, 2025 | Tauseef | 2025-05-15
17 | Minutes of the meeting via the email to Moiz | Review by May 15, 2025 | Tauseef | 2025-05-15
18 | Monitoring Capacity and Usage | Review by May 15, 2025 | Tao | 2025-05-15
19 | Sample Employee Termination Checklist | Review by May 15, 2025 | Tauseef | 2025-05-15 | Evidence has been updated | Complete | 2025-04-23
20 | Unique user ID | Review by May 15, 2025 | Tao | 2025-05-02 | Evidence has been updated | Complete | 2025-04-23
21 | customer data is segregated from the data of other customers | Review by May 30, 2025 | Tauseef | 2025-05-15 | Evidence has been updated | Complete | 2025-04-23
22 | Logging and Monitoring - The logs are stored centrally by Cl... | Review by May 30, 2025 | Tao | 2025-05-15
23 | Remote Server Access Register | Review by May 30, 2025 | Tauseef | 2025-05-15 | Evidence has been updated | Complete
24 | Sample Job Offer and Employment Agreement | Review by May 30, 2025 | Tauseef | 2025-05-15 | Evidence has been updated | Complete | 2025-04-23

## Lookups (hidden)
Status
To Do
In Progress
Complete
On Hold
Out of Scope
Question?