## APWorks 2024.2 - Ph 3
Project Profile
APWorks Phase 3
Period: September 2024
Project / Release | Task | Planned |  |  | Project Overhead |  |  |  |  | Test | Code | Analysis | Design | Development Time |  |  | Testing |  |  | Bug Fixing Time |  |  | Total | Total
|  | Development | QA | Bug Fixing | Mgmt | Meetings | Deployments | Client Items | Leaves | Cases | Review |  |  | Estimate | Actual | Difference | Planned | Actual | Variance | Planned | Actual | Variance | Planned | Hours
APWORKS 2024.2 - PHASE 3
| Add Media Type/Service type/Roles | 4 hrs | 8 |  |  | 7 |  |  |  | 9 |  | 2 |  | 4 |  |  | 8 | [5 empty] | 12 | 18
| Google Drive integration. (Setup and Integration development) | 44 hrs | 8 |  |  | 5 |  |  |  | 70 |  |  | 15 | 44 | 58 | -14 | 8 | [5 empty] | 52 | 148
| Ability to automatically attach additional documents (tear sheets, afidavit) to the invoice | 30 hrs | 20 |  |  | 7 |  |  |  | 54 |  | 0.5 |  | 30 |  |  | 20 | [5 empty] | 50 | 61.5
| We need to read the company on the invoice document to route to the right company. If the company is not detected properly we will default to a company and mark it with a status. | 56 hrs | 20 | [8 empty] | 1 |  | 56 |  |  | 20 | [5 empty] | 76 | 1
| Broadcast Invoices | [21 empty] | 0 | 0
| We will need a separate node for "Broadcast Invoices" added at the end of Production Invoices. | 4 hrs | [11 empty] | 4 | 22 | -18 | [6 empty] | 4 | 22
| User Group management changes | 12 hrs | [11 empty] | 12 | 4 | 8 | [6 empty] | 12 | 4
| Dashboard | 16 hrs | [11 empty] | 16 | [8 empty] | 16 | 0
| Manage Invoice Models list | 0 hrs | [11 empty] | 0 | [8 empty] | 0 | 0
| Manage Non-Mapped Production Invoices | 0 hrs | [11 empty] | 0 | 2 | [7 empty] | 0 | 2
| Manage Invoice Documents | 4 hrs | [9 empty] | 2 |  | 4 | 2 | 2 | [6 empty] | 4 | 4
| Invoice List UI | 32 hrs | [11 empty] | 32 | [8 empty] | 32 | 0
| EDI file processing | 62 hrs | 40 | [10 empty] | 62 | 10.5 | 51.5 | 40 | [5 empty] | 102 | 10.5
| PDF file generation | 50 hrs | 6 | [8 empty] | 5 |  | 50 | 5 | 45 | 6 | [5 empty] | 56 | 10
| Invoice View UI | 30 hrs | 12 | [7 empty] | 2 |  |  | 30 | 4 | 26 | 12 | [5 empty] | 42 | 6
| Customer Information : Selection of the client on the vendor invoice header level. This will help route the invoice to the appropriate client team. - (Sync and a lookup field on invoice) | 10 hrs | [9 empty] | 0.5 |  | 10 | [8 empty] | 10 | 0.5
| We will need to introduce tolerance by media type. | 20 hrs | [11 empty] | 20 | [8 empty] | 20 | 0
| Read data from Media Ocean Jobs, IOs (buying), Customer Master, Vendor Master, Currencies, Tax codes, Payment terms, EDI?, payment information | 80 hrs | 40 | [10 empty] | 80 |  |  | 40 | [5 empty] | 120 | 0
| vendor/stations/sites can be associated to multiple pay to. EX: Bell Media is linked to Bill pay to | 32 hrs | [9 empty] | 1 | 3 | 32 | 23 | 9 | [6 empty] | 32 | 27
| Checkbox to filter discrepant lines | 8 hrs | [11 empty] | 8 | [8 empty] | 8 | 0
| Ability to assign Employees to Roles by Media type and by Client | 70 hrs | 8 |  |  | 2 | [5 empty] | 3 |  | 70 | 112 | -42 | 8 | 16 | -8 |  |  |  | 78 | 117
| Project Overhead |  |  |  | 1 | 20.5 | 2.5 |  |  |  |  | 4 | [10 empty] | 0 | 28
Overall Performance |  |  |  |  | 1 | 41.5 | 2.5 | 0 | 0 | 133 | 2 | 19 | 18 | 564 | 242.5 | 67.5 | 162 | 16 | -8 | 0 | 0 | 0 | 726 | 459.5
Note on S35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is difference for tasks where estimate is provided and Actual Work is performed

## APWorks 2024.2 Ph 2
Project Profile
APWorks Phase 2 and Prior Versions
Period: September 2024
Project / Release | Task | Planned |  |  | Project Overhead |  |  |  |  | Test | Code | Analysis | Design | Development Time |  |  | QA verification |  |  | Bug Fixing Time |  |  | ToTal Hours
|  | Development | QA | Bug Fixing | Mgmt | Meetings | Deployments | Client Items | Leaves | Cases | Review |  |  | Estimate | Actual | Difference | Planned | Actual | Difference | Planned | Actual | Difference | Planned | Actual
AP WORKFLOW
| Analysis of the new project/assignment/task | [10 empty] | 5 | [10 empty] | 0 | 5
APWORKS PHASE2 | [22 empty] | 0
| Analysis of the new project/assignment/task | [13 empty] | 6 | -6 | [6 empty] | 0 | 6
| Dev Support |  |  |  |  | 1 |  | 4 | [14 empty] | 0 | 5
| Meetings, mails, communication, TFS, Interviews |  |  |  |  | 25 | [6 empty] | 1 | [9 empty] | 0 | 26
| Regular bug fixing activity | [16 empty] | 180 | -180 |  | 21 | -21 | 0 | 21
| Regular testing and QA new project/assignment/task | [19 empty] | 184 | -184 | 0 | 184
| Support Items |  |  |  |  | 1 | [16 empty] | 0 | 1
[23 empty] | 0 | 0
0
Overall Performance |  |  |  |  | 0 | 27 | 0 | 4 | 0 | 0 | 0 | 5 | 1 | 0 | 6 | -6 | 0 | 180 | -180 | 0 | 205 | -205 | 0 | 248
Note on S19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is difference for tasks where estimate is provided and Actual Work is performed

## Nexelus 2024.2
Project Profile
Nexelus 2024.2
Period: September 2024
Project / Release | Task | Planned |  |  | Project Overhead |  |  |  |  | Test | Code | Analysis | Design | Development Time |  |  | QA Verification |  |  | Bug Fixing Time |  |  | Total
|  | Development | QA | Bug Fixing | Mgmt | Meetings | Deployments | Client Items | Leaves | Cases | Review |  |  | Estimate | Actual | Difference | Planned | Actual | Variance | Planned | Actual | Variance | Planned | Actual
NEXELUS 2024.2
| Analysis of the new project/assignment/task | [10 empty] | 22 | 6
| Client Items |  |  |  |  | 1 |  | 92 | [6 empty] | 2 | -2
| Development of new project/assignment/task | [13 empty] | 3 | -3
| Meetings, mails, communication, TFS, Interviews |  |  |  |  | 3 | [11 empty] | 24
| Regular bug fixing activity | [13 empty] | 44 | -44 |  | 6
| Regular testing and QA new project/assignment/task | [16 empty] | 1
| Support Items | [6 empty] | 140 |  |  |  | 4 | [8 empty] | 2
| Time Off - Planned | [7 empty] | 8
Overall Performance |  |  |  |  | 0 | 4 | 0 | 232 | 8 | 0 | 0 | 26 | 6 | 0 | 49 | -49 | 0 | 31 | 0 | 0 | 2 | 0 | 0 | 0
Note on S32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is difference for tasks where estimate is provided and Actual Work is performed